## DIXIE_CUST_0000173555.0001
Pending Repair in 2021 Work Plan
*Workplan Bucket | Notification | Category | Work Description | Order | ETL Name | Structure Number | MAT | Priority | Priority Bucket | Work Approved Outside Workplan | Date Found in Field | *ReqEnd/Funded Due Date | Clearance Start | Clearance End | Scheduled End | Scheduled Start | Completion Date | CIRT Action | CIRT Response | Tier | Late Tag | WSIP Area | WSIP | Inspection | WM Notes | Assigned Crew/Contractor | WV Action Needed | Late Code | Late Explanation | GIS Longitude | GIS Latitude | ETL | Equipment Number | Facility | Damage | Action | Order User Status | Order Status Code | Order Status Description | Estimating Status | Notification Status | Notification type | Planner group | Resource Group | Cost Category | WTC | HQ | Land Agent | Partial RTC | Full RTC | *2021 Work Plan | *Approved Outside 2021 Plan | *BF MAT Code | *FSR | *Real WSIP Area | *Distribution | *CGI/Patrol | *COMP/WV/Pending | *Repaired Status | *Due Before Today | *On-Time Repair | *Scheduled Past Due | *Schedule Status | *Detail Tag Status | *Found 2020, Tag Status | *Found 2021 Tag Status | *FSR Upgraded Tag Status | *MAT Type | *Work Plan Tag Status | *A Tag Cost Category | *WV Summary | ERTC Release Date | ERTC Release Status | *Job Package | *ERTC Readiness | *WV Duration | *Audit A/B Bucket | *Completed Status | Approved Work Plan | Work Plan Due Date
2021 Work Plan | 112806346 | Not Scheduled | COOLEYLANDING/LOS ALTOS A1/38G RPL PL | 31323739 | COOLEY LANDING-LOS ALTOS | A001/038 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-04-19 | 2019-04-19 | [8 empty] | LATE | Central | Non-WSIP |  | Completed |  |  |  |  | '-122.101553 | 37.4047 | ETL.6560 | 44303481 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 112845022 | Q2 | SONOMA-PUEBLO 8/12 REPLACE POLE | 31325180 | SONOMA-PUEBLO | 008/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-04-20 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.329865 | 38.3051 | ETL.3810 | 40689183 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-01 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113021508 | Not Scheduled | URICH TAP 000/001A REPLACE POLE | 31337142 | URICH TAP | 000/001A | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-06-07 | 2019-06-07 | [8 empty] | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | ACOE permit | '-122.102692 | 38.0273 | ETL.6373 | 40577476 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  | ACOE | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113118667 | Mar | HENRIETTA-LEMOORE NAS :060/006 RPLC POLE | 31343477 | HENRIETTA-LEMOORE NAS | :060/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-03 | 2022-08-03 |  |  | 2021-03-16 | 2021-03-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Cust Outage Consideration | Had to push it out due to the loads. If the load is not down by October 1st, then we will have to push it out farther - [REDACTED] | '-119.90527 | 36.2484 | ETL.8780 | 40820773 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-05-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113134079 | Not Scheduled | DIXON-VACA #1 6/148 REPLACE POLE | 31343167 | DIXON-VACA #1 | 006/148 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-07-17 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.84138 | 38.4277 | ETL.6730 | 40759893 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113134150 | Not Scheduled | DIXON-VACA #1 9/209 REPLACE POLE | 31343167 | DIXON-VACA #1 | 009/209 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-07-13 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.810854 | 38.461 | ETL.6730 | 40665510 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113135608 | Q2 | DIXON-VACA #2 7/173 REPLACE POLE | 31347877 | DIXON-VACA #2 | 007/173 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-07-16 | 2021-05-31 |  |  | 2021-04-06 | 2021-04-06 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.828627 | 38.4419 | ETL.6740 | 40869019 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-11-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113135639 | Not Scheduled | DIXON-VACA #2 10/227 REPLACE POLE | 31347877 | DIXON-VACA #2 | 010/227 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-07-13 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.801522 | 38.4714 | ETL.6740 | 40825232 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113135777 | Not Scheduled | DIXON-VACA #2 A8/188 REPLACE POLE | 31343168 | DIXON-VACA #2 | A008/188 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-07-22 | 2019-07-22 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-121.928517 | 38.3287 | ETL.6740 | 40665467 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113162817 | Q3 | CHRISTIE-WILLOW PASS 6/78 REPLACE POLE | 31343162 | CHRISTIE-WILLOW PASS | 006/078 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-06-07 | 2019-06-07 |  |  | 2021-09-09 | 2021-09-09 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.107878 | 38.0261 | ETL.6370 | 40695932 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  | ACOE | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113167060 | Feb | PEASE-MARYSVILLE-HARTER 0/010 RPL POLE | 31348031 | PEASE-MARYSVILLE-HARTER | 000/010 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-17 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.653255 | 39.1707 | ETL.7770 | 40610094 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113186694 | Not Scheduled | PASO ROBLES-TEMPLETON+ 2/42 REPL POLE | 31347872 | PASO ROBLES-TEMPLETON | 002/042 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-23 | 2021-05-31 | [8 empty] | XMPT | South | Non-WSIP | FSRP |  |  |  | Estimating |  | '-120.681075 | 35.5812 | ETL.9400 | 40754833 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113186715 | Not Scheduled | PASO ROBLES-TEMPLETON+ 2/43 REPL POLE | 31389712 | PASO ROBLES-TEMPLETON | 002/043 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-12 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.681198 | 35.5803 | ETL.9400 | 40823296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113190216 | Mar | GLENN #3 000/010 STRW NG REPL | 31379483 | GLENN #3 | 000/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-24 | 2021-05-31 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.132076 | 39.777 | ETL.6940 | 40818067 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113220647 | Q2 | LVNGSTON-LVNGSTON JCT 4/0 REPLACE POLE | 31318833 | LIVINGSTON-LIVINGSTON JCT | 004/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-31 | 2019-08-31 |  |  | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | South | Non-WSIP |  |  |  |  | Clearance Denied by GCC | distribution OE has denied the clearance for this. Not able to do this in the summer will need to submit for fall. New scheduled date is Nov 1st 2019. | '-120.760577 | 37.3031 | ETL.8920 | 40584029 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113238411 | Mar | NICOLAUS-MARYSVILLE 17/376 RPLC POLE | 31379484 | NICOLAUS-MARYSVILLE | 017/376 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-24 | 2021-05-31 |  |  | 2021-03-05 | 2021-03-04 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.54348 | 38.9145 | ETL.7690 | 40611723 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113238417 | Mar | NICOLAUS-MARYSVILLE 17/382 RPLC POLE | 31379484 | NICOLAUS-MARYSVILLE | 017/382 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-24 | 2021-05-31 |  |  | 2021-03-05 | 2021-03-04 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.543522 | 38.9104 | ETL.7690 | 40815209 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113249375 | Not Scheduled | 7TH STANDARD-KERN REPAIR DEFLECTION | 31351241 | KERN-KERN OIL-FAMOSO |  | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-09-14 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | [8 empty] | ETL.8870 |  | Pole | Out of plumb | Tested | FICL | FICL | Financial closing (no labor) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113266683 | Q2 | SEQUOIA TAP (IDLE) 0/3 REPLACE POLE | 31379485 | SEQUOIA TAP (IDLE) | 000/003 | 70Y | F | Pre-2020_(1b) Lines with special commitments |  | 2017-08-28 | 2019-08-28 |  |  | 2021-05-23 | 2021-05-22 |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | Awaiting Caltrans Permit | '-122.267049 | 38.014 | ETL.6361 | 40643934 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-05-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113771862 | Q2 | COLEMAN-COTTONWD 1/020 STRW ROTN REPL | 31379566 | COLEMAN-COTTONWOOD | 001/020 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-10-27 | 2019-10-27 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.141392 | 40.4092 | ETL.6430 | 40601085 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113819272 | Not Scheduled | CORTINA #4 C21/378 RPLC GUY POLE | 31379441 | CORTINA #4 | C021/378 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-10 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.035808 | 39.2792 | ETL.6610 | 40609984 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113819637 | Mar | CORTINA #4 A7/124 REPLACE POLE | 31379441 | CORTINA #4 | A007/124 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-07-13 | 2019-07-13 |  |  | 2021-03-27 | 2021-03-26 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.152913 | 39.1629 | ETL.6610 | 40737571 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113819688 | Mar | CORTINA #4 C23/415 REPLACE POLE | 31379441 | CORTINA #4 | C023/415 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-10 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-26 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.033325 | 39.3051 | ETL.6610 | 40757500 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113819702 | Not Scheduled | CORTINA #4 C28/527 REPLACE POLE | 31379441 | CORTINA #4 | C028/527 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-15 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.017175 | 39.3847 | ETL.6610 | 40873197 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 113870534 | Q2 | TABLE MTN-VACA 02/011 RPL INSULATOR | 31402249 | TABLE MTN-VACA | 002/011 | 93K | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-08 | 2021-05-31 |  |  | 2021-05-19 | 2021-05-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.677946 | 39.5239 | ETL.6090 | 40590039 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114033522 | 2022 | NICOLAUS-MARYSVILLE 0/4B RPLC POLE | 31381811 | NICOLAUS-MARYSVILLE | 000/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-08-18 | 2019-08-18 |  |  | 2022-04-30 | 2022-04-01 |  |  |  |  | LATE | North Valley | Non-WSIP | [8 empty] | ETL.7690 | 44296324 | Structure-Wood | Rotten | Replace | PROD | PROD | Prod Special (No Labor) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | 2022 |  |  | 2019-08-07 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114067119 | Mar | KINGSBURG-LEMOORE 017/006 RPL POLE | 31369297 | KINGSBURG-LEMOORE | 017/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-12-07 | 2021-05-31 |  |  | 2021-03-09 | 2021-03-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.65501 | 36.284 | ETL.8910 | 40821414 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-05-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114069612 | Not Scheduled | IGNACIO-ALTO 13/114 REPL LSP W/TSP | 31368895 | IGNACIO-ALTO | 013/114 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-12-08 | 2022-12-08 | [6 empty] | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.514403 | 37.9429 | ETL.7150 | 40592199 | Structure-Steel | No Good/Out of Stdrd | Replace | FICL | FICL | Financial closing (no labor) | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114153550 | Q2 | HUMBOLDT-BRIDGEVILLE 115/6""CTR"" REPL PL | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-28 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322752 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114153555 | Q2 | HUMBOLDT-BRIDGEVILLE 115/6""LFT"" REPL PL | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-28 | 2019-11-28 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322751 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114153556 | Q2 | HUMBOLDT-BRIDGEVILLE 115/6""RT"" REPL PL | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-28 | 2019-11-28 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322753 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114175648 | Q2 | EXCHEQUER-LE GRAND 11/010 RPLC POLE | 31419516 | EXCHEQUER-LE GRAND | 011/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269099 | 37.4035 | ETL.1560 | 41130100 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114175695 | Q2 | EXCHEQUER-LEGRAND 2/0 repl 3 pole strctr | 31391051 | EXCHEQUER-LE GRAND | 002/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.26589 | 37.5532 | ETL.1560 | 40618907 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114182205 | Q2 | HUMBOLDT-BRIDGEVILLE 115/0 RPL PL ""LFT"" | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-30 | 2019-11-30 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.096557 | 40.7784 | ETL.1810 | 40619207 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114182330 | Q2 | HUMBOLDT-BRIDGEVILLE 115/0 RPL PL ""RT"" | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-30 | 2019-11-30 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.096557 | 40.7784 | ETL.1810 | 40619207 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114182339 | Q2 | HUMBOLDT-BRIDGEVILLE 115/0 RPL PL ""CTR"" | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-11-30 | 2019-11-30 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.096557 | 40.7784 | ETL.1810 | 40619207 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114223195 | Not Scheduled | BUTTE-ESQUON 08/185 STRW NG REPL | 31379732 | BUTTE-ESQUON | 008/185 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-11 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.766473 | 39.61 | ETL.6270 | 40768755 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLZ | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114230951 | Not Scheduled | MORRO BAY-SAN LUIS OBISPO #1 0/4 RPL TWR | 31374734 | MORRO BAY-SAN LUIS OBISPO #1 | 000/004 | 92S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-01-18 | 2020-01-18 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-120.848954 | 35.3767 | ETL.2810 | 40752726 | Structure-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLQ | Tower | Capital | 426 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114233033 | Not Scheduled | BUTTE-ESQUON 006/133 STRW ROTN REPL | 31381841 | BUTTE-ESQUON | 006/133 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-16 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.743165 | 39.6431 | ETL.6270 | 40816828 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2021-01-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114239110 | Mar | SRGENT SS-HOLISTER-HOLISTR 0/4 REPL POLE | 31498606 | SARGENT SW STA-HOLLISTER (IDLE) | 000/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-22 | 2023-01-22 |  |  | 2021-03-23 | 2021-03-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.550954 | 36.8955 | ETL.2870 | 44414126 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114239114 | Mar | SRGENT SS-HOLISTER-HOLISTR 0/4 REPL POLE | 31498606 | SARGENT SW STA-HOLLISTER (IDLE) | 000/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-11 | 2023-01-11 |  |  | 2021-03-23 | 2021-03-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.550954 | 36.8955 | ETL.2870 | 44414125 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114239477 | Feb | SYCAM CK-NOTRE DAME-TBL 18/175 STRW NG | 31388889 | SYCAMORE CREEK-NOTRE DAME-TABLE MT | 018/175 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-19 | 2021-05-31 |  |  | 2021-02-24 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.803699 | 39.7611 | ETL.4314 | 40575472 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114239479 | Feb | SYCAM CK-NOTRE DAME-TBL 18/183 STRW ROTN | 31388889 | SYCAMORE CREEK-NOTRE DAME-TABLE MT | 018/183 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-19 | 2021-05-31 |  |  | 2021-02-24 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.805882 | 39.7646 | ETL.4314 | 40575430 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114275067 | Mar | BUTTE-CHICO #2 000/017 STRW ROTN REPL | 31381840 | BUTTE-CHICO #2 | 000/017 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-05 | 2021-05-31 |  |  | 2021-03-31 | 2021-03-30 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.820657 | 39.7191 | ETL.6260 | 44190834 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114278847 | Q2 | COLEMAN-COTTONWOOD 001/019 STRW NG RPL | 31381842 | COLEMAN-COTTONWOOD | 001/019 | 70Y | F | Pre-2020_(5b) On structure in bucket 5 |  | 2018-01-29 | 2020-01-29 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.140996 | 40.4091 | ETL.6430 | 40594912 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLZ | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114286234 | Q2 | HUMBOLDT-BRIDGEVILLE 105/4 RPL PL ""LFT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 105/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-06 | 2020-02-06 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.944318 | 40.72 | ETL.1810 | 44322551 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114286263 | Q2 | HUMBOLDT-BRIDGEVILL 103/3 RPL PL ""LFT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 103/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-06 | 2020-02-06 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.936211 | 40.6911 | ETL.1810 | 44322508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114286693 | Mar | CLEAR LAKE-HOPLAND 11/1 REPLACE POLE | 31379236 | CLEAR LAKE-HOPLAND | 011/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-05 | 2021-05-31 |  |  | 2021-03-30 | 2021-03-30 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.89417 | 39.0001 | ETL.6390 | 40584501 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-09-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114309724 | Mar | KINGSBURG-LEMOORE 14/001 RPLC POLE | 31455718 | KINGSBURG-LEMOORE | 014/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-13 | 2021-05-31 |  |  | 2021-03-09 | 2021-03-09 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.655077 | 36.3327 | ETL.8910 | 40596429 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114314666 | Q3 | CRAG VIEW-CASCADE 13/116 SHLS NG REPL | 43487698 | CRAG VIEW-CASCADE | 013/116 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2018-02-13 | 2019-02-13 |  |  | 2021-09-28 | 2021-09-27 |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Internal Process | Scope of work is being reevaluated | '-122.306934 | 40.7633 | ETL.1350 | 40761919 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-03-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114317066 | Mar | CORTINA #4 A7/127 REPLACE POLE | 31381813 | CORTINA #4 | A007/127 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-12-21 | 2019-12-21 |  |  | 2021-03-27 | 2021-03-26 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.151855 | 39.1625 | ETL.6610 | 40737648 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114317067 | Not Scheduled | SAN RAMON-RADUM 2/70 REPLACE POLE | 31381844 | SAN RAMON-RADUM | 002/070 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-08 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.911276 | 37.7107 | ETL.7960 | 40613244 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114329415 | Mar | GLENN #2 023/435 STRW ROTN REPL | 31388891 | GLENN #2 | 023/435 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-07 | 2021-05-31 |  |  | 2021-03-10 | 2021-03-08 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.006004 | 39.5638 | ETL.6930 | 40814716 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-09-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114339555 | Q2 | LAKEVILLE #1 00/06 REFRAME POLE | 31382640 | LAKEVILLE #1 | 000/006 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-26 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | XMPT | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.581557 | 38.2532 | ETL.7360 | 41107031 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114352548 | Q2 | ATWTR-LVNGSTN-MRCD 19/007 RPLC POLE | 31382936 | ATWATER-MERCED | 019/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-02 | 2023-03-02 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.727367 | 37.3606 | ETL.1030 | 40805413 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114352660 | Q2 | ATWTR-LVNGSTN-MRCD 19/008 RPLC POLE | 31382936 | ATWATER-MERCED | 019/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-02 | 2023-03-02 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.728568 | 37.3606 | ETL.1030 | 40873506 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114409277 | Mar | COTTONWOOD #1 BA029/303 STRW ROTN REPL | 31391452 | COTTONWOOD #1 | BA029/303 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-14 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.15884 | 40.0684 | ETL.6620 | 40905992 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114423633 | Q2 | FULTON-SANTA ROSA #1 04/69 REP GUY F/S | 43541342 | FULTON-SANTA ROSA #1 NF | 004/069 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-19 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.743585 | 38.4439 | ETL.1620 | 40594341 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114434246 | Mar | CORTINA #4 A7/128 REPLACE POLE | 31386146 | CORTINA #4 | A007/128 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-12-21 | 2019-12-21 |  |  | 2021-03-27 | 2021-03-26 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.151756 | 39.1625 | ETL.6610 | 40574906 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114435142 | Q2 | SEQUOIA TAP 0/4 REPLACE POLE | 31386147 | SEQUOIA TAP (IDLE) | 000/004 | 70Y | F | Pre-2020_(1b) Lines with special commitments |  | 2017-12-22 | 2021-05-31 |  |  | 2021-05-23 | 2021-05-22 |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | Awaiting Caltrans Permit | '-122.26739 | 38.0151 | ETL.6361 | 40745626 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114435674 | Not Scheduled | WEST SACRAMENTO-DAVIS 10/164 RPLC POLE | 31386145 | WEST SACRAMENTO-DAVIS | 010/164 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2017-12-20 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.728126 | 38.5624 | ETL.4120 | 40590285 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114438564 | Mar | COTTONWOOD #1 B024/204 STRW NG REPL | 31391452 | COTTONWOOD #1 | B024/204 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233197 | 40.0791 | ETL.6620 | 40909848 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114438945 | Mar | COTTONWOOD #1 B024/205 STRW NG REPL | 31391452 | COTTONWOOD #1 | B024/205 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233195 | 40.0784 | ETL.6620 | 40909849 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114439097 | Mar | COTTONWOOD #1 B023/195 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/195 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233033 | 40.0854 | ETL.6620 | 40909839 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114439116 | Mar | COTTONWOOD #1 B023/194 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/194 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233029 | 40.0862 | ETL.6620 | 40909838 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114439139 | Mar | COTTONWOOD #1 B023/188 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/188 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.232902 | 40.0905 | ETL.6620 | 40909832 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-02-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114439155 | Mar | COTTONWOOD #1 B023/191 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/191 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.232952 | 40.0883 | ETL.6620 | 40909835 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114439271 | Mar | COTTONWOOD #1 B021/160 STRW NG REPL | 31391452 | COTTONWOOD #1 | B021/160 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.232241 | 40.1118 | ETL.6620 | 40909804 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114439690 | Q2 | BUTTE-ESQUON 0/011 STRW NG REPL | 31388884 | BUTTE-ESQUON | 000/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-23 | 2021-05-31 |  |  | 2021-04-07 | 2021-04-06 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.809467 | 39.7092 | ETL.6270 | 40826354 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2021-01-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114448828 | Q2 | GARBERVILLE-LAYTONVILLE 60kV 34/9 NG POL | 31404618 | GARBERVILLE-LAYTONVILLE | 034/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-28 | 2020-03-28 |  |  | 2021-05-17 | 2021-04-19 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.577342 | 39.8306 | ETL.8365 | 40875241 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114448873 | Q2 | GARBERVILLE-LAYTONVILLE 60kV 35/0 NG POL | 31404618 | GARBERVILLE-LAYTONVILLE | 035/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-28 | 2020-03-28 |  |  | 2021-05-17 | 2021-04-19 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.578193 | 39.8314 | ETL.8365 | 40614542 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114469839 | Feb | DINUBA ENERGY TAP 2/009 RPLC POLE | 31389710 | DINUBA ENERGY TAP | 002/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-04 | 2022-04-04 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.408345 | 36.5714 | ETL.9051 | 40873004 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114469982 | Feb | DINUBA ENERGY TAP 02/008 RPLC POLE | 31389710 | DINUBA ENERGY TAP | 002/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-04 | 2022-04-04 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.407227 | 36.5714 | ETL.9051 | 40873844 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114475329 | Q2 | CHOWCHILLA-KERCKHOFF 31/010 RPL POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 031/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-05 | 2021-05-31 | 2021-04-27 | 2021-04-29 | 2021-04-29 | 2021-04-26 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.092917 | 37.1268 | ETL.1250 | 40584956 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114477817 | Q2 | CHOWCHILLA-KERCKHOFF 28/010 REPL POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 028/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-06 | 2021-05-31 | 2021-04-27 | 2021-04-29 | 2021-04-29 | 2021-04-26 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.035507 | 37.1266 | ETL.1250 | 40584947 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114477857 | Q2 | CHOWCHILLA-KERCKHOFF 27/008A RPLC POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 027/008A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-06 | 2021-05-31 | 2021-04-27 | 2021-04-29 | 2021-04-29 | 2021-04-26 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.020386 | 37.1244 | ETL.1250 | 41109571 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114477911 | Q2 | CHOWCHILLA-KERCKHOFF 28/011 RPLC POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 028/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-06 | 2021-05-31 | 2021-04-27 | 2021-04-29 | 2021-04-29 | 2021-04-26 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.037018 | 37.1267 | ETL.1250 | 40592031 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114491791 | Q2 | SONOMA-PUEBLO 02/07 REPL OVRLD POLE | 31390594 | SONOMA-PUEBLO | 002/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-10 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.422026 | 38.2697 | ETL.3810 | 40818672 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-05 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114494421 | Not Scheduled | BAIR-COOLEY LNDING #1-60 kV_2/17A RPL PL | 31389708 | BAIR-COOLEY LANDING #1 | 002/017A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-11 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.185119 | 37.4874 | ETL.6200 | 44378240 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLZ | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114494798 | Not Scheduled | GEYSERS #7-EAGLE ROCK 0/002 | 43761575 | GEYSERS #7-EAGLE ROCK | 000/002 | ICS | F | Pre-2020_(5) TD tag on other lines |  | 2018-04-11 | 2020-04-11 | [6 empty] | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1680 | 44298667 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114494871 | Not Scheduled | GEYSERS #7-EAGLE ROCK 0/01B CANCEL | 43761575 | GEYSERS #7-EAGLE ROCK | 000/001B | ICS | F | Pre-2020_(5) TD tag on other lines |  | 2018-04-11 | 2020-04-11 | 2020-10-07 | 2020-10-07 |  |  |  |  | CANCEL/CNCL |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.801462 | 38.8145 | ETL.1680 | 40740487 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-31 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114496955 | Q2 | MENDOCINO-UKIAH 3/11B RPL STRW | 31391191 | MENDOCINO-UKIAH | 003/011B | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-12 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.192766 | 39.1973 | ETL.2420 | 40740255 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114498679 | Not Scheduled | KETTLEMAN HILLS TAP 0/002 RPLACE POLE | 31389711 | KETTLEMAN HILLS TAP | 000/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-11 | 2023-04-11 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.09778 | 36.0436 | ETL.8701 | 40684781 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-10-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114516978 | Q2 | HUMBOLDT-BRIDGEVILLE 103/3 RPL PL ""RT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 103/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-06 | 2020-02-06 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.936211 | 40.6911 | ETL.1810 | 44322509 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114517356 | Q2 | HUMBOLDT-BRIDGEVILLE 105/4 RPL PL ""RT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 105/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-06 | 2020-02-06 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.944318 | 40.72 | ETL.1810 | 44322552 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114531042 | Feb | NICOLAUS-CATLETT JCT 4/086 RPL POLE | 31404628 | NICOLAUS-CATLETT JCT | 004/086 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-24 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-25 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.539166 | 38.8477 | ETL.7680 | 40757082 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114531110 | Feb | NICOLAUS-CATLETT 3/080 RPL POLE | 31404628 | NICOLAUS-CATLETT JCT | 003/080 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-24 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-25 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.541722 | 38.8522 | ETL.7680 | 40866785 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114535342 | Feb | KEARNEY-BIOLA 10/009 RPLC POLE | 31391046 | KEARNEY-BIOLA | 010/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-25 | 2021-05-31 |  |  | 2021-02-13 | 2021-02-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.961266 | 36.7933 | ETL.8810 | 40858702 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114535749 | Feb | KEARNEY-BIOLA 11/000 RPLC POLE | 31391047 | KEARNEY-BIOLA | 011/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-25 | 2021-05-31 |  |  | 2021-02-13 | 2021-02-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.970139 | 36.7933 | ETL.8810 | 40583383 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114535944 | Feb | KEARNEY-BIOLA 11/009 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-25 | 2021-05-31 |  |  | 2021-02-13 | 2021-02-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.97935 | 36.7933 | ETL.8810 | 40872050 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114536191 | Feb | KEARNEY-BIOLA 13/000 RPLC POLE | 31391049 | KEARNEY-BIOLA | 013/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-25 | 2021-05-31 |  |  | 2021-02-13 | 2021-02-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.00639 | 36.7933 | ETL.8810 | 40606721 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114536273 | Feb | KEARNEY-BIOLA 13/010 RPLC POLE | 31391049 | KEARNEY-BIOLA | 013/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-25 | 2021-05-31 |  |  | 2021-02-13 | 2021-02-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.015618 | 36.7933 | ETL.8810 | 40583392 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114549634 | Q2 | EXCHEQUER-LE GRAND 24/000 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 024/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-01 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.252551 | 37.2419 | ETL.1560 | 40913270 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114553087 | Q2 | EXCHEQUER-LE GRAND 16/005 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 016/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-01 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.2516 | 37.351 | ETL.1560 | 40762233 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114557370 | Mar | MENDOCINOPHILO JCTHOPLND 10/11 RPLC POLE | 31390919 | MENDOCINO-PHILO JCT-HOPLAND | 010/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-01-25 | 2021-05-31 | 2021-03-07 | 2021-03-07 | 2021-03-07 | 2021-03-07 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.16022 | 39.1233 | ETL.7520 | 40600784 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114557450 | Mar | MENDOCINOPHILO JCTHOPLAND 10/8 RPLC POLE | 31390919 | MENDOCINO-PHILO JCT-HOPLAND | 010/008 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2018-01-25 | 2021-03-22 |  |  | 2021-03-07 | 2021-03-07 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.1602 | 39.125 | ETL.7520 | 40876887 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-04-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 114562395 | Q2 | EXCHEQUER-LE GRAND 05/008 RPLC POLE | 31391051 | EXCHEQUER-LE GRAND | 005/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-03 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267107 | 37.4968 | ETL.1560 | 40873655 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114562438 | Q2 | EXCHEQUER-LE GRAND 05/009 RPLC POLE | 31391051 | EXCHEQUER-LE GRAND | 005/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-03 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267127 | 37.4959 | ETL.1560 | 40865250 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114570245 | Q2 | EXCHEQUER-LE GRAND 008/001 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2022-05-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267943 | 37.457 | ETL.1560 | 40588982 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114570285 | Q2 | EXCHEQUER-LE GRAND 008/002 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2022-05-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267966 | 37.4558 | ETL.1560 | 40689666 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114570315 | Q2 | EXCHEQUER-LE GRAND 008/003 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267992 | 37.4545 | ETL.1560 | 40662962 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114570319 | Q2 | EXCHEQUER-LE GRAND 08/004 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268026 | 37.4532 | ETL.1560 | 40755522 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114570393 | Q2 | EXCHEQUER-LE GRAND 008/009 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268151 | 37.4466 | ETL.1560 | 40864755 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114571472 | Q2 | EXCHEQUER-LE GRAND 009/009 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 009/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2020-05-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.268446 | 37.4314 | ETL.1560 | 40877006 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114571476 | Q2 | EXCHEQUER-LE GRAND 010/002 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 010/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.26853 | 37.4264 | ETL.1560 | 40669620 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114572979 | Q2 | EXCHEQUER-LE GRAND 010/007 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 010/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268621 | 37.4201 | ETL.1560 | 40812814 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575140 | Q2 | EXCHEQUER-LE GRAND 12/000 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269177 | 37.4009 | ETL.1560 | 41130102 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575218 | Q2 | EXCHEQUER-LE GRAND 12/001 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269223 | 37.3999 | ETL.1560 | 40588985 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575289 | Q2 | EXCHEQUER-LE GRAND 12/002 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269252 | 37.3986 | ETL.1560 | 40702433 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575295 | Q2 | EXCHEQUER-LE GRAND 12/003 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269266 | 37.3978 | ETL.1560 | 40653443 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575343 | Q2 | EXCHEQUER-LE GRAND 12/004 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269305 | 37.3963 | ETL.1560 | 40762493 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575815 | Q2 | EXCHEQUER-LE GRAND 013/008 RPLC POLE | 31462751 | EXCHEQUER-LE GRAND | 013/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.26981 | 37.3763 | ETL.1560 | 40865249 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114575931 | Q2 | EXCHEQUER-LE GRAND 014/007 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 014/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-08 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269889 | 37.3644 | ETL.1560 | 40826573 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114584230 | Q2 | EXCHEQUER-LE GRAND 009/006 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 009/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-07 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268398 | 37.435 | ETL.1560 | 40813576 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114595870 | Q2 | ROUND MTN-TBL MTN #2 50/219 CONS NG REPA | 43621090 | ROUND MTN-TABLE MTN #2 | 050/219 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-05-03 | 2021-05-31 |  |  | 2021-04-08 | 2021-01-12 |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.891019 | 40.0748 | ETL.6070 | 40863109 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 114608714 | Mar | BUTTE-CHICO #2 000/016 STRW ROTN REPL | 31397866 | BUTTE-CHICO #2 | 000/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-16 | 2021-05-31 |  |  | 2021-03-31 | 2021-03-30 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.820573 | 39.7189 | ETL.6260 | 40771361 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114626587 | Mar | CLEARLAKE-HOPLAND 00/10 REPL NG POLE | 31397870 | CLEAR LAKE-HOPLAND | 000/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-24 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.072631 | 38.9706 | ETL.6390 | 40587010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-09-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114628867 | Q2 | HUMBOLDT-BRIDGEVILLE-107/1L RPL POLE | 31404623 | HUMBOLDT-BRIDGEVILLE | 107/001 | 70Y | F | Pre-2020_(4b) On structure in bucket 4 |  | 2018-05-23 | 2020-05-23 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.962404 | 40.7423 | ETL.1810 | 44322571 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114636964 | Q2 | SEQUOIA TAP (IDLE) 000/005 rpl pole | 31395987 | SEQUOIA TAP (IDLE) | 000/005 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2018-05-25 | 2021-05-31 |  |  | 2021-05-23 | 2021-05-22 |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | Awaiting Caltrans Permit | '-122.266913 | 38.0161 | ETL.6361 | 40745606 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114641696 | Not Scheduled | KONOCTI-MIDDLETOWN ;20/9 REPL NG POLE | 31396373 | KONOCTI-MIDDLETOWN |  | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-02-04 | 2019-04-30 | [8 empty] | XMPT | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.6380 |  | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  | Additonal Land, Biological, and/or Cultural Review Required | 2019-05-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 70 | Not Scheduled |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114644327 | Not Scheduled | ARCO-TULARE LAKE 000/006 RPL POLE | 31394816 | ARCO-TULARE LAKE | 000/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-30 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915348 | 35.7809 | ETL.8460 | 40806920 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114649176 | Not Scheduled | ARCO-TULARE LAKE 003/050 RPL POLE | 31394816 | ARCO-TULARE LAKE | 003/050 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-31 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915404 | 35.8208 | ETL.8460 | 40748386 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114649267 | Not Scheduled | ARCO-TULARE LAKE 003/059 RPL POLE | 31394816 | ARCO-TULARE LAKE | 003/059 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-31 | 2023-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915417 | 35.8291 | ETL.8460 | 40763112 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114651739 | Not Scheduled | ARCO-TULARE LAKE 005/081 RPL POLE | 31394816 | ARCO-TULARE LAKE | 005/081 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-31 | 2023-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915423 | 35.8497 | ETL.8460 | 40748390 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114653167 | Mar | HENRIETTA-LEMOORE NAS :059/011 RPL POLE | 31394819 | HENRIETTA-LEMOORE NAS | :059/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-31 | 2022-05-31 |  |  | 2021-03-16 | 2021-03-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905277 | 36.26 | ETL.8780 | 40595948 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114653225 | Mar | HENRIETTA-LEMOORE NAS :059/012 RPL POLE | 31394819 | HENRIETTA-LEMOORE NAS | :059/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-31 | 2022-05-31 |  |  | 2021-03-16 | 2021-03-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905278 | 36.2591 | ETL.8780 | 40686217 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114653259 | Mar | HENRIETTA-LEMOORE NAS :059/013 RPL POLE | 31394819 | HENRIETTA-LEMOORE NAS | :059/013 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-31 | 2022-05-31 |  |  | 2021-03-16 | 2021-03-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905236 | 36.258 | ETL.8780 | 40656332 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114660872 | Not Scheduled | ARCO-TULARE LAKE 007/115 RPL POLE | 31394816 | ARCO-TULARE LAKE | 007/115 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-04 | 2023-06-04 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.91548 | 35.8824 | ETL.8460 | 40870928 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114660997 | Not Scheduled | ARCO-TULARE LAKE 008/127 RPL POLE | 31394816 | ARCO-TULARE LAKE | 008/127 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-04 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915498 | 35.8937 | ETL.8460 | 40806924 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114664927 | Not Scheduled | ARCO-TULARE LAKE 010/164 RPLC POLE | 31394816 | ARCO-TULARE LAKE | 010/164 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-05 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.920655 | 35.9271 | ETL.8460 | 40582870 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114667511 | Q2 | EUREKA-STA A _000/002 REPLACE POLE | 31404617 | EUREKA-STA "A" (NO FLY) | 000/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-06 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-01 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.180503 | 40.793 | ETL.6820 | 40658147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114669318 | Not Scheduled | ARCO-TULARE LAKE 015/245 rpl pole | 31394816 | ARCO-TULARE LAKE | 015/245 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-06 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.946425 | 35.998 | ETL.8460 | 40763130 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114679493 | Q2 | PARADISE-TABLE MTN_016/134_INSUL | 31397719 | PARADISE-TABLE MTN | 016/134 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2018-06-08 | 2019-06-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 41176826 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114691402 | Mar | BADGER HILL TAP 001/012 RPLC POLE | 31398364 | BADGER HILL TAP | 001/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-12 | 2021-05-31 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-03-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.934887 | 35.8356 | ETL.8452 | 40595362 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114691793 | Q2 | GARBERVILLE-LAYTONVILLE 60kV 33/0B RP PL | 31454647 | GARBERVILLE-LAYTONVILLE | 033/000B | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-30 | 2019-05-30 |  |  | 2021-05-17 | 2021-04-19 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.55375 | 39.8114 | ETL.8365 | 40906580 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114699493 | Not Scheduled | BRIGHTON-BELLOTA 36/249 RPR TWR | 43910331 | BRIGHTON-BELLOTA | 036/249 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-14 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.317813 | 38.4287 | ETL.4420 | 40864821 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114727427 | Q2 | ORO LOMA-CANAL #1 001/002 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 001/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-25 | 2022-06-25 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.654594 | 36.9039 | ETL.9020 | 40650331 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114727853 | Not Scheduled | PITTSBG-SAN MATEO 021/084A RPL POLE TSP | 31425596 | PITTSBURG-SAN MATEO | 021/084A | 70S | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-25 | 2021-05-31 | [5 empty] | TLN/TLQ error |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.936022 | 37.7433 | ETL.5463 | 44553742 | Structure-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114729264 | Q2 | ORO LOMA-CANAL #1 001/014 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 001/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-26 | 2021-05-31 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.65476 | 36.9142 | ETL.9020 | 40747784 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114729325 | Q2 | ORO LOMA-CANAL #1 001/015A RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 001/015A | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-26 | 2023-06-26 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.654768 | 36.9153 | ETL.9020 | 40905699 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114729470 | Q2 | ORO LOMA-CANAL #1 002/009 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 002/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-26 | 2021-05-31 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.654435 | 36.925 | ETL.9020 | 40871474 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114729504 | Q2 | ORO LOMA-CANAL #1 002/010 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 002/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-26 | 2021-05-31 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.654238 | 36.9261 | ETL.9020 | 40607092 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730128 | Q2 | KING CITY-COBURN #1 60KV 1/24 REPL POLE | 31398372 | KING CITY-COBURN #1 | 001/024 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-10 | 2021-05-31 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-14 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.142661 | 36.2103 | ETL.7320 | 40826679 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-03-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730295 | Q3 | KING CITY-COBURN #1 6/98LFT REPL POLE | 31469910 | KING CITY-COBURN #1 | 006/098 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-05 | 2021-05-31 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-12 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [7 empty] | ETL.7320 | 44405219 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730462 | Q3 | KING CITY-COBURN #1 A9/132 REPLACE POLE | 31398371 | KING CITY-COBURN #1 | A009/132 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-19 | 2021-05-31 | 2021-07-20 | 2021-07-21 | 2021-07-21 | 2021-07-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.194274 | 36.2875 | ETL.7320 | 40876859 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730519 | Q3 | KING CITY-COBURN #1 A9/147 RPLC POLE | 31398371 | KING CITY-COBURN #1 | A009/147 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-19 | 2021-05-31 | 2021-08-02 | 2021-08-12 | 2021-08-12 | 2021-08-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.2043 | 36.2952 | ETL.7320 | 40652511 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730662 | Q3 | KING CITY-COBURN#1 A11/179 REPL GUY POLE | 31398371 | KING CITY-COBURN #1 | A011/179 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-20 | 2021-05-31 | 2021-08-02 | 2021-08-12 | 2021-08-12 | 2021-08-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.229178 | 36.3089 | ETL.7320 | 40864463 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-06-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730687 | Q3 | KING CITY-COBURN#1 A11/185 REPL POLE | 31398371 | KING CITY-COBURN #1 | A011/185 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-24 | 2021-05-31 | 2021-08-02 | 2021-08-12 | 2021-08-12 | 2021-08-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.234313 | 36.3128 | ETL.7320 | 40666217 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730761 | Q3 | KING CITY-COBURN #1 A13/222 REPL POLE | 31398371 | KING CITY-COBURN #1 | A013/222 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-25 | 2021-05-31 | 2021-08-02 | 2021-08-12 | 2021-08-12 | 2021-08-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.246653 | 36.3312 | ETL.7320 | 40864095 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114730766 | Q3 | KING CITY-CBURN#1 60KV A14/243 REPL POLE | 31398371 | KING CITY-COBURN #1 | A014/243 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-18 | 2021-05-31 | 2021-08-02 | 2021-08-12 | 2021-08-12 | 2021-08-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.259503 | 36.3445 | ETL.7320 | 40826694 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114731290 | Q3 | SALINAS-FIRESTONE #2 2/76 REPL GUY POLE | 31398376 | SALINAS-FIRESTONE #2 (NO FLY) | 002/076 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-05-14 | 2020-05-14 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-30 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.611215 | 36.6728 | ETL.7910 | 40811963 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 1 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-03-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114732563 | Q2 | ORO LOMA-CANAL #1 004/005 RPL POLE | 31398375 | ORO LOMA-CANAL #1 | 004/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2023-06-27 |  |  | 2021-04-09 | 2021-04-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.65394 | 36.95 | ETL.9020 | 40747779 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114732715 | Q2 | MIDWAY-WHEELER RIDGE #1 47/210 GRDE BEAM | 31401786 | MIDWAY-WHEELER RIDGE #1 | 047/210 | 70S | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2021-05-31 |  |  | 2021-05-07 | 2021-05-03 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-118.993464 | 35.0273 | ETL.5190 | 40586560 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114733713 | Q2 | ORO LOMA-CANAL #1 006/002 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 006/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2023-06-27 |  |  | 2021-04-09 | 2021-04-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635808 | 36.9618 | ETL.9020 | 40686878 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114733792 | Q2 | ORO LOMA-CANAL #1 006/003 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 006/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2022-06-27 |  |  | 2021-04-09 | 2021-04-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635806 | 36.9627 | ETL.9020 | 40646013 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114733800 | Q2 | ORO LOMA-CANAL #1 006/004 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 006/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2023-06-27 |  |  | 2021-04-09 | 2021-04-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635798 | 36.9637 | ETL.9020 | 40747796 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114734404 | Q2 | ORO LOMA-CANAL #1 007/010 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 007/010 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2022-06-27 |  |  | 2021-04-10 | 2021-04-10 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635744 | 36.9792 | ETL.9020 | 40607101 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114737367 | Q2 | ORO LOMA-CANAL #1 012/003 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 012/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-28 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-10 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.63551 | 37.0274 | ETL.9020 | 40663409 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114743614 | Q2 | DISCOVERY TAP 0/2 POLE REPLACEMENT | 31406081 | DISCOVERY TAP | 000/002 | 92T | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-30 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-13 |  |  | 92T/IBT |  | LATE | South | Non-WSIP | [6 empty] | '-119.01215 | 35.4266 | ETL.1921 | 40652639 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 92 | Q2 |  |  | 2019-11-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114746208 | Q2 | ORO LOMA-CANAL #1 013/011 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 013/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-10 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.635432 | 37.0492 | ETL.9020 | 40596868 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114746227 | Q2 | ORO LOMA-CANAL #1 013/014 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 013/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-10 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.635449 | 37.0516 | ETL.9020 | 40764078 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114746692 | Q2 | ORO LOMA-CANAL #1 014/009 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 014/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2023-07-02 |  |  | 2021-04-12 | 2021-04-12 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.644431 | 37.0545 | ETL.9020 | 40859033 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114746998 | Q2 | DISCOVERY TAP 115KV 0/3 SEECO SW165 REPL | 31406081 | DISCOVERY TAP | 000/003 | 92T | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-13 |  |  | 92T/IBT |  | LATE | South | Non-WSIP | [6 empty] | '-119.01111 | 35.4266 | ETL.1921 | 40743293 | Switch-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 92 | Q2 |  |  | 2019-05-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114747217 | Q2 | DISCOVERY TAP 115KV 0/4 REPL POLE | 31406081 | DISCOVERY TAP | 000/004 | 92T | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-13 |  |  | 92T/IBT |  | LATE | South | Non-WSIP | [6 empty] | '-119.00986 | 35.4266 | ETL.1921 | 40748726 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 92 | Q2 |  |  | 2019-11-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114747523 | Q2 | ORO LOMA-CANAL #1 15/006 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 015/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-12 | 2021-04-12 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.658442 | 37.0546 | ETL.9020 | 40806394 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114747683 | Q2 | ORO LOMA-CANAL #1 015/013 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 015/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-12 | 2021-04-12 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.666903 | 37.0546 | ETL.9020 | 40662495 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-08-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114748611 | Not Scheduled | T2 CC-MORAGA #1 024/113 HELI WASH |  | CONTRA COSTA-MORAGA #1 | 024/113 | ICI | E | Pre-2020_(4) TD tag on high spread line |  | 2018-07-02 | 2019-07-02 | [8 empty] | LATE | Central | Non-WSIP |  |  |  |  | Sick/Capacity | Due to helo equipment constraints, work would not be completed prior to required end date. Work is being incorporated into helo wash program for Q4 2018/ Q1 2019. | '-122.120896 | 37.8621 | ETL.5452 | 44291689 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114753000 | Q3 | KING CITY-COBURN #1 A7/117 REPL POLE | 31455717 | KING CITY-COBURN #1 | A007/117 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-05 | 2021-05-31 | 2021-07-19 | 2021-07-21 | 2021-07-21 | 2021-07-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.185138 | 36.276 | ETL.7320 | 40615515 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114760201 | Q2 | ORO LOMA-CANAL #1 016/003 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 016/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-12 | 2021-04-12 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.673183 | 37.0547 | ETL.9020 | 40661644 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114760242 | Q2 | ORO LOMA-CANAL #1 016/009 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 016/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-13 | 2021-04-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.68019 | 37.0547 | ETL.9020 | 40859035 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114760731 | Q2 | ORO LOMA-CANAL #1 017/007 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 017/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-13 | 2021-04-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.695859 | 37.0548 | ETL.9020 | 40820261 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114760836 | Q2 | ORO LOMA-CANAL #1 018/003 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 018/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2023-07-09 |  |  | 2021-04-13 | 2021-04-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.708073 | 37.0548 | ETL.9020 | 40661652 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114760838 | Q2 | ORO LOMA-CANAL #1 018/004 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 018/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-13 | 2021-04-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.709214 | 37.0548 | ETL.9020 | 40764387 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114761264 | Q2 | ORO LOMA-CANAL #1 018/008 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 018/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-14 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.713684 | 37.0549 | ETL.9020 | 40873774 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114761269 | Q2 | ORO LOMA-CANAL #1 019/003 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 019/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-14 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.724967 | 37.0551 | ETL.9020 | 40646030 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114761501 | Q2 | ORO LOMA-CANAL #1 019/013 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 019/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-14 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.735954 | 37.0553 | ETL.9020 | 40661653 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114761599 | Q2 | ORO LOMA-CANAL #1 019/016 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 019/016 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2020-07-09 |  |  | 2021-04-14 | 2021-04-14 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.739542 | 37.0553 | ETL.9020 | 40821621 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114762044 | Q2 | ORO LOMA-CANAL #1 020/005 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 020/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-09 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-15 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.745276 | 37.0554 | ETL.9020 | 40764071 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114768995 | Q2 | ORO LOMA-CANAL #1 020/007 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 020/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.747641 | 37.0555 | ETL.9020 | 40806246 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114769661 | Q2 | ORO LOMA-CANAL #1 021/006 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 021/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.764302 | 37.0558 | ETL.9020 | 40806403 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114769890 | Q2 | ORO LOMA-CANAL #1 021/011 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 021/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-15 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.770073 | 37.0559 | ETL.9020 | 40582360 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CDFW | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114770637 | Q2 | ORO LOMA-CANAL #1 023/003 RPLC POLE | 31402077 | ORO LOMA-CANAL #1 | 023/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2021-05-31 |  |  | 2021-04-16 | 2021-04-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.794611 | 37.0563 | ETL.9020 | 40646037 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114770742 | Q2 | ORO LOMA-CANAL #1 023/005 RPLC POLE | 31402077 | ORO LOMA-CANAL #1 | 023/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2021-05-31 |  |  | 2021-04-16 | 2021-04-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.797091 | 37.0563 | ETL.9020 | 40747805 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114773656 | Q2 | ORO LOMA-CANAL #1 23/012 RPL STBD POLE | 31402077 | ORO LOMA-CANAL #1 | 023/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-11 | 2021-05-31 |  |  | 2021-04-16 | 2021-04-16 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.804896 | 37.0565 | ETL.9020 | 40688764 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114773706 | Q2 | ORO LOMA-CANAL #1 024/004 RPL STBD POLE | 31402077 | ORO LOMA-CANAL #1 | 024/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-11 | 2021-05-31 |  |  | 2021-04-16 | 2021-04-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.812653 | 37.0572 | ETL.9020 | 40747826 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114773736 | Q2 | ORO LOMA-CANAL #1 024/006 RPLC STBD POLE | 31402077 | ORO LOMA-CANAL #1 | 024/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-11 | 2021-05-31 |  |  | 2021-04-17 | 2021-04-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.81493 | 37.0572 | ETL.9020 | 40823183 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114791671 | Q2 | ORO LOMA-CANAL #1 013/015 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 013/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-02 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-10 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.635456 | 37.0526 | ETL.9020 | 40747797 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114792562 | Q2 | IGNACIO-S.RAFAEL#3 7/148 REPL O/L POLE | 31404626 | IGNACIO-SAN RAFAEL #3 NF | 007/148 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-17 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.523508 | 37.9742 | ETL.1860 | 40811035 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114796313 | Q2 | CLEAR LAKE-KONOCTI 15/00 REPL NG POLE | 31404612 | CLEAR LAKE-KONOCTI | 015/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-17 | 2021-05-31 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.856964 | 38.9822 | ETL.6852 | 40587043 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-02-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114800273 | Q2 | EXCHEQUER-LE GRAND 027/001 RPL POLE | 31394006 | EXCHEQUER-LE GRAND | 027/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-19 | 2021-05-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.270741 | 37.2115 | ETL.1560 | 40594871 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114800289 | Mar | COTTONWOOD #1 B035/456 SWIW NG REPA | 43747300 | COTTONWOOD #1 | B035/456 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-19 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.189412 | 39.9352 | ETL.6620 | 42578800 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-04-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114810459 | Q2 | COLEMAN-COTTONWOOD 0/018 SWIS NG REPA | 43746654 | COLEMAN-COTTONWOOD | 000/018 | ICE | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-12 | 2019-07-12 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.139721 | 40.4087 | ETL.6430 | 44419030 | Switch-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 623 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114837253 | Not Scheduled | TAFT-ELK HILLS 70KV 1/19 SEPARATE DISTRO | 31404130 | TAFT-ELK HILLS | 001/019 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP |  |  |  | Distribution |  | '-119.482981 | 35.1489 | ETL.9220 | 40609377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114837692 | Feb | HUMBOLDT BAY-RIO DELL JCT 10/8 RPLC POLE | 31404621 | HUMBOLDT BAY-RIO DELL JCT | 010/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-26 | 2020-07-26 | 2021-02-08 | 2021-02-10 | 2021-02-10 | 2021-02-08 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.197485 | 40.6373 | ETL.7100 | 40860998 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838107 | Q2 | ATWATER-LIVINGSTON-MERCED 21/005 rplc pl | 31402129 | ATWATER-MERCED | 021/005 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.759935 | 37.3615 | ETL.1030 | 40746673 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838160 | Q2 | ATWATER-LIVINGSTON-MERCED 21/4A RPL POLE | 31402129 | ATWATER-MERCED | 021/004A | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.759934 | 37.3606 | ETL.1030 | 40576639 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838161 | Q2 | ATWATER-LIVINGSTON-MERCED 21/4 RPL POLE | 31402129 | ATWATER-MERCED | 021/004 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.759722 | 37.3605 | ETL.1030 | 40762822 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838162 | Q2 | ATWATER-LIVINGSTON-MERCED 21/3 RPL POLE | 31402129 | ATWATER-MERCED | 021/003 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.758757 | 37.3605 | ETL.1030 | 40644995 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838163 | Q2 | ATWATER-LIVINGSTON-MERCED 21/2 RPL POLE | 31402129 | ATWATER-MERCED | 021/002 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.757535 | 37.3605 | ETL.1030 | 40647809 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838164 | Q2 | ATWATER-LIVINGSTON-MERCED 21/1 RPL POLE | 31402129 | ATWATER-MERCED | 021/001 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.756354 | 37.3605 | ETL.1030 | 40594361 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838165 | Q2 | ATWATER-LIVINGSTON-MERCED 21/0 RPL POLE | 31402129 | ATWATER-MERCED | 021/000 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.755148 | 37.3605 | ETL.1030 | 40582611 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838166 | Q2 | ATWATER-LIVINGSTON-MERCED 20/14 RPL POLE | 31402129 | ATWATER-MERCED | 020/014 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.753925 | 37.3605 | ETL.1030 | 40764912 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838168 | Q2 | ATWATER-LIVINGSTON-MERCED 20/13 RPL POLE | 31402128 | ATWATER-MERCED | 020/013 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.752718 | 37.3605 | ETL.1030 | 40644992 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838169 | Q2 | ATWATER-LIVINGSTON-MERCED 20/12 RPL POLE | 31402128 | ATWATER-MERCED | 020/012 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.751517 | 37.3605 | ETL.1030 | 40677061 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838190 | Q2 | ATWATER-LIVINGSTON-MERCED 20/11 RPL POLE | 31402128 | ATWATER-MERCED | 020/011 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.750287 | 37.3605 | ETL.1030 | 40581436 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838191 | Q2 | ATWATER-LIVINGSTON-MERCED 20/10 RPL POLE | 31402128 | ATWATER-MERCED | 020/010 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.749111 | 37.3605 | ETL.1030 | 40608973 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838192 | Q2 | ATWATER-LIVINGSTON-MERCED 20/9 RPL POLE | 31402128 | ATWATER-MERCED | 020/009 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.747906 | 37.3605 | ETL.1030 | 40862991 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838193 | Q2 | ATWATER-LIVINGSTON-MERCED 20/8 RPL POLE | 31402128 | ATWATER-MERCED | 020/008 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.746692 | 37.3605 | ETL.1030 | 40868704 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838196 | Q2 | ATWATER-LIVINGSTON-MERCED 20/7 RPL POLE | 31402128 | ATWATER-MERCED | 020/007 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.745514 | 37.3605 | ETL.1030 | 40805415 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838198 | Q2 | ATWATER-LIVINGSTON-MERCED 20/6 RPL POLE | 31402128 | ATWATER-MERCED | 020/006 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.744294 | 37.3605 | ETL.1030 | 40817376 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838199 | Q2 | ATWATER-LIVINGSTON-MERCED 20/4 RPL POLE | 31402128 | ATWATER-MERCED | 020/004 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.741697 | 37.3605 | ETL.1030 | 40759520 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838261 | Q2 | ATWATER-LIVINGSTON-MERCED 20/1 RPL POLE | 31402127 | ATWATER-MERCED | 020/001 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.738223 | 37.3605 | ETL.1030 | 40597106 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838262 | Q2 | ATWATER-LIVINGSTON-MERCED 20/0 RPL POLE | 31402127 | ATWATER-MERCED | 020/000 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.736985 | 37.3606 | ETL.1030 | 40582608 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838263 | Q2 | XTWATER-LIVINGSTON-MERCED 19/14 RPL POLE | 31402127 | ATWATER-MERCED | 019/014 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.735788 | 37.3605 | ETL.1030 | 40759518 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838264 | Q2 | ATWATER-LIVINGSTON-MERCED 19/13 RPL POLE | 31402127 | ATWATER-MERCED | 019/013 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.734581 | 37.3605 | ETL.1030 | 40644988 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838265 | Q2 | ATWATER-LIVINGSTON-MERCED 19/12 RPL POLE | 31402127 | ATWATER-MERCED | 019/012 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.733383 | 37.3605 | ETL.1030 | 40677055 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838267 | Q2 | ATWATER-LIVINGSTON-MERCED 19/11 RPL POLE | 31402127 | ATWATER-MERCED | 019/011 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.732178 | 37.3605 | ETL.1030 | 40581435 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838268 | Q2 | ATWATER-LIVINGSTON-MERCED 19/10 RPL POLE | 31402127 | ATWATER-MERCED | 019/010 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.730979 | 37.3605 | ETL.1030 | 40600765 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838269 | Q2 | ATWATER-LIVINGSTON-MERCED 19/09 RPL POLE | 31402127 | ATWATER-MERCED | 019/009 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.729771 | 37.3605 | ETL.1030 | 40858289 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838332 | Q2 | ATWATER-LIVINGSTON-MERCED 19/6 RPL POLE | 31402127 | ATWATER-MERCED | 019/006 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.726178 | 37.3605 | ETL.1030 | 40817374 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114838333 | Q2 | ATWATER-LIVINGSTON-MERCED 19/5 RPL POLE | 31402127 | ATWATER-MERCED | 019/005 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-05-13 | 2021-05-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.72496 | 37.3605 | ETL.1030 | 40746671 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114839337 | Q2 | LIVINGSTON-LIVINGSTN JCT 13/04 RPL POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 013/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2021-05-31 |  |  | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.807467 | 37.2054 | ETL.8920 | 40747891 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | NWR | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114839338 | Q2 | LIVINGSTN-LIVINGSTN JCT 012/16 RPL POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 012/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2021-05-31 |  |  | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.807467 | 37.2101 | ETL.8920 | 41116220 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | NWR | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114839598 | Q2 | LIVINGSTON-LIVINGSTON JCT 03/03 RPL POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 003/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2021-05-31 |  |  | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.76046 | 37.3139 | ETL.8920 | 40646084 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114839604 | Mar | CLEARLAKE-HOPLAND 9/12 REPL NG POLE | 31404610 | CLEAR LAKE-HOPLAND | 009/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2021-05-31 |  |  | 2021-03-30 | 2021-03-30 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.911522 | 38.9968 | ETL.6390 | 40699113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114839613 | Q2 | LIVINGSTON-LIVINGSTN JCT 04/03 RPLC POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 004/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-31 | 2023-07-31 |  |  | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.762898 | 37.3026 | ETL.8920 | 40661955 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114849117 | Q2 | PANOCHE-ORO LOMA 013/009 RPLC POLE | 31402122 | PANOCHE-ORO LOMA | 013/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-02 | 2023-08-02 |  |  | 2021-04-06 | 2021-04-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.602034 | 36.8439 | ETL.3240 | 40869997 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114850008 | Q2 | KEARNEY-BOWLES 000/010 RPL POLE | 31403396 | KEARNEY-BOWLES | 000/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-02 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.872845 | 36.6982 | ETL.8820 | 40607346 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114850055 | Q2 | KEARNEY-BOWLES 001/004 RPLC POLE | 31403396 | KEARNEY-BOWLES | 001/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-02 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.866545 | 36.6902 | ETL.8820 | 40764624 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114850072 | Q2 | KEARNEY-BOWLES 001/001 TRUSS POLE | 31403396 | KEARNEY-BOWLES | 001/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-02 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.868882 | 36.6932 | ETL.8820 | 40596315 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856303 | Mar | HENRIETTA-LEMOORE NAS:059/014 RPLC POLE | 31403111 | HENRIETTA-LEMOORE NAS | :059/014 | 93I | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2022-08-06 |  |  | 2021-03-16 | 2021-03-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905233 | 36.2568 | ETL.8780 | 40758601 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856539 | Q2 | KEARNEY-BOWLES 002/005 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.855147 | 36.6785 | ETL.8820 | 40764291 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856566 | Q2 | KEARNEY-BOWLES 002/000 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.860103 | 36.683 | ETL.8820 | 40584540 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856611 | Q2 | KEARNEY-BOWLES 002/003 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.857077 | 36.6803 | ETL.8820 | 40646442 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856614 | Q2 | KEARNEY-BOWLES 002/007 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.853541 | 36.6771 | ETL.8820 | 40821710 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856621 | Q2 | PANOCHE-ORO LOMA 017/000 RPLC POLE | 31402122 | PANOCHE-ORO LOMA | 017/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2023-08-06 |  |  | 2021-04-06 | 2021-04-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.629883 | 36.8822 | ETL.3240 | 40596842 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856637 | Q2 | KEARNEY-BOWLES 002/009 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.851124 | 36.6749 | ETL.8820 | 40871508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856654 | Q2 | KEARNEY-BOWLES 003/007 REPLACE POLE | 31403396 | KEARNEY-BOWLES | 003/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.841225 | 36.6657 | ETL.8820 | 40820309 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856658 | Q2 | KEARNEY-BOWLES 004/007 RPLC POLE | 31403396 | KEARNEY-BOWLES | 004/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.830156 | 36.6544 | ETL.8820 | 40820311 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856875 | Q2 | PANOCHE-ORO LOMA 017/006 REPLACE POLE | 31402122 | PANOCHE-ORO LOMA | 017/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2023-08-06 |  |  | 2021-04-06 | 2021-04-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.63781 | 36.8835 | ETL.3240 | 40805693 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114856969 | Q2 | PANOCHE-ORO LOMA 017/012 RPLC POLE | 31402122 | PANOCHE-ORO LOMA | 017/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2023-08-06 |  |  | 2021-04-06 | 2021-04-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.645736 | 36.8849 | ETL.3240 | 40648486 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114857247 | Mar | STROUD SW STA-STROUD 000/017 RPLC POLE | 31404129 | STROUD SW STA-STROUD | 000/017 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2018-08-06 | 2021-03-21 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.151686 | 36.5313 | ETL.9190 | 40806067 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 114857645 | Q2 | KEARNEY-BOWLES 005/003 RPL POLE | 31402120 | KEARNEY-BOWLES | 005/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-06 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.823092 | 36.6473 | ETL.8820 | 40646444 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114859423 | Mar | STROUD S S-SCHINDLER 06/007 RPL STB POLE | 31404128 | STROUD SW STA-SCHINDLER | 006/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-07 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-27 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.170488 | 36.5013 | ETL.9180 | 40815627 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114860644 | Mar | STROUD SW STA-SCHINDLER 006/008 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 006/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-07 | 2023-08-07 |  |  | 2021-03-27 | 2021-03-27 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.170462 | 36.5003 | ETL.9180 | 40872875 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114861216 | Q2 | KEARNEY-BOWLES 007/010 RPLC POLE | 31402120 | KEARNEY-BOWLES | 007/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-07 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.791681 | 36.6184 | ETL.8820 | 40609435 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114861245 | Q2 | KEARNEY-BOWLES 007/000 RPLC POLE | 31402120 | KEARNEY-BOWLES | 007/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-07 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.801467 | 36.6269 | ETL.8820 | 40607710 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114861291 | Q2 | KEARNEY-BOWLES 009/001 RPLC POLE | 31402120 | KEARNEY-BOWLES | 009/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-07 | 2021-05-31 |  |  | 2021-06-19 | 2021-06-15 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.775003 | 36.606 | ETL.8820 | 40596601 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114863139 | Mar | STROUD S S SCHINDLER 007/007 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 007/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-08 | 2023-08-08 |  |  | 2021-03-27 | 2021-03-27 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.16797 | 36.4876 | ETL.9180 | 40819988 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114863796 | Mar | GLENN #3_008/163 CNDW NG REPA | 43621091 | GLENN #3 | 008/163 | ICW | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-03 | 2021-08-03 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.00965 | 39.7474 | ETL.6940 | 40893865 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114864112 | Mar | CRSCNT SW STA-SCHNDLR 009/002 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 009/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-08 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-27 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139818 | 36.4848 | ETL.9180 | 40685909 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114864482 | Mar | CRSCNT SW STA-SCHNDLR 009/011 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 009/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-08 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-27 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139327 | 36.4762 | ETL.9180 | 40597553 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114864576 | Mar | CRSNT SW STA-SCHNDLR 009/012 RPLC POLE | 31404128 | STROUD SW STA-SCHINDLER | 009/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-08 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-27 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.13926 | 36.4752 | ETL.9180 | 40675104 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114883785 | Q2 | IGNACIO-ALTO 14/125 CLEAN INSULATORS | 43749531 | IGNACIO-ALTO | 014/125 | ICD | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-13 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.514064 | 37.9373 | ETL.7150 | 40651470 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-12 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114883821 | Not Scheduled | IGNACIO-ALTO 14/124 CLEAN INSULATORS | 43749531 | IGNACIO-ALTO | 014/124 | ICD | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-13 | 2019-08-13 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.514076 | 37.9375 | ETL.7150 | 40701420 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114886826 | Mar | GLENN #3 015/275 RPL X ARM | 31409743 | GLENN #3 | 015/275 | 93E | B | Pre-2020_(0) A and B Tags |  | 2018-08-14 | 2021-03-02 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.919297 | 39.796 | ETL.6940 | 40587302 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 114887464 | Q2 | MALIN-ROUND MTN #2 92/469 INSS NG REPL | 31438846 | MALIN-ROUND MTN #2 | 092/469 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2018-08-14 | 2022-08-14 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled - Internal |  | '-121.911872 | 40.8342 | ETL.6020 | 40869048 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-11-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114893598 | Feb | METCALF-GREEN VALLEY 9/63B BOND WIRE | 43659892 | METCALF-GREEN VALLEY | 009/063B | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-14 | 2021-05-31 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Internal Process | This section of the line is idle and not a fire risk. This tag will be addressed as part of a future capital project. | '-121.657777 | 37.1258 | ETL.2540 | 44181141 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Arcadis | 2019-03-20 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-03-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114896321 | Feb | METCALF-GREEN VALLEY 9/63B SW147 ADJ SW | 43659892 | METCALF-GREEN VALLEY | 009/063B | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-16 | 2021-05-31 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Internal Process | This section of the line is idle and not a fire risk. This tag will be addressed as part of a future capital project. | '-121.657777 | 37.1258 | ETL.2540 | 44181141 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Arcadis | 2019-03-20 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-03-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114907950 | Mar | GLENN #3 019/354 RPR STRW | 31410027 | GLENN #3 | 019/354 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-21 | 2021-05-31 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.946022 | 39.8461 | ETL.6940 | 40910207 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114909275 | Feb | PEASE-MARYSVILLE-HARTER 004/084 INSULT | 31403990 | PEASE-MARYSVILLE-HARTER | 004/084 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-21 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.580296 | 39.1699 | ETL.7770 | 40840155 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114910650 | Q2 | Parkway-Moraga 03/24 REPL BRKN INSUL | 31414411 | PARKWAY-MORAGA | 003/024 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-21 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.207411 | 38.086 | ETL.5930 | 40899171 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-03-25 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-03-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114911833 | Mar | GLENN #3 023/435 RPL STRW | 31410027 | GLENN #3 | 023/435 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-22 | 2021-05-31 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.988481 | 39.8935 | ETL.6940 | 40911984 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2021-02-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114912330 | Mar | GLENN #3 025/466 RPL STRW | 31410027 | GLENN #3 | 025/466 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-22 | 2021-05-31 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.00623 | 39.9114 | ETL.6940 | 40911560 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2021-02-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114914126 | Not Scheduled | T2 MALIN-RND MTN#2 72/364A MRKS MISS INS | 43621093 | MALIN-ROUND MTN #2 | 072/364A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2018-08-22 | 2022-08-22 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.80103 | 41.0756 | ETL.6020 | 41111835 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114914140 | Not Scheduled | T2 MALIN-RND MTN#2 71/359A CANCEL | 43621093 | MALIN-ROUND MTN #2 | 071/359A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2018-08-22 | 2023-08-22 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.788889 | 41.0846 | ETL.6020 | 40576661 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 114914465 | Not Scheduled | BRIGHTON-GRAND ISL #1 19/14 RPR FOOTING | 43748622 | BRIGHTON-GRAND ISLAND #1 | 019/146 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-23 | 2019-08-23 | [8 empty] | LATE | North Valley | Non-WSIP | [5 empty] | Circuit Based Scheduling | '-121.548352 | 38.3087 | ETL.1150 | 40820324 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114921800 | Feb | SLAC TAP 000/019 pole replacment | 31418454 | SLAC TAP (NO FLY) | 000/019 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-27 | 2021-05-31 |  |  | 2021-02-21 | 2021-02-21 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.19979 | 37.4133 | ETL.7221 | 40594869 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1 | 2019-03-01 | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114927782 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVEN 3/020 STUBS | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 003/020 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-29 | 2019-08-29 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-124.147943 | 40.8655 | ETL.6800 | 40616125 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114928343 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVEN 9/52 MEMBER | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 009/052 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-29 | 2024-08-29 | [8 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.195692 | 40.8 | ETL.6800 | 40700344 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114928417 | Q2 | ESSEX JCT-ARCATA-FAIRHAVEN 9/051 MEMBER | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 009/051 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-29 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.197183 | 40.8 | ETL.6800 | 40601243 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114928934 | Q2 | MERCED #1 004/013 RPLC POLE | 31406698 | MERCED #1 | 004/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-29 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.488198 | 37.2022 | ETL.9000 | 40661554 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114931218 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVEN 8/042 STUBS | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 008/042 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-30 | 2022-08-30 | [8 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.189689 | 40.8211 | ETL.6800 | 40700336 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114937999 | Not Scheduled | CANTUA TAP 001/001 REPLACE POLE | 31405867 | CANTUA TAP | 001/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.355397 | 36.4285 | ETL.3251 | 40589243 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114938002 | Not Scheduled | CANTUA TAP 001/002 REPLACE POLE | 31405867 | CANTUA TAP | 001/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.354088 | 36.4285 | ETL.3251 | 40648333 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114938070 | Not Scheduled | CANTUA TAP 001/007 RPLC POLE | 31405867 | CANTUA TAP | 001/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.347105 | 36.4285 | ETL.3251 | 40818556 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114938072 | Not Scheduled | CANTUA TAP 001/008 RPLC POLE | 31405867 | CANTUA TAP | 001/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.3458 | 36.4285 | ETL.3251 | 40865582 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114938112 | Q2 | MERCED #1 006/006 REPLACE POLE | 31406698 | MERCED #1 | 006/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2023-09-04 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.491972 | 37.18 | ETL.9000 | 40806318 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114938596 | Mar | GLENN #3 000/009 REFRAME | 31409743 | GLENN #3 | 000/009 | 93E | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2022-09-04 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.132429 | 39.7767 | ETL.6940 | 40822357 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114938956 | Mar | GLENN #3 001/021REPL INSUL | 31409372 | GLENN #3 | 001/021 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2021-05-31 |  |  | 2021-03-01 | 2021-02-24 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.1145 | 39.777 | ETL.6940 | 40618588 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114939258 | Q2 | MERCED #1 011/002 REPLACE POLE | 31406698 | MERCED #1 | 011/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-04 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473417 | 37.1283 | ETL.9000 | 40686712 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114941091 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVEN 7/37 STRUT | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 007/037 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-05 | 2019-09-05 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-124.177913 | 40.8273 | ETL.6800 | 40825227 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114941598 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVEN 6/35 STRUT | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 006/035 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-05 | 2023-09-05 | [8 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.176047 | 40.832 | ETL.6800 | 40769538 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114946593 | Mar | DEL MAR-ATLANTIC #2 001/028 RPL POLE | 31413325 | DEL MAR-ATLANTIC #2 | 001/028 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-06 | 2021-05-31 |  |  | 2021-03-03 | 2021-03-03 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.231716 | 38.79 | ETL.6170 | 40645364 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114946888 | Q2 | LS BNOS-LIVINGSTN JCT-CNL S0/3 RPLC POLE | 31406692 | LOS BANOS-LIVINGSTON JCT-CANAL | S000/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-06 | 2021-05-31 |  |  | 2021-04-20 | 2021-04-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.016346 | 37.076 | ETL.8940 | 40653025 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 | CDFW | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-10-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114946889 | Q2 | LS BNOS-LIVINGSTN JCT-CNL S0/2 RPLC POLE | 31406692 | LOS BANOS-LIVINGSTON JCT-CANAL | S000/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-06 | 2021-05-31 |  |  | 2021-04-20 | 2021-04-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.016544 | 37.076 | ETL.8940 | 40667417 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 | CDFW | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-10-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114949445 | Not Scheduled | SCHULTE SW STA-KASSON-MANTECA -115 kV_00 | 43632326 | SCHULTE SW STA-KASSON-MANTECA | 009/070 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-07 | 2019-09-07 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.45152 | 37.7203 | ETL.7472 | 40579835 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114959966 | Q2 | MERCED #1 012/001 RPLC POLE | 31406698 | MERCED #1 | 012/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-10 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47339 | 37.1147 | ETL.9000 | 40582260 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114960085 | Q2 | MERCED #1 012/004 RPLC POLE | 31406698 | MERCED #1 | 012/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-10 | 2023-09-10 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473373 | 37.112 | ETL.9000 | 40747705 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114960231 | Feb | SANGER-MALAGA 000/011 RPLC POLE | 31406693 | SANGER-MALAGA | 000/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-10 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.620579 | 36.7104 | ETL.3600 | 40582683 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114960286 | Feb | SANGER-MALAGA 000/016 RPLC POLE | 31406693 | SANGER-MALAGA | 000/016 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-10 | 2023-09-10 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.624819 | 36.7125 | ETL.3600 | 40806741 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114960288 | Q2 | MERCED #1 012/009 RPLC POLE | 31406698 | MERCED #1 | 012/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-10 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47334 | 37.1074 | ETL.9000 | 40858983 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114960350 | Q2 | MERCED #1 012/013 RPLC POLE | 31406698 | MERCED #1 | 012/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-10 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473377 | 37.1038 | ETL.9000 | 40645941 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114960941 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVEN 6/34 STRUT | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 006/034 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-05 | 2019-09-05 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-124.174939 | 40.835 | ETL.6800 | 40753489 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114961304 | Feb | KELLEY TAP 70KV 1/13 REPL POLE | 31406691 | KELLEY TAP | 001/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-02-25 | 2021-02-25 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.06495 | 35.0448 | ETL.9293 | 40760917 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  | Y - Prog Land | DWR | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114961883 | Q2 | MERCED #1 014/001 RPLC POLE | 31406698 | MERCED #1 | 014/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473523 | 37.0859 | ETL.9000 | 40582265 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114961888 | Q2 | MERCED #1 014/000 RPLC POLE | 31406698 | MERCED #1 | 014/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473348 | 37.0859 | ETL.9000 | 40583822 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114962656 | Not Scheduled | WESTLANDS #18 RA TAP 002/001 RPLC POLE | 31406697 | WESTLANDS #18 RA TAP | 002/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.262002 | 36.3739 | ETL.3252 | 40581640 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | DWR | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114962708 | Not Scheduled | WESTLANDS #18 RA TAP 002/003 RPLC POLE | 31406697 | WESTLANDS #18 RA TAP | 002/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2020-09-11 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-120.260861 | 36.3723 | ETL.3252 | 40645211 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 3 | DWR | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114962875 | Not Scheduled | WESTLANDS #18 RA TAP 003/006 RPLC POLE | 31406697 | WESTLANDS #18 RA TAP | 003/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.251668 | 36.3577 | ETL.3252 | 40805651 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 3 | DWR | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114963070 | Q4 | SMARTVILLE-MARYSVILLE 019/385 RPL POLE | 31409909 | SMARTVILLE-MARYSVILLE | 019/385 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-10-31 | 2021-09-01 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.579668 | 39.1468 | ETL.7980 | 40868724 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114963079 | Q2 | MERCED #1 017/012 RPLC POLE | 31406720 | MERCED #1 | 017/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473443 | 37.0319 | ETL.9000 | 40688748 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114963165 | Q2 | MERCED #1 017/013 RPLC POLE | 31406720 | MERCED #1 | 017/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47346 | 37.0307 | ETL.9000 | 40661923 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114963676 | Q2 | SMARTVILLE-MARYSVILLE 17/344 RPL AUTO SP | 43760141 | SMARTVILLE-MARYSVILLE | 017/344 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-04-13 | 2021-04-12 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.55554 | 39.1699 | ETL.7980 | 40602060 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114963941 | Q2 | SMARTVILLE-MARYSVILLE 17/336 RPL INSUL | 31409747 | SMARTVILLE-MARYSVILLE | 017/336 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-04-13 | 2021-04-12 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.55109 | 39.1735 | ETL.7980 | 40694087 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114967589 | Not Scheduled | TESLA-METCALF 006/025 RPL INSS | 31431935 | TESLA-METCALF | 006/025 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-12 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP |  |  |  | Internal Process | This is a 500kV line and it could not be done barehand because of the tower arm condition. The crew ruled that this w unsa | '-121.587724 | 37.6217 | ETL.6110 | 40790481 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | 2019-06-04 | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-06-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968158 | Not Scheduled | CARIBOU-PALERMO 27/221 INSS NG REPA | 43735847 | CARIBOU-PALERMO | :027/221 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40617147 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968341 | Not Scheduled | CARIBOU PALERMO 02/022 INSS NG REPL | 31413180 | CARIBOU-PALERMO | 002/022 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP |  |  |  | Field Operations |  | '-121.539982 | 39.4859 | ETL.3190 | 40726131 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968786 | Q2 | MERCED #1 019/011 RPLC POLE | 31406720 | MERCED #1 | 019/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2023-09-13 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473635 | 37.0046 | ETL.9000 | 40582275 | Structure-Wood | Rotten | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968803 | Q2 | MERCED #1 019/009 REPLC POLE | 31406720 | MERCED #1 | 019/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473667 | 37.0064 | ETL.9000 | 40871658 | Structure-Wood | Rotten | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968825 | Q4 | PEASE-MARYSVILLE-HARTER 7/150 RPL POLE | 31409617 | PEASE-MARYSVILLE-HARTER | 007/150 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-10-31 | 2021-09-01 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.58322 | 39.1421 | ETL.7770 | 40766646 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Encroachment Permit Needed | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968884 | Q2 | MERCED #1 019/014 REPL POLE | 31406720 | MERCED #1 | 019/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473615 | 37.0019 | ETL.9000 | 40747719 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114968910 | Not Scheduled | ESSEX JCT-ARCATA-FAIRHAVN 4/22 RPL TOWER | 31483156 | ESSEX JCT-ARCATA-FAIRHAVEN | 004/022 | 70S | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2019-09-13 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-124.154314 | 40.8639 | ETL.6800 | 40663729 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Eureka |  |  | 2019-07-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969488 | Q2 | MERCED #1 021/005 RPLC POLE | 31406720 | MERCED #1 | 021/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473817 | 36.9802 | ETL.9000 | 40763667 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969551 | Q2 | MERCED #1 021/004 REPLC POLE | 31406720 | MERCED #1 | 021/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473807 | 36.9811 | ETL.9000 | 40764358 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969562 | Q2 | MERCED #1 021/007 REPLC POLE | 31406720 | MERCED #1 | 021/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473762 | 36.9784 | ETL.9000 | 40806190 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969735 | Q2 | MERCED #1 022/007 RPLC POLE | 31406721 | MERCED #1 | 022/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473569 | 36.9639 | ETL.9000 | 40806192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969770 | Q2 | MERCED #1 022/006 RPLC POLE | 31406721 | MERCED #1 | 022/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47357 | 36.9648 | ETL.9000 | 40821545 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969916 | Q2 | MERCED #1 022/014 RPLC POLE | 31406721 | MERCED #1 | 022/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473442 | 36.9575 | ETL.9000 | 40747723 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114969993 | Q2 | MERCED #1 022/013 REPLC POLE | 31406721 | MERCED #1 | 022/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473463 | 36.9585 | ETL.9000 | 40661928 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970045 | Q2 | MERCED #1 022/016A REPLACE POLE | 31406721 | MERCED #1 | 022/016A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473424 | 36.9548 | ETL.9000 | 44400727 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970159 | Q2 | MERCED #1 023/003 RPLC POLE | 31406722 | MERCED #1 | 023/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473355 | 36.9521 | ETL.9000 | 40645961 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970469 | Q2 | MERCED #1 023/005 RPLC POLE | 31406722 | MERCED #1 | 023/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473312 | 36.9502 | ETL.9000 | 40747722 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970563 | Q2 | MERCED #1 023/004 REPLACE POLE | 31406722 | MERCED #1 | 023/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473337 | 36.9512 | ETL.9000 | 40747725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970641 | Q2 | MERCED #1 023/006 REPLC POLE | 31406722 | MERCED #1 | 023/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473285 | 36.9493 | ETL.9000 | 40806350 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970671 | Q2 | MERCED #1 023/007 RPLC POLE | 31406722 | MERCED #1 | 023/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473283 | 36.9484 | ETL.9000 | 40820201 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970682 | Q2 | MERCED #1 023/009 REPLC POLE | 31406722 | MERCED #1 | 023/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473242 | 36.9466 | ETL.9000 | 40858991 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970722 | Q2 | MERCED #1 023/011 RPLC POLE | 31406722 | MERCED #1 | 023/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473203 | 36.9448 | ETL.9000 | 40582286 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970790 | Q2 | MERCED #1 023/002A REPLACE POLE | 31406722 | MERCED #1 | 023/002A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473398 | 36.953 | ETL.9000 | 44400728 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970879 | Q2 | MERCED #1 022/009 RPLC POLE | 31406721 | MERCED #1 | 022/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473478 | 36.9621 | ETL.9000 | 40858989 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970946 | Q2 | MERCED #1 022/011 RPLC POLE | 31406721 | MERCED #1 | 022/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47352 | 36.9603 | ETL.9000 | 40582283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970962 | Q2 | MERCED #1 022/008 RPLC POLE | 31406721 | MERCED #1 | 022/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473507 | 36.963 | ETL.9000 | 40873086 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970963 | Q2 | MERCED #1 021/013 RPLC POLE | 31406720 | MERCED #1 | 021/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473685 | 36.973 | ETL.9000 | 40645957 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970971 | Q2 | MERCED #1 022/010 RPLC POLE | 31406721 | MERCED #1 | 022/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473553 | 36.9612 | ETL.9000 | 40583834 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114970981 | Q2 | MERCED #1 021/012 RPLCE POLE | 31406720 | MERCED #1 | 021/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473688 | 36.9739 | ETL.9000 | 40650217 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114977254 | Q2 | MERCED #1 023/012 RPLC POLES | 31406722 | MERCED #1 | 023/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-17 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473205 | 36.9439 | ETL.9000 | 40650229 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114978090 | Q2 | MERCED #1 024/006 RPLC POLE | 31406722 | MERCED #1 | 024/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-17 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.472502 | 36.9367 | ETL.9000 | 40806352 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114978112 | Q2 | MERCED #1 024/008 RPLC BURNT POLE | 31406722 | MERCED #1 | 024/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-17 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.471177 | 36.9352 | ETL.9000 | 40859090 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114978834 | Q2 | MERCED #1 031/015 RPLC POLE | 31412921 | MERCED #1 | 031/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-17 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.207305 | 36.9238 | ETL.9000 | 40747745 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114979164 | Q2 | MERCED #1 032/010 REPL POLE | 31412921 | MERCED #1 | 032/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-17 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.220478 | 36.9238 | ETL.9000 | 40583864 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114979955 | Not Scheduled | LOCKEFORD-LODI #3 001/032 rpl pole | 31418885 | LOCKEFORD-LODI #3 | 001/032 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  |  | 2021-03-31 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.187137 | 38.1016 | ETL.7450 | 40864302 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-09-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114980125 | Q2 | MERCED #1 034/006 REPLACE POLE | 31412921 | MERCED #1 | 034/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.250418 | 36.9239 | ETL.9000 | 40806364 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114980683 | Q2 | MERCED #1 035/013 RPLC POLE | 31412921 | MERCED #1 | 035/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.276888 | 36.9237 | ETL.9000 | 40645978 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114980824 | Feb | SANGER-MALAGA 004/007 RPLC POLE | 31406693 | SANGER-MALAGA | 004/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.679938 | 36.7143 | ETL.3600 | 40806523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114980889 | Feb | SANGER-MALAGA 005/010 RPLC POLE | 31406693 | SANGER-MALAGA | 005/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.691085 | 36.7084 | ETL.3600 | 40596887 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981455 | Q2 | MERCED #1 037/009 RPLC POLE | 31412921 | MERCED #1 | 037/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.308753 | 36.9237 | ETL.9000 | 40859010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981514 | Q2 | MERCED #1 037/015 RPLC POLE | 31412921 | MERCED #1 | 037/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.315183 | 36.9236 | ETL.9000 | 40747755 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981598 | Feb | SANGER-MALAGA 005/016 RPLC POLE | 31406693 | SANGER-MALAGA | 005/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.691038 | 36.7039 | ETL.3600 | 40806753 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981646 | Feb | SANGER-MALAGA 006/004 RPLC POLE | 31406693 | SANGER-MALAGA | 006/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.695435 | 36.7004 | ETL.3600 | 40748226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981651 | Feb | SANGER-MALAGA 006/005 RPLC POLE | 31406693 | SANGER-MALAGA | 006/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.696581 | 36.7004 | ETL.3600 | 40756735 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981681 | Q2 | MERCED #1 038/004 RPLC POLE | 31412921 | MERCED #1 | 038/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.321195 | 36.9236 | ETL.9000 | 40763983 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981712 | Q2 | MERCED #1 038/009 RPLC POLE | 31412921 | MERCED #1 | 038/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.32716 | 36.9236 | ETL.9000 | 40872071 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981859 | Q2 | HUMBOLDT #1 1/5 REPLACE POLE | 31409910 | HUMBOLDT #1 | 001/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-07 | 2020-07-07 |  |  | 2021-04-14 | 2021-04-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.092664 | 40.7905 | ETL.7113 | 40769620 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-02-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981875 | Q2 | HUMBOLDT #1 2/6 REPLACE POLE | 31409910 | HUMBOLDT #1 | 002/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-07 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-12 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.091234 | 40.8066 | ETL.7113 | 40809387 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-05 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2021-02-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981877 | Q2 | HUMBOLDT #1 4/5 REPLACE POLE | 31409910 | HUMBOLDT #1 | 004/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-18 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-12 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.080208 | 40.832 | ETL.7113 | 40751048 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2021-02-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114981879 | Q2 | HUMBOLDT #1 5/6 REPLACE POLE | 31409910 | HUMBOLDT #1 | 005/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-16 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-12 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.077988 | 40.8435 | ETL.7113 | 40827179 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-05 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2021-02-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982064 | Mar | HUMBOLDT BAY-HUMBOLDT #1 7/9 RPLC POLE | 31411534 | HUMBOLDT BAY-HUMBOLDT #1 | 007/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-07 | 2020-07-07 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-30 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.116503 | 40.7807 | ETL.7080 | 40860888 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-04-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982250 | Feb | HUMBOLDT-EUREKA 3/22 RPLC GUY POLE | 31475440 | HUMBOLDT-EUREKA | 003/022 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-06 | 2020-07-06 |  |  | 2021-02-11 | 2021-02-11 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.175959 | 40.7928 | ETL.7120 | 40658249 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-02-17 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-02-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982298 | Q2 | HUMBOLDT BAY-EUREKA 2/16 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 002/016 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2020-07-10 |  |  | 2021-04-10 | 2021-04-05 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.177995 | 40.7591 | ETL.7070 | 40809383 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982320 | Q2 | MERCED #1 039/010 RPLC POLE | 31412921 | MERCED #1 | 039/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.346317 | 36.9236 | ETL.9000 | 40606976 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982342 | Q2 | HUMBOLDT BAY-EUREKA 4/4 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2020-07-10 |  |  | 2021-04-10 | 2021-04-05 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.180214 | 40.7742 | ETL.7070 | 40751057 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982394 | Q2 | HUMBOLDT BAY-EUREKA 4/9 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-10 | 2020-07-10 |  |  | 2021-04-10 | 2021-04-05 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.180204 | 40.7791 | ETL.7070 | 40876284 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982483 | Q2 | HUMBOLDT BAY-EUREKA 4/12 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2020-06-27 |  |  | 2021-04-10 | 2021-04-05 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.178475 | 40.7806 | ETL.7070 | 40701275 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982514 | Q2 | HUMBOLDT BAY-EUREKA 4/13 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/013 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-06-27 | 2020-06-27 |  |  | 2021-04-10 | 2021-04-05 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.177165 | 40.7806 | ETL.7070 | 40668002 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114982703 | Q3 | KING CITY-COBURN #1 A19/315 REPLC POLE | 31398371 | KING CITY-COBURN #1 | A019/315 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-04-23 | 2021-05-31 | 2021-08-02 | 2021-08-13 | 2021-08-13 | 2021-08-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.311143 | 36.3961 | ETL.7320 | 40699583 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-03-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114983798 | Feb | SANGER-MALAGA 008/004 RPLC POLE | 31406693 | SANGER-MALAGA | 008/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.727292 | 36.6984 | ETL.3600 | 40759153 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114983910 | Feb | SANGER-MALAGA 008/006 RPLC POLE | 31406693 | SANGER-MALAGA | 008/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.727292 | 36.6972 | ETL.3600 | 40806760 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114984988 | Q2 | MERCED #1 040/007 RPLC POLE | 31412920 | MERCED #1 | 040/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.361878 | 36.9236 | ETL.9000 | 40806217 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114985541 | Q2 | MERCED #1 041/014 RPLC POLE | 31412920 | MERCED #1 | 041/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.388192 | 36.9235 | ETL.9000 | 40764371 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114985563 | Q2 | MERCED #1 042/000 RPLC POLE | 31412920 | MERCED #1 | 042/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.38939 | 36.9235 | ETL.9000 | 40606982 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114986867 | Q2 | MERCED #1 043/002 RPLC POLE | 31412920 | MERCED #1 | 043/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.409748 | 36.9234 | ETL.9000 | 40650296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114986885 | Not Scheduled | LOS BANOS-PACHECO 008/004 RPLC POLE | 31412756 | LOS BANOS-PACHECO | 008/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2023-09-20 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.189732 | 37.0745 | ETL.8960 | 40764182 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 | CDFW/ NWR | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-09-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114987072 | Q2 | MERCED #1 044/002 RPLC POLE | 31412920 | MERCED #1 | 044/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.427708 | 36.9234 | ETL.9000 | 40687524 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114987101 | Q2 | MERCED #1 044/005 RPLC POLE | 31412920 | MERCED #1 | 044/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.431312 | 36.9234 | ETL.9000 | 40763651 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114987104 | Q2 | MERCED #1 044/007 RPLC POLE | 31412920 | MERCED #1 | 044/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.433693 | 36.9234 | ETL.9000 | 40806222 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114987221 | Q2 | MERCED #1 044/012 RPLC POLE | 31412920 | MERCED #1 | 044/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.439692 | 36.9234 | ETL.9000 | 40687529 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114987383 | Q2 | MERCED #1 045/000 RPLC POLE | 31412920 | MERCED #1 | 045/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.443433 | 36.9234 | ETL.9000 | 40606985 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114987447 | Q2 | MERCED #1 045/005 RPLC POLE | 31412920 | MERCED #1 | 045/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-06-02 | 2021-05-17 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.449241 | 36.9234 | ETL.9000 | 40763653 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114997982 | Feb | DINUBA-OROSI 011/010 RPLC POLE | 31412754 | DINUBA-OROSI | 011/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-25 | 2021-05-31 |  |  | 2021-02-20 | 2021-02-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.250922 | 36.5362 | ETL.8610 | 44249966 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114998025 | Feb | DINUBA-OROSI 011/011 RPLC POLE | 31412754 | DINUBA-OROSI | 011/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-25 | 2021-05-31 |  |  | 2021-02-20 | 2021-02-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.250926 | 36.5353 | ETL.8610 | 40591606 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114998093 | Q2 | CENTERVILLE-TBL MTN-OROV 21/439 STRW ROT | 31418882 | CENTERVILLE-TABLE MTN-OROVILLE | 021/439 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-25 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.5727 | 39.5001 | ETL.6330 | 40815809 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-07-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 114998250 | Feb | DINUBA-OROSI 012/009 RPLC POLE | 31412754 | DINUBA-OROSI | 012/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-25 | 2021-05-31 |  |  | 2021-02-22 | 2021-02-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.256412 | 36.5297 | ETL.8610 | 40871129 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115002646 | Not Scheduled | T2 SPAULDING-SUMMIT 011/387 RPL POLE | 31445623 | SPAULDING-SUMMIT | 011/387 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2018-09-26 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.453502 | 39.3179 | ETL.8060 | 40876696 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115004849 | Q2 | MONTE RIO-FULTON :00/16 REPLC POLE | 31411002 | MONTE RIO-FULTON | :000/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.842292 | 38.4337 | ETL.7630 | 40811767 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-03 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115007714 | Not Scheduled | NICOLAUS-WILKINS SLOUGH 32/577 RPL POLE | 31410569 | NICOLAUS-WILKINS SLOUGH | 032/577 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-28 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.821794 | 38.8786 | ETL.7710 | 40875126 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115007760 | Not Scheduled | NICOLAUS-WILKINS SLOUGH 33/608 RP POLE | 31410569 | NICOLAUS-WILKINS SLOUGH | 033/608 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-28 | 2023-09-28 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.822054 | 38.9 | ETL.7710 | 40813718 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115013178 | Feb | DINUBA-OROSI 018/010 RPLC POLE | 31412755 | DINUBA-OROSI | 018/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-01 | 2021-05-31 |  |  | 2021-02-22 | 2021-02-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.357446 | 36.5237 | ETL.8610 | 40607894 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 8 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115013293 | Feb | DINUBA-OROSI 018/016 RPLC POLE | 31412755 | DINUBA-OROSI | 018/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-01 | 2021-05-31 |  |  | 2021-02-22 | 2021-02-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.363544 | 36.5237 | ETL.8610 | 40821028 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115015387 | Feb | DINUBA-OROSI 019/002 RPLC POLE | 31412755 | DINUBA-OROSI | 019/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-02 | 2021-05-31 |  |  | 2021-02-22 | 2021-02-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.366246 | 36.5237 | ETL.8610 | 40675083 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115015439 | Feb | DINUBA-OROSI 019/011 RPLC POLE | 31412755 | DINUBA-OROSI | 019/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-02 | 2020-10-02 |  |  | 2021-02-23 | 2021-02-23 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.37322 | 36.5237 | ETL.8610 | 40591615 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | RR | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115015461 | Feb | DINUBA-OROSI _019/006 RPLC POLE | 31412755 | DINUBA-OROSI | 019/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-02 | 2023-10-02 |  |  | 2021-02-23 | 2021-02-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.369238 | 36.5238 | ETL.8610 | 40821030 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115015540 | Feb | DINUBA-OROSI 019/014 RPLC POLE | 31412755 | DINUBA-OROSI | 019/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-02 | 2021-05-31 |  |  | 2021-02-23 | 2021-02-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.375626 | 36.5238 | ETL.8610 | 40771277 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115015605 | Feb | DINUBA-OROSI 019/018 RPLC POLE | 31412755 | DINUBA-OROSI | 019/018 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-02 | 2021-05-31 |  |  | 2021-02-24 | 2021-02-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.376749 | 36.522 | ETL.8610 | 40877893 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115015633 | Not Scheduled | T2 CRIBOU-PLERMO:013/102 REMV/REPLC BENT | 44051480 | CARIBOU-PALERMO | :013/102 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-10-02 | 2019-10-02 | [6 empty] | Check FDA | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.276601 | 39.9638 | ETL.3190 | 40738338 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115015692 | Not Scheduled | T2 CARIBOU-PALERMO :12/098 STRS NG REPA | 44051480 | CARIBOU-PALERMO | :012/098 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-10-02 | 2019-10-02 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.27494 | 39.9661 | ETL.3190 | 40910337 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115015921 | Feb | DINUBA-OROSI 020/005 RPLC POLE | 31412755 | DINUBA-OROSI | 020/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-02 | 2021-05-31 |  |  | 2021-02-24 | 2021-02-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.383193 | 36.5203 | ETL.8610 | 40770441 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115017828 | Not Scheduled | T2 CARIBOU-PARADISE 12/110 COND NG REPA | 43496873 | CARIBOU-PALERMO | 012/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-10-03 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115018418 | Q2 | WINDSOR-FITCH MTN 09/21 REPL POLE | 31413326 | FULTON #1 | 009/021 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.854528 | 38.6084 | ETL.6900 | 41119954 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115018482 | Q2 | Lakeville-Ignacio #1 00/02 REPL INSUL | 31414403 | LAKEVILLE-IGNACIO #1 | 000/002 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-26 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.57888 | 38.2513 | ETL.4940 | 40723454 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115032771 | Not Scheduled | MORRO BAY-SOLAR SW STA #1 9/38 PAINT | 43769237 | MORRO BAY-SOLAR SW STA #1 | 009/038 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2018-10-06 | 2022-10-06 | [7 empty] | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.69268 | 35.3796 | ETL.5300 | 40863432 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115033144 | Q3 | CARIBOU-PLUMAS JCT 018/001 SWIW NG REPA | 43538949 | CARIBOU-PLUMAS JCT | 018/001 | ICW | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-04 | 2022-10-04 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.901554 | 39.9347 | ETL.6290 | 40591674 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115034121 | Not Scheduled | STONE CORRAL TAP 006/006 RPLC POLE | 31414887 | STONE CORRAL TAP | 006/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-08 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.211067 | 36.4718 | ETL.8611 | 40821808 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115034200 | Not Scheduled | STONE CORRAL TAP 006/009 RPLC POLE | 31414887 | STONE CORRAL TAP | 006/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-08 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.207673 | 36.4718 | ETL.8611 | 40871143 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115035624 | Q3 | ESSEX JCT-ORICK - 60 kV_007/001 NEW GUY | 43683300 | ESSEX JCT-ORICK | 007/001 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-08 | 2019-10-08 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.047884 | 41.0032 | ETL.6810 | 40585285 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115035811 | Not Scheduled | T2 CRIBOU-PLERMO:013/109 RPR STUB LWR SW | 44051480 | CARIBOU-PALERMO | :013/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-10-08 | 2019-10-08 | [6 empty] | Check FDA | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.288193 | 39.9584 | ETL.3190 | 40738826 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115036370 | Not Scheduled | T2 CARIBOU-PALERMO-:013/110 B LEG BENT | 43740857 | CARIBOU-PALERMO | :013/110 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-10-09 | 2019-10-09 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.290832 | 39.9582 | ETL.3190 | 40642211 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115049768 | Q3 | ESSEX JCT-ORICK 1/006 RPL INS | 31418510 | ESSEX JCT-ORICK | 001/006 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-10 | 2019-10-10 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.033909 | 40.9268 | ETL.6810 | 40809342 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115052312 | Q2 | VACA-BAHIA 33/182 REPL BTM BRACES | 43761053 | VACA-BAHIA | 033/182 | ICJ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-11 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.137523 | 38.0822 | ETL.5810 | 40592024 | Bay Water-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 510 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-02-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115052467 | Q3 | ESSEX JCT-ORICK-4/9 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 004/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-11 | 2019-10-11 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.038868 | 40.9712 | ETL.6810 | 40861283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115052572 | Q3 | ESSEX JCT-ORICK-4/11 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 004/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-11 | 2019-10-11 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.038202 | 40.9727 | ETL.6810 | 40601263 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115057175 | Q2 | CENTERVILLE-TBL MTN OROV 018/357 CNDW NG | 43621288 | CENTERVILLE-TABLE MTN-OROVILLE | 018/357 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-12 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.585873 | 39.5408 | ETL.6330 | 40721132 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115059513 | Q3 | ESSEX JCT-ORICK-5/0 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 005/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-15 | 2019-10-15 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.037336 | 40.9758 | ETL.6810 | 40616175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115059578 | Q3 | ESSEX JCT-ORICK_5/2_INSTALL ANCHOR | 31418514 | ESSEX JCT-ORICK | 005/002 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-15 | 2019-10-15 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.037124 | 40.9777 | ETL.6810 | 40658062 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115059900 | Q3 | ESSEX JCT-ORICK-6/4 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 006/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-15 | 2019-10-15 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.041536 | 40.9942 | ETL.6810 | 40751020 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-14 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115063155 | Feb | ESSEX JCT-ARCATA-FAIRHAVEN-:3/6 WP RPR | 43509319 | ESSEX JCT-ARCATA-FAIRHAVEN | :003/006 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-16 | 2021-05-31 |  |  | 2021-02-05 | 2021-01-25 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.6800 | 44300540 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-06-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-06-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115063178 | Q3 | EI ESSEX JCT-ORICK 6/1 RPL PL | 31440270 | ESSEX JCT-ORICK | 006/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-15 | 2019-10-15 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.040465 | 40.9909 | ETL.6810 | 40601266 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115063224 | Q3 | ESSEX JCT-ORICK-5/1 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 005/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-15 | 2019-10-15 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.037246 | 40.9768 | ETL.6810 | 40601264 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115066698 | Mar | DIABLO-MIDWAY#3 500KV 64/262 REPL INSULS | 31414035 | DIABLO-MIDWAY #3 | 064/262 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-17 | 2021-05-31 |  |  | 2021-03-12 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.770437 | 35.3225 | ETL.5980 | 40682337 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-05-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115067216 | Mar | DIABLO-MIDWAY#3 500KV 64/260 REPL INSULS | 31414035 | DIABLO-MIDWAY #3 | 064/260 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-17 | 2021-05-31 |  |  | 2021-03-12 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.77672 | 35.3193 | ETL.5980 | 40586619 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-05-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115069615 | Feb | CHEVRON (LOST HILLS) TAP 2/37 REPL POLE | 31414883 | CHEVRON (LOST HILLS) TAP | 002/037 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-18 | 2021-05-31 |  |  | 2021-02-24 | 2021-02-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.830054 | 35.7115 | ETL.8472 | 40702607 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 6 | BLM | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-01-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115070110 | Feb | CHEVRON (LOST HILLS)TAP 11/174 REPL POLE | 31414883 | CHEVRON (LOST HILLS) TAP | 011/174 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-18 | 2021-05-31 |  |  | 2021-02-24 | 2021-02-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.742999 | 35.6227 | ETL.8472 | 40826701 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115070882 | Q2 | T2 CNTRVLE-TBL MTN-ORO 7/154 RPL STRW NG | 31416811 | CENTERVILLE-TABLE MTN-OROVILLE | 007/154 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-10-18 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.636215 | 39.6796 | ETL.6330 | 40824065 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115077396 | Not Scheduled | MENDO-REDBUD 48/235 REPL FLSH INSUL | 31505573 | MENDOCINO-REDBUD | 048/235 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-18 | 2019-10-18 | [8 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.979702 | 39.2025 | ETL.2410 | 40778624 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115077617 | Mar | T2 PLACER-DEL MAR 0/017 RPL POLE | 31416815 | PLACER-DEL MAR | 000/017 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-10-22 | 2019-10-22 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.095172 | 38.8924 | ETL.7800 | 40606312 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115077693 | Mar | T2 DIABLO-MIDWAY #2 36/148 REPL INSULS | 31415341 | DIABLO-MIDWAY #2 | 036/148 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2018-10-17 | 2021-05-31 | 2021-03-08 | 2021-03-10 | 2021-03-10 | 2021-03-08 |  |  |  | TR2 | LATE | South | Non-WSIP |  |  |  |  | Estimating | Diablo imposed clearance constraints; tag requires additional time to prepare a job package because it exceeds PG&E maximum standard 50kip rated insulators; | '-120.219166 | 35.1747 | ETL.5970 | 40887903 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115080560 | Mar | T2 PLACER-DEL MAR-000/015 REPLACE POLE | 31416815 | PLACER-DEL MAR | 000/015 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-10-23 | 2019-10-23 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.093649 | 38.8936 | ETL.7800 | 40867710 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115080596 | Mar | T2 PLACER-DEL MAR-0/14 REPLAE LEG | 31416815 | PLACER-DEL MAR | 000/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-10-23 | 2019-10-23 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.09321 | 38.8939 | ETL.7800 | 40822785 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115080976 | Mar | DIABLO-MIDWAY#3 500KV 63/257 REPL INSULS | 31414035 | DIABLO-MIDWAY #3 | 063/257 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-23 | 2021-05-31 |  |  | 2021-03-12 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.786776 | 35.3141 | ETL.5980 | 40807914 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-05-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115084437 | Q2 | KONOCTI-EAGLE ROCK 07/15 RPL STRW | 31418884 | KONOCTI-EAGLE ROCK | 007/015 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-24 | 2021-05-31 |  |  | 2021-05-07 | 2021-05-07 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.756728 | 38.9132 | ETL.6861 | 40750940 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-03 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115085168 | Q2 | IGNACIO-ALTO 11/68 REPL FLSH INSUL | 31445562 | IGNACIO-ALTO | 011/068 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-24 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.525373 | 37.9683 | ETL.7150 | 40887385 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115089461 | Q3 | ESSEX JCT-ORICK 27/5 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 027/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-25 | 2019-10-25 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.086383 | 41.267 | ETL.6810 | 40769581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115093258 | Not Scheduled | HUMBOLDT BAY-HUMBOLDT#1 001/7 BENT STEEL | 43720602 | HUMBOLDT BAY-HUMBOLDT #1 | 001/007 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-26 | 2019-10-26 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-124.188031 | 40.7408 | ETL.1800 | 40818721 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Eureka |  |  | 2019-07-09 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115093363 | Not Scheduled | HUMBOLDT BAY-HUMBOLDT#1 001/00 SWAYS | 43720602 | HUMBOLDT BAY-HUMBOLDT #1 | 001/008 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-26 | 2019-10-26 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-124.184146 | 40.7423 | ETL.1800 | 40870925 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Eureka |  |  | 2019-07-11 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115097562 | Q2 | T2 CENTERVILLE-TBL MTN-OROV-8/166 RPL PL | 31416811 | CENTERVILLE-TABLE MTN-OROVILLE | 008/166 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-10-22 | 2019-10-22 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.63629 | 39.6701 | ETL.6330 | 40585932 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115097623 | Q3 | ESSEX JCT-ORICK 29/001 RPL POLE | 31460464 | ESSEX JCT-ORICK | 029/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-29 | 2019-10-29 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.070493 | 41.2891 | ETL.6810 | 40601290 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115097640 | Q3 | ESSEX JCT-ORICK 29/002 RPL INS | 31418510 | ESSEX JCT-ORICK | 029/002 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-29 | 2019-10-29 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.069234 | 41.2897 | ETL.6810 | 40700444 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115097669 | Q3 | ESSEX JCT-ORICK 23/001 RPL POLE | 31452193 | ESSEX JCT-ORICK | 023/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-23 | 2019-10-23 |  |  | 2021-07-24 | 2021-07-12 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.103795 | 41.2034 | ETL.6810 | 40585311 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115100588 | Not Scheduled | RAVENSWD-BAIR #1 006/041 HELI WASH |  | RAVENSWOOD-BAIR #1 | 006/041 | ICI | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.22554 | 37.4983 | ETL.3380 | 40586711 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115100725 | Not Scheduled | VACA-TESLA 30/126 RPL FOUNDATION | 43852492 | VACA-TESLA | 030/126 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2023-10-30 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.714349 | 38.0648 | ETL.6140 | 40814936 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115100728 | Not Scheduled | VACA-TESLA-500kV_029/124-PILES EXPOSED | 43852492 | VACA-TESLA | 029/124 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2023-10-30 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.7222 | 38.0682 | ETL.6140 | 40756868 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101318 | Not Scheduled | PITTSBURG-SAN MATEO 037/155 rust footngs |  | PITTSBURG-SAN MATEO | 037/155 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.162469 | 37.6143 | ETL.5463 | 44188722 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101343 | Not Scheduled | PITSBURG-SAN MATEO 037/156 crack foundat |  | PITTSBURG-SAN MATEO | 037/156 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.168649 | 37.6125 | ETL.5463 | 44188721 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101389 | Not Scheduled | PITSBURG-SAN MATEO 041/165 crack foundat |  | PITTSBURG-SAN MATEO | 041/165 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.224244 | 37.596 | ETL.5463 | 44188712 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101442 | Not Scheduled | PITSBURG-SAN MATEO 040/164 crack foundat |  | PITTSBURG-SAN MATEO | 040/164 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.218067 | 37.5978 | ETL.5463 | 44188713 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101449 | Not Scheduled | PITSBURG-SAN MATEO 039/159 crack foundat |  | PITTSBURG-SAN MATEO | 039/159 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.187181 | 37.607 | ETL.5463 | 44188718 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101450 | Not Scheduled | PITSBURG-SAN MATEO 040/162 crack foundat |  | PITTSBURG-SAN MATEO | 040/162 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.20571 | 37.6015 | ETL.5463 | 44188715 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101452 | Not Scheduled | PITSBURG-SAN MATEO 039/161 crack foundat |  | PITTSBURG-SAN MATEO | 039/161 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.199534 | 37.6033 | ETL.5463 | 44188716 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115101460 | Not Scheduled | PITTSBURG-SAN MATEO 039/160 rust footngs |  | PITTSBURG-SAN MATEO | 039/160 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.193358 | 37.6051 | ETL.5463 | 44188717 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115102458 | Not Scheduled | IGNACIO-STAFFORD A00/11 REPL NG POLE | 31469867 | ETL.1042.POLE.WOOD | A000/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2020-10-30 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.545948 | 38.0833 | ETL.1042 | 40617241 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115102799 | Not Scheduled | IGNACIO-STAFFORD A00/07 REPL MUD SIL | 43714573 | ETL.1042.POLE.WOOD | A000/007 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-10-30 | 2019-10-30 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.54409 | 38.0808 | ETL.1042 | 40811643 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115131007 | Not Scheduled | TABLE MTN-PEACHTON 007/140 STRW NG REPL | 31433711 | TABLE MTN-PEACHTON | 007/140 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-01 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.688767 | 39.4839 | ETL.8425 | 40590274 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115190209 | Q2 | BIOLA-GLASS-MADERA ?002/012 RPL POLE | 31415244 | GLASS-BIOLA-MADERA | ?002/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-01 | 2023-11-01 | 2021-04-09 | 2021-04-09 | 2021-04-09 | 2021-04-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.115018 | 36.831 | ETL.9350 | 40651286 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115190322 | Q2 | MENDOTA-SN JOAQUIN-HLM 010/012 RPL POLE | 31415256 | MENDOTA-SAN JOAQUIN-HELM | 010/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-01 | 2021-05-31 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.324008 | 36.6175 | ETL.8980 | 40685992 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115190542 | Q2 | MERCY SPRNGS S S CNL 016/010 REFRAME | 31415257 | LOS BANOS-CANAL-ORO LOMA | 016/010 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-01 | 2021-05-31 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.819348 | 36.9939 | ETL.8930 | 40637566 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115223165 | Q2 | MRCY SPRGS SW STA-CANAL-ORO LOMA-19/18 | 31415259 | LOS BANOS-CANAL-ORO LOMA | 019/018 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-01 | 2021-05-31 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-06 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.817857 | 37.0439 | ETL.8930 | 40859173 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115276519 | Q2 | CARTHRS-LEMRE NAS-CMDN :055/3 RPLC POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :055/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-06 | 2020-11-06 |  |  | 2021-04-02 | 2021-04-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905328 | 36.3247 | ETL.8550 | 40663059 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 70 | Q2 |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115276640 | Q2 | CARTHRS-LMRE NAS-CMDN :053/13 RPLC POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :053/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-06 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905268 | 36.3453 | ETL.8550 | 40656319 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115276739 | Mar | GUERNSEY-HENRIETTA 013/013 RPLC POLE | 31418450 | GUERNSEY-HENRIETTA | 013/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-06 | 2021-05-31 |  |  | 2021-03-13 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.66135 | 36.2259 | ETL.8720 | 40661432 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115276830 | Mar | GUERNSEY-HENRIETTA 013/014 RPLC POLE | 31418450 | GUERNSEY-HENRIETTA | 013/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-06 | 2021-05-31 |  |  | 2021-03-13 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.662393 | 36.2259 | ETL.8720 | 40747313 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115278094 | Not Scheduled | BRIGHTON-GRAND ISL #1 2/023 RPL CONN | 43742052 | BRIGHTON-GRAND ISLAND #1 | 002/023 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-06 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.408907 | 38.5088 | ETL.1150 | 40690737 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115279444 | Mar | GUERNSEY-HENRIETTA 016/001 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 016/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2023-11-07 |  |  | 2021-03-13 | 2021-03-12 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.70233 | 36.2256 | ETL.8720 | 40596024 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115280790 | Mar | GUERNSEY-HENRIETTA 016/002 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 016/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2021-05-31 |  |  | 2021-03-13 | 2021-03-12 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.703541 | 36.2256 | ETL.8720 | 44190842 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115318314 | Mar | GUERNSEY-HENRIETTA 017/015A RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 017/015A | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2023-11-07 |  |  | 2021-03-13 | 2021-03-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.737427 | 36.2255 | ETL.8720 | 40575820 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115318323 | Mar | GUERNSEY-HENRIETTA 017/015 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 017/015 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2023-11-07 |  |  | 2021-03-13 | 2021-03-12 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.736477 | 36.2255 | ETL.8720 | 40763594 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115319110 | Feb | GLENN #4 002/045 STRW ROTN REPL | 31418859 | GLENN #4 | 002/045 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-23 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.140945 | 39.8056 | ETL.8424 | 41104769 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115322692 | Not Scheduled | MORRO BAY-TEMPLETON 16/67 REPL INSUL | 31418426 | MORRO BAY-TEMPLETON | 016/067 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-08 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.681305 | 35.5551 | ETL.5933 | 40835880 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 10 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-05-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115322762 | Mar | GUERNSEY-HENRIETTA 018/007 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 018/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-08 | 2023-11-08 |  |  | 2021-03-13 | 2021-03-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.745552 | 36.2255 | ETL.8720 | 40821692 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115322825 | Mar | GUERNSEY-HENRIETTA 019/004 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 019/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-08 | 2023-11-08 |  |  | 2021-03-13 | 2021-03-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.758979 | 36.2256 | ETL.8720 | 40747324 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115322955 | Mar | GUERNSEY-HENRIETTA 019/009A rplc pole | 31415833 | GUERNSEY-HENRIETTA | 019/009A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-08 | 2021-05-31 |  |  | 2021-03-13 | 2021-03-13 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.765648 | 36.2257 | ETL.8720 | 40576957 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115323313 | Feb | FAIRHAVEN #1 000/002 REPLACE POLE | 31418857 | FAIRHAVEN #1 NF | 000/002 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2018-07-06 | 2021-03-31 | 2021-02-26 | 2021-02-27 | 2021-02-27 | 2021-02-26 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.196829 | 40.8008 | ETL.6850 | 40685935 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-22 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-12-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 115323781 | Not Scheduled | T2 CARIBOU-PALERMO :014/116 BENT LEG | 44051499 | CARIBOU-PALERMO | :014/116 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-08 | 2019-11-08 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.301792 | 39.9518 | ETL.3190 | 40811629 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115323881 | Q3 | ESSEX JCT-ARCATA-FAIRHVN :3/7C RPLC POLE | 31418855 | ESSEX JCT-ARCATA-FAIRHAVEN | :003/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-01 | 2020-08-01 |  |  | 2021-07-17 | 2021-07-16 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.6800 | 44300538 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-06-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115323888 | Feb | FAIRHAVEN #1 0/1B RPLC POL | 31418858 | FAIRHAVEN #1 NF | 000/001B | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-06 | 2020-07-06 | 2021-02-26 | 2021-02-27 | 2021-02-27 | 2021-02-26 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.195899 | 40.8007 | ETL.6850 | 40599067 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-22 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-12-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115324839 | Not Scheduled | RAVENSWD-AMES #1 004/031 RPL INSULATOR | 31435258 | RAVENSWOOD-AMES #1 | 004/031 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-09 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.077317 | 37.4481 | ETL.3360 | 40838064 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115324904 | Not Scheduled | RAVENSWD-AMES #1 004/032 RPL INSULATOR | 31435258 | RAVENSWOOD-AMES #1 | 004/032 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-09 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.074483 | 37.4472 | ETL.3360 | 40813462 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115335990 | Q3 | CARIBOU-PLUMAS JCT 017/003 CONN NG REPL | 43686351 | CARIBOU-PLUMAS JCT | 017/003 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-11 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP | [6 empty] | '-120.914667 | 39.9403 | ETL.6290 | 40656478 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115342023 | Not Scheduled | T2 CARIBOU-PALERMO _015/123 RUSTED BOLTS | 44051499 | CARIBOU-PALERMO | 015/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-13 | 2019-11-13 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115343528 | Not Scheduled | T2 CARIBOU-PALERMO 15/123 RPL STRS |  | CARIBOU-PALERMO | 015/123 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-13 | 2019-11-13 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344265 | Not Scheduled | T2 CARIBOU-PALERMO 10/088 LOOSE BOLT | 44051499 | CARIBOU-PALERMO | 010/088 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-13 | 2019-11-13 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.522492 | 39.5992 | ETL.3190 | 40867947 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344796 | Not Scheduled | T2 CARIBOU-PALERMO :000/008 BENT X | 44051499 | CARIBOU-PALERMO | :000/008 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344798 | Not Scheduled | T2 CARIBOU-PALERMO - 005/039 RPL HRDWARE | 43735847 | CARIBOU-PALERMO | :000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.147242 | 40.0864 | ETL.3190 | 44190134 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344799 | Not Scheduled | T2 CARIBOU-PALERMO -005/039 RPL HRDWARE | 43735847 | CARIBOU-PALERMO | :000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.149439 | 40.0846 | ETL.3190 | 44190135 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344820 | Not Scheduled | T2 CARIBOU-PALERMO :000/008 CONCRETE CAP | 44051499 | CARIBOU-PALERMO | :000/008 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344829 | Not Scheduled | T2 CARIBOU-PALERMO :003/022 D LEG BENT | 44051499 | CARIBOU-PALERMO | :003/022 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40910266 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344833 | Not Scheduled | T2 CARIBOU-PALERMO :001/010 SWAY A PAHSE | 44051499 | CARIBOU-PALERMO | :001/010 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.164829 | 40.0739 | ETL.3190 | 40910257 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115344835 | Not Scheduled | CARIBOU PALERMO_003/022 HRDS NG REPL | 43735847 | CARIBOU-PALERMO | :003/022 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-14 | 2019-11-14 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40920005 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115346203 | Mar | GUERNSEY-HENRIETTA ;020/007 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | ;020/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-14 | 2023-11-14 |  |  | 2021-03-13 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.654922 | 36.239 | ETL.8720 | 41198017 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115346438 | Not Scheduled | T2 CARIBOU-PALERMO :003/028 RPL BOLTS | 44051499 | CARIBOU-PALERMO | :003/028 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115347116 | Not Scheduled | T2 CARIBOU-PALERMO :2/020 RPR C LEG | 44051499 | CARIBOU-PALERMO | :002/020 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.18454 | 40.065 | ETL.3190 | 40910264 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115347117 | Not Scheduled | T2 CARIBOU-PALERMO :2/019 RPR BENT STEEL | 44051499 | CARIBOU-PALERMO | :002/019 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115347118 | Not Scheduled | T2 CARIBOU-PALERMO :1/012 RPL INS BOLT | 44051499 | CARIBOU-PALERMO | :001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.166469 | 40.0723 | ETL.3190 | 40912339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115347562 | Not Scheduled | T2 CARIBOU-PALERMO :4/37 BENT SWAY | 44051499 | CARIBOU-PALERMO | :004/037 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.216388 | 40.0451 | ETL.3190 | 40907002 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115347568 | Not Scheduled | T2 CARIBOU-PALERMO :5/039 SWAY-DIG OUT | 44051499 | CARIBOU-PALERMO | :005/039 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-14 | 2019-11-14 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.217637 | 40.0409 | ETL.3190 | 40910282 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115348822 | Not Scheduled | T2 CARIBOU-PALERMO-115 kV_003/027 Steel |  | CARIBOU-PALERMO | :003/027 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-15 | 2019-11-15 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.199707 | 40.0633 | ETL.3190 | 40910271 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115348823 | Not Scheduled | T2 CARIBOU-PALERMO :5/042 D LEG BENT | 44051499 | CARIBOU-PALERMO | :005/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-15 | 2019-11-15 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.218237 | 40.0358 | ETL.3190 | 40910285 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115350150 | Mar | CAMDEN-KINGSBURG 000/003 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2023-11-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.595015 | 36.4859 | ETL.8653 | 40652982 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350260 | Mar | CAMDEN-KINGSBURG 000/009 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.598153 | 36.4815 | ETL.8653 | 40864389 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350320 | Mar | CAMDEN-KINGSBURG 000/012 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2023-11-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.601861 | 36.4815 | ETL.8653 | 40667299 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350421 | Mar | CAMDEN-KINGSBURG 001/000 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.606246 | 36.4815 | ETL.8653 | 40606200 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350428 | Mar | CAMDEN-KINGSBURG 001/001 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.607655 | 36.4816 | ETL.8653 | 40595951 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350434 | Mar | CAMDEN-KINGSBURG 001/002 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2023-11-15 |  |  | 2021-03-06 | 2021-03-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.609065 | 36.4816 | ETL.8653 | 40667303 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350500 | Mar | CAMDEN-KINGSBURG 001/005 RPL POLE | 31418233 | CAMDEN-KINGSBURG | 001/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2023-11-15 |  |  | 2021-03-06 | 2021-03-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.613454 | 36.4816 | ETL.8653 | 40763508 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350513 | Mar | CAMDEN-KINGSBURG 001/006 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-03 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.61502 | 36.4816 | ETL.8653 | 40813105 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350515 | Mar | CAMDEN-KINGSBURG 001/007 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-03 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.616495 | 36.4816 | ETL.8653 | 40820074 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350532 | Mar | CAMDEN-KINGSBURG 001/008 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-03 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.617887 | 36.4816 | ETL.8653 | 40864858 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115350989 | Mar | CAMDEN-KINGSBURG 002/000 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-03 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.624817 | 36.4818 | ETL.8653 | 40594572 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115351023 | Mar | CAMDEN-KINGSBURG 002/002 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-04 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.626999 | 36.4819 | ETL.8653 | 40686226 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115351246 | Mar | CAMDEN-KINGSBURG 002/004 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-04 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.629794 | 36.4818 | ETL.8653 | 40755021 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115351258 | Not Scheduled | T2 CARIBOU-PALERMO :20/160 BENT SWAY | 43740857 | CARIBOU-PALERMO | :020/160 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-15 | 2019-11-15 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642284 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115351279 | Not Scheduled | CARIBOU PALERMO 020/160 HRDS NG REPL | 43735847 | CARIBOU-PALERMO | :020/160 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-11-15 | 2019-11-15 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642431 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115351335 | Mar | CAMDEN-KINGSBURG 002/007 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2020-11-15 |  |  | 2021-03-06 | 2021-03-04 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.633603 | 36.4819 | ETL.8653 | 40812388 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-11-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115351355 | Mar | CAMDEN-KINGSBURG 002/008 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2020-11-15 |  |  | 2021-03-06 | 2021-03-04 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.634726 | 36.4819 | ETL.8653 | 40872283 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115352894 | Mar | EAST DUBLIN (BART) TAP A003/086 RPL SWTC | 31418506 | EAST DUBLIN (BART) TAP | A003/086 | 93H | B | Pre-2020_(0) A and B Tags |  | 2018-11-16 | 2021-03-22 | 2021-03-20 | 2021-03-21 | 2021-03-21 | 2021-03-20 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.901118 | 37.7041 | ETL.7962 | 41112603 | Switch-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 115353654 | Not Scheduled | CARIBOU-PALERMO-002/018 REPL 4 CAPS | 44069801 | CARIBOU-PALERMO | 002/018 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-16 | 2020-11-16 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539864 | 39.4771 | ETL.3190 | 40867943 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115363064 | Not Scheduled | CARIBOU-PALERMO-002/025 BENT 90 OF CAGE | 44051499 | CARIBOU-PALERMO | 002/025 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-16 | 2019-11-16 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539987 | 39.4918 | ETL.3190 | 40758454 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115363101 | Not Scheduled | CARIBOU-PALERMO-001/012 RPR A/B CAPS | 44051499 | CARIBOU-PALERMO | 001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-16 | 2019-11-16 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.541011 | 39.4665 | ETL.3190 | 40674849 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115363206 | Not Scheduled | CARIBOU-PALERMO 003/034 RPR FOND | 44051499 | CARIBOU-PALERMO | 003/034 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-16 | 2019-11-16 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539981 | 39.5072 | ETL.3190 | 40762751 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115363271 | Not Scheduled | CARIBOU-PALERMO 003/029 RPR FOND | 44051499 | CARIBOU-PALERMO | 003/029 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-16 | 2019-11-16 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539991 | 39.4999 | ETL.3190 | 40864873 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115363274 | Not Scheduled | EI CARIBOU-PALERMO 3/035 RPR FOND | 44051499 | CARIBOU-PALERMO | 003/035 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-16 | 2019-11-16 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539983 | 39.5093 | ETL.3190 | 40765056 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115363354 | Not Scheduled | T2NT EI CRIBU-PLERM 4/42 INS MRKS | 44051499 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-11-16 | 2019-11-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115363635 | Not Scheduled | T2 CARIBOU-PALERMO 5/051 RPR FOND | 44051499 | CARIBOU-PALERMO | 005/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-16 | 2019-11-16 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.540481 | 39.5377 | ETL.3190 | 40591544 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115363696 | Not Scheduled | T2 CARIBOU-PALERMO - 115 kV_006/053 | 43586842 | CARIBOU-PALERMO | 006/053 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-16 | 2019-11-16 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.540497 | 39.5401 | ETL.3190 | 40660305 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375395 | Not Scheduled | T2 CARIBOU-PALERMO 12/108 RPL STRS |  | CARIBOU-PALERMO | 012/108 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-17 | 2019-11-17 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.511776 | 39.637 | ETL.3190 | 40867949 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375775 | Not Scheduled | T2 CARIBOU-PALERMO 11/096 RPL STRS |  | CARIBOU-PALERMO | 011/096 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-11-18 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.517387 | 39.6172 | ETL.3190 | 40816574 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375818 | Not Scheduled | T3NT CARIBOU-PALERMO 016/129 BENT SWAY | 44051499 | CARIBOU-PALERMO | 016/129 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-11-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.491351 | 39.6771 | ETL.3190 | 41162783 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375943 | Not Scheduled | T3 CARIBOU-PALERMO :036/288 MISSING BOLT | 43725390 | CARIBOU-PALERMO | :036/288 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-05-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.482728 | 39.7047 | ETL.3190 | 40867981 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375963 | Not Scheduled | T3 CARIBOU-PALERMO :034/278 BOLT REPR | 43725390 | CARIBOU-PALERMO | :034/278 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-05-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.480133 | 39.7207 | ETL.3190 | 40878263 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375966 | Not Scheduled | T3 CARIBOU-PLRMO :035/280 RPLC SWAY | 43740857 | CARIBOU-PALERMO | :035/280 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-18 | 2019-05-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.480864 | 39.7162 | ETL.3190 | 40618602 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115375974 | Not Scheduled | T3NT CARIBOU-PALERMO-:034/274 BENT SWAY | 44051499 | CARIBOU-PALERMO | :034/274 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-11-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.478839 | 39.7286 | ETL.3190 | 40758638 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115375977 | Not Scheduled | T3 CARIBOU-PALERMO :034/279 REPLC BOLTS | 43725390 | CARIBOU-PALERMO | :034/279 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-05-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.480326 | 39.7195 | ETL.3190 | 40867378 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115376014 | Not Scheduled | T3 CARIBOU-PALERMO :034/276 BENT SWAY | 43725390 | CARIBOU-PALERMO | :034/276 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-05-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40828377 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115376015 | Not Scheduled | T3 EI Caribou Plrmo 34/276 RPL CTTR KEY | 43725390 | CARIBOU-PALERMO | :034/276 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-18 | 2019-05-18 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40856088 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115376328 | Not Scheduled | BRIGHTON-GRAND ISL #2 12/100 RPR CONNECT | 43742054 | BRIGHTON-GRAND ISLAND #2 | 012/100 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-19 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.482521 | 38.3823 | ETL.1160 | 40633085 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115388448 | Mar | CAMDEN-KINGSBURG 003/007 RPL POLE | 31416230 | CAMDEN-KINGSBURG | 003/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-19 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.642925 | 36.4746 | ETL.8653 | 40812390 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115388735 | Not Scheduled | T3 EI CRIBOU-PLRM :033/268 RPR STRT | 43725390 | CARIBOU-PALERMO | :033/268 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-19 | 2019-05-19 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.477302 | 39.7381 | ETL.3190 | 40867979 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115388826 | Not Scheduled | T3 EI CARIBOU-PLRMO :032/260 BENTSWAY | 43725390 | CARIBOU-PALERMO | :032/260 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-19 | 2019-05-19 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.474651 | 39.7549 | ETL.3190 | 40599300 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115388828 | Not Scheduled | T3 EI CARIBOU-PLRMO :031/251A BENT SWAY | 43725390 | CARIBOU-PALERMO | :031/251A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-19 | 2019-05-19 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.460698 | 39.7661 | ETL.3190 | 41147754 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115388913 | Not Scheduled | T3 CARIBOU-PALERMO :031/256 BENT MEMB | 44051416 | CARIBOU-PALERMO | :031/256 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-19 | 2019-05-19 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115388920 | Not Scheduled | T3 EI CARIBOU-PALERMO :031/255 BENT SWAY | 43725390 | CARIBOU-PALERMO | :031/255 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-19 | 2019-05-19 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.464758 | 39.7615 | ETL.3190 | 40770937 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115388925 | Mar | GUERNSEY-HENRIETTA ;019/006 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | ;019/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2023-11-20 |  |  | 2021-03-13 | 2021-03-11 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.654918 | 36.2548 | ETL.8720 | 41198051 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115389151 | Feb | GOLD HILL-BELLOTA-LOCKEFORD 35/211H CONN | 43755513 | GOLD HILL-BELLOTA-LOCKEFORD | 035/211H | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2019-11-20 |  |  | 2021-02-17 | 2021-02-17 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.13459 | 38.6546 | ETL.1690 | 40743138 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-03-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115394486 | Q2 | TRINITY-MPL CRK-45/6 RMV PL BTT DEBR LFT | 43683556 | TRINITY-MAPLE CREEK | 045/006 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-11-20 | 2019-11-20 |  |  | 2021-04-17 | 2021-04-05 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.718597 | 40.7502 | ETL.8170 | 44565516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-03-15 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115397067 | Q2 | CRTHRS-LEMOORE NAS-CMDN :049/15 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :049/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905037 | 36.3659 | ETL.8550 | 40758446 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115401593 | Q2 | CRTHRS-LEMOORE NAS-CMDN :044/14 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :044/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.89606 | 36.434 | ETL.8550 | 40763084 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115401681 | Q2 | CRTHRS-LEMOORE NAS-CMDN :043/07 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :043/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896137 | 36.4538 | ETL.8550 | 40815563 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115401683 | Q2 | CARTHRS-LEMOORE NAS-CMDN :043/5 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :043/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896144 | 36.4559 | ETL.8550 | 40758432 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115401776 | Mar | CAMDEN-KINGSBURG 008/002 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 008/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.726279 | 36.4745 | ETL.8653 | 40688159 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115401822 | Mar | CAMDEN-KINGSBURG 008/005 RPL POLE | 31416230 | CAMDEN-KINGSBURG | 008/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.731631 | 36.4746 | ETL.8653 | 40763516 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115402371 | Feb | GOLD HILL-BELLOTA-LOCKEFORD 41/251 CONN | 43755513 | GOLD HILL-BELLOTA-LOCKEFORD | 041/251 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2019-11-20 |  |  | 2021-02-17 | 2021-02-17 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.143449 | 38.5698 | ETL.1690 | 40594112 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115402810 | Not Scheduled | REEDLEY OROSI 009/004 RPR PT WIRING | 43959939 | REEDLEY-OROSI | 009/004 | ICE | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.251182 | 36.5711 | ETL.9060 | 44670526 | Switch-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115402913 | Not Scheduled | T2 CARIBOU-PALERMO :0/6 RPR STRT | 44054700 | CARIBOU-PALERMO | :000/006 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.157122 | 40.0804 | ETL.3190 | 40828375 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402916 | Not Scheduled | T2 CARIBOU-PALERMO :3/30 RPR BENT MEMBER | 44054700 | CARIBOU-PALERMO | :003/030 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.205437 | 40.0561 | ETL.3190 | 40910274 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402941 | Not Scheduled | T2 CARIBOU-PALERMO :003/026 BENT MEMB | 44054700 | CARIBOU-PALERMO | :003/026 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.19843 | 40.0636 | ETL.3190 | 40910270 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402945 | Not Scheduled | T2 CARIBOU-PALERMO :1/13 RPR STRT | 44054700 | CARIBOU-PALERMO | :001/013 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.167509 | 40.072 | ETL.3190 | 40910258 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402946 | Not Scheduled | T2 CARIBOU-PALERMO :1/016 BENT STEEL | 44054700 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402980 | Not Scheduled | T2 CARIBOU-PALERMO :004/031 RPR STRT | 44054700 | CARIBOU-PALERMO | :004/031 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.206015 | 40.0557 | ETL.3190 | 40910275 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402981 | Not Scheduled | T2 CARIBOU-PALERMO :5/43 RPR STRT | 44054700 | CARIBOU-PALERMO | :005/043 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.218331 | 40.0326 | ETL.3190 | 40907003 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115402993 | Not Scheduled | T2 EI CARIBOU-PALERMO-:006/050 RPL HRDT | 44054700 | CARIBOU-PALERMO | :006/050 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.221018 | 40.0214 | ETL.3190 | 40910292 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115402995 | Not Scheduled | T2 CARIBOU-PALERMO :04/035 RPL INS | 31426476 | CARIBOU-PALERMO | :004/035 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-02-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115403009 | Not Scheduled | T2 CARIBOU-PALERMO :3/28 RPL BENT MEMBER | 44054700 | CARIBOU-PALERMO | :003/028 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-20 | 2019-11-20 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115403758 | Mar | CAMDEN-KINGSBURG 010/005 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 010/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-21 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-05 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.762395 | 36.4703 | ETL.8653 | 40764317 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115403850 | Mar | CAMDEN-KINGSBURG 000/013 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-15 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.603305 | 36.4815 | ETL.8653 | 40652981 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115404327 | Mar | RESERVE OIL TAP 018/003 RPLC POLE | 31418449 | RESERVE OIL TAP | 018/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-21 | 2021-05-31 |  |  | 2021-03-09 | 2021-03-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.654653 | 36.272 | ETL.8721 | 41217686 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115404561 | Mar | RESERVE OIL TAP 017/016B RPLC POLE | 31418449 | RESERVE OIL TAP | 017/016B | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-21 | 2023-11-21 |  |  | 2021-03-09 | 2021-03-09 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.653648 | 36.2765 | ETL.8721 | 40740115 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-11-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115408522 | Not Scheduled | DIABLO-GATES #1 500KV 12/52 REPL INSULS | 31403823 | DIABLO-GATES #1 | 012/052 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-06 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.773846 | 35.3629 | ETL.5960 | 40715277 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-04-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409182 | Q2 | CARTHRS-LEMRE NAS-CAMDN :42/15 RPL POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :042/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896167 | 36.4627 | ETL.8550 | 40763494 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409193 | Q2 | CARTHRS-LEMRE NAS-CAMDN :42/12 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :042/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2023-11-26 |  |  | 2021-04-02 | 2021-04-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896191 | 36.4656 | ETL.8550 | 40674880 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409268 | Q2 | CARTHRS-LEMRE NAS-CAMDN :40/19 RPL POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :040/019 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-04-02 | 2021-04-01 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.887418 | 36.483 | ETL.8550 | 40872848 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409742 | Q2 | CARTHRS-LEMRE NAS-CAMDN :39/9 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-31 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881568 | 36.4988 | ETL.8550 | 40867328 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409746 | Q2 | CARTHRS-LEMRE NAS-CAMDN :39/8 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-31 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881573 | 36.4999 | ETL.8550 | 40872271 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409747 | Q2 | CARTHRS-LEMRE NAS-CAMDN :39/7 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-31 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881539 | 36.5008 | ETL.8550 | 40815557 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115409748 | Q2 | CARTHRS-LEMRE NAS-CAMDN :39/5 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-31 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881527 | 36.5026 | ETL.8550 | 40758424 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410024 | Feb | GOLD HILL-BELLOTA-LOCKEFORD 48/293 CNT | 43755513 | GOLD HILL-BELLOTA-LOCKEFORD | 048/293 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-17 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.141602 | 38.4779 | ETL.1690 | 40659254 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410750 | Q2 | STOCKTONA-WEBER#3 AB1/057 RPLC GUY POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | AB001/057 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-15 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-09 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.267851 | 37.9605 | ETL.8140 | 40813770 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410752 | Q2 | STOCKTON A WEBER #3 3/85 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 003/085 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-14 | 2021-05-31 |  |  | 2021-04-12 | 2021-04-12 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.25457 | 37.9219 | ETL.8140 | 40588139 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410753 | Q2 | STOCKTON A-WEBER #3 2/70 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 002/070 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-14 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-15 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.263621 | 37.923 | ETL.8140 | 40812594 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410754 | Q2 | STOCKTON A WEBER #3 2/57 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 002/057 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-14 | 2021-05-31 |  |  | 2021-04-12 | 2021-04-12 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.268122 | 37.9286 | ETL.8140 | 40681297 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410755 | Q2 | STOCKTON A-WEBER #3 3/76 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 003/076 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-14 | 2021-05-31 |  |  | 2021-04-13 | 2021-04-13 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.262138 | 37.9203 | ETL.8140 | 40665909 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115410899 | Not Scheduled | T3 EI CARIBOU-PALERMO :006/054 BENT BRAC | 43725390 | CARIBOU-PALERMO | :006/054 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.224373 | 40.0128 | ETL.3190 | 40910296 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410955 | Not Scheduled | T3 EI CARIBOU-PALERMO :007/057 BENT SWAY | 43725390 | CARIBOU-PALERMO | :007/057 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.226794 | 40.0078 | ETL.3190 | 40910299 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410957 | Not Scheduled | T3 EI CARIBOU-PALERMO :011/089 BENT SWAY | 43725390 | CARIBOU-PALERMO | :011/089 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410959 | Not Scheduled | T3 EI CARIBOU-PALERMO :007/060 BENT LEG | 43725390 | CARIBOU-PALERMO | :007/060 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.231928 | 40.0059 | ETL.3190 | 40910302 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410961 | Not Scheduled | T3 EI CARIBOU-PALERMO :008/064 RPR STRT | 43725390 | CARIBOU-PALERMO | :008/064 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.239441 | 40.0064 | ETL.3190 | 40910306 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410965 | Not Scheduled | T2 CARIBOU-PALERMO :008/069 RPL INSS | 44304491 | CARIBOU-PALERMO | :008/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-26 | 2019-11-26 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.252392 | 40.0071 | ETL.3190 | 40920050 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115410966 | Not Scheduled | T3 EI CARBOU-PALERMO :011/087 BENT BRACE | 44054700 | CARIBOU-PALERMO | :011/087 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-26 | 2019-11-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.280057 | 39.9886 | ETL.3190 | 40910327 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115410968 | Not Scheduled | T3 CARIBOU-PALERMO :009/076 RPR LEGS | 44051416 | CARIBOU-PALERMO | :009/076 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.266062 | 40.0033 | ETL.3190 | 40910318 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410980 | Not Scheduled | T2 CARIBOU-PALERMO :009/072 WORN EYES | 43664533 | CARIBOU-PALERMO | :009/072 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-26 | 2019-11-26 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.258867 | 40.0049 | ETL.3190 | 40910314 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-02-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115410983 | Not Scheduled | T3 CARIBOU-PALERMO-:009/076 RPR COTT KEY | 44304458 | CARIBOU-PALERMO | :009/076 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.266062 | 40.0033 | ETL.3190 | 40910318 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115410986 | Not Scheduled | T3 CARIBOU-PALERMO :010/084 RPR INSS | 44304458 | CARIBOU-PALERMO | :010/084 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411013 | Not Scheduled | T3 CARIBOU-PALERMO :010/085 RPLC ARM | 43725390 | CARIBOU-PALERMO | :010/085 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.277044 | 39.9919 | ETL.3190 | 40910325 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411014 | Not Scheduled | T3 EI CARIBOU-PALERMO :009/077 BENT SWAY | 43725390 | CARIBOU-PALERMO | :009/077 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.266703 | 40.0021 | ETL.3190 | 40910319 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411016 | Not Scheduled | T3 CARIBOU-PALERMO-:010/084 RPLC EYE | 44304458 | CARIBOU-PALERMO | :010/084 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411018 | Not Scheduled | T3 CARIBOU-PALERMO :010/078 BENT MEMB | 44051416 | CARIBOU-PALERMO | :010/078 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.267244 | 40.0011 | ETL.3190 | 40907020 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411019 | Not Scheduled | T3 CARIBOU-PALERMO :010/078 RPL INSS |  | CARIBOU-PALERMO | :010/078 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.267244 | 40.0011 | ETL.3190 | 40916721 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115411026 | Not Scheduled | T3 CARIBOU-PALERMO :010/082 RPR STRUT | 44051416 | CARIBOU-PALERMO | :010/082 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.272037 | 39.994 | ETL.3190 | 40910323 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411043 | Not Scheduled | T3 CARIBOU-PALERMO :010/079 BENT MEMB | 44051416 | CARIBOU-PALERMO | :010/079 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.268442 | 39.9988 | ETL.3190 | 40910320 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115411519 | Q2 | STOCKTON A-WEBER#3 3/80 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 003/080 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-14 | 2021-05-31 |  |  | 2021-04-14 | 2021-04-14 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.260288 | 37.9205 | ETL.8140 | 40812596 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115411574 | Q2 | STOCKTON A-WEBER#3 A001/44 RPLC POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | A001/044 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-15 | 2022-08-15 |  |  | 2021-04-16 | 2021-04-16 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.274412 | 37.9574 | ETL.8140 | 40864344 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115411590 | Q2 | STOCKTON A-WEBER#3 AB001/49 RPLC POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | AB001/049 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-08-15 | 2021-05-31 |  |  | 2021-04-19 | 2021-04-19 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.270074 | 37.9582 | ETL.8140 | 40643292 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115411593 | Mar | SUTERHME SW ST-LKFRD-LODI 9/138 RPL PL | 31418856 | ETL.8068.POLE.WOOD | 009/138 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-11 | 2021-05-31 |  |  | 2021-03-02 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.254066 | 38.1892 | ETL.8068 | 40807971 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115411640 | Not Scheduled | SUTER HOME SWSTA-LCKFRD-LODI 3/40 RPLC | 31418856 | ETL.8068.POLE.WOOD | 003/040 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-21 | 2020-09-21 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.17849 | 38.1596 | ETL.8068 | 40652303 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Released | CVFPB | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115411643 | Mar | SUTR HME SW ST-LCKFRD-LDI 2/33 RPLC PL | 31418856 | ETL.8068.POLE.WOOD | 002/033 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-21 | 2021-05-31 |  |  | 2021-03-01 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.175944 | 38.1519 | ETL.8068 | 40811808 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115411648 | Mar | SUTER HOME SWSTA-LCKFRD-LODI 10/151 RPLC | 31418856 | ETL.8068.POLE.WOOD | 010/151 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-03-04 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26223 | 38.1877 | ETL.8068 | 40666052 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115412411 | Not Scheduled | IGNACIO-SN RAFAEL#1 07/39 REP ACC RD | 31486234 | IGNACIO-SAN RAFAEL #1 | 007/039 | 71Y | F | Pre-2020_(5b) On structure in bucket 5 |  | 2018-11-27 | 2020-11-27 |  |  |  | 2021-07-15 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.494875 | 37.9845 | ETL.1850 | 40863149 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115412486 | Feb | GLENN # 4 02/053_REPL INSUL | 31418507 | GLENN #4 | 002/053 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-27 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-23 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.140943 | 39.8118 | ETL.8424 | 41176180 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115412728 | Mar | SUTER HOME SWTA-LKFRD-LDI 10/153 RPL PL | 31418856 | ETL.8068.POLE.WOOD | 010/153 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2022-09-13 |  |  | 2021-03-04 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26219 | 38.1858 | ETL.8068 | 40754293 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115412756 | Mar | SUTER HOME SWSTA-LCKFRD-LODI 10/159 RPL | 31418856 | ETL.8068.POLE.WOOD | 010/159 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-03-08 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.262044 | 38.1807 | ETL.8068 | 40588068 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115412790 | Mar | SUTTER HME SW STA-LCKFRD-LODI 10/163 RPL | 31418856 | ETL.8068.POLE.WOOD | 010/163 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-03-10 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261969 | 38.1777 | ETL.8068 | 40754295 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115412796 | Mar | SUTER HOME SW STA-LCKFRD-LODI 11/183 RPL | 31418856 | ETL.8068.POLE.WOOD | 011/183 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-12 | 2021-05-31 |  |  | 2021-03-11 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26152 | 38.1658 | ETL.8068 | 40665729 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115412984 | Not Scheduled | T2 CARIBOU-PALERMO :006/047 RPR STRT | 44054700 | CARIBOU-PALERMO | :006/047 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-27 | 2019-11-27 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.219269 | 40.0274 | ETL.3190 | 40910289 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115413018 | Mar | SUTR HME SWSTA-LCKFRD-LDI 11/186 RPL PLE | 31418856 | ETL.8068.POLE.WOOD | 011/186 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-12 | 2021-05-31 |  |  | 2021-03-12 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261447 | 38.164 | ETL.8068 | 40762864 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413117 | Mar | SUTER HM SWSTA-LCKFRDLODI 12/195G RPLC | 31430342 | ETL.8068.POLE.WOOD | 012/195 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-03-16 | 2021-03-15 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26132 | 38.1587 | ETL.8068 | 40588071 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413119 | Mar | SUTERHME SW ST-LKFRD-LDI 12/199 RPLC PL | 31430342 | ETL.8068.POLE.WOOD | 012/199 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-12 | 2021-05-31 |  |  | 2021-03-17 | 2021-03-17 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261262 | 38.1563 | ETL.8068 | 40768060 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413174 | Mar | SUTERHOME SWSTA-LCKFRD-LODI 12/203G RPLC | 31430342 | ETL.8068.POLE.WOOD | 012/203 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-13 | 2021-05-31 |  |  | 2021-03-18 | 2021-03-18 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261171 | 38.1537 | ETL.8068 | 40863950 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413238 | Mar | SUTERHOME SWSTA-LCKFD-LDI 12/215 RPR PL | 44610158 | ETL.8068.POLE.WOOD | 012/215 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-27 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261841 | 38.1472 | ETL.8068 | 40863952 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-12-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413303 | Mar | SUTER HM SW ST-LKFRD-LDI 12/217 RPL PL | 31430342 | ETL.8068.POLE.WOOD | 012/217 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-05 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261783 | 38.146 | ETL.8068 | 40603939 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413421 | Mar | SUTRHME SWSTALCKFRD-LDI 13/226 RPLC PL | 31430342 | ETL.8068.POLE.WOOD | 013/226 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-14 | 2021-05-31 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.260829 | 38.1402 | ETL.8068 | 40869735 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413424 | Mar | SUTERHOME SWSTA-LCKFRD-LODI 16/299 RPLC | 31430342 | ETL.8068.POLE.WOOD | 016/299 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-25 | 2020-09-25 |  |  | 2021-03-23 | 2021-03-23 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.405537 | 38.1896 | ETL.8068 | 40655530 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413467 | Mar | SUTERHOME SWSTA-LCKFRD-LODI 18/323 RPLC | 31430342 | ETL.8068.POLE.WOOD | 018/323 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-24 | 2021-05-31 |  |  | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.384251 | 38.1895 | ETL.8068 | 40863912 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413484 | Not Scheduled | T3 CARIBOU-PALERMO :010/081 SHOE BOL RPL | 43725390 | CARIBOU-PALERMO | :010/081 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-11-26 | 2019-05-26 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.271411 | 39.9963 | ETL.3190 | 40910322 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115413557 | Mar | SUTERHOME SW ST-LKFRD-LDI 18/327 RPL PL | 31430342 | ETL.8068.POLE.WOOD | 018/327 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-24 | 2021-05-31 |  |  | 2021-03-25 | 2021-03-25 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.380611 | 38.1894 | ETL.8068 | 40754252 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413559 | Mar | SUTERHOME SWSTA-LCKFRD-LODI 20/380 RPLC | 31430343 | ETL.8068.POLE.WOOD | 020/380 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-26 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.332588 | 38.1891 | ETL.8068 | 40768720 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413594 | Mar | SUTER HME SW ST-LKFRD-LDI 22/405 RPL PL | 31430343 | ETL.8068.POLE.WOOD | 022/405 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-19 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-26 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.308395 | 38.1891 | ETL.8068 | 40588034 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413623 | Mar | SUTER HM SWSTA-LCKFRD-LODI C17/305 RPLC | 31430343 | ETL.8068.POLE.WOOD | C017/305 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-18 | 2021-05-31 |  |  | 2021-03-29 | 2021-03-29 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.409373 | 38.197 | ETL.8068 | 40586694 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413626 | Mar | SUTER HM SWSTA-LCKFRD-LODI C21/395 RPLC | 31430343 | ETL.8068.POLE.WOOD | C021/395 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-27 | 2021-05-31 |  |  | 2021-03-30 | 2021-03-30 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.466846 | 38.2253 | ETL.8068 | 40608334 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413628 | Not Scheduled | LOCKEFORD-LODI #3 4/93 REPLACE POLE | 31418885 | LOCKEFORD-LODI #3 | 004/093 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-17 | 2020-09-17 |  |  |  | 2021-04-01 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.242574 | 38.1013 | ETL.7450 | 40613617 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413657 | Not Scheduled | LOCKEFORD-LODI #3 B008/164 RPLC POLE | 31418885 | LOCKEFORD-LODI #3 | B008/164 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-20 | 2021-05-31 |  |  |  | 2021-04-02 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.287556 | 38.0819 | ETL.7450 | 40666111 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-09-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115413703 | Not Scheduled | LOCKEFORD-LODI #3 B10/197 RPLC POLE | 31418885 | LOCKEFORD-LODI #3 | B010/197 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-09-26 | 2022-09-26 |  |  |  | 2021-04-05 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.290093 | 38.0576 | ETL.7450 | 40593615 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115414213 | Q2 | COBURN-OIL FIELDS #20 28/378 RPL POLE | 31418447 | COBURN-OIL FIELDS #2 | 028/378 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-27 | 2021-05-31 | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.863016 | 35.9909 | ETL.6420 | 40615517 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 5 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115414269 | Q2 | ARCATA-HUMBOLDT 7/5 RPLACE POLE | 31418678 | ARCATA-HUMBOLDT | 007/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-07-11 | 2020-07-11 |  |  | 2021-04-11 | 2021-04-10 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.08477 | 40.8652 | ETL.7110 | 40827173 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115417047 | Before Feb | T2 EXCHEQUER-YOSEMITE 11/33 COATING | 43825051 | EXCHEQUER-YOSEMITE | 011/033 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2018-11-28 | 2019-11-28 | 2020-11-03 | 2020-12-16 | 2020-12-16 | 2020-11-03 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.179863 | 37.5902 | ETL.8650 | 40660802 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 42 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115421866 | Before Feb | T2 EXCHEQUER-YOSEMITE 13/41 PAINT | 43726815 | EXCHEQUER-YOSEMITE | 013/041 | ICY | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2018-11-29 | 2019-11-29 | 2020-11-03 | 2020-12-16 | 2020-12-16 | 2020-11-03 |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | Non-WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with SB67 | '-120.151129 | 37.5908 | ETL.8650 | 40582619 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 38 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439242 | Not Scheduled | T3 EI CARIBOU-PALERMO :011/090 BENT MEMB | 44051416 | CARIBOU-PALERMO | :011/090 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-06-01 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.27741 | 39.9833 | ETL.3190 | 40910330 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439244 | Not Scheduled | T3 CARIBOU-PALERMO :11/91 RPR BENT MEMBE |  | CARIBOU-PALERMO | :011/091 | 70S | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-06-01 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.276852 | 39.9826 | ETL.3190 | 40912111 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439245 | Not Scheduled | T3 CARIBOU-PALERMO :012/095 BENT MEMB | 44051416 | CARIBOU-PALERMO | :012/095 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-06-01 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.274963 | 39.9723 | ETL.3190 | 40912114 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439247 | Not Scheduled | T2 CARIBOU-PALERMO :013/103 BENT MEMB | 44054700 | CARIBOU-PALERMO | :013/103 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.278836 | 39.963 | ETL.3190 | 40738339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439248 | Not Scheduled | T2 CARIBOU-PALERMO :013/106 BENT MEMB | 44054700 | CARIBOU-PALERMO | :013/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.283913 | 39.9602 | ETL.3190 | 40738342 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115439273 | Not Scheduled | T2 EI CARIBOU-PALERMO :14/114 RPR STRT | 44054700 | CARIBOU-PALERMO | :014/114 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.299352 | 39.9544 | ETL.3190 | 40738344 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439300 | Not Scheduled | T2 EI CARIBOU-PALERMO :014/111 RPR STRT | 43725390 | CARIBOU-PALERMO | :014/111 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.293251 | 39.9571 | ETL.3190 | 40642567 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439301 | Not Scheduled | T2 CARIBOU-PALERMO :14/110A RPR STRS | 44054700 | CARIBOU-PALERMO | :014/110A | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.29189 | 39.9578 | ETL.3190 | 41162771 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439304 | Not Scheduled | T2 CARIBOU-PALERMO :16/130 INS HRDT | 44054700 | CARIBOU-PALERMO | :016/130 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.318519 | 39.9331 | ETL.3190 | 40642212 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115439305 | Not Scheduled | T2 EI CARIBOU-PALERMO-:014/118 RPR CONS | 44304491 | CARIBOU-PALERMO | :014/118 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.304514 | 39.949 | ETL.3190 | 40738823 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439307 | Not Scheduled | T2 EI CARIBOU-PALERMO 14/118A RPR STRT | 44054700 | CARIBOU-PALERMO | 014/118A | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.304531 | 39.949 | ETL.3190 | 43249803 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439365 | Not Scheduled | T3 CARIBOU-PALERMO :012/093 RPR LEG | 44051416 | CARIBOU-PALERMO | :012/093 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-06-01 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.274659 | 39.9777 | ETL.3190 | 40912112 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439368 | Not Scheduled | T2 CARIBOU-PALERMO :012/098 BENT MEMB | 44054700 | CARIBOU-PALERMO | :012/098 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.27494 | 39.9661 | ETL.3190 | 40910337 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115439383 | Not Scheduled | T3 CARIBOU-PALERMO :012/096 WRN EYE BENT | 43725390 | CARIBOU-PALERMO | :012/096 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-06-01 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.274824 | 39.9695 | ETL.3190 | 40910335 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439405 | Not Scheduled | T2 EI CARIBOU-PALERMO :014/117 RPR STRT | 44054700 | CARIBOU-PALERMO | :014/117 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.303758 | 39.9498 | ETL.3190 | 40738345 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439406 | Not Scheduled | T2 CARIBOU-PALERMO-:015/120 BRKN SWAY | 44054700 | CARIBOU-PALERMO | :015/120 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.30764 | 39.9455 | ETL.3190 | 40642193 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115439424 | Not Scheduled | T2 CARIBOU-PALERMO :016/128 BENT MEMB | 44054700 | CARIBOU-PALERMO | :016/128 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.317529 | 39.9366 | ETL.3190 | 40738819 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439453 | Not Scheduled | T2 CARIBOU-PALERMO-:013/104 RPR INSS | 44304491 | CARIBOU-PALERMO | :013/104 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.280354 | 39.9626 | ETL.3190 | 40747408 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115439457 | Not Scheduled | T2 CARIBOU-PALERMO :13/110 RPR STRT | 44054700 | CARIBOU-PALERMO | :013/110 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.290832 | 39.9582 | ETL.3190 | 40642211 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115439471 | Not Scheduled | T2 CARIBOU-PALERMO :015/124 BENT MEMB | 44054700 | CARIBOU-PALERMO | :015/124 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-01 | 2019-12-01 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.31064 | 39.9396 | ETL.3190 | 40747414 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115442251 | Not Scheduled | IGNACIO-ALTO 10/52 REPL ANCHOR |  | IGNACIO-ALTO | 010/052 |  | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2019-11-28 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.501014 | 37.953 | ETL.7150 | 41196488 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2020-11-12 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115443508 | Not Scheduled | T2 COLGATE-PALERMO 007/137 RPL POLE | 31417717 | COLGATE-PALERMO | 007/137 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-03 | 2019-12-03 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.309629 | 39.347 | ETL.6500 | 40598475 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115443515 | Not Scheduled | SCHINDLER-COALINGA #2 004/007 RPLC POLE | 31418453 | SCHINDLER-COALINGA #2 | 004/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-03 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.19293 | 36.3576 | ETL.9150 | 40821791 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115443589 | Not Scheduled | T2 COLGATE-PALERMO 008/154 RPL POLE | 31417717 | COLGATE-PALERMO | 008/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-03 | 2019-12-03 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.326412 | 39.3509 | ETL.6500 | 40866214 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115443678 | Not Scheduled | T2 COLGATE-PALERMO 010/198 RPL STRW | 31434603 | COLGATE-PALERMO | 010/198 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-03 | 2019-12-03 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.360994 | 39.3645 | ETL.6500 | 40598472 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115444841 | Mar | FIVE PTS SW STA HRN GTS 01/014 RPLC POLE | 31418455 | SCHINDLER-HURON-GATES | 001/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-04 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139233 | 36.3751 | ETL.9160 | 41107525 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115444872 | Mar | FIVE PTS SW STA HRN GTS 01/015 RPLC POLE | 31418455 | SCHINDLER-HURON-GATES | 001/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-04 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139256 | 36.3742 | ETL.9160 | 41107526 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115445093 | Not Scheduled | T2 CARIBOU-PALERMO :016/136 BENT MEMB | 44056391 | CARIBOU-PALERMO | :016/136 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.318125 | 39.9254 | ETL.3190 | 40738352 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445125 | Not Scheduled | T2 CARIBOU-PALERMO :17/144 RPR STRT | 44056391 | CARIBOU-PALERMO | :017/144 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.325693 | 39.9173 | ETL.3190 | 40738818 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445131 | Not Scheduled | T2 CARIBOU-PALERMO :17/139 INS HRDT | 44056391 | CARIBOU-PALERMO | :017/139 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.318496 | 39.9218 | ETL.3190 | 40738353 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445154 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/155 RPR STRT | 44056391 | CARIBOU-PALERMO | :018/155 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.338847 | 39.909 | ETL.3190 | 40747480 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445195 | Not Scheduled | T2 CARIBOU-PALERMO :020/165 BENT MEMB |  | CARIBOU-PALERMO | :020/165 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.36186 | 39.8977 | ETL.3190 | 40747482 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445275 | Not Scheduled | NICOLAUS-CATLETT 74/546 RPL INSS | 31457035 | NICOLAUS-CATLETT JCT | 074/546 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-04 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-121.486874 | 38.7202 | ETL.7680 | 40643300 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115445292 | Not Scheduled | T2 EI CARIBOU-PALERMO :023/193 RPL HRDT | 44056391 | CARIBOU-PALERMO | :023/193 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.395764 | 39.8578 | ETL.3190 | 40668938 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445357 | Mar | RIO OSO-WEST SACRAMENTO 3/022 RPL INSUL | 31457038 | RIO OSO-WEST SACRAMENTO | 003/022 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-04 | 2019-12-04 |  |  | 2021-03-02 | 2021-03-01 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.515646 | 38.8701 | ETL.3450 | 40911135 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115445388 | Not Scheduled | T3 EI CARIBOU-PALERMO :30/242 RPR STRT | 43725390 | CARIBOU-PALERMO | :030/242 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-06-04 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.451805 | 39.7819 | ETL.3190 | 40702267 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445413 | Feb | GLENN #4 006/134 STRW ROTN REPL | 31418859 | GLENN #4 | 006/134 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-04 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-23 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.163338 | 39.8588 | ETL.8424 | 41104681 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115445514 | Not Scheduled | T2 EI CARIBOU-PALERMO :017/141 RPR STRT | 43725390 | CARIBOU-PALERMO | :017/141 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.321058 | 39.9198 | ETL.3190 | 40642499 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445517 | Not Scheduled | T2 CARIBOU-PALERMO-:018/150 MISS NUT SHO |  | CARIBOU-PALERMO | :018/150 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.330456 | 39.9121 | ETL.3190 | 40642283 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 531 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445584 | Not Scheduled | T2 CARIBOU-PLRMO :018/153 RPL BENT MEMB |  | CARIBOU-PALERMO | :018/153 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.334702 | 39.9097 | ETL.3190 | 40738358 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445656 | Not Scheduled | T2 EI CARIBOU-PALERMO :020/169 BRKN SWAY |  | CARIBOU-PALERMO | :020/169 | 70S | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445685 | Not Scheduled | T2 EI CARIBOU-PALERMO :020/169 REGRADE | 44304491 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(3) On high spread structure |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445696 | Not Scheduled | T2 CARIBOU-PALERMO :021/174 BENT MEMB | 44056391 | CARIBOU-PALERMO | :021/174 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.368699 | 39.8875 | ETL.3190 | 40753390 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445712 | Not Scheduled | T2 EI CARIBOU-PALERMO :021/178 BENT MEMB | 44056391 | CARIBOU-PALERMO | :021/178 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.373611 | 39.881 | ETL.3190 | 40858945 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445745 | Not Scheduled | T2 CARIBOU-PALERMO-:021/179 PAINT STRT | 44056391 | CARIBOU-PALERMO | :021/179 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.37491 | 39.8785 | ETL.3190 | 40738369 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445762 | Not Scheduled | T2 CARIBOU-PALERMO :022/184 BENT MEMB | 44056391 | CARIBOU-PALERMO | :022/184 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.378747 | 39.8714 | ETL.3190 | 40753356 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445816 | Not Scheduled | T2 CARIBOU-PALERMO-:024/198 RPL CTR KEY | 44304491 | CARIBOU-PALERMO | :024/198 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.401589 | 39.8512 | ETL.3190 | 40867974 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445847 | Not Scheduled | T2 CARIBOU-PALERMO :024/200 BENT MEMB | 44056391 | CARIBOU-PALERMO | :024/200 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.40384 | 39.85 | ETL.3190 | 40599288 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445854 | Not Scheduled | T2 CARIBU-PALERMO :25/207 RPL BENT MEBER |  | CARIBOU-PALERMO | :025/207 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.417991 | 39.8408 | ETL.3190 | 40826431 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445911 | Not Scheduled | T2 EI CARIBOU-PALERMO :026/213 RPR STRT | 44056391 | CARIBOU-PALERMO | :026/213 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.421318 | 39.8294 | ETL.3190 | 40668942 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445917 | Not Scheduled | T2 CARIBOU-PALERMO :029/237 RPR INSS | 44304491 | CARIBOU-PALERMO | :029/237 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.45426 | 39.7907 | ETL.3190 | 40826433 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115445970 | Not Scheduled | T3 EI CARIBOU-PALERMO :30/246 RPR STRT |  | CARIBOU-PALERMO | :030/246 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-06-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.452706 | 39.7765 | ETL.3190 | 40816591 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115445976 | Not Scheduled | T3 CARIBOU-PALERMO :30/249A RPR STRS | 44304458 | CARIBOU-PALERMO | :030/249A | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-06-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.456308 | 39.7717 | ETL.3190 | 41162678 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115446061 | Not Scheduled | T2 CARIBOU-PALERMO :17/140 RPR STRT | 44056391 | CARIBOU-PALERMO | :017/140 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.319376 | 39.9211 | ETL.3190 | 40642213 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115446063 | Not Scheduled | T2 CARIBOU-PALERMO :017/143 BENT MEMB | 44056391 | CARIBOU-PALERMO | :017/143 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40738355 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115446131 | Not Scheduled | T2 CARIBOU-PALERMO :020/162 BENT MEMB | 44056391 | CARIBOU-PALERMO | :020/162 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.357958 | 39.9029 | ETL.3190 | 40738811 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115446134 | Not Scheduled | T2 CARIBOU-PALERMO :020/168 BENT MEMB | 44056391 | CARIBOU-PALERMO | :020/168 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.361944 | 39.8926 | ETL.3190 | 40858943 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115446181 | Not Scheduled | T2 CARIBOU-PALERMO :022/185 RPR STRT | 44056391 | CARIBOU-PALERMO | :022/185 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.380738 | 39.8706 | ETL.3190 | 40738371 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115446205 | Not Scheduled | T2 CARIBOU-PALERMO :023/194 RPR FOND | 44056391 | CARIBOU-PALERMO | :023/194 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2018-12-04 | 2019-12-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.396832 | 39.8566 | ETL.3190 | 40758632 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115446257 | Not Scheduled | T2 CARIBOU-PALERMO :025/209 BENT STEEL | 44056391 | CARIBOU-PALERMO | :025/209 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [8 empty] | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.420523 | 39.8364 | ETL.3190 | 40863363 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115446274 | Not Scheduled | T2 CARIBOU-PALERMO-:025/209 RPL CTTR KEY | 44304491 | CARIBOU-PALERMO | :025/209 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-12-04 | [7 empty] | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.420523 | 39.8364 | ETL.3190 | 40863363 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115446392 | Not Scheduled | T3 CARIBOU-PALERMO :030/247 BENT SWAY | 43735849 | CARIBOU-PALERMO | :030/247 | ICS | E | 2020_(4) TD tag on high spread line |  | 2018-12-04 | 2019-06-04 | [7 empty] | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.454013 | 39.7748 | ETL.3190 | 40826439 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115447759 | Mar | T2 HUMBOLDT-TRINITY 76/0R RPL POLE | 31497850 | HUMBOLDT-TRINITY | 076/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-10-09 | 2019-10-09 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.442836 | 40.6977 | ETL.1820 | 44565523 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-10-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115448774 | Not Scheduled | IGNACIO-ALTO - 60 replace pole 12/94 | 31418881 | IGNACIO-ALTO | 012/094 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-05 | 2020-12-05 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.508622 | 37.9569 | ETL.7150 | 40877635 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115448861 | Q2 | IGNACIO-ALTO 13/101 REPL NG POLE | 31433716 | IGNACIO-ALTO | 013/101 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-05 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.509876 | 37.9524 | ETL.7150 | 40753385 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-12 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115451003 | Not Scheduled | IGNACIO-ALTO 014/122 CANCEL | 43762410 | IGNACIO-ALTO | 014/122 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-06 | 2020-12-06 | [6 empty] | CANCEL/CNCL |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.516055 | 37.9382 | ETL.7150 | 40863517 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115451102 | Not Scheduled | IGNACIO-ALTO -014/125 mud sill | 43749533 | IGNACIO-ALTO | 014/125 | ICW | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-06 | 2022-12-06 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.514064 | 37.9373 | ETL.7150 | 40651470 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115453212 | Mar | GLENN-DELEVAN 127/999 INSS NG REPL | 31439322 | GLENN-DELEVAN | 127/999 | 93K | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-05 | 2021-12-05 |  |  | 2021-03-09 | 2021-03-08 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.263122 | 39.4204 | ETL.7042 | 40897192 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115454057 | Mar | GLENN-DELEVAN 104/850 INSS NG REPL | 31439322 | GLENN-DELEVAN | 104/850 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-05 | 2021-05-31 |  |  | 2021-03-09 | 2021-03-08 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.264942 | 39.7445 | ETL.7042 | 40635120 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115455381 | Not Scheduled | PALERMO WYANDOTTE_001/016 INSS NG REPL | 31441968 | PALERMO-WYANDOTTE | 001/016 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-06 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.539547 | 39.4754 | ETL.4315 | 40843426 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115461120 | Mar | FIVE PTS SW STA HRN GTS 03/001 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 003/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-06 | 2022-12-06 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139395 | 36.357 | ETL.9160 | 41107547 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115462585 | Mar | CONTRA COSTA-BALFOUR 009/226 Repl pole | 31418424 | CONTRA COSTA-BALFOUR | 009/226 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-06 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-26 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.677654 | 37.9538 | ETL.8420 | 40643956 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115463683 | Mar | GLENN #2_006/118 RPL INSUL | 31418508 | GLENN #2 | 006/118 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-29 | 2021-05-31 |  |  | 2021-03-10 | 2021-03-08 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.038467 | 39.7756 | ETL.6930 | 40630386 | Insulator-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115464060 | Mar | FIVE PTS SW STA HRN GTS 03/005 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 003/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-06 | 2022-12-06 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139432 | 36.3534 | ETL.9160 | 41107551 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115464595 | Q2 | T2 TRINITY-MAPLE CREEK 16/003C RPL POLE | 31418582 | TRINITY-MAPLE CREEK | 016/003B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-10-30 | 2019-10-30 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.195171 | 40.7387 | ETL.8170 | 40642840 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115464915 | Not Scheduled | WEBER-FRENCH CAMP #1 2/43 REPLACE POLE |  | WEBER #1 | 002/043 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-14 | 2020-11-14 | [5 empty] | Will be completed under LC 120135402; can we DLFL? |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.273092 | 37.9073 | ETL.8320 | 40825591 | Structure-Wood | Rotten | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115464917 | Feb | WEBER-FRENCH CAMP #1 2/50 REPLACE POLE | 31418889 | WEBER #1 | 002/050 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-14 | 2020-11-14 |  |  | 2021-02-16 | 2021-02-12 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.272326 | 37.9025 | ETL.8320 | 40643597 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115464919 | Feb | WEBER-FRENCH CAMP #1 3/81 REPLACE POLE | 31418889 | WEBER #1 | 003/081 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-21 | 2021-05-31 |  |  | 2021-02-16 | 2021-02-12 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.273306 | 37.8827 | ETL.8320 | 40875866 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115465061 | Feb | WEBER-FRENCH CAMP #1 4/86 REPLACE POLE | 31418889 | WEBER #1 | 004/086 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-21 | 2021-05-31 |  |  | 2021-02-16 | 2021-02-12 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.276059 | 37.8817 | ETL.8320 | 44229259 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115469273 | Feb | GLENN #4 011/229 STRW ROTN REPL | 31418859 | GLENN #4 | 011/229 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-08 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-23 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.18826 | 39.9151 | ETL.8424 | 41104583 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115469690 | Feb | GLENN #4 012/251 STRW ROTN REPL | 31418859 | GLENN #4 | 012/251 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-09 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-23 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.188145 | 39.9294 | ETL.8424 | 41104568 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115477377 | Q2 | WEBER-FRENCH CAMP #2 5/122 REPLACE POLE | 31418887 | SPARE T-LINE RECORD | 005/122 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-13 | 2021-05-31 |  |  | 2021-04-06 | 2021-04-06 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.303388 | 37.881 | ETL.8321 | 40580385 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115477892 | Q2 | WEBER-FRENCH CAMP #2 A000/21 RPLC POLE | 31418887 | SPARE T-LINE RECORD | A000/021 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2021-05-31 |  |  | 2021-04-07 | 2021-04-07 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.251938 | 37.9161 | ETL.8321 | 40823876 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115477894 | Q2 | WEBER-FRENCH CAMP #2 A000/22 RPLC POLE | 31418887 | SPARE T-LINE RECORD | A000/022 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2021-05-31 |  |  | 2021-04-07 | 2021-04-07 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.252803 | 37.9159 | ETL.8321 | 40875895 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115477897 | Q2 | WEBER-FRENCH CAMP #2 A001/36 RPLC POLE | 31418887 | SPARE T-LINE RECORD | A001/036 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-07 | 2021-05-31 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.264963 | 37.9127 | ETL.8321 | 40593088 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115477919 | Q2 | WEBER-FRENCH CAMP#2 AC008/137 RPLC POLE | 31418887 | SPARE T-LINE RECORD | AC008/137 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-13 | 2021-05-31 |  |  | 2021-04-08 | 2021-04-08 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.309609 | 37.881 | ETL.8321 | 40804168 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478012 | Mar | FIVE PTS SW STA HRN GTS 05/004 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-10 | 2023-12-10 |  |  | 2021-03-20 | 2021-03-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139571 | 36.326 | ETL.9160 | 40766105 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478055 | Mar | T2 HUMBOLDT-TRINITY 88/3A RPLC POLE |  | HUMBOLDT-TRINITY | 088/003 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-10-16 | 2019-10-16 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.662205 | 40.7274 | ETL.1820 | 44562991 | Structure-Wood | Rotten | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-10-04 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115478182 | Mar | FIVE PTS SW STA HRN GTS 05/009 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-10 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139582 | 36.3215 | ETL.9160 | 40859327 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478213 | Not Scheduled | NICOLAUS-WILKINS SLOUGH 3/068 REFRAME T1 | 31418512 | NICOLAUS-WILKINS SLOUGH | 003/068 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.582697 | 38.8838 | ETL.7710 | 40866132 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478266 | Not Scheduled | NICOLAUS-WILKINS SLOUGH 3/071 RPL INSUL | 31418512 | NICOLAUS-WILKINS SLOUGH | 003/071 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.584816 | 38.8824 | ETL.7710 | 40599032 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478352 | Not Scheduled | NICOLAUS-PLAINFIELD 20/330 AUTO SPLICE | 43910652 | NICOLAUS-PLAINFIELD | 020/330 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.721818 | 38.7128 | ETL.7700 | 40756534 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478542 | Not Scheduled | NICOLAUS-PLAINFIELD 25/419 RPR CONNECTOR | 43910650 | NICOLAUS-PLAINFIELD | 025/419 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.752624 | 38.6555 | ETL.7700 | 43702314 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478544 | Not Scheduled | NICOLAUS-PLAINFIELD 25/416 RPR CONNECTOR | 43910650 | NICOLAUS-PLAINFIELD | 025/416 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.748513 | 38.6555 | ETL.7700 | 43702323 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115478896 | Not Scheduled | T2 LAYTONVILLE-WILLITS 16/01 REPL POLE | 31418219 | LAYTONVILLE-WILLITS | 016/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-10 | 2019-12-10 | 2020-10-14 | 2020-10-17 | [5 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.452355 | 39.594 | ETL.8360 | 40584828 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-08 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115480772 | Mar | FIVE PTS SW STA HRN GTS 05/015 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.13961 | 36.3163 | ETL.9160 | 40765650 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115480779 | Mar | FIVE PTS SW STA HRN GTS 05/017 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/017 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139627 | 36.3146 | ETL.9160 | 40806535 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115481587 | Mar | FIVE PTS SW STA HRN GTS 007/013 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 007/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-20 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.126421 | 36.2989 | ETL.9160 | 40663610 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115482779 | Mar | FIVE PTS SW STA HRN GTS 009/001 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 009/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2022-12-11 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121524 | 36.2844 | ETL.9160 | 40597743 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483059 | Mar | FIVE PTS SW STA HRN GTS 009/008 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 009/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2020-12-11 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.121519 | 36.2773 | ETL.9160 | 40859398 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483231 | Feb | GLENN #4 000/004 RPR BOND WIRE | 43890231 | GLENN #4 | 000/004 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-23 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.140809 | 39.7771 | ETL.8424 | 41104810 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483583 | Mar | FIVE PTS SW STA HRN GTS 011/004 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 011/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2022-12-11 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121597 | 36.2518 | ETL.9160 | 40766116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483590 | Mar | FIVE PTS SW STA HRN GTS 011/005 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 011/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2022-12-11 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121601 | 36.2506 | ETL.9160 | 40748252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483620 | Mar | FIVE PTS SW STA HRN GTS 011/007 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 011/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-23 | 2021-03-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121645 | 36.2481 | ETL.9160 | 40821835 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483652 | Mar | FIVE PTS SW STA HRN GTS 011/010 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 011/010 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-23 | 2021-03-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.12166 | 36.2445 | ETL.9160 | 40625660 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483655 | Mar | FIVE PTS SW STA HRN GTS 011/012 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 011/012 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-23 | 2021-03-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121633 | 36.2421 | ETL.9160 | 40707868 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115483690 | Mar | FIVE PTS SW STA HRN GTS 012/004 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 012/004 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-11 | 2021-05-31 |  |  | 2021-03-23 | 2021-03-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121712 | 36.2374 | ETL.9160 | 40776864 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115490262 | Mar | FIVE PTS SW STA HRN GTS 012/011 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 012/011 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-12 | 2021-05-31 |  |  | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121693 | 36.229 | ETL.9160 | 40624363 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115490297 | Mar | FIVE PTS SW STA HRN GTS 012/013 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 012/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-12 | 2021-05-31 |  |  | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121677 | 36.2265 | ETL.9160 | 40663614 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115490772 | Mar | FIVE PTS SW STA HRN GTS 014/006 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 014/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-12 | 2022-12-12 |  |  | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121425 | 36.2058 | ETL.9160 | 40823327 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115490984 | Not Scheduled | T3 EI DRM-GRS VLY-WMR B17/386 RPR GYWW | 43746390 | DRUM-GRASS VALLEY-WEIMAR | B017/386 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-12 | 2019-12-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9653 | 39.1328 | ETL.6760 | 40814230 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115492434 | Mar | T3 EI DRUM-GRASS VALLEY-WEIMAR-009/221 | 43746390 | DRUM-GRASS VALLEY-WEIMAR | 009/221 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-12 | 2019-06-12 |  |  | 2021-03-21 | 2021-03-15 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.869466 | 39.1718 | ETL.6760 | 40824302 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-02-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115504353 | Not Scheduled | DISTRIBUTION |  | DRUM-GRASS VALLEY-WEIMAR | 020/463 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-12 | 2019-12-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.983208 | 39.0546 | ETL.6760 | 40766710 | Crossarm-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-04-01 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115506701 | Mar | TABLE MTN-VACA 041/164 RPL INSS | 31528801 | TABLE MTN-VACA | 041/164 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2021-05-31 |  |  | 2021-03-31 | 2021-03-31 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.847458 | 38.9902 | ETL.6090 | 40756826 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115506822 | Q2 | TABLE MTN-TESLA 019/075 RPL INSULATOR | 31455289 | TABLE MTN-TESLA | 019/075 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-08 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-30 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.752022 | 39.2951 | ETL.6080 | 40761251 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115507534 | Mar | T2 EI DRUM-GRASS VALLEY-WEIMAR-014/333 | 43746390 | DRUM-GRASS VALLEY-WEIMAR | 014/333 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-13 | 2019-12-13 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.942933 | 39.1254 | ETL.6760 | 40867122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115507579 | Q2 | T2 Round Mtn_Table Mt#2_061/258 RPL INSS | 31455287 | ROUND MTN-TABLE MTN #2 | 061/258 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-12 | 2019-12-12 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.831989 | 39.9305 | ETL.6070 | 40895430 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115508735 | Mar | FIVE PTS SW STA HRN GTS 015/003 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 015/003 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-14 | 2021-05-31 |  |  | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.120042 | 36.1957 | ETL.9160 | 40694973 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115508851 | Mar | FIVE PTS SW STA HRN GTS 015/009 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 015/009 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-14 | 2019-12-14 |  |  | 2021-03-25 | 2021-03-25 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.110891 | 36.1958 | ETL.9160 | 40897382 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115508854 | Mar | FIVE PTS SW STA HRN GTS 15/10 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 015/010 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-14 | 2021-05-31 |  |  | 2021-03-25 | 2021-03-25 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.109458 | 36.1958 | ETL.9160 | 40638624 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115510745 | Q2 | T2 RND MTN-TBLE MT#2 049/215 RPL SPAS | 43347033 | ROUND MTN-TABLE MTN #2 | 049/215 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-12-12 | 2021-05-31 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.899595 | 40.0979 | ETL.6070 | 40759771 | Spacer-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115511533 | Mar | T3 EI DRUM-HIGGINS-9/87C REP ANCHOR | 31423105 | DRUM-HIGGINS | 009/087C | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892097 | 39.1661 | ETL.4393 | 44202750 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115511566 | Mar | T3 EI DRUM-HIGGINS 009/092R RPL PL | 31423101 | DRUM-HIGGINS | 009/092 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8925829 | 39.1723 | ETL.4393 | 44172128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115515465 | Q2 | T3 EI DRUM-HIGGINS 3/32L REPLACE POLE | 31423101 | DRUM-HIGGINS | 003/032 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.799724 | 39.2229 | ETL.4393 | 44172142 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115515697 | Q2 | T3 EI DRUM-HIGGINS-115 KV_003/042C | 43687142 | DRUM-HIGGINS | 003/042C | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-04-03 | 2021-03-22 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817605 | 39.2192 | ETL.4393 | 44313914 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115515711 | Q2 | T3 EI DRUM-HIGGINS 3/042B RPL ANCHOR | 31432820 | DRUM-HIGGINS | 003/042B | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.81757 | 39.2191 | ETL.4393 | 44313913 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115515722 | Q2 | T3 EI DRUM-HIGGINS-3/42A CORRODED ANCHOR | 43687142 | DRUM-HIGGINS | 003/042A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-04-03 | 2021-03-22 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817539 | 39.2191 | ETL.4393 | 44313912 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115515787 | Q4 | T3 EI MIDDLE FORK-GOLD HILL 003/028 REPL | 31421211 | MIDDLE FORK-GOLD HILL | 003/028 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-12-15 | 2019-06-15 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 2021 - Micro pile vendor (Crux) unavailable in 2020 | '-120.630383 | 38.9995 | ETL.5140 | 44761223 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-07-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115523853 | Not Scheduled | T2 IGNACIO-ALTO 16/162 RE-ESTAB ROW RD |  | IGNACIO-ALTO | 016/162 | CHR | E | Pre-2020_(5b) On structure in bucket 5 |  | 2018-12-17 | 2019-12-17 | [7 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.51965 | 37.9151 | ETL.7150 | 40617235 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115540807 | Q2 | T2 RND MT-TBL MT#2 49/216 RPR JUMS | 43621090 | ROUND MTN-TABLE MTN #2 | 049/216 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-12-17 | 2021-05-31 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.897092 | 40.0912 | ETL.6070 | 40817857 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115541557 | Q2 | T2 EI SANTA ROSA-CORONA 11/265 GYWW | 43749631 | SANTA ROSA-CORONA (NO FLY) | 011/265 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-18 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.68236 | 38.2851 | ETL.4309 | 41104271 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115541879 | Not Scheduled | T3 EI FULTON-CLSTG :006/004 RPL CRSW | 31424405 | FULTON-CALISTOGA | :006/004 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-18 | 2019-06-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588338 | 38.675 | ETL.6880 | 40912474 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115542061 | Not Scheduled | T3 EI FULTON-CLSTG :006/004 RPR CNDW | 43736233 | FULTON-CALISTOGA | :006/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-18 | 2019-06-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588338 | 38.675 | ETL.6880 | 40912474 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115542284 | Not Scheduled | T3 EI FULTON-CALISTOGA :008/002 INS GYWW | 43749446 | FULTON-CALISTOGA | :008/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-18 | 2019-06-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.600416 | 38.7031 | ETL.6880 | 40905729 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115542802 | Q2 | T3 EI FULTON-CALISTOGA :3/6 RPR GYWW | 43749446 | FULTON-CALISTOGA | :003/006 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-18 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.594766 | 38.6397 | ETL.6880 | 40912436 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115543257 | Not Scheduled | T2 EI CARIBOU-WESTWD 007/140B CANCEL | 43640851 | CARIBOU-WESTWOOD | 007/140 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-18 | 2019-12-18 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08781 | 40.1717 | ETL.6300 | 42624246 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115543874 | Not Scheduled | T2 EI COLGATE-PALERMO 010/199 RPL STRW | 31423185 | COLGATE-PALERMO | 010/199 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-14 | 2019-12-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.361873 | 39.3648 | ETL.6500 | 40672059 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115544601 | Not Scheduled | T2 COLGATE-PALERMO 013/260 CONN NG REPL | 43878339 | COLGATE-PALERMO | 013/260 | ICM | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-18 | 2019-12-18 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.403352 | 39.3876 | ETL.6500 | 40610864 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115544660 | Q2 | T2 EI COLGATE-PALERMO 013/267 RPL STRW | 31423185 | COLGATE-PALERMO | 013/267 | 70Y | E | 2020_(1a) PSPS |  | 2018-12-18 | 2019-12-18 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.407265 | 39.3898 | ETL.6500 | 40822476 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115545480 | Not Scheduled | T2 EI LAKEVILLE #1 005/009 RMV DEB | 43749612 | LAKEVILLE #1 | 005/009 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2018-12-19 | 2022-12-19 | [7 empty] | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.586797 | 38.3337 | ETL.7360 | 40861378 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-02-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115546051 | Not Scheduled | T2 EI TULUCAY-NAPA #1 007/004 RPL STRW | 31460465 | TULUCAY-NAPA #1 | 007/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.206128 | 38.2672 | ETL.8180 | 40763973 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115546193 | Not Scheduled | T2 EI TULUCAY-NAPA #1 006/017 RPR GYWW | 43740449 | TULUCAY-NAPA #1 | 006/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.203099 | 38.2633 | ETL.8180 | 40809019 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115546198 | Not Scheduled | T2 EI TULUCAY-NAPA #1 007/007 RPL STRW | 31460465 | TULUCAY-NAPA #1 | 007/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.208458 | 38.2702 | ETL.8180 | 40809021 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115546737 | Not Scheduled | T3 EI FULTON-CALISTGA 000/001 INS GYWW | 43749446 | FULTON-CALISTOGA | 000/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-19 | 2019-06-19 |  |  |  | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.443127 | 38.5075 | ETL.6880 | 40585438 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115548600 | Not Scheduled | T2 EI TULUCAY-NAPA #1 007/006 RPL ANCW | 31434773 | TULUCAY-NAPA #1 | 007/006 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.207683 | 38.2692 | ETL.8180 | 40821522 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115548602 | Not Scheduled | T2 EI TULUCAY-NAPA #1 007/008 REPL ANCW | 31506249 | TULUCAY-NAPA #1 | 007/008 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.2101 | 38.2705 | ETL.8180 | 40872385 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557429 | Not Scheduled | T2 EI SPLDNG #3-SPLDNG #1 00/018 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/018 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.640103 | 39.3349 | ETL.8050 | 40862188 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557524 | Q3 | T2 EI CARIBOU-WESTWOOD 007/137C GYWW | 43640851 | CARIBOU-WESTWOOD | 007/137C | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-19 | 2021-05-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.090679 | 40.1713 | ETL.6300 | 42624243 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557543 | Not Scheduled | T3 EI FULTON-CALISTOGA :010/002 RPR GYWW | 43668969 | FULTON-CALISTOGA | :010/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-19 | 2019-06-19 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.608146 | 38.731 | ETL.6880 | 40905749 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-02-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557642 | Q2 | T3 EI FULTON-CALISTOGA 002/007 RPL POLE | 31481143 | FULTON-CALISTOGA | 002/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2021-05-31 | 2020-09-21 | 2020-09-25 | 2021-05-31 |  |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.48011 | 38.5294 | ETL.6880 | 40825320 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557663 | Not Scheduled | T2 EI SPLDNG #3-SPLDNG #1 00/016 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.641346 | 39.3339 | ETL.8050 | 40810192 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557812 | Not Scheduled | T2 EI TULUCAY-NAPA #1 T003/000 GYWW | 43740449 | TULUCAY-NAPA #1 | T003/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.20938 | 38.2567 | ETL.8180 | 40603472 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115557821 | Feb | EI WINTU TAP 000/002 RPL POLE | 31436367 | WINTU TAP | 000/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-19 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.353124 | 40.5799 | ETL.6311 | 40701918 | Structure-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115559431 | Not Scheduled | T2 EI CARIBOU-WESTWD 005/104 RMV VEGN |  | CARIBOU-WESTWOOD | 005/104 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-19 | 2019-12-19 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.110202 | 40.1498 | ETL.6300 | 44191069 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  | Not Released | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115559596 | Q2 | T2 COLGATE-PALERMO 018/374 RPL STRW | 31417717 | COLGATE-PALERMO | 018/374 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-19 | 2019-12-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.457958 | 39.4465 | ETL.6500 | 40866835 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115582004 | Not Scheduled | CHRISTIE-WILLOW PASS-60 kV_5/72 RPR FND | 44110982 | CHRISTIE-WILLOW PASS | 005/072 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-19 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.11946 | 38.0256 | ETL.6370 | 40768258 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115582245 | Q2 | T3 EI FULTON-CALISTOGA :002/000 RMV STRW | 43749446 | FULTON-CALISTOGA | :002/000 | ICW | E | 2020_(1a) PSPS |  | 2018-12-20 | 2019-06-20 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585691 | 38.6206 | ETL.6880 | 40912423 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-28 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115584011 | Q2 | T3 EI FULTON-CALISTOGA :002/005 RPL POLE | 31505615 | FULTON-CALISTOGA | :002/005 | 70Y | E | 2020_(1a) PSPS |  | 2018-12-20 | 2019-06-20 |  |  | 2021-05-31 |  |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.59216 | 38.6281 | ETL.6880 | 40912428 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115584019 | Not Scheduled | T3 EI MONTE RIO-FORT ROSS 17/3 RPR PL | 43713924 | ETL.6979.POLE.WOOD | 017/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-06-20 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.056451 | 38.4782 | ETL.6979 | 40667838 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115584138 | Q2 | T2 EI BRIDGVILL-CTTNWD 32/265L RPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 032/265 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.880879 | 40.365 | ETL.1110 | 44423882 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115584319 | Not Scheduled | NEWARK-MILPITAS #1 004/033 RPLC INSS |  | DIXON LANDING-MCKEE | 004/033 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-20 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.920375 | 37.4552 | ETL.1390 | 43242856 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115584409 | Not Scheduled | T2 EI SPAULDING-SUMMIT 000/017 RMV VEGN | 43760150 | SPAULDING-SUMMIT | 000/017 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2018-12-20 | 2019-12-20 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.638295 | 39.3231 | ETL.8060 | 40826222 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115584503 | Q2 | T2 EI DRUM-SPAULDING 008/217 RPL STRW | 31451875 | DRUM-SPAULDING | 008/217 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.649682 | 39.3171 | ETL.6770 | 40877168 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115584572 | Not Scheduled | T2 EI SPLDN #3-SPLDN #1 000/012 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/012 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.642112 | 39.3319 | ETL.8050 | 40702888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115584583 | Not Scheduled | T2 EI SPLDNG #3-SPLDNG #1 00/014 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/014 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-12-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Weather | '-120.641792 | 39.3329 | ETL.8050 | 40751875 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115584798 | Feb | CASCADE-BENTON-DESCHTS 10/223 RPR JUMW | 43900811 | CASCADE-BENTON-DESCHUTES | 010/223 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-17 | 2022-12-17 |  |  | 2021-02-18 | 2021-02-16 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.379564 | 40.5631 | ETL.6310 | 40592280 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115584844 | Feb | CASCADE-BENTON-DESCHUTES 010/224 REFRAME | 31460661 | CASCADE-BENTON-DESCHUTES | 010/224 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-17 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.380627 | 40.5633 | ETL.6310 | 40600612 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115585107 | Q2 | T3 EI FULTON-CALISTOGA -012/005 REPL PL | 31502249 | FULTON-CALISTOGA | '-012/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2021-05-31 | 2020-09-21 | 2020-09-25 | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.521678 | 38.4069 | ETL.6880 | 40751129 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115586132 | Not Scheduled | T2 EI SPLDNG #3-SPLDNG #1 0/01A REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/001A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644763 | 39.3248 | ETL.8050 | 40590201 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115586357 | Q2 | T2 COLGATE-PALERMO 013/272 RPL POLE | 31423185 | COLGATE-PALERMO | 013/272 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.410082 | 39.3925 | ETL.6500 | 41146789 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115586521 | Q2 | T2 EI COLGATE-PALERMO 014/289 RPL POLE | 31423185 | COLGATE-PALERMO | 014/289 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.416212 | 39.403 | ETL.6500 | 40824110 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115587137 | Not Scheduled | T2 EI DRUM-SUMMIT #2 010/126 RPL POL | 31421446 | DRUM-SUMMIT #2 | 010/126 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.603803 | 39.3267 | ETL.1450 | 44558984 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115587217 | Q2 | T2 EI BVILLE-CTNWD 033/274 RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 033/274 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.9024672 | 40.3663 | ETL.1110 | 44424386 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115587465 | Q2 | T2 EI BRIDGVILL-CTTNWD 17/154L RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 017/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.583763 | 40.3819 | ETL.1110 | 44423379 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115587587 | Not Scheduled | EI VALLEY SPRINGS #1 012/243 RPR STRW | 44290814 | VALLEY SPRINGS #1 | 012/243 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.921396 | 38.1031 | ETL.8210 | 40904218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115588445 | Q2 | T2 EI COLGATE-PALERMO 018/358 RPL POLE | 31423185 | COLGATE-PALERMO | 018/358 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.444447 | 39.4453 | ETL.6500 | 40672083 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115588500 | Q4 | T2 EI MIDDLE FORK-GLD H 26/207R RPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 026/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.945506 | 38.8126 | ETL.5140 | 44558315 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115588646 | Q2 | T2 EI BRDGVLE-CTTNWD 024/210L REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 024/210 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.72074 | 40.3723 | ETL.1110 | 44423242 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589065 | Not Scheduled | T2 EI DRUM-SUMMIT #2-9/114L RPL POLE | 31498154 | DRUM-SUMMIT #2 | 009/114 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.620933 | 39.3211 | ETL.1450 | 44553512 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589188 | Q2 | T2 EI BRDGVILLE-CTNWD 023/207L RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 023/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.71398 | 40.3728 | ETL.1110 | 44424462 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589496 | Q2 | T2 EI BVILLE-CTNWD 013/127C ANTI SPLIT | 43742050 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-21 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424422 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589541 | Not Scheduled | T2 EI BVILLE-CTNWD 039/312 CANCEL | 43770771 | BRIDGEVILLE-COTTONWOOD | 039/312 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2018-12-21 | 2019-12-21 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. |  |  | ETL.1110 | 44424595 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115589798 | Q2 | T2 EI BRDGVLLE-CTNWD A041/332B REPL STRW | 31422962 | BRIDGEVILLE-COTTONWOOD | A041/332B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-123.043825 | 40.3873 | ETL.1110 | 41198659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589926 | Not Scheduled | T2 EI VALLEY SPRINGS #1 10/200 RPR INSW | 43830873 | VALLEY SPRINGS #1 | 010/200 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.888976 | 38.1166 | ETL.8210 | 40908285 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589927 | Q3 | T2 EI HMLTN BRNCH-CHSTR 008/185 RPL STRW | 31439198 | HAMILTON BRANCH-CHESTER | 008/185 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.17314 | 40.3091 | ETL.7000 | 40758793 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589928 | Mar | T2 EI KNCTI-MDLTOWN 012/003 RPR STRW | 43749609 | KONOCTI-MIDDLETOWN | 012/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 |  |  | 2021-03-01 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610385 | 38.7543 | ETL.6380 | 40666998 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589954 | Q3 | T2 EI HMLTN BRNCH-CHSTR 009/197 RPL STRW | 31421720 | HAMILTON BRANCH-CHESTER | 009/197 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.183783 | 40.3128 | ETL.7000 | 40809579 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-07-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589966 | Not Scheduled | DISTRIBUTION |  | LIMESTONE TAP | 001/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-22 | 2019-06-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.98146 | 38.6374 | ETL.6951 | 40875182 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589981 | Q3 | T2 EI HMLTN BRNCH-CHSTR 007/163 RPL CRSW | 31433532 | HAMILTON BRANCH-CHESTER | 007/163 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.154893 | 40.3037 | ETL.7000 | 40659934 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589984 | Not Scheduled | T2 EI VALLEY SPRINGS #1 012/239 RPR POLE | 43831006 | VALLEY SPRINGS #1 | 012/239 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.918854 | 38.1049 | ETL.8210 | 40906501 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589985 | Not Scheduled | T2 EI VALLEY SPRINGS #1 12/238 RPL POLE | 31426054 | VALLEY SPRINGS #1 | 012/238 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.918388 | 38.1055 | ETL.8210 | 40906500 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115589989 | Not Scheduled | EI VALLEY SPRINGS #1 12/242 RPR POLE | 43831011 | VALLEY SPRINGS #1 | 012/242 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.920581 | 38.1034 | ETL.8210 | 40904217 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590014 | Not Scheduled | T2 EI SPAULDING-SUMMIT 000/027 RPL PL | 31445623 | SPAULDING-SUMMIT | 000/027 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.632402 | 39.322 | ETL.8060 | 40809698 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590015 | Not Scheduled | EI VALLEY SPRINGS #1 012/241 RPR GYWW | 43831010 | VALLEY SPRINGS #1 | 012/241 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.919877 | 38.1037 | ETL.8210 | 40904216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590072 | Q3 | T2 EI HAMILTON BRANCH-CH 09/196 RPR POLE | 43879596 | HAMILTON BRANCH-CHESTER | 009/196 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.182692 | 40.3127 | ETL.7000 | 40827421 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590081 | Not Scheduled | T2 EI VALLEY SPRINGS #1 10/195 RPR POLE | 43830872 | VALLEY SPRINGS #1 | 010/195 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.885409 | 38.1181 | ETL.8210 | 40908280 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590082 | Not Scheduled | EI VALLEY SPRINGS #1 006/131 RPL STRW | 31426053 | VALLEY SPRINGS #1 | 006/131 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.853151 | 38.1552 | ETL.8210 | 40905594 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Not Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590095 | Not Scheduled | EI VALLEY SPRINGS #1 12/240 RPL POLE | 31426054 | VALLEY SPRINGS #1 | 012/240 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.919405 | 38.1042 | ETL.8210 | 40904215 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590110 | Mar | T2 EI KNCTI-MIDDLTWN 12/13 RPL GYWW | 43749609 | KONOCTI-MIDDLETOWN | 012/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.600755 | 38.7619 | ETL.6380 | 40650678 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590142 | Not Scheduled | T2 EI VALLEY SPRINGS #1 11/230 RPR POLE | 43831005 | VALLEY SPRINGS #1 | 011/230 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.912855 | 38.109 | ETL.8210 | 40908321 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590154 | Not Scheduled | EI VALLEY SPRINGS #1 05/100 RPR POLE | 43830786 | VALLEY SPRINGS #1 | 005/100 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.836587 | 38.1719 | ETL.8210 | 40905515 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590200 | Not Scheduled | EI VALLEY SPRINGS #1 11/221 RPR POLE | 43831013 | VALLEY SPRINGS #1 | 011/221 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.906023 | 38.1122 | ETL.8210 | 40908306 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590218 | Not Scheduled | EI VALLEY SPRINGS #1 011/218 RPR POLE | 44290815 | VALLEY SPRINGS #1 | 011/218 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.903569 | 38.113 | ETL.8210 | 40908303 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590224 | Not Scheduled | T2 EI SMARTVILLE-NIC #2 0/004 RPR SEAL |  | SMARTVILLE-NICOLAUS #2 | 000/004 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3028 | 39.2071 | ETL.8000 | 44177580 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590232 | Q2 | T2 EI BVILLE-CTNWD 015/143L RPL ANCH | 31456191 | BRIDGEVILLE-COTTONWOOD | 015/143 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1110 | 44232660 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-04-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590238 | Feb | T2 EI SMARTVILLE-NIC #2 0/005 RPR POLE | 43760147 | SMARTVILLE-NICOLAUS #2 | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-22 | 2019-12-22 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.30243 | 39.2064 | ETL.8000 | 40907130 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590277 | Mar | T2 EI KONOCTI-MDDLTWN 013/000 RPL STRW | 31502250 | KONOCTI-MIDDLETOWN | 013/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.597631 | 38.7634 | ETL.6380 | 40615192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590288 | Not Scheduled | T2 EI VALLEY SPRINGS #1 009/184 RPR INSW | 43830869 | VALLEY SPRINGS #1 | 009/184 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.878384 | 38.1244 | ETL.8210 | 40908269 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590294 | Not Scheduled | T2 EI VALLEY SPRINGS #1 009/179 RPR INSW | 43830867 | VALLEY SPRINGS #1 | 009/179 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.875976 | 38.1272 | ETL.8210 | 40908264 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590332 | Mar | T2 EI KNCTI-MIDDLETWN 13/1 RPR INSW | 43749609 | KONOCTI-MIDDLETOWN | 013/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.595048 | 38.7643 | ETL.6380 | 40586656 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590410 | Not Scheduled | EI VALLEY SPRINGS #1 010/208 RPR GYWW | 43830877 | VALLEY SPRINGS #1 | 010/208 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.89528 | 38.1155 | ETL.8210 | 40908293 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590433 | Not Scheduled | T2 EI VALLEY SPRINGS #1 07/147 RPR POLE | 43830861 | VALLEY SPRINGS #1 | 007/147 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.860995 | 38.1462 | ETL.8210 | 40908230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590438 | Q2 | T2 EI KNCTI-MIDDLETWN ;23/7 RPR GYWW | 43749609 | KONOCTI-MIDDLETOWN | ;023/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2021-05-31 | 2020-10-26 |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610015 | 38.8986 | ETL.6380 | 40810259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590445 | Not Scheduled | EI VALLEY SPRINGS #1 10/203 RPL POLE | 31426054 | VALLEY SPRINGS #1 | 010/203 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.891032 | 38.1157 | ETL.8210 | 40908288 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-05-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590456 | Not Scheduled | T2 EI VALLEY SPRINGS #1 007/138 RPR STRW | 43830789 | VALLEY SPRINGS #1 | 007/138 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.85734 | 38.1514 | ETL.8210 | 40905601 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590461 | Q2 | T2 EI KNCTI-MDLTOWN ;023/008 RPR GYWW | 43749609 | KONOCTI-MIDDLETOWN | ;023/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610737 | 38.8993 | ETL.6380 | 40876736 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590487 | Not Scheduled | T2 EI VALLEY SPRINGS #1 007/141 RPR GYWW | 43830860 | VALLEY SPRINGS #1 | 007/141 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.858584 | 38.1497 | ETL.8210 | 40905604 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590501 | Not Scheduled | T2 EI COLEMAN-SOUTH NONCERAM 012/263 VEG |  | COLEMAN-SOUTH | 012/263 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.10883 | 40.4037 | ETL.6450 | 40826891 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2020-02-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590524 | Q2 | T2 EI KONOCTI-MIDDLETOWN ;024/001 RPR IN | 43749609 | KONOCTI-MIDDLETOWN | ;024/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.614959 | 38.9036 | ETL.6380 | 40586670 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590525 | Not Scheduled | T2 EI VALLEY SPRINGS #1 004/088 RPL STRW | 31425843 | VALLEY SPRINGS #1 | 004/088 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Access Issues | No access /land owner | '-120.830887 | 38.1786 | ETL.8210 | 40903818 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - FF |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115590942 | Q2 | T2 Cottonwood Glenn 066/587 INSS NG REPL | 31423197 | COTTONWOOD-GLENN | 066/587 | 93K | E | Pre-2020_(5b) On structure in bucket 5 |  | 2018-12-21 | 2019-12-21 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.267917 | 40.3007 | ETL.4560 | 40846323 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115591518 | Feb | GUARDIAN #1 TAP 000/015 RPLC POLE | 31419918 | GUARDIAN #1 TAP | 000/015 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-24 | 2023-12-24 |  |  | 2021-02-24 | 2021-02-24 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.581892 | 36.5406 | ETL.2301 | 40759927 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115593220 | Feb | GUARDIAN #2 TAP 000/003 pole replacement | 31419917 | GUARDIAN #2 TAP | 000/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-24 | 2023-12-24 |  |  | 2021-02-23 | 2021-02-23 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.581756 | 36.5406 | ETL.2292 | 40656494 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115596051 | Not Scheduled | EI VALLEY SPRINGS #1 002/034 RPR STRW | 43830784 | VALLEY SPRINGS #1 | 002/034 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.791471 | 38.2048 | ETL.8210 | 40905861 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596607 | Q2 | T2 EI CLEMAN-CTTNWD 0/08 RPR PL | 43743036 | COLEMAN-COTTONWOOD | 000/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-26 | 2019-12-26 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126777 | 40.406 | ETL.6430 | 40825004 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596672 | Not Scheduled | T2 EI VALLEY SPRINGS #1 04/079 RPL POLE | 31426053 | VALLEY SPRINGS #1 | 004/079 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-26 | 2019-12-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.825687 | 38.1839 | ETL.8210 | 40903840 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Not Released | CalTrans | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596714 | Q2 | EI CLEMAN-CTTNWD 0/11 RPR PL | 43743036 | COLEMAN-COTTONWOOD | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-26 | 2019-12-26 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.129304 | 40.4065 | ETL.6430 | 40598761 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596739 | Not Scheduled | T2 EI VALLEY SPRINGS #1 003/070 RPL STRW | 31425843 | VALLEY SPRINGS #1 | 003/070 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-26 | 2019-12-26 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Access Issues | No access /land owner | '-120.819703 | 38.1896 | ETL.8210 | 40903831 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - FF |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-03-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596761 | Not Scheduled | T2 EI SPAULDING-SUMMIT 1/042 RPL CRSW | 31415019 | SPAULDING-SUMMIT | 001/042 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2018-12-22 | 2019-12-22 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.6257 | 39.3196 | ETL.8060 | 44420792 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596872 | Q2 | T2 EI CLMN-CTTNWD 000/013B RPR STRW | 43743036 | COLEMAN-COTTONWOOD | 000/013B | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-26 | 2019-12-26 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.131036 | 40.4068 | ETL.6430 | 42578763 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115596985 | Q2 | EI CLMN-CTTNWD 001/019 RPR STRW | 43743036 | COLEMAN-COTTONWOOD | 001/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-26 | 2019-12-26 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.140996 | 40.4091 | ETL.6430 | 40594912 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115597090 | Feb | T3 EI KILARC-CEDAR C 006/142 RPR INSW | 43724327 | KILARC-CEDAR CREEK | 006/142 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-26 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983317 | 40.7118 | ETL.7290 | 40759573 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-05-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115597091 | Feb | T3 EI KILARC-CEDAR C 006/146 RPR INSW | 43724327 | KILARC-CEDAR CREEK | 006/146 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-26 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.985897 | 40.7125 | ETL.7290 | 40868735 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-05-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115597799 | Q4 | T3 EI MIDDLE FORK-GOLD HILL 9/79L RPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 009/079 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-12-26 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.738363 | 38.9879 | ETL.5140 | 44553749 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115597838 | Q2 | EI COLEMAN-COTTONWOOD 002/056 RPR STRW | 43743036 | COLEMAN-COTTONWOOD | 002/056 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-26 | 2019-12-26 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.173568 | 40.4155 | ETL.6430 | 40809542 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115597872 | Not Scheduled | T2 EI VALLEY SPRINGS #1 001/019 RPR STRW | 43830781 | VALLEY SPRINGS #1 | 001/019 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-26 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.776724 | 38.207 | ETL.8210 | 40908569 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599077 | Not Scheduled | T2 EI VOLTA-DESCHUTES 009/208 RMV VEGN |  | VOLTA-DESCHUTES | 009/208 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.045267 | 40.5028 | ETL.8290 | 40877091 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-06-26 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599658 | Feb | T2 EI EL DRAD-MISRI FLAT #1 09/75 RPL PL | 31456633 | ELDORADO-MISSOURI FLAT #1 | 009/075 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 |  |  | 2021-02-21 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.770789 | 38.7471 | ETL.1530 | 40764844 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599733 | Not Scheduled | T2 EI APPLE HILL #2 TAP 000/002 INS GYWW | 43740228 | APPLE HILL #2 TAP | 000/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.683089 | 38.7579 | ETL.1541 | 40683627 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599775 | Feb | EI DORADO-MSSRI FLAT#1 09/74 RPL STRW | 31456633 | ELDORADO-MISSOURI FLAT #1 | 009/074 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 |  |  | 2021-02-21 | 2021-02-16 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.770053 | 38.7477 | ETL.1530 | 40762138 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599778 | Feb | T2 EL DRAD-MISSRI FLAT #1 9/76 RPR INSW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 009/076 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 |  |  | 2021-02-21 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.771565 | 38.7464 | ETL.1530 | 40818661 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599820 | Not Scheduled | T2 EI VALLEY SPRINGS #1 A1/023 RPL SPLW | 43831612 | VALLEY SPRINGS #1 | A001/023 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.746632 | 38.2066 | ETL.8210 | 40907082 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115599932 | Not Scheduled | T2 EI COLEMAN-SOUTH 000/002 RMV VEGN |  | COLEMAN-SOUTH | 000/002 | HNA | F | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2023-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.879032 | 40.3957 | ETL.6450 | 40740387 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600121 | Not Scheduled | T2 EI VALLEY SPRINGS #1 A2/053 RPL POLE | 31425598 | VALLEY SPRINGS #1 | A002/053 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.723369 | 38.1992 | ETL.8210 | 40907108 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600184 | Mar | T2 EI CLAY-MARTEL 025/349 REPL STRW | 31422461 | CLAY-MARTEL | 025/349 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 |  |  | 2021-03-20 | 2021-03-18 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.80962 | 38.3606 | ETL.8250 | 40873176 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600234 | Not Scheduled | T2 EI VALLEY SPRINGS #1 A2/055 RPL POLE | 31426055 | VALLEY SPRINGS #1 | A002/055 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.722136 | 38.1989 | ETL.8210 | 40907109 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 | BLM | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600629 | Not Scheduled | T2NT EI EL DRD-MISRI FT #1 10/88 STR PNT | 44585955 | ELDORADO-MISSOURI FLAT #1 | 010/088 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2022-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.781625 | 38.7361 | ETL.1530 | 40862228 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600687 | Not Scheduled | T2 EI VALLY SPRNGS-MRTLL#1 10/015 RPL PL | 31421728 | VALLEY SPRINGS-MARTELL #1 | 010/015 | 70Y | E | 2020_(1a) PSPS |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Access Issues | land owner | '-120.784316 | 38.3452 | ETL.8240 | 40758344 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 19 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115600709 | Not Scheduled | T2 EI DORADO-MISSRI FLT#1 10/89 PNT STR | 44585955 | ELDORADO-MISSOURI FLAT #1 | 010/089 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2022-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.782118 | 38.735 | ETL.1530 | 40861985 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600737 | Not Scheduled | T2NT EI EL DRD-MISRI FLT #1 10/90 PNT ST | 44585955 | ELDORADO-MISSOURI FLAT #1 | 010/090 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2022-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.782491 | 38.7343 | ETL.1530 | 40580975 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600750 | Not Scheduled | T2 EI APPLE HILL #2 TAP 000/011 RPL PL | 31423866 | APPLE HILL #2 TAP | 000/011 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.683081 | 38.7521 | ETL.1541 | 40590196 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600754 | Not Scheduled | T2 EI VLY SPRNGS-MRTL#1 011/006 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 011/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.785554 | 38.3523 | ETL.8240 | 40816463 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600759 | Not Scheduled | T2 EI VALLEY SPRINGS #1 A1/029 RPL POLE | 31469597 | VALLEY SPRINGS #1 | A001/029 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.741868 | 38.2053 | ETL.8210 | 40907086 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115600863 | Q2 | T3 EI GOLD HILL #1 024/361 CANCEL | 31429371 | GOLD HILL #1 | 024/361 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-06-27 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.849102 | 38.5823 | ETL.6950 | 44174895 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115601183 | Mar | T2 EI VLY SPRNGS-MRTL#1 010/014 RPL CNDW | 31489036 | VALLEY SPRINGS-MARTELL #1 | 010/014 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 |  |  | 2021-03-12 | 2021-03-11 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.783152 | 38.3432 | ETL.8240 | 40768889 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115601223 | Not Scheduled | T2 EI VLY SPRGS-MRTL #1 007/004 INS MRKW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 007/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.758242 | 38.2948 | ETL.8240 | 40768887 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115601322 | Not Scheduled | T2 EI VOLTA-SOUTH 001/038 RMV VEGN |  | VOLTA-SOUTH | 001/038 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.872598 | 40.4377 | ETL.8300 | 40759554 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-08-15 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115601366 | Not Scheduled | T2 EI VLY SPRNGS-MRTL#1 009/015 RPR SPLW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 009/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.775398 | 38.3284 | ETL.8240 | 40753644 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115601375 | Not Scheduled | T2 EI CARIBOU-PALERMO 006/059 REPL INSS | 31426491 | CARIBOU-PALERMO | 006/059 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536845 | 39.5515 | ETL.3190 | 40867352 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115601404 | Not Scheduled | T2 DI CARIBOU-PALERMO 007/061 RPL HRDT | 43659205 | CARIBOU-PALERMO | 007/061 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536011 | 39.5542 | ETL.3190 | 40591546 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115602042 | Not Scheduled | T2 EI CARIBOU-PALERMO 007/062 RPL INSS | 31426587 | CARIBOU-PALERMO | 007/062 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.535336 | 39.5565 | ETL.3190 | 40674915 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115604728 | Not Scheduled | T2 EI VALLEY SPRINGS #2 10/183 RPL GYWW | 43843583 | VALLEY SPRINGS #2 | 010/183 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.893785 | 38.1384 | ETL.9460 | 40907512 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115605818 | Feb | EI COLGATE-GRASS VALLEY 010/249 RPL CRSW | 31423183 | COLGATE-GRASS VALLEY | 010/249 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.079193 | 39.2283 | ETL.6490 | 40823565 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-04-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115605839 | Q2 | T2 EI VOLTA-DESCHUTES 019/433 RPL POLE | 31426666 | VOLTA-DESCHUTES | 019/433 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.218462 | 40.5501 | ETL.8290 | 40817193 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115605845 | Q2 | T2 EI VOLTA-DESCHUTES 019/439 RPL SPLW | 43736446 | VOLTA-DESCHUTES | 019/439 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.223502 | 40.5511 | ETL.8290 | 40676454 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115605855 | Not Scheduled | T2 EI VLY SPRGS-MRTL #1 003/017 RPL STRW | 31422462 | VALLEY SPRINGS-MARTELL #1 | 003/017 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.773129 | 38.2544 | ETL.8240 | 40805165 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115606124 | Q2 | T3 EI GOLD HILL #1 022/333 RPR POLE | 43708673 | GOLD HILL #1 | 022/333 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-28 | 2021-05-31 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.843256 | 38.6166 | ETL.6950 | 40768214 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115606198 | Q2 | T3 EI KONOCTI-EGL RCK 003/000 ISTL GYWW | 43685216 | KONOCTI-EAGLE ROCK | 003/000 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-28 | 2019-06-28 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.78634 | 38.8575 | ETL.6861 | 40588400 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115607779 | Not Scheduled | T2NT EI APPLE HILL #2 TAP 0/9 RMV DEBRIS | 43740228 | APPLE HILL #2 TAP | 000/009 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.683092 | 38.7533 | ETL.1541 | 40865547 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608069 | Not Scheduled | T2 EI APPLE HILL #2 TAP 001/028 INS GYWW | 43740228 | APPLE HILL #2 TAP | 001/028 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.679582 | 38.7426 | ETL.1541 | 40762386 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608263 | Not Scheduled | EI COLLINS PINE TAP 000/005 REPL SPLW | 43743558 | COLLINS PINE TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.228734 | 40.3014 | ETL.7001 | 42623453 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608652 | Q2 | T2 EI IONE TAP 002/013 RPR WDPCKR HOLE | 43844195 | IONE TAP | 002/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.93719 | 38.3764 | ETL.8253 | 40643631 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608674 | Not Scheduled | T2 EI VOLTA-DESCHUTES 017/370 CANCEL |  | VOLTA-DESCHUTES | 017/370 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.173695 | 40.5407 | ETL.8290 | 40656945 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-06-26 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608717 | Q2 | T2 EI IONE TAP 002/014 REPL PL | 31425589 | IONE TAP | 002/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.938225 | 38.3768 | ETL.8253 | 40745291 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608756 | Q2 | T2 EI VOLTA-DESCHUTES 015/330 RPL POLE | 31426666 | VOLTA-DESCHUTES | 015/330 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.14795 | 40.534 | ETL.8290 | 40667449 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608779 | Q2 | T2 EI IONE TAP 002/015 STRW | 43844195 | IONE TAP | 002/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.939235 | 38.3772 | ETL.8253 | 40745290 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115608878 | Not Scheduled | T2 EI WEIMAR-HALSEY-5/133 REPLACE POLE | 31454601 | WEIMAR-HALSEY | 005/133 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.040222 | 38.9598 | ETL.8340 | 40674277 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609078 | Not Scheduled | T2 EI PINE GROVE TAP 001/041 RPR GYWW | 43691348 | PINE GROVE TAP | 001/041 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651834 | 38.4072 | ETL.8351 | 40864228 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609081 | Not Scheduled | T2 EI WEIMAR-HALSEY-5/136 REPLACE POLE | 31454601 | WEIMAR-HALSEY | 005/136 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.041672 | 38.9583 | ETL.8340 | 40758135 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609100 | Not Scheduled | T2 EI PINE GROVE TAP 1/38 RPR GYWW | 43691348 | PINE GROVE TAP | 001/038 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.650316 | 38.4067 | ETL.8351 | 40754201 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609134 | Mar | T2 EI KILARC-DESCHUTES 000/021 RPL CRSW | 31498148 | KILARC-DESCHUTES | 000/021 | 93E | E | 2020_(1a) PSPS |  | 2018-12-28 | 2019-12-28 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875629 | 40.664 | ETL.7300 | 40701770 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115609137 | Q2 | T3 EI KONOCTI-EAGLE RCK 003/11 INST GYWW | 43685216 | KONOCTI-EAGLE ROCK | 003/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-28 | 2021-05-31 |  |  | 2021-05-06 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.788183 | 38.8691 | ETL.6861 | 40585197 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-03-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609139 | Q2 | T3 EI KNCTI-EAGL RCK 3/012 ISTL GYWW | 43685216 | KONOCTI-EAGLE ROCK | 003/012 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-28 | 2019-06-28 |  |  | 2021-05-06 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.788235 | 38.8706 | ETL.6861 | 40698955 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609483 | Q2 | T2 EI WEIMAR-HALSEY 005/124 RPL STRW | 31517752 | WEIMAR-HALSEY | 005/124 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 |  |  | 2021-05-17 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.036378 | 38.9638 | ETL.8340 | 40656025 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609544 | Not Scheduled | T2 EI COLGATE-PALERMO-3/51 RPL POLE | 31506819 | COLGATE-PALERMO | 003/051 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Could not complete work due to Scope Change Required. No work to verify. |  |  | '-121.246833 | 39.3217 | ETL.6500 | 40692947 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  | Reject | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609559 | Not Scheduled | T2 EI WEIMAR-HALSEY 005/125 RPL PL | 31454601 | WEIMAR-HALSEY | 005/125 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.03657 | 38.9636 | ETL.8340 | 40767370 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609646 | Not Scheduled | T2 EI WEIMAR-HALSEY 005/128 RPL PL | 31454601 | WEIMAR-HALSEY | 005/128 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.038275 | 38.9619 | ETL.8340 | 40822758 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609650 | Not Scheduled | T2 EI WEIMAR-HALSEY 005/129 RPL PL | 31454601 | WEIMAR-HALSEY | 005/129 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.038527 | 38.9615 | ETL.8340 | 40874760 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609687 | Not Scheduled | T2 EI KESWICK-CASCADE-3/75 REMV BRUSH |  | KESWICK-CASCADE | 003/075 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.37536 | 40.6614 | ETL.7260 | 40601921 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609694 | Not Scheduled | T2 EI SMARTVILLE-NIC #1 01/028 RMV VEGN |  | SMARTVILLE-NICOLAUS #1 | 001/028 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.307287 | 39.1911 | ETL.7990 | 40908933 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609697 | Q2 | T2 EI CLR LK-KNCTI 021/006 RPR INSW | 43749310 | CLEAR LAKE-KONOCTI | 021/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-29 | 2019-12-29 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.752875 | 38.9373 | ETL.6852 | 40826574 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-25 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609733 | Not Scheduled | T2 EI KESWICK-CASCADE 005/098 RMV VEGN |  | KESWICK-CASCADE | 005/098 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.396911 | 40.6489 | ETL.7260 | 40770316 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-08-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115609968 | Not Scheduled | T2 EI KESWICK-CASCADE 005/109 VEG | 43726760 | KESWICK-CASCADE | 005/109 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-29 | 2019-12-29 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.402665 | 40.6445 | ETL.7260 | 44811123 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610063 | Q2 | T2 EI WEIMAR-HALSEY 005/120 RPL PL | 31517752 | WEIMAR-HALSEY | 005/120 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 |  |  | 2021-05-17 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.033478 | 38.9667 | ETL.8340 | 40767389 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610112 | Feb | T2 EI SMARTVILL-NICO #2 002/043 RPL INSW | 31451776 | SMARTVILLE-NICOLAUS #2 | 002/043 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 |  |  | 2021-02-25 | 2021-02-24 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3071826 | 39.1807 | ETL.8000 | 44179489 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610113 | Q2 | T2 EI CLAY-MARTEL 32/485 RPR POLE | 31430278 | CLAY-MARTEL | 032/485 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-29 | 2019-12-29 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84033 | 38.4539 | ETL.8250 | 40904103 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610197 | Not Scheduled | T2 EI KESWICK-CASCADE 005/107 RMV VEGN |  | KESWICK-CASCADE | 005/107 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.401822 | 40.6451 | ETL.7260 | 42671336 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-08-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610275 | Q2 | T2 EI WEIMAR-HALSEY 002/048 RPL STRW | 31517752 | WEIMAR-HALSEY | 002/048 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 |  |  | 2021-05-17 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.000504 | 39.0043 | ETL.8340 | 40874846 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610278 | Q2 | T2 EI CLAY-MARTEL 32/496 REPL POLE | 31430278 | CLAY-MARTEL | 032/496 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-29 | 2019-12-29 |  |  | 2021-05-01 | 2021-04-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844423 | 38.4635 | ETL.8250 | 40912855 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 34 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610303 | Not Scheduled | T2 EI WEIMAR-HALSEY 004/108 RPR STRW | 44365514 | WEIMAR-HALSEY | 004/108 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.028822 | 38.9717 | ETL.8340 | 40693590 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610332 | Q2 | T2 EI CLAY-MARTEL 33/498 RPR POLE | 43792833 | CLAY-MARTEL | 033/498 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-29 | 2019-12-29 |  |  | 2021-05-01 | 2021-04-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844726 | 38.465 | ETL.8250 | 40912853 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115610370 | Not Scheduled | T2 EI WEIMAR-HALSEY 004/103 RPL STRW | 31498142 | WEIMAR-HALSEY | 004/103 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-12-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.027144 | 38.9733 | ETL.8340 | 40810010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115617911 | Q2 | T3 EI KONOCTI-EAGLE RCK 004/009 RPR GYWW | 43685216 | KONOCTI-EAGLE ROCK | 004/009 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2018-12-29 | 2021-05-31 |  |  | 2021-05-06 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.787713 | 38.878 | ETL.6861 | 40861216 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-03-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618245 | Q2 | T2 EI CLAY-MARTEL 33/501 RPR POLE | 43793200 | CLAY-MARTEL | 033/501 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-29 | 2019-12-29 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845314 | 38.4677 | ETL.8250 | 40912850 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618603 | Not Scheduled | T2 EI MTN GATE JCT-CSCADE 006/075 RPL PL | 31472704 | MTN GATE JCT-CASCADE | 006/075 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.335583 | 40.6533 | ETL.7640 | 40826105 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-02-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618610 | Not Scheduled | T2 EI HALSEY-PLACER 000/006 RPL POLE | 31506123 | HALSEY-PLACER | 000/006 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.044931 | 38.9549 | ETL.6990 | 40598705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618805 | Q2 | T2 EI CSCAD-BNTN-DSCHUTES 1/34 RPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 001/034 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.328658 | 40.632 | ETL.6310 | 40759460 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618815 | Q3 | T2 EI CRBOU-PLMS JCT 014/007A RPR JMPW | 43640453 | CARIBOU-PLUMAS JCT | 014/007A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.953736 | 39.9571 | ETL.6290 | 42601243 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618816 | Q3 | T2 EI CRBOU-PLMS JCT 014/007A RPR GYWW | 43640453 | CARIBOU-PLUMAS JCT | 014/007A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.953736 | 39.9571 | ETL.6290 | 42601243 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618890 | Not Scheduled | T3 EI COLGATE-CHALLENGE 02/042 RPL POLE | 31475095 | COLGATE-CHALLENGE | 002/042 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.176289 | 39.3546 | ETL.6480 | 40594209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-07-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115618891 | Not Scheduled | T3 EI COLGATE-CHALLENGE 2/043 REPL POLE | 31428954 | COLGATE-CHALLENGE | 002/043 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.17581 | 39.355 | ETL.6480 | 40590456 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619043 | Q2 | T2NT EI FORT ROSS-GUALALA 44/4 RPR INSW | 43714574 | GUALALA-MONTE RIO | 044/004 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2020-01-02 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.323228 | 38.6974 | ETL.6980 | 40750348 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619048 | Not Scheduled | EI HALSEY-PLACER 000/010 RPL POLE | 31517753 | HALSEY-PLACER | 000/010 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.047915 | 38.9517 | ETL.6990 | 40656028 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619088 | Q2 | T2 EI CASCADE-BNTN-DSCHTS 0/20 REPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 000/020 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.333157 | 40.6418 | ETL.6310 | 40759462 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619094 | Q2 | T2 EI CASCADE-BNTN-DSCHTS 0/016 REPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 000/016 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.334906 | 40.6454 | ETL.6310 | 40868659 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619157 | Not Scheduled | T2 RND MT-TBL MT #2 055/236 CANCEL | 43621090 | ROUND MTN-TABLE MTN #2 | 055/236 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2018-12-22 | 2019-12-22 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.866989 | 40.013 | ETL.6070 | 40820562 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115619189 | Q2 | T2 RND MT-TBLE MT#2 56/240 INST DAMS | 43740168 | ROUND MTN-TABLE MTN #2 | 056/240 | ICS | E | Pre-2020_(3) On high spread structure |  | 2018-12-22 | 2021-05-31 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.860403 | 39.9978 | ETL.6070 | 40635089 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115619314 | Not Scheduled | T2 EI HALSEY-PLACER 000/011 REFRAME | 31462290 | HALSEY-PLACER | 000/011 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.048355 | 38.9513 | ETL.6990 | 40767376 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619488 | Not Scheduled | EI HALSEY-PLACER 003/075 RFRM PL | 31462290 | HALSEY-PLACER | 003/075 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.072356 | 38.9144 | ETL.6990 | 40611383 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619614 | Not Scheduled | T3 EI COLGATE-CHALLENGE 1/031 RPR POLE | 43687147 | COLGATE-CHALLENGE | 001/031 | ICW | E | 2020_(1a) PSPS |  | 2019-01-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.184353 | 39.3483 | ETL.6480 | 40874645 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115619700 | Q3 | T2 EI CRBOU-PLMS JCT 015/015 CLN INSS | 43729366 | CARIBOU-PLUMAS JCT | 015/015 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2020-01-02 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.927219 | 39.9542 | ETL.6290 | 44163158 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619800 | Q2 | T2 EI PIT #7 TAP 2/24 CENT RPR GYWW | 43877044 | PIT #7 TAP | 002/024 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.94041 | 40.8282 | ETL.5442 | 44553692 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619866 | Q2 | T2 EI PIT #7 TAP 2/24L RPL POLE | 31432828 | PIT #7 TAP | 002/024 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.94041 | 40.8282 | ETL.5442 | 44553693 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619893 | Q2 | T2 EI CSCD-BNTN-DSCHTS 001/044 RPR CRSW | 43690811 | CASCADE-BENTON-DESCHUTES | 001/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.326293 | 40.6262 | ETL.6310 | 40759296 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619963 | Not Scheduled | EI HALSEY-PLACER 003/077 REPL POLE | 31404619 | HALSEY-PLACER | 003/077 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.073228 | 38.914 | ETL.6990 | 40674286 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619983 | Not Scheduled | T2 EI HALSEY-PLACER 000/015 RPR POLE | 43740262 | HALSEY-PLACER | 000/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.050654 | 38.9488 | ETL.6990 | 44235941 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115619984 | Not Scheduled | T2 EI WEIMAR-HALSEY 004/086 RPR GYWW | 44365514 | WEIMAR-HALSEY | 004/086 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.019082 | 38.9819 | ETL.8340 | 40591268 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115620037 | Q2 | T2 EI PIT #7 TAP 003/025 RPR GYWW | 43877044 | PIT #7 TAP | 003/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939086 | 40.827 | ETL.5442 | 44553738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115620322 | Not Scheduled | T2 EI HALSEY-PLACER 000/016 RPR ANCW | 43852441 | HALSEY-PLACER | 000/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.051259 | 38.9482 | ETL.6990 | 40873793 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115620435 | Not Scheduled | T2 EI HALSEY-PLACER 000/018 RPR POLE | 43740262 | HALSEY-PLACER | 000/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.052439 | 38.947 | ETL.6990 | 40591274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115620569 | Not Scheduled | T2 EI VALLEY SPRINGS-C 5/083 RPR GYWW | 43712664 | VALLEY SPRINGS-CLAY | 005/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.831632 | 38.2054 | ETL.8264 | 40905032 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115620662 | Not Scheduled | T2 EI VALLEY SPRINGS-CL 5/081 RPL SPLW | 43712664 | VALLEY SPRINGS-CLAY | 005/081 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.831266 | 38.2045 | ETL.8264 | 40904718 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115620689 | Not Scheduled | T2 EI WEIMAR-HALSEY 04/085 REPL POLE | 31498143 | WEIMAR-HALSEY | 004/085 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.018473 | 38.9825 | ETL.8340 | 40611380 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115621304 | Q3 | T2 EI CRBOU-PLMS JCT 015/000 RPR INSW | 43640453 | CARIBOU-PLUMAS JCT | 015/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.942611 | 39.9571 | ETL.6290 | 40614959 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115621336 | Q3 | T2 EI CRBOU-PLMS JCT 015/007 RPR GYWW | 43640453 | CARIBOU-PLUMAS JCT | 015/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-13 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.934872 | 39.9571 | ETL.6290 | 40824657 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115621811 | Not Scheduled | T3 EI COLGATE-CHALLENGE 01/024 REPL STRW | 31428954 | COLGATE-CHALLENGE | 001/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.188812 | 39.3449 | ETL.6480 | 40590453 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115621857 | Not Scheduled | EI HALSEY-PLACER 001/022 RPL PL | 31404619 | HALSEY-PLACER | 001/022 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-02 | 2020-01-02 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.055862 | 38.9433 | ETL.6990 | 40758139 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115621940 | Q2 | T2 EI CASCADE-BENTN-DES 002/054 RPL HRDW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/054 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.3233 | 40.6215 | ETL.6310 | 40657147 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115622030 | Q2 | T2 EI CASCADE-BENTN-DES 002/054 RPL SPLW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/054 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.3233 | 40.6215 | ETL.6310 | 40657147 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115622034 | Not Scheduled | T2 EI VLY SPRNGS-CLY 009/127 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 009/127 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850963 | 38.2553 | ETL.8264 | 40904754 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115622035 | Not Scheduled | T2 EI VLY SPRNGS-CLY 009/127 RPR GYWW | 43687883 | VALLEY SPRINGS-CLAY | 009/127 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850963 | 38.2553 | ETL.8264 | 40904754 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 15 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115624626 | Q2 | T2 EI PIT #7 TAP 002/019 RPR GYWW | 43877044 | PIT #7 TAP | 002/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9531 | 40.8316 | ETL.5442 | 44553524 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115628880 | Mar | EI CLAY-MARTEL 25/350 RPL POLE | 31422461 | CLAY-MARTEL | 025/350 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-19 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.809587 | 38.3609 | ETL.8250 | 40864589 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115630096 | Not Scheduled | T2 EI VLY SPRNGS-CLY 009/126 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 009/126 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850981 | 38.2519 | ETL.8264 | 40904753 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115630488 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/156 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 011/156 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.882948 | 38.274 | ETL.8264 | 40904771 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115630489 | Not Scheduled | T2 EI VALLY SPRNGS-CLAY 11/155 RPLC INSL | 31425636 | VALLEY SPRINGS-CLAY | 011/155 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8821551 | 38.2735 | ETL.8264 | 40921416 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115632110 | Mar | T2 EI EGL RCK-CRTN :014/018 RPR INSW | 43730688 | EAGLE ROCK-CORTINA | :014/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609317 | 38.936 | ETL.1470 | 41176321 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115632113 | Not Scheduled | T2 EI VLY SPRNGS-CLY 009/126 RPR GUY | 43712679 | VALLEY SPRINGS-CLAY | 009/126 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850981 | 38.2519 | ETL.8264 | 40904753 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115633910 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/155 RPR POLE | 43712679 | VALLEY SPRINGS-CLAY | 011/155 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.882142 | 38.2735 | ETL.8264 | 40911610 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115633918 | Mar | T2 EI EAGLE ROCK-CORTINA :14/19 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/019 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609304 | 38.9365 | ETL.1470 | 41176322 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115634025 | Mar | T2 EI EAGLE ROCK-COR :17/017 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61258 | 38.9795 | ETL.1470 | 41176381 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115636953 | Q2 | T2 EI FORT ROSS-GUAL 054/000 RPL STRW | 31462486 | GUALALA-MONTE RIO | 054/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2020-09-16 | 2020-09-19 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.473967 | 38.7351 | ETL.6980 | 40587401 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115636969 | Not Scheduled | T2 EI VLY SPRNGS-CLY 009/125 RPR GYWW | 43687883 | VALLEY SPRINGS-CLAY | 009/125 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850969 | 38.2495 | ETL.8264 | 40904752 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637000 | Mar | T2 EI EAGLE RK-CORTINA :14/20 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/020 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609255 | 38.9368 | ETL.1470 | 41176323 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637003 | Mar | T2 EI EAGLE ROCK-CORT :012/003 RPL HRDW | 43730688 | EAGLE ROCK-CORTINA | :012/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.618203 | 38.9133 | ETL.1470 | 41176415 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637028 | Q2 | T2 EI FORT ROSS-GUALALA 49/008 RPL ANCH | 31430306 | GUALALA-MONTE RIO | 049/008 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.400986 | 38.7214 | ETL.6980 | 40860968 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637029 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/153 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 011/153 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.880443 | 38.2724 | ETL.8264 | 40904769 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637034 | Q2 | T2 EI FORT ROSS-GUALALA 55/004 RPL SPLW | 43714438 | GUALALA-MONTE RIO | 055/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2020-09-16 | 2020-09-19 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.495173 | 38.7428 | ETL.6980 | 40750363 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637048 | Mar | T2 EI PLACER-DEL MAR 3/81 REPL POLE | 31454612 | PLACER-DEL MAR | 003/081 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.12884 | 38.8637 | ETL.7800 | 40820912 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637280 | Not Scheduled | T2 EI VLY SPRNGS-CLY 008/121 ANTI SPLIT | 43712679 | VALLEY SPRINGS-CLAY | 008/121 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637312 | Q2 | T2 EI CASCADE-BENTON-D 2/055 RPL POLE | 31427801 | CASCADE-BENTON-DESCHUTES | 002/055 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.323146 | 40.6211 | ETL.6310 | 40676918 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637442 | Mar | T2 EI PLACER-DEL MAR 3/80 RPL POLE | 31502247 | PLACER-DEL MAR | 003/080 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.128154 | 38.8641 | ETL.7800 | 40805781 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637453 | Mar | T2 EI EAGLE RK-CRTINA :014/021 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/021 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609158 | 38.9373 | ETL.1470 | 41176324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637458 | Q2 | T2 EI PIT #7 TAP 1/12B RPR GYWW | 43877044 | PIT #7 TAP | 001/012B | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971515 | 40.836 | ETL.5442 | 41162602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637481 | Mar | T2 EI EAGLE ROCK-CORT :018/012 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611461 | 38.9916 | ETL.1470 | 41176395 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637502 | Q2 | T2 EI PIT #7 TAP 001/012A RPR GYWW | 43877044 | PIT #7 TAP | 001/012A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971536 | 40.836 | ETL.5442 | 41162601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637522 | Mar | T2 EI EAGLE ROCK-COR :18/011 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611613 | 38.9906 | ETL.1470 | 41176394 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637530 | Q2 | T2 EI CASCADE-BENTN-DES 003/083 RPL STRW | 31427801 | CASCADE-BENTON-DESCHUTES | 003/083 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.313147 | 40.6005 | ETL.6310 | 40657141 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637553 | Q2 | T2 EI PIT #7 TAP 1/12C RPR GYWW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637555 | Q2 | T2 EI PIT #7 TAP 1/12C RPR GRWW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637557 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/154 REPL STRW | 31426450 | VALLEY SPRINGS-CLAY | 011/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.881326 | 38.273 | ETL.8264 | 40904770 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637558 | Mar | T2 EI EGL RCK-CRTN :014/004 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607913 | 38.9259 | ETL.1470 | 41176307 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637600 | Mar | T2 EI EAGLE ROCK-COR :18/011 RPR POLE | 43730688 | EAGLE ROCK-CORTINA | :018/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611613 | 38.9906 | ETL.1470 | 41176394 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637607 | Mar | T2 EI EAGLE ROCK-CRTN :014/005 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608214 | 38.9267 | ETL.1470 | 41176308 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637617 | Q2 | T2 EI FORT ROSS-GUAL 049/009 RPL ANCW | 31430306 | GUALALA-MONTE RIO | 049/009 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.402144 | 38.722 | ETL.6980 | 40876078 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637619 | Q2 | T2 EI EAGLE RCK-CORTINA :14/001 RPR ANCH | 43730688 | EAGLE ROCK-CORTINA | :014/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607904 | 38.9246 | ETL.1470 | 41176304 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637668 | Mar | T2 EI EAGLE ROCK-CORT :017/018 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :017/018 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613113 | 38.98 | ETL.1470 | 41176382 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637715 | Mar | T2 EI EAGLE ROCK-CORTINA :13/2 RPR POLE | 43730688 | EAGLE ROCK-CORTINA | :013/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61819 | 38.9164 | ETL.1470 | 41176282 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637722 | Mar | T2 EI EAGLE ROCK-C :015/000 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/000 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608804 | 38.9378 | ETL.1470 | 41176325 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637729 | Not Scheduled | EI VALLEY SPRINGS-CLAY 013/189 REPL INSW | 31433173 | VALLEY SPRINGS-CLAY | 013/189 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [6 empty] | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-120.9094669 | 38.2899 | ETL.8264 | 40914398 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637771 | Not Scheduled | T2 EI TESLA-SLDO-MNTCA 25/152 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 025/152 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.207111 | 37.4701 | ETL.4000 | 40912757 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637789 | Not Scheduled | T2 EI TESLA-SLDO-MNTCA 25/150 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 025/150 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.206138 | 37.4731 | ETL.4000 | 40912755 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637797 | Mar | T2 EI EAGLE ROCK-COR :015/001 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608649 | 38.9383 | ETL.1470 | 41176326 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637798 | Mar | T2 EI EAGLE ROCK-COR :015/001 RPR POLE | 43730688 | EAGLE ROCK-CORTINA | :015/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608649 | 38.9383 | ETL.1470 | 41176326 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115637993 | Mar | T2 EI PLACER-DEL MAR 3/74 RPR GYWW | 43755677 | PLACER-DEL MAR | 003/074 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.125078 | 38.8665 | ETL.7800 | 40583100 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638036 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/158 RPR STRW | 43727736 | VALLEY SPRINGS-CLAY | 011/158 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.884655 | 38.2749 | ETL.8264 | 40911612 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638054 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/157 RPL GUYPOLE | 31501103 | VALLEY SPRINGS-CLAY | 011/157 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.883769 | 38.2745 | ETL.8264 | 41196644 | Guy Pole-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638151 | Not Scheduled | T2 EI VLY SPRNGS-CLY 006/087 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 006/087 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833763 | 38.2121 | ETL.8264 | 40904722 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638152 | Not Scheduled | T2 EI VLY SPRNGS-CLY 006/087 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 006/087 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833763 | 38.2121 | ETL.8264 | 40904722 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638160 | Q2 | T2 EI EAGLE ROCK-CRTN :013/004 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :013/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61817 | 38.9177 | ETL.1470 | 41176284 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638219 | Q2 | T2 EI CASCADE-BNTN-DES A005/114 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/114 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.293202 | 40.5879 | ETL.6310 | 40600705 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2021-02-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638245 | Q2 | T2 EI EGL RCK-CRTN :013/005 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :013/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61811 | 38.9177 | ETL.1470 | 41176285 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638247 | Mar | T2 EI EAGLE ROCK-COR :18/013 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :018/013 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611311 | 38.9928 | ETL.1470 | 41176396 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638250 | Mar | T2 EI EAGLE ROCK-CORT :018/010 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/010 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611749 | 38.9896 | ETL.1470 | 41176393 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638258 | Mar | T2 EI PLACER-DEL MR 002/054 RPL STRW | 31454612 | PLACER-DEL MAR | 002/054 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117343 | 38.8767 | ETL.7800 | 40660918 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638296 | Mar | T2 EI EAGLE ROCK-COR :18/009 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611914 | 38.9886 | ETL.1470 | 41176392 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638341 | Mar | T2 EI PLACER-DEL MAR 2/55 RPL POLE | 31498224 | PLACER-DEL MAR | 002/055 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117381 | 38.8761 | ETL.7800 | 40758280 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | 11/20: New UPRR extension or permit started. Existing to expire 12/23_cxu7 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638359 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/110 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638366 | Mar | T2 EI EAGLE ROCK-CORT :018/008 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612069 | 38.9875 | ETL.1470 | 41176391 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638369 | Mar | T2 EI EAGLE ROCK-COR :16/001 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :016/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607849 | 38.9536 | ETL.1470 | 41176347 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638385 | Q2 | T2 EI FORT ROSS-GUAL 054/010 RPR STRS | 43714436 | GUALALA-MONTE RIO | 054/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2020-09-16 | 2020-09-19 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.489291 | 38.74 | ETL.6980 | 40587404 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638415 | Not Scheduled | T2 EI TESLA-SLDO-MNTCA 25/149 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 025/149 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.205785 | 37.4741 | ETL.4000 | 40912754 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638422 | Q2 | T2 EI FORT ROSS-GUALALA 56/001 RPL POLE | 31492553 | GUALALA-MONTE RIO | 056/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-08 | 2021-06-08 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.506423 | 38.7492 | ETL.6980 | 40584667 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638460 | Mar | T2 EI EAGLE ROCK-CORT :018/007 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612189 | 38.9867 | ETL.1470 | 41176390 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638488 | Feb | T2 EI CSCDE-BNTN-DSCHTS 004/101 REPL PL | 31431551 | CASCADE-BENTON-DESCHUTES | 004/101 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.310886 | 40.5899 | ETL.6310 | 40868647 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638489 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/107 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/107 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843693 | 38.2299 | ETL.8264 | 40906848 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638491 | Not Scheduled | T2 EI VLY SPRNGS-CLY 006/092 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 006/092 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.835735 | 38.2184 | ETL.8264 | 40905035 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638516 | Q2 | T2 EI FORT ROSS-GUAL 050/002 RPL STRW | 31462486 | GUALALA-MONTE RIO | 050/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.411617 | 38.7273 | ETL.6980 | 40700990 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638543 | Q3 | T2 EI CRIBOU-PLUMS JCT 15/9 RPL PL | 31455444 | CARIBOU-PLUMAS JCT | 015/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2020-01-02 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.932785 | 39.9564 | ETL.6290 | 40875447 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638547 | Q3 | T2 EI CRBOU-PLMS JCT 015/006 RPR STRW | 43640453 | CARIBOU-PLUMAS JCT | 015/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.935513 | 39.9572 | ETL.6290 | 40826475 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638550 | Mar | T2 EI EAGLE ROCK-C :16/000 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :016/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607787 | 38.9527 | ETL.1470 | 41176346 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638556 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/107 REPL SPLW | 43899852 | VALLEY SPRINGS-CLAY | 007/107 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843693 | 38.2299 | ETL.8264 | 40906848 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638557 | Not Scheduled | T2 EI VLY SPRNGS-CLY 008/111 REFRAME | 31426625 | VALLEY SPRINGS-CLAY | 008/111 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.847418 | 38.2341 | ETL.8264 | 40906849 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638583 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/106 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/106 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8421 | 38.2282 | ETL.8264 | 40904739 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638592 | Q2 | T2 EI FORT ROSS-GUAL 057/004 RPL ANCW | 31430306 | GUALALA-MONTE RIO | 057/004 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.515513 | 38.7667 | ETL.6980 | 40770601 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638604 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/108 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638609 | Mar | T2 EI EAGLE ROCK-CORTINA :14/8 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608898 | 38.9289 | ETL.1470 | 41176311 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638631 | Q2 | T2 EI FORT ROSS-GUAL 054/004 RPL DAMW | 43714438 | GUALALA-MONTE RIO | 054/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2020-09-16 | 2020-09-19 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.479236 | 38.7353 | ETL.6980 | 40750362 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638747 | Mar | T2 EI EAGLE ROCK-CORT :018/005 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612724 | 38.9852 | ETL.1470 | 41176388 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638815 | Mar | T2 EI EAGLE ROCK-CORT :015/019 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/019 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607646 | 38.9511 | ETL.1470 | 41176344 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638860 | Mar | T2 EI EAGLE ROCK-COR :17/014 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612526 | 38.9777 | ETL.1470 | 41176378 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115638909 | Mar | T2 EI EAGLE ROCK-CORT :018/004 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61296 | 38.9844 | ETL.1470 | 41176387 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639006 | Mar | T2 EI EAGLE ROCK-CORT :017/015 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612473 | 38.9783 | ETL.1470 | 41176379 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639009 | Mar | T2 EI EAGLE ROCK-COR :18/003 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613086 | 38.9836 | ETL.1470 | 41176386 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639041 | Q2 | T2 EI COTTONWOOD-PAN 000/003 RPR STRW | 43749232 | COTTONWOOD-PANORAMA | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267204 | 40.4019 | ETL.1340 | 40655968 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639063 | Mar | T2 EI EAGLE ROCK-CORT :017/015 RPL HRDW | 43730688 | EAGLE ROCK-CORTINA | :017/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612473 | 38.9783 | ETL.1470 | 41176379 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639076 | Mar | T2 EI EAGLE ROCK-COR :18/002 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613052 | 38.9828 | ETL.1470 | 41176385 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639079 | Mar | T2 EI EAGLE ROCK-COR :15/018 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607675 | 38.9502 | ETL.1470 | 41176343 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639128 | Mar | T2 EI EAGLE ROCK-COR :015/005 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608179 | 38.9409 | ETL.1470 | 41176330 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639210 | Q2 | T3 EI MONTE RIO-FULTON 010/003 REPL POLE | 31428882 | MONTE RIO-FULTON | 010/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 | 2020-11-10 | 2020-11-10 | 2021-05-31 |  |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.94677 | 38.4864 | ETL.7630 | 44178462 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639216 | Not Scheduled | T2 EI PARDEE #1 TAP 009/127 RPL STRW | 31426446 | PARDEE #1 TAP | 009/127 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.851035 | 38.2554 | ETL.8231 | 40679939 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 5 | EBMUD | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-07-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639224 | Not Scheduled | T2 EI FULTON-PUEBLO 012/059B RPR STRW | 43720985 | FULTON-PUEBLO | 012/059B | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.214927 | 38.509 | ETL.1600 | 43249714 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-25 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639232 | Feb | T2 EI CASCADE-BENTON-D 04/100 RPL POLE | 31431551 | CASCADE-BENTON-DESCHUTES | 004/100 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.310608 | 40.59 | ETL.6310 | 40867946 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639264 | Mar | T2 EI EAGLE ROCK-CORT :015/017 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607722 | 38.9494 | ETL.1470 | 41176342 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639280 | Mar | T2 EI EAGLE ROCK-CORT :015/006 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608192 | 38.9419 | ETL.1470 | 41176331 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639285 | Not Scheduled | T2 E1 TSLA-SLD-MNTCA 024/134 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 024/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.21818 | 37.4914 | ETL.4000 | 40912743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639505 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/109 RPR GYWW | 43727736 | VALLEY SPRINGS-CLAY | 007/109 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84561 | 38.2321 | ETL.8264 | 40904741 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639506 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/108 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639507 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/110 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639580 | Not Scheduled | EI BN VST BMSS PWR TP 000/008 INST DAMW | 43712666 | BUENA VISTA BIOMASS POWER TAP | 000/008 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-03 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-120.911483 | 38.2812 | ETL.8252 | 40857199 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639618 | Mar | T2 EI KILARC-DESCHUTES 011/249 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/249 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.031697 | 40.5686 | ETL.7300 | 40600393 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639619 | Mar | T2 EI KILARC-DESCHUTES 011/247 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/247 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.030005 | 40.5691 | ETL.7300 | 40868569 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639680 | Mar | T2 EI KILARC-DESCHUTES 011/246 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/246 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.029125 | 40.5693 | ETL.7300 | 40816232 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639683 | Mar | T2 EI KILARC-DESCHUTES 011/245 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/245 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.028085 | 40.5695 | ETL.7300 | 40810441 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639705 | Q2 | T2 EI CASCADE-BENTN-DES 004/096 REFRAME | 31486305 | CASCADE-BENTON-DESCHUTES | 004/096 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2020-01-03 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.30836 | 40.5906 | ETL.6310 | 40600710 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115639980 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/107 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 007/107 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843693 | 38.2299 | ETL.8264 | 40906848 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115640972 | Q2 | T2 EI CASCDE-BENTN-DES A004/098 RPL STRW | 31427801 | CASCADE-BENTON-DESCHUTES | A004/098 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-03 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.307173 | 40.5898 | ETL.6310 | 40868676 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641025 | Q2 | T2 EI FORT ROSS-GUALALA 49/003 RPL POLE | 31492553 | GUALALA-MONTE RIO | 049/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.395777 | 38.7218 | ETL.6980 | 40648495 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641084 | Not Scheduled | EI VALLEY SPRINGS-CLAY 013/180 RPR STRW | 43727736 | VALLEY SPRINGS-CLAY | 013/180 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.904357 | 38.2851 | ETL.8264 | 40904785 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641248 | Not Scheduled | T2 EI PIT #5-ROUD MTN #2 11/111 RMV VEGN |  | PIT #5-ROUND MTN #2 | 011/111 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-04 | 2020-01-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.933528 | 40.8221 | ETL.5430 | 44561309 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-01-13 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641308 | Mar | T2 EI EAGLE ROCK-COR :015/008 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608154 | 38.9434 | ETL.1470 | 41176333 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641527 | Q2 | T2 EI EGLE ROCK-REDBUD :012/003 RPL STRW | 31502251 | EAGLE ROCK-REDBUD | :012/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2019-09-13 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.618032 | 38.9133 | ETL.1480 | 40648900 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641609 | Q2 | T2 EI HAT CRK #1-WSTWD 003/073 REFRAME | 31471575 | HAT CREEK #1-WESTWOOD | 003/073 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-03 | 2020-01-03 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4757 | 40.9175 | ETL.7030 | 40591002 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115641750 | Not Scheduled | EI VALLY SPRGS-MRTLL #1 004/008 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 004/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.768506 | 38.2603 | ETL.8240 | 40876087 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Victor |  | Y - Prog Multi | Yes | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115642050 | Q3 | T2 EI DLTA-MTN GTE JCT 001/037 RPL STRW | 31456311 | DELTA-MOUNTAIN GATE JCT | 001/037 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-04 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.397335 | 40.9159 | ETL.6750 | 40771404 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115642147 | Not Scheduled | EI VALLEY SPRGS-MRTLL #1 003/014 RPL STR | 31422462 | VALLEY SPRINGS-MARTELL #1 | 003/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.774555 | 38.2525 | ETL.8240 | 40768883 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115642184 | Not Scheduled | EI VALLEY SPRGS-MRTLL #1 004/009 RPL STR | 31422462 | VALLEY SPRINGS-MARTELL #1 | 004/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.767795 | 38.2612 | ETL.8240 | 40864366 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 16 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115642338 | Mar | T2 EI EGLE RCK-CRTN :015/016 RPL STRW | 31502252 | EAGLE ROCK-CORTINA | :015/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607747 | 38.9486 | ETL.1470 | 41176341 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115642546 | Not Scheduled | T2 EI PIT #5-RND MTN #2 8/83 CANCEL | 43755674 | PIT #5-ROUND MTN #2 | 008/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929556 | 40.8715 | ETL.5430 | 44561259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115642555 | Q2 | T2 EI EAGLE ROCK-REDBUD :13/6 RPL POLE | 31492608 | EAGLE ROCK-REDBUD | :013/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-04-11 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.616438 | 38.9176 | ETL.1480 | 40809077 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115643406 | Mar | T2 EI KILARC-DESCHUTES 011/251 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/251 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.033329 | 40.5682 | ETL.7300 | 40676511 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115643407 | Mar | T2 EI KILARC-DESCHUTES 012/259 RPL STRW | 31423831 | KILARC-DESCHUTES | 012/259 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.040326 | 40.5665 | ETL.7300 | 40826000 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115643409 | Mar | T2 EI KILARC-DESCHUTES 012/252 RPL STRW | 31423831 | KILARC-DESCHUTES | 012/252 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.034268 | 40.568 | ETL.7300 | 40617703 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115643443 | Q2 | T2 EI EGLE RCK RDBD :013/010 RPL PL | 31488228 | EAGLE ROCK-REDBUD | :013/010 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613373 | 38.9176 | ETL.1480 | 40588093 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115643586 | Not Scheduled | T2 EI VLY SPRNGS-CLY 011/160 RPR STRW | 43712893 | VALLEY SPRINGS-CLAY | 011/160 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.886319 | 38.2758 | ETL.8264 | 40904773 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115644088 | Mar | T2 EI KILARC-DESCHUTES A025/530 RPL PL | 31440586 | KILARC-DESCHUTES | A025/530 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-04 | 2020-01-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.285286 | 40.5711 | ETL.7300 | 40702809 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115644207 | Mar | T2 EI KILARC-DESCHUTES 012/254 RPL STRW | 31423831 | KILARC-DESCHUTES | 012/254 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2020-01-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.036153 | 40.5675 | ETL.7300 | 40676515 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115644972 | Q2 | T2 EI HAT CREK #1-WSTWD 005/115 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 005/115 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-04 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.43772 | 40.9036 | ETL.7030 | 40816098 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645090 | Q2 | EI CSCD-BTN-DSCHTS A009/188 RPR CRSW | 43690811 | CASCADE-BENTON-DESCHUTES | A009/188 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-30 | 2021-04-12 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.239968 | 40.5556 | ETL.6310 | 40868661 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645097 | Q2 | T2 EI CSCD-BTN-DSCHTS A008/171 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A008/171 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255309 | 40.5579 | ETL.6310 | 40868663 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645126 | Q2 | T2 EI CSCD-BTN-DSCHTS A008/176 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/176 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.25055 | 40.5569 | ETL.6310 | 41177755 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645147 | Q2 | T2 EI CSCDE-BNTN-DSCHUTS A009/184 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A009/184 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2435 | 40.5557 | ETL.6310 | 40676943 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645154 | Q2 | T2 EI CSCDE-BNTN-DSCHUTS A008/166 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A008/166 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.259242 | 40.5591 | ETL.6310 | 40650234 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645179 | Mar | T2 EI EGLE RCK-CRTINA :019/011 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :019/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-04 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611403 | 39.0063 | ETL.1470 | 41176409 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645198 | Q2 | T2 EI FORT ROSS-GUALALA 58/11 RPL PL | 31462486 | GUALALA-MONTE RIO | 058/012 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.521627 | 38.7866 | ETL.6980 | 40686400 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645289 | Q2 | T2 EI CORDELIA #2 TAP 003/067 RPL SPLW | 43743931 | CORDELIA #2 TAP | 003/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.154242 | 38.2508 | ETL.8184 | 40599323 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645305 | Q2 | T2 EI PLRMO-ORVILLE #2 A006/082 RPR STRW | 43724470 | PALERMO-OROVILLE #2 | A006/082 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502582 | 39.5195 | ETL.7740 | 40585852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645330 | Q2 | T2 EI CSCDE-BNTN-DSCHTS A006/125 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A006/125 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.285091 | 40.5829 | ETL.6310 | 41177763 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645335 | Q2 | T2 EI PALERMO-OROVILLE #2 A7/85 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A007/085 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502255 | 39.523 | ETL.7740 | 40599877 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645346 | Q2 | T2 EI PLRMO-ORVILLE #2 A007/084 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A007/084 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5026 | 39.5221 | ETL.7740 | 44196306 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645392 | Not Scheduled | T2 EI PALRMO-ORVILLE #1 1/24 REFRAME PLE | 31474478 | PALERMO-OROVILLE #1 | 001/024 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.533728 | 39.4592 | ETL.7730 | 40598414 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-04-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645405 | Q2 | T2 EI CSCD-BTN-DSCHTS A007/161 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A007/161 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.260352 | 40.5614 | ETL.6310 | 40590319 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645406 | Q2 | T2 EI CSCD-BTN-DSCHTS A007/160 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A007/160 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.260419 | 40.562 | ETL.6310 | 40586274 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645414 | Mar | T2 EI EAGL RCK-CRTINA :20/001 RPR GYWR | 43730688 | EAGLE ROCK-CORTINA | :020/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611978 | 39.0104 | ETL.1470 | 41176412 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645418 | Q2 | T2 EI CSCD-BTN-DSCHTS A006/144 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A006/144 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.270148 | 40.5724 | ETL.6310 | 40600697 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645469 | Q2 | T2 EI HTCRK #1-WSTWD 013/261 RPR CRSW | 43736796 | HAT CREEK #1-WESTWOOD | 013/261 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.359967 | 40.8109 | ETL.7030 | 40676252 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645481 | Q2 | T2 EI HAT CRK #1-WESTWD 13/265 RPR CRSW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645483 | Q2 | T2 EI HAT CRK #1-WESTWD 13/265 RPL SPLW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645495 | Q2 | T2 EI HAT CREK #1-WSTWD 13/265 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645505 | Q2 | T2 EI HTCRK #1-WSTWD 013/267 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 013/267 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.355795 | 40.8075 | ETL.7030 | 40759174 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645591 | Q2 | T2 EI CSCD-BTN-DSCHTS A007/147 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A007/147 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267637 | 40.5706 | ETL.6310 | 40759308 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645597 | Q2 | T2 EI HAT CRK #1-WESTWD 14/274 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 014/274 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.350953 | 40.8036 | ETL.7030 | 40600202 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645599 | Q2 | T2 EI HTCRK #1-WSTWD 014/271 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 014/271 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.352952 | 40.8053 | ETL.7030 | 40759176 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645676 | Feb | T3 EI ORO FINO TAP 000/015 INS GYWW | 43758390 | ORO FINO TAP | 000/015 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-05 | 2020-01-05 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.615663 | 39.8698 | ETL.6721 | 40751729 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645715 | Q2 | T2 EI HAT CREK #1-WSTWD 14/272 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 014/272 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.352368 | 40.8047 | ETL.7030 | 40817107 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645770 | Q2 | T2 EI CSCDE-BNTN-DSCHTES A005/123 RPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | A005/123 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-30 | 2021-04-12 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.286632 | 40.584 | ETL.6310 | 40600702 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645785 | Q2 | T2 EI CSCDE-BNTN-DSCHUTS A006/135 RPL PL | 31421915 | CASCADE-BENTON-DESCHUTES | A006/135 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.277243 | 40.5774 | ETL.6310 | 40868669 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645786 | Q2 | T2 EI CSCDE-BNTN-DSCHTES A6/131 RPPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A006/131 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.280549 | 40.5797 | ETL.6310 | 44630141 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115645930 | Feb | T2 EI COLGATE-PALERMO-13/254 RPL POLE | 31517754 | COLGATE-PALERMO | 013/254 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-02-10 | 2021-01-28 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.400295 | 39.3854 | ETL.6500 | 40757199 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115647683 | Q2 | T2 EI HT CRK #1-WSTWD 010/198 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 010/198 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.396302 | 40.8495 | ETL.7030 | 40825661 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115647837 | Q3 | T2 EI CRBOU-PLMS JCT 014/015 RPR JMPW | 43640453 | CARIBOU-PLUMAS JCT | 014/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.9445 | 39.9571 | ETL.6290 | 40768906 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115647913 | Q3 | T2 EI CARIBOU-PLUMAS JCT 14/14 RPR JUMW | 43640453 | CARIBOU-PLUMAS JCT | 014/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-02 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.944982 | 39.9571 | ETL.6290 | 40758743 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115648018 | Q2 | T2 EI PALRM-ORVILL #2 A6/79 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A006/079 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-05 | 2020-01-05 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502572 | 39.5141 | ETL.7740 | 40767027 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649647 | Q2 | T2 EI HT CRK #1-WSTWD 012/239 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 012/239 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.375418 | 40.8233 | ETL.7030 | 40827604 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649649 | Q2 | T2 EI HT CRK #1-WSTWD 011/224 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 011/224 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.384298 | 40.8322 | ETL.7030 | 40770717 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649666 | Q2 | T2 EI HT CRK #1-WSTWD 012/236 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 012/236 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.377247 | 40.8248 | ETL.7030 | 40600155 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649667 | Q2 | T2 EI HT CRK #1-WSTWD 012/235 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 012/235 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.378 | 40.8254 | ETL.7030 | 40868436 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649729 | Q2 | T2 EI HT CRK #1-WSTWD 014/277 REFRAME | 31471575 | HAT CREEK #1-WESTWOOD | 014/277 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.348833 | 40.8019 | ETL.7030 | 40817109 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649801 | Q2 | T2 EI PARADISE-TABLE MTN 24/185 RPL POLE | 31453760 | PARADISE-TABLE MTN | 024/185 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.639516 | 39.6996 | ETL.4316 | 40656378 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649804 | Q2 | T2 EI HT CRK #1-WSTWD 014/277 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 014/277 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.348833 | 40.8019 | ETL.7030 | 40817109 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649820 | Q2 | T2 EI HT CRK #1-WSTWD 014/276 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 014/276 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-02-23 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.349582 | 40.8025 | ETL.7030 | 40770724 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649821 | Q2 | T2 EI HT CRK #1-WSTWD 014/279 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 014/279 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2020-01-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.347463 | 40.8008 | ETL.7030 | 40617047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649978 | Not Scheduled | T2 EI COLGATE-PALERMO-8/156 REPLACE POLE | 31423185 | COLGATE-PALERMO | 008/156 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-07 | 2020-01-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.327757 | 39.3513 | ETL.6500 | 40598487 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115649979 | Mar | T2 EI PARADISE-BUTTE 06/066 RPR PL | 43758389 | PARADISE-BUTTE | 006/066 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.680342 | 39.7039 | ETL.4396 | 40758512 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650317 | Q2 | T3 EI PRDSE-TBLE MTN 022/172L RPR GYWW | 43724325 | PARADISE-TABLE MTN | 022/172 | ICW | E | 2020_(1a) PSPS |  | 2019-01-07 | 2019-07-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383223 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115650404 | Mar | T2 EI KILARC-DESCHUTES A023/489 RPL PL | 31440586 | KILARC-DESCHUTES | A023/489 | 70Y | E | 2020_(1a) PSPS |  | 2019-01-07 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.250632 | 40.5639 | ETL.7300 | 40594917 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115650529 | Q2 | T2 EI PARADISE-TABLE MTN 24/182L REPL PL | 31453760 | PARADISE-TABLE MTN | 024/182 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383234 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650539 | Q2 | T2 EI PARADISE-TABLE MTN 24/182C REPL PL | 31453760 | PARADISE-TABLE MTN | 024/182 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383235 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650558 | Feb | T2 EI COLGATE-PALERMO-12/234 RPL POLE | 31517754 | COLGATE-PALERMO | 012/234 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-07 | 2020-01-07 |  |  | 2021-02-10 | 2021-01-28 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Per email from [REDACTED], this notification was submit in error. Submission intended for 115650557 |  |  | '-121.385235 | 39.3793 | ETL.6500 | 40824152 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  | Reject | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650569 | Q2 | T2 EI PARADISE-TABLE MTN 25/192L RPL PL | 31453760 | PARADISE-TABLE MTN | 025/192 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6579093 | 39.7015 | ETL.4316 | 44383250 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650650 | Not Scheduled | T2 EI PARADISE-BUTTE 5/058 PAINT STRS | 43758389 | PARADISE-BUTTE | 005/058 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-07 | 2022-10-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.669565 | 39.7109 | ETL.4396 | 41127253 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650723 | Mar | T2 EI PARADISE-BUTTE 8/078 RPR GYWW | 43758389 | PARADISE-BUTTE | 008/078 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.707534 | 39.7064 | ETL.4396 | 40618590 | Ground Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115650889 | Q2 | T3 EI PRDSE-TBLE MTN 21/167 MRKR BALL | 43724325 | PARADISE-TABLE MTN | 021/167 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712236 | FAA Lighting-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115651060 | Q2 | T2 EI PARADISE-TABLE MTN 24/188L RPL PL | 31453760 | PARADISE-TABLE MTN | 024/188 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6518538 | 39.7009 | ETL.4316 | 44383247 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115651176 | Mar | T2 EI KILARC-DESCHUTES A023/488 RPL PL | 31440586 | KILARC-DESCHUTES | A023/488 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-07 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.249914 | 40.5639 | ETL.7300 | 40864633 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115651503 | Not Scheduled | MANTECA-LOUISE 001/037 REPLACE POLE | 31425591 | MANTECA-LOUISE | 001/037 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-13 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.248711 | 37.812 | ETL.7470 | 40768622 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-11-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115652279 | Not Scheduled | VALLEY SPRINGS #2 2/32 REPLACE POLE | 31431649 | VALLEY SPRINGS #2 | 002/032 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-19 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-120.791403 | 38.2134 | ETL.9460 | 40907391 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 16 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-10-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115652301 | Not Scheduled | VALLEY SPRINGS #2 2/46 REPLACE POLE | 31431649 | VALLEY SPRINGS #2 | 002/046 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-10 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-120.800546 | 38.206 | ETL.9460 | 40907401 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 16 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-10-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115652392 | Q2 | T2 EI ELK-GUALALA 59/003 RPR GYWW | 43735921 | ELK-GUALALA | 059/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-07 | 2020-01-07 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.590239 | 38.8683 | ETL.8410 | 40667888 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115652396 | Mar | T2 EI PARADISE-BUTTE 06/068 RPR PL | 43758389 | PARADISE-BUTTE | 006/068 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.683961 | 39.7043 | ETL.4396 | 41127267 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115652581 | Q2 | T2 EI ELK-GUALALA 39/6 RPR SPLC | 43735736 | ELK-GUALALA | 039/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-07 | 2020-01-07 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.698819 | 39.0933 | ETL.8410 | 40820732 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115652582 | Q2 | T2 EI ELK-GUALALA 39/8 RPL ANCH | 31431175 | ELK-GUALALA | 039/008 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-07 | 2020-01-07 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.698251 | 39.0922 | ETL.8410 | 40877405 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-03-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-03-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115653473 | Not Scheduled | T2 EI COLGATE-PALERMO 10/203 RPL POLE | 31506096 | COLGATE-PALERMO | 010/203 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-07 | 2020-01-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.364803 | 39.3666 | ETL.6500 | 40815251 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655299 | Not Scheduled | T2 EI COLGATE-PALERMO 010/197 RPL STRW | 31423185 | COLGATE-PALERMO | 010/197 | 70Y | E | 2020_(1a) PSPS |  | 2019-01-07 | 2020-01-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.360004 | 39.3641 | ETL.6500 | 40611003 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115655434 | Q2 | T2 EI MNDCNO-PHL JCT-HPLND 00/4 INS GYWW | 43731263 | MENDOCINO-PHILO JCT-HOPLAND | 000/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-08 | 2021-05-31 |  |  | 2021-05-14 | 2021-05-11 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.194151 | 39.2497 | ETL.7520 | 40769897 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655463 | Mar | T2 EI PARADISE-BUTTE 7/76B RPR GYWS | 43881381 | PARADISE-BUTTE | 007/076B | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701932 | 39.7059 | ETL.4396 | 40758514 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655520 | Mar | T2 EI PRDS-BTT 007/076C RPR GYWS | 43758389 | PARADISE-BUTTE | 007/076C | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701948 | 39.7058 | ETL.4396 | 44382704 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655526 | Mar | T2 EI PARADISE-BUTTE 007/076A RPR GYWS | 43758389 | PARADISE-BUTTE | 007/076A | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7019 | 39.706 | ETL.4396 | 44382703 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655671 | Q2 | T3 EI PARADISE-TABLE MTN 16/134 RPR GYWW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.4994124 | 39.6792 | ETL.4316 | 44552419 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655714 | Not Scheduled | T3 EI PARADISE-TABLE MTN 16/134 CANCEL | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.4994124 | 39.6792 | ETL.4316 | 44552419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655779 | Q2 | T2 EI CORDELIA #2 TAP 5/110 RPL POLE | 31433523 | CORDELIA #2 TAP | 005/110 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 |  |  | 2021-05-04 | 2021-04-26 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.187984 | 38.2523 | ETL.8184 | 40768057 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-05-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655908 | Q2 | T3 EI PARADISE-TABLE MTN 16/136R RPL PL | 31459421 | PARADISE-TABLE MTN | 016/136 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.50381 | 39.6798 | ETL.4316 | 44552464 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115655966 | Q2 | T3 EI PARADISE-TABLE MTN 16/136L RPL PL | 31459421 | PARADISE-TABLE MTN | 016/136 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.5038231 | 39.6798 | ETL.4316 | 44552371 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656021 | Not Scheduled | T3 EI GYSRS #7-EGLE RCK 00/005A RPR GRWW | 43693045 | GEYSERS #7-EAGLE ROCK | 000/005A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 | 2020-10-07 | 2020-10-07 | [5 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.808631 | 38.8157 | ETL.1680 | 40576079 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656151 | Not Scheduled | T2 DI CARIBOU-PALERMO 8/73 PAINT TOWER | 44056495 | CARIBOU-PALERMO | 008/073 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52867 | 39.5783 | ETL.3190 | 40656339 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656186 | Not Scheduled | T2 DI CARIBOU PALERMO 14/118 PAINT TOWER | 44056495 | CARIBOU-PALERMO | 014/118 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-28 | 2019-12-28 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656267 | Not Scheduled | T2 EI JEFFERSON-STANFORD 1/036 REPL POLE | 31426911 | JEFFERSON-STANFORD (NO FLY) | 001/036 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.261563 | 37.4615 | ETL.7220 | 40755284 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656590 | Not Scheduled | T2 DI CARIBOU PALERMO 15/119 CORROSION S | 44056495 | CARIBOU-PALERMO | 015/119 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-28 | 2019-12-28 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506565 | 39.6554 | ETL.3190 | 40913201 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656687 | Not Scheduled | T2 EI JEFFERSON-STANFORD 1/23 RPR INSW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/023 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.269243 | 37.4614 | ETL.7220 | 40599123 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656747 | Not Scheduled | T2 DI CARIBOU-PALERMO 5/51 RPL INS | 31423830 | CARIBOU-PALERMO | 005/051 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.540459 | 39.5419 | ETL.3190 | 40617124 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656861 | Q2 | T2 EI MENDCIN-PHL JCT-HPLND 4/0 RMV STUB | 43762361 | MENDOCINO-PHILO JCT-HOPLAND | 004/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-08 | 2022-01-08 |  |  | 2021-05-14 | 2021-05-11 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.15516 | 39.2122 | ETL.7520 | 44140502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656863 | Mar | EI GLENN #2 026/486 RPR STRW | 43748401 | GLENN #2 | 026/486 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2020-01-08 |  |  | 2021-03-10 | 2021-03-08 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.012339 | 39.5284 | ETL.6930 | 44421367 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656903 | Not Scheduled | T2 DI CARIBOU-PALERMO 5/46 RPR INS | 31426498 | CARIBOU-PALERMO | 005/046 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54042 | 39.5282 | ETL.3190 | 40816564 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656911 | Not Scheduled | DISTRIBUTION RPL POLE |  | COLGATE-PALERMO | 013/259 | 70Y | E | 2020_(1a) PSPS |  | 2019-01-08 | 2020-01-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.403219 | 39.3875 | ETL.6500 | 40873550 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115656971 | Not Scheduled | T2 DI CARIBOU-PALERMO- 5/45 RPL FNDTN |  | CARIBOU-PALERMO | 005/045 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540407 | 39.526 | ETL.3190 | 40755507 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115656975 | Not Scheduled | T2 DI CARIBOU PALERMO 12/101 RPL INS | 31426499 | CARIBOU-PALERMO | 012/101 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515151 | 39.6251 | ETL.3190 | 41162739 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657042 | Q2 | T2 EI MNDCNO-PHL JCT-HPLND 1/11 INS GYWW | 43731263 | MENDOCINO-PHILO JCT-HOPLAND | 001/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-08 | 2021-05-31 |  |  | 2021-05-14 | 2021-05-11 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.165327 | 39.2387 | ETL.7520 | 40584524 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657146 | Not Scheduled | T2 DI CARIBOU-PALERMO 5/49 RPL INS | 31425651 | CARIBOU-PALERMO | 005/049 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540447 | 39.5329 | ETL.3190 | 40870660 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657177 | Not Scheduled | T2 DI CARIBOU PALERMO 15/122 RPL BOLTS | 43735847 | CARIBOU-PALERMO | 015/122 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.50374 | 39.6632 | ETL.3190 | 40913204 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657205 | Q2 | T2 EI MNDCNO-PHL JCT-HPLND 1/9 INS GYWW | 43731263 | MENDOCINO-PHILO JCT-HOPLAND | 001/009 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-08 | 2021-05-31 |  |  | 2021-05-14 | 2021-05-11 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.16894 | 39.2391 | ETL.7520 | 40875541 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657364 | Not Scheduled | T2 DI CARIBOU PALERMO 10/90 RPL INS | 31426588 | CARIBOU-PALERMO | 010/090 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.521192 | 39.6038 | ETL.3190 | 40599266 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657366 | Not Scheduled | T2 DI CARIBOU PALERMO 12/105 RPL INS | 31426498 | CARIBOU-PALERMO | 012/105 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.51301 | 39.6326 | ETL.3190 | 40765166 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657534 | Not Scheduled | T2 DI CARIBOU-PALERMO-8/66 TWR RPL FNDTN |  | CARIBOU-PALERMO | 008/066 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657726 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 10/86 RPL HRDW | 43659205 | CARIBOU-PALERMO | 010/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523581 | 39.5954 | ETL.3190 | 40816572 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657896 | Not Scheduled | T2 DI CARIBOU-PALERMO 08/66 RPR STUB | 44056495 | CARIBOU-PALERMO | 008/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657933 | Not Scheduled | T2 DI CARIBOU-PALERMO 15/122 RPR FNDTN | 44056495 | CARIBOU-PALERMO | 015/122 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.50374 | 39.6632 | ETL.3190 | 40913204 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657936 | Not Scheduled | T2 DI CARIBOU-PALERMO 11/97 RPL AUT SPL | 43659205 | CARIBOU-PALERMO | 011/097 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115657991 | Not Scheduled | T2 DI CARIBOU PALERMO 10/88 RPL INS | 31425651 | CARIBOU-PALERMO | 010/088 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.522492 | 39.5992 | ETL.3190 | 40867947 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115658016 | Not Scheduled | T2 DI CARIBOU PALERMO 11/95 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 011/095 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.518138 | 39.6146 | ETL.3190 | 40755509 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115658030 | Not Scheduled | T2 DI CARIBOU PALERMO 11/93 RPR FNDTN | 44056495 | CARIBOU-PALERMO | 011/093 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115658033 | Not Scheduled | T2 DI CARIBOU PALERMO 10/91 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 010/091 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520902 | 39.6048 | ETL.3190 | 40591547 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115658045 | Not Scheduled | T2 DI CARIBOU PALERMO 10/92 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 010/092 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115658156 | Mar | T2 EI KILARC-DESCHUTES A024/506 RFRM | 31498148 | KILARC-DESCHUTES | A024/506 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-08 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.265184 | 40.5669 | ETL.7300 | 40878612 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659159 | Mar | T2 EI KILARC-DESCHUTES A024/509 RPL PL | 31440586 | KILARC-DESCHUTES | A024/509 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-09 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267598 | 40.5678 | ETL.7300 | 40602862 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-01-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659399 | Not Scheduled | T3 DI CARIBOU PALERMO 16/128 RPR HRDWR | 43735847 | CARIBOU-PALERMO | 016/128 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-06-21 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659423 | Not Scheduled | T2 DI CARIBOU-PALERMO-011/100 RPL INSUL | 31426588 | CARIBOU-PALERMO | 011/100 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659468 | Not Scheduled | T2 DI CARIBOU-PALERMO 10/85 RPL INS | 31426498 | CARIBOU-PALERMO | 010/085 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523861 | 39.5944 | ETL.3190 | 40761090 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659580 | Not Scheduled | T3 DI CARIBOU-PALERMO 16/128 RPR INS | 43735847 | CARIBOU-PALERMO | 016/128 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-05-21 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659705 | Not Scheduled | T2 DI CARIBOU PALERMO 11/100 RPL INS | 31423830 | CARIBOU-PALERMO | 011/100 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659733 | Q2 | T2 EI CRDLA #2 TAP 003/057 RPL POLE | 31460585 | CORDELIA #2 TAP | 003/057 | 70Y | E | 2020_(1a) PSPS |  | 2019-01-09 | 2020-01-09 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147225 | 38.2411 | ETL.8184 | 40612468 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115659873 | Q2 | T2 EI COTTONWOOD-DELEVAN #1 007/049 DMP | 43726632 | COTTONWOOD-DELEVAN #1 | 007/049 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-09 | 2020-01-09 |  |  | 2021-04-02 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.268085 | 40.2928 | ETL.4550 | 44233320 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115659923 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 14/117 RPL HRW | 43735847 | CARIBOU-PALERMO | 014/117 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.507554 | 39.6519 | ETL.3190 | 40913199 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115660084 | Q2 | T2 EI OCEANO-CAL 19/127 RPR GYWW | 43689786 | OCEANO-CALLENDAR SW STA | 019/127 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-09 | 2021-05-31 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-24 |  |  |  | TR2 | LATE | South | WSIP | FSRP | Completed |  |  |  |  | '-120.57744 | 35.1003 | ETL.2394 | 40809743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 6 | 00/00/0000 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115660416 | Q2 | T2 EI MENDOCINO-PHILO 11/8 RPL POLE | 31471950 | MENDOCINO-PHILO JCT-HOPLAND | 011/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-09 | 2020-01-09 |  |  | 2021-05-14 | 2021-05-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.156625 | 39.106 | ETL.7520 | 40860850 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2020-06-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115660713 | Mar | T2 DI DRM-GRSS VLLY WMR 14/333 RPR WPH | 43746391 | DRUM-GRASS VALLEY-WEIMAR | 014/333 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-05 | 2021-05-31 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.942933 | 39.1254 | ETL.6760 | 40867122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115661151 | Q2 | T2 EI OCEANO-CAL 21/154 RPL POLE | 31426920 | OCEANO-CALLENDAR SW STA | 021/154 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-09 | 2021-05-31 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-24 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.582418 | 35.0761 | ETL.2394 | 40590137 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 6 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115661368 | Q2 | T2 EI CLGTE-PLRMO 019/381 RPL SPLW | 43728970 | COLGATE-PALERMO | 019/381 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-09 | 2020-01-09 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.464652 | 39.4466 | ETL.6500 | 40757211 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115661772 | Not Scheduled | T2 EI CLLNDR SW STA-MSA 004/073 RPL STRW | 31426164 | CALLENDAR SW STA-MESA | 004/073 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-09 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.512083 | 35.0528 | ETL.1210 | 40751944 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-05-29 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115662162 | Q2 | T2 EI CLGTE-PLRMO 017/353 RPR STRW | 43728970 | COLGATE-PALERMO | 017/353 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-09 | 2020-01-09 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.441702 | 39.4426 | ETL.6500 | 40866833 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115662321 | Not Scheduled | EI CALLENDER SS-MESA 1/21 REPL SPLICE | 43686102 | CALLENDAR SW STA-MESA | 001/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-09 | 2020-01-09 | [8 empty] | LATE | South | WSIP | [6 empty] | '-120.570748 | 35.051 | ETL.1210 | 40618576 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115670784 | Mar | T2 DI DRM-GRSS VLLY-WMR 15/348 RPL SPLCE | 43746394 | DRUM-GRASS VALLEY-WEIMAR | 015/348 | ICW | E | 2020_(1a) PSPS |  | 2019-01-07 | 2020-01-07 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.950421 | 39.1183 | ETL.6760 | 40598931 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-07 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115671028 | Q2 | T2 EI COTTONWD-RED BLF 014/286 RPR STRW | 43744380 | COTTONWOOD-RED BLUFF | 014/286 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-01 | 2020-09-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255555 | 40.2195 | ETL.6660 | 40909622 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115671126 | Q2 | T2 EI COTTONWOOD-PAN 000/015 REPR INSW | 43881008 | COTTONWOOD-PANORAMA | 000/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267411 | 40.4131 | ETL.1340 | 40600908 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115671221 | Not Scheduled | T2 EI SN LUS OBSPO-OCNO 019/113 WSH INSW | 44585464 | SAN LUIS OBISPO-OCEANO | 019/113 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-10 | 2021-05-31 |  | 2021-01-12 | [5 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.5731258 | 35.0983 | ETL.3530 | 40678317 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115671290 | Not Scheduled | T2 EI DUNLAP TAP 12/2 RPLC CRSW | 31426901 | DUNLAP TAP | 012/002 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.090968 | 36.6812 | ETL.9061 | 40685439 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Fresno |  | Y - 9 | LNW | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115671291 | Q2 | T2 EI COTTONWOOD-PAN 000/003 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267204 | 40.4019 | ETL.1340 | 40655968 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115671459 | Not Scheduled | T2NT DI DRM-GRS VLY-WMR B016/368 RPR MKR | 43746394 | DRUM-GRASS VALLEY-WEIMAR | B016/368 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-09 | 2020-01-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.958042 | 39.121 | ETL.6760 | 40767280 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115671668 | Q2 | T2 EI COTTONWOOD-PAN 000/002 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267306 | 40.401 | ETL.1340 | 40674162 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672588 | Not Scheduled | T2 DI CARIBOU-PALERMO 13/114 RPR CNDCTR | 43659205 | CARIBOU-PALERMO | 013/114 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509255 | 39.6459 | ETL.3190 | 40762753 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672614 | Not Scheduled | T2 DI CARIBOU-PALERMO 13/114 RPR INSL CP | 43659205 | CARIBOU-PALERMO | 013/114 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509255 | 39.6459 | ETL.3190 | 40762753 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672736 | Q2 | T2NT EI COLGATE-PALRMO 20/409 RPL PL | 31505737 | COLGATE-PALERMO | 020/409 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-10 | 2020-01-10 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.489608 | 39.4531 | ETL.6500 | 40664454 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672763 | Not Scheduled | T2 DI CARIBOU-PALERMO 13/113 RPR INSULTR | 43659205 | CARIBOU-PALERMO | 013/113 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509591 | 39.6447 | ETL.3190 | 40656347 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672764 | Q2 | T2 EI COLGATE-PALERMO 020/408 REPL PL | 31423185 | COLGATE-PALERMO | 020/408 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-10 | 2020-01-10 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.488785 | 39.4529 | ETL.6500 | 40672097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672784 | Q2 | T2 EI COLGATE-PALERMO 017/346 RPL POLE | 31423185 | COLGATE-PALERMO | 017/346 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-10 | 2020-01-10 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.43732 | 39.4388 | ETL.6500 | 40590395 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672805 | Q2 | T2 EI COTTONWOOD-PAN 001/021 REPR INSW | 43881008 | COTTONWOOD-PANORAMA | 001/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.26533 | 40.4178 | ETL.1340 | 40804914 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672809 | Not Scheduled | T2 DI CARIBOU-PALERMO 11/97 RPR BUR FOOT | 44056495 | CARIBOU-PALERMO | 011/097 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115672994 | Not Scheduled | T3 DI CARIBOU-PALMERO 16/127 RPL STRCTUR |  | CARIBOU-PALERMO | 016/127 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-06-21 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.495461 | 39.6739 | ETL.3190 | 41162781 | Structure-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673220 | Q2 | T2 EI COTTONWOOD-PAN 002/032 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 002/032 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.266086 | 40.4272 | ETL.1340 | 40591236 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673236 | Not Scheduled | T2 DI CARIBOU-PALERMO 11/100 RPR STRCTUR | 43725390 | CARIBOU-PALERMO | 011/100 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-21 | 2019-12-21 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673332 | Not Scheduled | EI PALERMO-WYANDOTTE 001/015 REPL HRDS | 43754992 | PALERMO-WYANDOTTE | 001/015 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.539609 | 39.4733 | ETL.4315 | 40757544 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673434 | Q2 | T2 EI PARADISE-TBL MTN 006/057 REPL SPLS | 43727174 | PARADISE-TABLE MTN | 006/057 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537029 | 39.5503 | ETL.4316 | 40821426 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673475 | Not Scheduled | T2 DI CARIBOU-PALERMO 13/112 RPR TWR | 44056495 | CARIBOU-PALERMO | 013/112 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-22 | 2019-12-22 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.510109 | 39.6429 | ETL.3190 | 40668745 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673587 | Not Scheduled | STOCKTON A-WEBER#2 A005/157 RPL POLE | 31476291 | STOCKTON "A"-WEBER #2+ (NO FLY) | A005/157 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-20 | 2019-11-20 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.29758 | 37.9668 | ETL.8130 | 40613380 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115673628 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 15/121 RPL INS | 31426499 | CARIBOU-PALERMO | 015/121 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673640 | Not Scheduled | T2NT DI DRM-GRSS VALLY-MR B16/362 RPL HV | 43746394 | DRUM-GRASS VALLEY-WEIMAR | B016/362 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-09 | 2020-01-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.956069 | 39.1183 | ETL.6760 | 40874756 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673654 | Not Scheduled | T3 DI CARIBOU-PALMERO 16/128 RPR FNDTN | 43735848 | CARIBOU-PALERMO | 016/128 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-05-21 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673657 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 15/121 RPL | 31426499 | CARIBOU-PALERMO | 015/121 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673674 | Q2 | T2 EI COTTONWOOD-PAN 001/026 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 001/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.264002 | 40.4222 | ETL.1340 | 40591235 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673682 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 15/121 RPR FND | 44056495 | CARIBOU-PALERMO | 015/121 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673683 | Not Scheduled | T2 DI CARIBOU-PALERMO 5/48 RPL INS | 31426491 | CARIBOU-PALERMO | 005/048 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540439 | 39.5316 | ETL.3190 | 40865368 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673686 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 15/121 RPL HRD | 43735847 | CARIBOU-PALERMO | 015/121 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673930 | Q2 | T2 COTTONWOOD-PAN 001/027 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 001/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.263981 | 40.4235 | ETL.1340 | 40683759 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673951 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 15/121 RPL HRD | 44056495 | CARIBOU-PALERMO | 015/121 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-22 | 2019-12-22 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673952 | Not Scheduled | T3 DI CARIBOU-PALMERO 16/130 RPL INSS | 31426499 | CARIBOU-PALERMO | 016/130 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-06-22 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115673989 | Not Scheduled | T2 DI CARIBOU-PALERMO 6/57 RPL INS | 31426498 | CARIBOU-PALERMO | 006/057 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537334 | 39.5499 | ETL.3190 | 40815577 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115674142 | Not Scheduled | T2 DI CARIBOU-PALERMO 6/58 RPL SPLICES | 43659205 | CARIBOU-PALERMO | 006/058 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537213 | 39.5503 | ETL.3190 | 40873686 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115674167 | Not Scheduled | T2 DI CARIBOU-PALERMO 13/113 RPR HRDWARE | 44056495 | CARIBOU-PALERMO | 013/113 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509591 | 39.6447 | ETL.3190 | 40656347 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115675198 | Not Scheduled | T3 EI CNTRVLL-TBL MTN 003/057 RPL COND | 43724228 | CENTERVILLE-TABLE MTN | 003/057 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2019-07-10 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-121.691357 | 39.7468 | ETL.6320 | 44673294 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115675932 | Q2 | T2 EI COTTONWOOD-PAN 001/022 RPR GYWW | 43881008 | COTTONWOOD-PANORAMA | 001/022 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.264065 | 40.4184 | ETL.1340 | 40819247 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676366 | Not Scheduled | T2 DI CARIBOU-PALERMO 4/43 RMV VEG | 43659205 | CARIBOU-PALERMO | 004/043 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540099 | 39.5226 | ETL.3190 | 40656338 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676555 | Not Scheduled | T2 EI CRIBU-PLERM 4/42 RPR INSS | 44304495 | CARIBOU-PALERMO | 004/042 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676582 | Not Scheduled | T2 EI CRIBU-PLERM 4/42 RPR FOND | 44057199 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676592 | Not Scheduled | T2 EI CRIBU-PLERM 4/42 RPR STRT | 44057199 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676601 | Not Scheduled | T2NT EI CRIBU-PLERM 4/42 RPR STRT | 44057199 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-11 | 2020-01-11 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676611 | Not Scheduled | T2 EI CARIBOU-PALERMO 4/041 RPR FOND | 44057199 | CARIBOU-PALERMO | 004/041 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539984 | 39.5205 | ETL.3190 | 40595036 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676688 | Not Scheduled | T2 DI CARIBOU-PALERMO 8/73 RPL ANTIGRD | 31460573 | CARIBOU-PALERMO | 008/073 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2022-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52867 | 39.5783 | ETL.3190 | 40656339 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676812 | Not Scheduled | T2 DI CARIBOU-PALERMO 8/66 RPR XARM | 43659205 | CARIBOU-PALERMO | 008/066 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676818 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 4/41 RPL NSLTR | 31423830 | CARIBOU-PALERMO | 004/041 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539984 | 39.5205 | ETL.3190 | 40595036 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676873 | Not Scheduled | T2 DI CARIBOU-PALERMO 9/81 RPL TWR NO | 43725390 | CARIBOU-PALERMO | 009/081 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52542 | 39.5889 | ETL.3190 | 40597207 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676876 | Not Scheduled | T2 DI CARIBOU-PALERMO 9/81 RPL ANTIGRD | 31460573 | CARIBOU-PALERMO | 009/081 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52542 | 39.5889 | ETL.3190 | 40597207 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676991 | Not Scheduled | T2 EI CARIBOU-PALERMO 11/96 RPR MEMBER | 44057199 | CARIBOU-PALERMO | 011/096 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.517387 | 39.6172 | ETL.3190 | 40816574 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115676999 | Not Scheduled | T2 DI CARIBOU-PALERMO TWR 5/46 PNT TWR | 44056495 | CARIBOU-PALERMO | 005/046 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54042 | 39.5282 | ETL.3190 | 40816564 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677053 | Not Scheduled | T3 EI CRIBU-PLERM :36/295 SRTT-RMV SOIL | 44051417 | CARIBOU-PALERMO | :036/295 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-11 | 2019-07-11 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.484689 | 39.6927 | ETL.3190 | 40755760 | Structure-Tower | Soil | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677070 | Not Scheduled | T2 EI CARIBOU-PALERMO 4/43 RPR STRT | 44057199 | CARIBOU-PALERMO | 004/043 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540099 | 39.5226 | ETL.3190 | 40656338 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677221 | Not Scheduled | T2 DI CARIBOU-PALERMO 9/78 RPR HW INSLTR | 44056495 | CARIBOU-PALERMO | 009/078 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.526702 | 39.5847 | ETL.3190 | 40871570 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677251 | Q2 | T2 EI NEWARK-LIVERMORE 17/110 RPR SPLC | 43752138 | NEWARK-LIVERMORE | 017/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.783096 | 37.6462 | ETL.7660 | 40580692 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677354 | Not Scheduled | T2 DI CARIBOU-PALERMO 8/73 RPR CORROSION | 44056495 | CARIBOU-PALERMO | 008/073 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52867 | 39.5783 | ETL.3190 | 40656339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677389 | Not Scheduled | T2 DI CARIBOU-PALERMO 11/93 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 011/093 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677391 | Mar | T2 EI CBRLL-SNT YNZ SW STA 7/63 RPL INSS | 31498014 | CABRILLO-SANTA YNEZ SW STA | 007/063 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2021-05-31 | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-12 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.3073412 | 34.6499 | ETL.1200 | 40836545 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 9 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2020-08-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677403 | Not Scheduled | T2 DI CARIBOU-PALERMO 5/46 INSTL CL GR | 31460573 | CARIBOU-PALERMO | 005/046 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54042 | 39.5282 | ETL.3190 | 40816564 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677449 | Not Scheduled | T2 EI CARIBOU-PALERMO 004/044 INST HRDT | 44057199 | CARIBOU-PALERMO | 004/044 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540274 | 39.5245 | ETL.3190 | 40758609 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677464 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/110 RPR STRCTR | 43725390 | CARIBOU-PALERMO | 012/110 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677597 | Not Scheduled | T2CARIBOU-PALERMO 011/097 RPR CONDUCTOR | 44304495 | CARIBOU-PALERMO | 011/097 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677603 | Not Scheduled | T2 DI CARIBOU-PALERMO 0/3 RPL INSULATOR | 31426591 | CARIBOU-PALERMO | 000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-26 | 2019-12-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523682 | 39.4544 | ETL.3190 | 40663305 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677606 | Not Scheduled | T2 DI CARIBOU-PALERMO 6/55 RPL ANTIGRD | 31460573 | CARIBOU-PALERMO | 006/055 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.538613 | 39.5459 | ETL.3190 | 40765164 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677609 | Not Scheduled | T2 DI CARIBOU-PALERMO 4/42 REMOVE VEG | 44056495 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677627 | Not Scheduled | T2 EI CARIBOU-PALERMO 11/97 REPL INSS |  | CARIBOU-PALERMO | 011/097 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677676 | Not Scheduled | T3 EI CARIBOU-PLRMO :036/294 RPL INSS | 31426498 | CARIBOU-PALERMO | :036/294 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-01-11 | 2019-07-11 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.484451 | 39.6942 | ETL.3190 | 40771762 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115677841 | Q2 | T2 EI PARADISE-TABLE MTN 5/44 RPR SPLC | 43727174 | PARADISE-TABLE MTN | 005/044 | ICS | E | 2020_(1a) PSPS |  | 2019-01-11 | 2020-01-11 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540219 | 39.526 | ETL.4316 | 41101723 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115677860 | Q2 | T2 EI PARADISE-TABLE MTN 5/44 RPL INSS | 31451270 | PARADISE-TABLE MTN | 005/044 | 93K | E | 2020_(1a) PSPS |  | 2019-01-11 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5402324 | 39.526 | ETL.4316 | 40785398 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115677903 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/106 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 012/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.512607 | 39.6341 | ETL.3190 | 40813695 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115677979 | Q2 | EI CNTRVLLE TBL MTN 10/196 RPL INSW | 31431540 | CENTERVILLE-TABLE MTN-OROVILLE | 010/196 | 93I | F | Pre-2020_(5) TD tag on other lines |  | 2019-01-11 | 2022-01-11 |  |  | 2021-05-21 | 2021-05-17 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.6344857 | 39.6494 | ETL.6330 | 40634482 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-02-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678063 | Not Scheduled | EI CNTRVILE-TBL MTN-ORVLL 9/195 CANCEL | 43721205 | CENTERVILLE-TABLE MTN-OROVILLE | 009/195 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-11 | 2020-01-11 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.634668 | 39.6501 | ETL.6330 | 40873516 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678091 | Q2 | EI CNTVLLE TBL-MTN 9/195 RPL INSW | 31431540 | CENTERVILLE-TABLE MTN-OROVILLE | 009/195 | 93I | F | Pre-2020_(5) TD tag on other lines |  | 2019-01-11 | 2022-01-11 |  |  | 2021-05-21 | 2021-05-17 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.6346792 | 39.6501 | ETL.6330 | 40897922 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-02-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678170 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/110 RPL SPLICE | 43659205 | CARIBOU-PALERMO | 012/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678490 | Feb | T2 EI TRNTY-MPL CRK 17/001C RPL STRW | 31471999 | TRINITY-MAPLE CREEK | 017/001C | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.209491 | 40.7416 | ETL.8170 | 41115572 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-04-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-04-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678990 | Not Scheduled | T3 EI CARIBOU-PALERMO :037/299 FOND | 44051417 | CARIBOU-PALERMO | :037/299 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-11 | 2019-07-11 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486332 | 39.6826 | ETL.3190 | 40913194 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678991 | Not Scheduled | T3 EI CARIBOU-PLRMO :037/300A RPR JUMP | 43659205 | CARIBOU-PALERMO | :037/300A | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2019-07-11 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486615 | 39.6812 | ETL.3190 | 40913195 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115678992 | Not Scheduled | T3 EI CARIBOU-PALERMO :37/300A RPR GYWS | 43659205 | CARIBOU-PALERMO | :037/300A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-11 | 2019-07-11 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486615 | 39.6812 | ETL.3190 | 40913195 | Guy Wire-Steel | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679173 | Not Scheduled | T3 EI CRBOU-PLRMO 016/130 RPL INSS | 31426499 | CARIBOU-PALERMO | 016/130 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679202 | Q2 | T2 EI CNTRVLL-TBL MTN-RVLL 9/189 RPR PL | 43721205 | CENTERVILLE-TABLE MTN-OROVILLE | 009/189 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.635872 | 39.6542 | ETL.6330 | 40664419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679417 | Not Scheduled | T2 EI CARIBOU-PALERMO 7/065 RPR SPLS | 44304495 | CARIBOU-PALERMO | 007/065 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679439 | Not Scheduled | T2 EI CARIBOU-PALERMO 7/065 RPR SHIELD | 44304495 | CARIBOU-PALERMO | 007/065 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679447 | Q2 | T2 EI PARADISE-TABLE MTN 05/045 RPL HRDT | 43727174 | PARADISE-TABLE MTN | 005/045 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54023 | 39.528 | ETL.4316 | 40765159 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679448 | Not Scheduled | T2 EI CARIBOU-PALERMO 7/065 RPL INSS |  | CARIBOU-PALERMO | 007/065 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679455 | Not Scheduled | T2 EI CARIBOU-PALERMO 7/065 RPR FOND | 44057199 | CARIBOU-PALERMO | 007/065 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679474 | Q2 | T2 EI PARADISE-TABLE 005/046 RPR COND | 43727174 | PARADISE-TABLE MTN | 005/046 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540244 | 39.5301 | ETL.4316 | 40816518 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679692 | Q2 | DISTRIBUTION SLO SM | 31427096 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 012/226 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-04-30 |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.50648 | 35.1337 | ETL.9100 | 44191938 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115679699 | Mar | T2 EI POE-RIO OSO 026/169 RPL INSS | 31431911 | POE-RIO OSO | 026/169 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.516909 | 39.6212 | ETL.5540 | 40889529 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679767 | Not Scheduled | DISTRIBUTION GUY |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 012/225 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.506109 | 35.1344 | ETL.9100 | 44191207 | Guy Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679818 | Q2 | T2 EI PARADISE-TABLE MTN 5/047 RPR INSS | 43727174 | PARADISE-TABLE MTN | 005/047 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540254 | 39.5316 | ETL.4316 | 40815542 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679823 | Not Scheduled | T2 EI CARIBOU-PALERMO 005/048 RPR FOND | 44057199 | CARIBOU-PALERMO | 005/048 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540439 | 39.5316 | ETL.3190 | 40865368 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679825 | Q2 | T2 EI PARADISE-TABLE 005/046 RPL INSS | 43727174 | PARADISE-TABLE MTN | 005/046 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540244 | 39.5301 | ETL.4316 | 40816518 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115679842 | Not Scheduled | T2NT EI CARIBOU-PALERMO 005/048 REPAINT | 44302715 | CARIBOU-PALERMO | 005/048 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-12 | 2021-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540439 | 39.5316 | ETL.3190 | 40865368 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680074 | Not Scheduled | T2 EI CARIBOU-PALERMO 05/049 RPR FOND | 44057199 | CARIBOU-PALERMO | 005/049 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540447 | 39.5329 | ETL.3190 | 40870660 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680165 | Q2 | T2 EI PARADISE-TABLE MTN 5/048 RPR CONS | 43727174 | PARADISE-TABLE MTN | 005/048 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54026 | 39.5329 | ETL.4316 | 40871564 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680182 | Not Scheduled | T2 EI CARIBOU-PALERMO 005/050 RPL MEMBER | 44057199 | CARIBOU-PALERMO | 005/050 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540468 | 39.5359 | ETL.3190 | 40599254 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680192 | Not Scheduled | T2 EI CARIBOU-PALERMO 005/050 RPL INSS |  | CARIBOU-PALERMO | 005/050 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540468 | 39.5359 | ETL.3190 | 40599254 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680197 | Not Scheduled | T2 EI CARIBOU-PALERMO 006/057 RPR FOND |  | CARIBOU-PALERMO | 006/057 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537334 | 39.5499 | ETL.3190 | 40815577 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680222 | Q2 | T2 PARADISE-TABLE MTN 005/049 RPR INSS | 43727174 | PARADISE-TABLE MTN | 005/049 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54028 | 39.5358 | ETL.4316 | 40867305 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680228 | Not Scheduled | T2 EI CARIBOU-PALERMO 006/057 RPR SHIELD | 44304495 | CARIBOU-PALERMO | 006/057 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537334 | 39.5499 | ETL.3190 | 40815577 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680354 | Not Scheduled | DISTRIBUTION RPR BNDW | 43686013 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 012/220 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-12 | 2020-01-12 | [8 empty] | LATE | South | WSIP | FSRP | [5 empty] | '-120.509786 | 35.1347 | ETL.9100 | 42574223 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115680358 | Mar | T2 HUMBOLDT_TRINITY 060/001 RPR HRDW | 43729542 | HUMBOLDT-TRINITY | 060/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.1679194 | 40.7509 | ETL.1820 | 44565330 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680371 | Not Scheduled | T2 EI CNTRVILLE-TBLE MTN 4/70 RPR SPLC | 43724253 | CENTERVILLE-TABLE MTN | 004/070 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.70393 | 39.7365 | ETL.6320 | 40758778 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680377 | Feb | T2 EI TRINITY-MAPLE C 014/005 RPL POLE | 31440262 | TRINITY-MAPLE CREEK | 014/005 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-01-12 | 2021-05-31 | 2020-12-13 | 2020-12-15 | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.166325 | 40.7523 | ETL.8170 | 40761910 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115680395 | Not Scheduled | T3 EI CARIBOU-PALERMO :032/259 INST HRDT | 44051417 | CARIBOU-PALERMO | :032/259 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.473027 | 39.7568 | ETL.3190 | 40876880 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680401 | Not Scheduled | T3 EI CARIBOU-PLERMO :032/259 RPL INSS | 31425651 | CARIBOU-PALERMO | :032/259 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.473027 | 39.7568 | ETL.3190 | 40876880 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680643 | Q2 | T2 EI CNTRVL-TBL MTN-RVL 10/200 RPR COND | 43721205 | CENTERVILLE-TABLE MTN-OROVILLE | 010/200 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-12 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.633663 | 39.6467 | ETL.6330 | 40767069 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680776 | Q2 | T2 EI CTTNWD-RD BLFF 8/165 REGRADE | 43744380 | COTTONWOOD-RED BLUFF | 008/165 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-13 | 2020-01-13 |  |  | 2021-04-01 | 2020-09-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.258715 | 40.3032 | ETL.6660 | 40747092 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680802 | Q3 | T2 EI CARIBOU #2 - 002/012 RPL ANCH | 31456236 | CARIBOU #2 | 002/012 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.179159 | 40.068 | ETL.6280 | 40675373 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q3 |  |  | 2020-04-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115680969 | Q2 | T2 EI HAT CRK #1-WSTWD 13/251 RPLC SPLW | 43736796 | HAT CREEK #1-WESTWOOD | 013/251 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.366893 | 40.8165 | ETL.7030 | 40701217 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681000 | Q2 | T2 EI HAT CREEK #1-WSTWD 13/251 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 013/251 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.366893 | 40.8165 | ETL.7030 | 40701217 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681029 | Q2 | T2 EI HAT CREEK #1-WSTWD 12/247 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 012/247 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2020-01-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.369665 | 40.8186 | ETL.7030 | 40676248 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681031 | Q2 | T2 EI HAT CRK #1-WSTWD 12/248 RPLC STRW | 31426976 | HAT CREEK #1-WESTWOOD | 012/248 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2020-01-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.368945 | 40.8181 | ETL.7030 | 40759172 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681035 | Not Scheduled | T2 EI PIT #3-PIT #1 009/075 RPR STRT | 43685976 | PIT #3-PIT #1 | 009/075 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2020-01-13 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.640618 | 40.9154 | ETL.5400 | 40759437 | Structure-Tower | No Good/Out of Stdrd | Repair | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681675 | Not Scheduled | T3 EI CRB-PLRM :032/262 INST HRDT | 44051417 | CARIBOU-PALERMO | :032/262 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475245 | 39.7512 | ETL.3190 | 40702274 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681697 | Not Scheduled | T3 EI CARIBOU-PALERMO :032/263 RPR STRT | 44051417 | CARIBOU-PALERMO | :032/263 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681737 | Not Scheduled | T2 EI CARIBOU #2 002/014 CANCEL | 31456236 | CARIBOU #2 | 002/014 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2020-01-12 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.180647 | 40.0673 | ETL.6280 | 40769462 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-04-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681745 | Not Scheduled | T3 EI CARIBOU-PALERMO :33/266 RPL INSS | 31426491 | CARIBOU-PALERMO | :033/266 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.476538 | 39.743 | ETL.3190 | 40816595 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681747 | Not Scheduled | T3 EI CRESTA-RIO OSO 016/130 PNT TWR | 43708860 | CRESTA-RIO OSO | 016/130 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-12 | 2019-07-12 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.477186 | 39.7418 | ETL.4590 | 40910147 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681750 | Q2 | T2 EI HAT CREEK #1-WSTWD 13/254 RPL SPLW | 43736796 | HAT CREEK #1-WESTWOOD | 013/254 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2020-01-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.364833 | 40.8147 | ETL.7030 | 40877470 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681761 | Not Scheduled | T3 EI CARIBOU-PALERMO :033/267 WASH INSS |  | CARIBOU-PALERMO | :033/267 | ICI | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.476775 | 39.7415 | ETL.3190 | 40826427 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681802 | Not Scheduled | T3 EI DRM-HGGNS 013/124 RMV NEST | 43687142 | DRUM-HIGGINS | 013/124 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-12 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.95086 | 39.1636 | ETL.4393 | 41162645 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115681969 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/104 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 012/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513479 | 39.631 | ETL.3190 | 40758615 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115682061 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/103 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 012/103 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513986 | 39.6292 | ETL.3190 | 40656345 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115682226 | Q2 | T2 EI PHILO JCT-ELK 002/011 INS GYWW | 43762377 | PHILO JCT-ELK | 002/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-14 | 2021-05-31 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.20463 | 39.0983 | ETL.7780 | 40595265 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-06-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115682765 | Q2 | T2 EI LAYTONVILLE-WIL 12/000 RPR GYWW | 43761787 | LAYTONVILLE-WILLITS | 012/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2021-05-31 | 2020-10-14 | 2020-10-17 | 2021-05-28 | 2021-05-26 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.418734 | 39.5438 | ETL.8360 | 40614438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115682808 | Q2 | T2 EI LAYTONVILLE-WI 11/005 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 011/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2021-05-31 | 2021-05-26 | 2021-05-28 | 2021-05-27 | 2021-05-27 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.4172 | 39.5428 | ETL.8360 | 40750468 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-08 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115683042 | Not Scheduled | T2 DI CARIBOU-PALERMO 6/55 RPR CORROSION | 44056495 | CARIBOU-PALERMO | 006/055 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.538613 | 39.5459 | ETL.3190 | 40765164 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115683313 | Not Scheduled | T2 DI CARIBOU-PALERMO 8/66 RPR SHACKLES | 44056495 | CARIBOU-PALERMO | 008/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115683490 | Q4 | T2 EI KESWICK-TRINITY 029/502 RMV BUTT | 43661466 | KESWICK-TRINITY | 029/502 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-14 | 2024-01-14 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.910589 | 40.7127 | ETL.7270 | 40911329 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684155 | Not Scheduled | T2 DI CARIBOU-PALERMO 7/60 PAINT TOWER |  | CARIBOU-PALERMO | 007/060 |  | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53662 | 39.5522 | ETL.3190 | 40599257 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684353 | Not Scheduled | T2 DI CARIBOU-PALERMO 7/60 RPL SHLD WIRE | 44304495 | CARIBOU-PALERMO | 007/060 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53662 | 39.5522 | ETL.3190 | 40599257 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684418 | Not Scheduled | T2 DI CARIBOU-PALERMO 7/60 RPL HRDS | 44057199 | CARIBOU-PALERMO | 007/060 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-11 | 2020-01-11 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53662 | 39.5522 | ETL.3190 | 40599257 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684491 | Q2 | T2 EI LAYTONVILLE-WIL 9/000 RPL POLE | 31434842 | LAYTONVILLE-WILLITS | 009/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2021-05-31 | 2021-05-26 | 2021-05-28 | 2021-05-27 | 2021-05-27 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.384385 | 39.5146 | ETL.8360 | 40614431 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-08 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684574 | Q2 | T2 EI LAYTONVILLE-W 13/000E RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 013/000E | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2021-05-31 | 2021-05-26 | 2021-05-28 | 2021-05-28 | 2021-05-28 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.428494 | 39.5548 | ETL.8360 | 40905764 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684673 | Not Scheduled | T3 EI DRUM-RIO OSO #1 001/010 REPAINT | 43685808 | DRUM-RIO OSO #1 | 001/010 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-14 | 2023-01-14 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.786336 | 39.2566 | ETL.1420 | 40596150 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684755 | Not Scheduled | T3NT CARIBU-PALRMO :031/256A INS MRKW | 44304495 | CARIBOU-PALERMO | :031/256A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-14 | 2020-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467758 | 39.7593 | ETL.3190 | 44374354 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115684762 | Not Scheduled | T3NT EI TCRB-PLRM :031/256AC GMKS | 44304495 | CARIBOU-PALERMO | :031/256C | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-14 | 2020-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685176 | Q2 | T2 EI PRDSE-TBLE MTN 006/056 RPL INSS | 31451270 | PARADISE-TABLE MTN | 006/056 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-14 | 2020-01-14 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5378359 | 39.5477 | ETL.4316 | 40844441 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685193 | Not Scheduled | T3 EI CARIBOU-PLERMO :031/256 RPL HRDT | 44051417 | CARIBOU-PALERMO | :031/256 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2019-07-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685231 | Q2 | T2 EI PRDSE-TBLE MTN 006/055BA RPL STRW | 31453760 | PARADISE-TABLE MTN | 006/055BA | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-14 | 2020-01-14 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537173 | 39.5471 | ETL.4316 | 41184210 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685241 | Q2 | T2 EI PRDSE-TBLE MTN 006/055BB INS GYWW | 43724325 | PARADISE-TABLE MTN | 006/055BB | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-14 | 2020-01-14 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537116 | 39.5472 | ETL.4316 | 41184212 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685286 | Q2 | T2 EI PRDSE-TBLE MTN 006/055BC RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055BC | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-14 | 2020-01-14 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537064 | 39.5472 | ETL.4316 | 41184213 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685289 | Not Scheduled | T3 EI CARIBU-PALRMO :031/256A RPL GYYS | 43659205 | CARIBOU-PALERMO | :031/256A | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2019-07-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467758 | 39.7593 | ETL.3190 | 44374354 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685536 | Not Scheduled | STOCKTON""A""-WEBER#2 A4/113 RPL POLE | 31476291 | STOCKTON "A"-WEBER #2+ (NO FLY) | A003/113 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-19 | 2024-11-19 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.278047 | 37.9701 | ETL.8130 | 40754502 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-12-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115685938 | Not Scheduled | T3 EI CARIBOU-PLERMO :031/257 RPR STRT | 44051417 | CARIBOU-PALERMO | :031/257 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2019-07-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.468506 | 39.759 | ETL.3190 | 40826429 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115685939 | Not Scheduled | T3 EI CARIBOU-PLERMO :031/257 REPAINT | 44051417 | CARIBOU-PALERMO | :031/257 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-14 | 2019-07-14 | [6 empty] | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.468506 | 39.759 | ETL.3190 | 40826429 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115686280 | Q2 | T3 EI CRESTA-RIO OSO 13/110 REPL INSS | 31435732 | CRESTA-RIO OSO | 013/110 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-14 | 2019-07-14 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.4567151 | 39.7717 | ETL.4590 | 40919872 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-04-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115686282 | Not Scheduled | T3 EI CARIBOU-PLRMO :031/256 RPL INSS | 31426491 | CARIBOU-PALERMO | :031/256 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2019-07-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115687732 | Not Scheduled | T3 KESWICK-TRINITY 002/041 CANCEL | 43939188 | KESWICK-TRINITY | 002/041 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2019-07-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.498022 | 40.6169 | ETL.7270 | 40650304 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688019 | Not Scheduled | T2 EI JEFFER-HILL JCT 006/035C RPR GYWW | 43752126 | JEFFERSON-HILLSDALE JCT | 006/035C | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-15 | 2020-01-15 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.35638 | 37.5251 | ETL.7190 | 41162633 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 | SFPUC (4) | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688046 | Not Scheduled | DISTRIBUTION AUTO SPLICE | 43766561 | ATASCADERO-SAN LUIS OBISPO | 006/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.62473 | 35.3841 | ETL.8490 | 42699985 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688106 | Not Scheduled | T2 EI JEFFER-HILL JCT 006/035A RPR GYWW | 43752126 | JEFFERSON-HILLSDALE JCT | 006/035A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-15 | 2020-01-15 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.356328 | 37.5249 | ETL.7190 | 40577459 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 | SFPUC (4) | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688168 | Q2 | T2 EI PARADISE-TABLE MTN 5/051 RPR CONDS | 43727174 | PARADISE-TABLE MTN | 005/051 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-15 | 2020-01-15 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540302 | 39.5393 | ETL.4316 | 40596669 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688175 | Q2 | T2 EI PRDSE-TBLE MTN 006/056 RMV NEST | 43727174 | PARADISE-TABLE MTN | 006/056 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-15 | 2020-01-15 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537823 | 39.5477 | ETL.4316 | 40816520 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688437 | Q2 | T2 EI HAT CREEK #1-WEST 015/294 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 015/294 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.337078 | 40.7924 | ETL.7030 | 40616868 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688459 | Q2 | T2 EI HAT CREEK #1-WEST 15/295 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 015/295 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.336412 | 40.7918 | ETL.7030 | 40676268 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688495 | Q2 | T2 EI HAT CREEK #1-WEST 015/301 REFRAME | 31471575 | HAT CREEK #1-WESTWOOD | 015/301 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332242 | 40.7885 | ETL.7030 | 40770727 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688496 | Q2 | T2 EI HAT CREK #1-WSTWD 015/299 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 015/299 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.333618 | 40.7896 | ETL.7030 | 40617092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688550 | Not Scheduled | T2 EI CARIBOU-PALERMO 006/053 RPR FOND | 44057199 | CARIBOU-PALERMO | 006/053 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540497 | 39.5401 | ETL.3190 | 40660305 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688621 | Q2 | T2 EI LYTONVILLE-WILL 013/000G RPR GYWW | 43761787 | LAYTONVILLE-WILLITS | 013/000G | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2021-05-31 | 2021-05-26 | 2021-05-28 | 2021-05-28 | 2021-05-28 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.427169 | 39.5556 | ETL.8360 | 40905766 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688627 | Q2 | T2 EI HAT CREEK #1-WEST 16/309 INS HRDW | 43904280 | HAT CREEK #1-WESTWOOD | 016/309 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-15 | 2020-01-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.326777 | 40.784 | ETL.7030 | 44311020 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688733 | Q2 | T2 EI SANTA YNEZ TAP 3/30 REPL POLE | 31423339 | SANTA YNEZ TAP | 003/030 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 |  |  | 2021-05-01 | 2021-05-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.13458 | 34.6311 | ETL.3701 | 40649603 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115688768 | Q2 | T2 EI HAT CREEK #1-WEST 14/284 RPL INSW | 31456189 | HAT CREEK #1-WESTWOOD | 014/284 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 |  |  | 2021-06-25 | 2021-05-03 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3440784 | 40.798 | ETL.7030 | 40634668 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115691214 | Q2 | T3 DI IGNACIO-BOLINAS #1 08/84 RPL POLE | 31428896 | IGNACIO-BOLINAS #1 | 008/084 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-14 | 2021-05-31 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.653683 | 38.0123 | ETL.7140 | 40861141 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-01 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-03-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115691953 | Not Scheduled | T2 DI CARIBOU-PALERMO 11/100 RPR CNDCTR | 43659205 | CARIBOU-PALERMO | 011/100 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115691990 | Not Scheduled | T2 DI CARIBOU-PALERMO 1/8 RPR STRCTR | 44056495 | CARIBOU-PALERMO | 001/008 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536625 | 39.4611 | ETL.3190 | 40867924 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115691991 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/108 RPR INS | 43659205 | CARIBOU-PALERMO | 012/108 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511776 | 39.637 | ETL.3190 | 40867949 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115691994 | Not Scheduled | T2 DI CARIBOU-PALERMO 12/110 REPL INS | 43659205 | CARIBOU-PALERMO | 012/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115692046 | Not Scheduled | T2 DI CARIBOU-PALERMO 9/82 REPAIR STRCT | 44056495 | CARIBOU-PALERMO | 009/082 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115692353 | Q2 | T2 EI OCNO-CLLNDR SW 19/126 RPR GYWW | 43588178 | OCEANO-CALLENDAR SW STA | 019/126 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-15 | 2021-05-31 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-24 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.579354 | 35.1011 | ETL.2394 | 40812254 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115692871 | Not Scheduled | T2 EI CARIBOU-PALERMO 6/054 RPR FOND | 44057199 | CARIBOU-PALERMO | 006/054 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-15 | 2020-01-15 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540063 | 39.5414 | ETL.3190 | 40758611 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115692968 | Q2 | T2 EI FULTON JCT-VACA 050/312 RPR MEMBER | 44640352 | FULTON JCT-VACA | 050/312 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-16 | 2020-01-16 |  |  | 2021-04-12 | 2021-04-12 |  | TLN/TLQ error | Recommend delinking prior to editing | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-121.9893434 | 38.4183 | ETL.1590 | 44238422 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  | Reject | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115693287 | Not Scheduled | T2 DI CARIBOU-PALERMO 5/47 PNT TWR |  | CARIBOU-PALERMO | 005/047 |  | F | Pre-2020_(9a) Other ignition related |  | 2018-12-26 | 2019-12-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540432 | 39.5304 | ETL.3190 | 40815575 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115693783 | Not Scheduled | T2 DI CARIBOU-PALERMO 00/02 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-28 | 2019-12-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.521449 | 39.4545 | ETL.3190 | 40689941 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115693849 | Not Scheduled | DISTRIBUTION INSL | 31430822 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 008/150 | 93I | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-16 | 2020-01-16 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.5386611 | 35.1776 | ETL.9100 | 44189771 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115694533 | Not Scheduled | T2 DI CARIBOU-PALERMO 10/87 RPR INSULTOR | 43659205 | CARIBOU-PALERMO | 010/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-12-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.522843 | 39.598 | ETL.3190 | 40819278 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115697024 | Mar | T2 EI HUMBOLDT-TRINITY 61/5 INST HV | 43729518 | HUMBOLDT-TRINITY | 061/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-17 | 2025-01-17 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.1820 | 44324177 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115698144 | Not Scheduled | T2 EI MNDCNO-WLTS-FRT BRG 041/005 WASH | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 041/005 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-17 | 2020-01-17 | 2020-09-07 | 2020-09-10 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.782483 | 39.4304 | ETL.7550 | 40750988 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115698403 | Not Scheduled | T2 EI MNDCNO-WLTS-FRT BRG 041/008 WASH | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 041/008 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-17 | 2020-01-17 | 2020-09-07 | 2020-09-10 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.786946 | 39.431 | ETL.7550 | 40861439 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115698513 | Mar | T2 EI MNDCNO-WLTS-FT BRG 041/002 SPLICE | 43731276 | MENDOCINO-WILLITS-FORT BRAGG | 041/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-17 | 2020-01-17 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.776542 | 39.4295 | ETL.7550 | 40657967 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115698579 | Not Scheduled | T3NT EI ATASCADERO-SLO 8/134 CLIMB STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 008/134 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-17 | 2022-01-17 | [7 empty] | TR3 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.631192 | 35.3688 | ETL.8490 | 42700021 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 1 | 2019-03-15 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-03-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115698852 | Not Scheduled | T3NT EI ATSCDR-SN L OBISPO 008/133 STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 008/133 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-17 | 2022-01-17 | [7 empty] | TR3 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.630633 | 35.3701 | ETL.8490 | 42700019 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115698995 | Not Scheduled | T3NT EI ATSCDR-SN L OBISPO 008/132 STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 008/132 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-17 | 2022-01-17 | [7 empty] | TR3 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.630338 | 35.3707 | ETL.8490 | 42700017 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115699194 | Not Scheduled | T2 EI ATSCDR-SN L OBISPO 008/127 STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 007/127 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-17 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.628315 | 35.3753 | ETL.8490 | 42700003 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115699639 | Not Scheduled | T2 DI CARIBOU-PALERMO 07/65 RPR PAINT |  | CARIBOU-PALERMO | 007/065 |  | F | Pre-2020_(4b) On structure in bucket 4 |  | 2018-12-27 | 2019-12-27 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115702749 | Q2 | T2 EI LYTNVLLE-WLLTS 007/003 INS GYWW | 43761787 | LAYTONVILLE-WILLITS | 007/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-17 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.363436 | 39.4952 | ETL.8360 | 40648647 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-08 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703026 | Not Scheduled | T2 DI CARIBOU-PALERMO 14/115 RPR CORRSN | 44056495 | CARIBOU-PALERMO | 014/115 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.508354 | 39.6491 | ETL.3190 | 40913197 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703110 | Feb | T2 EI VACA-SUISUN-JMSN 003/031 RPR CONS | 44175847 | VACA-SUISUN-JAMESON | 003/031 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 |  |  | 2021-02-13 | 2021-02-11 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.990026 | 38.4012 | ETL.4080 | 40614338 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703179 | Q4 | T3 EI KESWICK-TRINITY 004/070 RPL ANCW | 31430073 | KESWICK-TRINITY | 004/070 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703180 | Not Scheduled | T3 EI DRM-HGGNS 005/052 PNT TWR | 43687142 | DRUM-HIGGINS | 005/052 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-18 | 2019-07-18 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.836325 | 39.2145 | ETL.4393 | 40682536 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703292 | Q4 | T3 EI KESWICK-TRINITY 004/070C RPR PL | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421136 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703293 | Q4 | T2 EI KESWICK-TRINITY 006/088A REPL ANCW | 31471077 | KESWICK-TRINITY | 006/088A | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.573205 | 40.6421 | ETL.7270 | 44649291 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2019-05-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703299 | Q4 | T3 EI KESWICK-TRINITY 004/070L RPR CNDW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703647 | Mar | T2 EI MNDC-WLTS-FRT BRG 040/000 RPL STRW | 31438704 | MENDOCINO-WILLITS-FORT BRAGG | 040/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.757435 | 39.4196 | ETL.7550 | 40588514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703675 | Not Scheduled | T3 EI KESWICK-TRINITY 004/069 RPR GYWW | 43939188 | KESWICK-TRINITY | 004/069 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 | [6 empty] | Likely veg | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.537899 | 40.6275 | ETL.7270 | 44164727 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703884 | Q4 | T3 EI KESWICK-TRINITY 004/069 RPR CONW | 43939188 | KESWICK-TRINITY | 004/069 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.537899 | 40.6275 | ETL.7270 | 44164727 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115703981 | Mar | T2 EI MNDC-WLTS-FRT BRG 040/002 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.759983 | 39.4213 | ETL.7550 | 40697902 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704027 | Not Scheduled | T2 EI VACA-PARKWAY 006/035 INST HRDT | 43760159 | VACA-PARKWAY | 006/035 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-18 | 2024-01-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.018743 | 38.3895 | ETL.5850 | 40756444 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704032 | Mar | T2 EI MENDOCINO-WILLITS-FB 29/5 RPL POLE | 31490869 | MENDOCINO-WILLITS-FORT BRAGG | 029/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 | 2020-09-07 | 2020-09-10 | 2021-03-16 | 2021-03-16 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.592351 | 39.3474 | ETL.7550 | 40750969 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704064 | Mar | T2 EI MNDC-WLTS-FRT BRG 040/003 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/003 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.761326 | 39.4222 | ETL.7550 | 40666502 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704086 | Mar | T2 EI HUMBOLDT-TRINITY 98/1L RPL PL | 31474285 | HUMBOLDT-TRINITY | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.829449 | 40.7658 | ETL.1820 | 44562866 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-03-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704178 | Q4 | T3 EI KESWICK-TRINITY 004/066 RPR GYWW | 43661466 | KESWICK-TRINITY | 004/066 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.531553 | 40.6241 | ETL.7270 | 40701679 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704733 | Not Scheduled | T3 EI DRM-HGGNS 005/059 PNT TWR | 43687142 | DRUM-HIGGINS | 005/059 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-18 | 2019-07-18 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.841496 | 39.2058 | ETL.4393 | 40861968 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115704967 | Feb | EI VACA-SUISUN-JAMESON 005/043 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 005/043 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-18 | 2020-01-18 |  |  | 2021-02-13 | 2021-02-11 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.000921 | 38.376 | ETL.4080 | 40690656 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115705266 | Mar | T2 EI MNDC-WLTS-FRT BRG 040/005 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/005 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.763427 | 39.4236 | ETL.7550 | 40750986 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-04-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115705580 | Not Scheduled | T3 EI DRM-HGGNS 007/073 REPAINT | 43687142 | DRUM-HIGGINS | 007/073 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-18 | 2019-07-18 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.861567 | 39.1864 | ETL.4393 | 40650082 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115705611 | Mar | T2 EI MNDC-WLTS-FRT BRG 040/007 RPL SPLW | 43731276 | MENDOCINO-WILLITS-FORT BRAGG | 040/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2020-01-18 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.76669 | 39.4258 | ETL.7550 | 40808842 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115705753 | Q2 | T2 EI PRDSE-TBL MTN 006/055D RPL POLE | 31453760 | PARADISE-TABLE MTN | 006/055D | 70Y | E | 2020_(1a) PSPS |  | 2019-01-18 | 2020-01-18 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535982 | 39.546 | ETL.4316 | 41184125 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 115705759 | Q2 | T2 EI PARADISE-TABLE MTN 6/55CB RPL PL | 31453760 | PARADISE-TABLE MTN | 006/055CB | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-18 | 2020-01-18 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536857 | 39.5464 | ETL.4316 | 41184220 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115705799 | Mar | T2 EI MORAG-CSTR VLLY 01/08 RPL INSS | 31427542 | MORAGA-CASTRO VALLEY | 001/008 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2021-05-31 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.1412126 | 37.8506 | ETL.5250 | 40890551 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 5 | 2019-04-01 | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115706786 | Not Scheduled | DISTRIBUTION RPR STRW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 009/170 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-01-19 | 2020-01-19 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.526 | 35.1641 | ETL.9100 | 44191873 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115706997 | Not Scheduled | T3 EI DRM-HGGNS 008/082 PNT TWR | 43687142 | DRUM-HIGGINS | 008/082 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2019-07-19 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.881084 | 39.1718 | ETL.4393 | 40660213 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707025 | Mar | T2 EI MNDC-WLTS-FRT BRG 040/008 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/008 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-19 | 2020-01-19 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.768016 | 39.4267 | ETL.7550 | 40876277 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707171 | Not Scheduled | T3 EI DRUM-RIO OSO #1 004/050 CANCEL | 43685808 | DRUM-RIO OSO #1 | 004/050 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2019-07-19 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.836556 | 39.2248 | ETL.1420 | 40596153 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707208 | Not Scheduled | T3 EI DRM-RI S#2 004/049 PAINT | 43685734 | DRUM-RIO OSO #2 | 004/049 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2023-01-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.835339 | 39.2258 | ETL.1430 | 40866278 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707339 | Q4 | T2 EI KESWICK-TRINITY 011/136 REPL CRSW | 31471077 | KESWICK-TRINITY | 011/136 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-19 | 2020-01-19 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.634596 | 40.676 | ETL.7270 | 40598899 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707403 | Not Scheduled | EI VC-VCVLL-JMSN-NTWR 6/48 PNT TWR | 43740701 | VACA-VACAVILLE-JAMESON-NTH TWR | 006/048 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2020-01-19 | [8 empty] | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.008861 | 38.367 | ETL.4100 | 40864914 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707549 | Not Scheduled | T2 EI CARIBOU-PALERMO 008/069 RPR FOND | 43727173 | CARIBOU-PALERMO | 008/069 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-19 | 2020-01-19 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53135 | 39.5695 | ETL.3190 | 40867354 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707581 | Not Scheduled | T3 EI DRUM-HIGGINS 007/078 PNT TWR | 43687142 | DRUM-HIGGINS | 007/078 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2019-07-19 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.870652 | 39.1765 | ETL.4393 | 40862209 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707606 | Not Scheduled | EI MRAG-CSTR VLLY 02/15 RPR FOND |  | MORAGA-CASTRO VALLEY | 002/015 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2024-01-19 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-122.122246 | 37.839 | ETL.5250 | 40762326 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | 2019-04-01 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-03-18 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115707938 | Not Scheduled | T3 EI DRM-HGGNS 008/083 PNT TWR | 43687142 | DRUM-HIGGINS | 008/083 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2019-07-19 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.882213 | 39.1713 | ETL.4393 | 40653945 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115708119 | Not Scheduled | T2 EI CARIBOU-PALERMO 12/104 RPR FOND | 44069597 | CARIBOU-PALERMO | 012/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-19 | 2020-01-19 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513479 | 39.631 | ETL.3190 | 40758615 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115708148 | Not Scheduled | T2 EI CARIBOU-PALERMO 12/104 RPL SPLS | 44304495 | CARIBOU-PALERMO | 012/104 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-19 | 2020-01-19 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513479 | 39.631 | ETL.3190 | 40758615 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115711510 | Feb | T2 EI CORTINA-MEND #1 25/118 RPL HRDS | 43721180 | CORTINA-MENDOCINO #1 | 025/118 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 |  |  | 2021-02-17 | 2021-02-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.641704 | 39.0268 | ETL.1330 | 40861151 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115712539 | Feb | T2 EI DRUM-RIO OSO #1 014/123 REPL INSS | 43687117 | DRUM-RIO OSO #1 | 014/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2021-05-31 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-120.979874 | 39.1518 | ETL.1420 | 44337165 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  | Reject | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713224 | Before Feb | T2 EI DRM-HGGNS 015/137 PNT STRT | 43687142 | DRUM-HIGGINS | 015/137 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-22 | 2020-01-22 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.982432 | 39.1506 | ETL.4393 | 40751902 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713608 | Feb | T2 EI DRM-HGGNS 015/138 RPL SPLS | 43687142 | DRUM-HIGGINS | 015/138 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.984931 | 39.1497 | ETL.4393 | 40764843 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713740 | Feb | T2 EI DRM-HGGNS 015/138 RPR COND | 43687142 | DRUM-HIGGINS | 015/138 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.984931 | 39.1497 | ETL.4393 | 40764843 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713834 | Not Scheduled | T2 EI CARIBOU-PALERMO :028/233 RPR STRT | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713836 | Not Scheduled | T2NT EI CARIBOU-PALERMO :28/233 RPR FOND | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713838 | Not Scheduled | T2 EI CARIBOU-PALERMO :028/232 RPR FOND | 44069597 | CARIBOU-PALERMO | :028/232 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450104 | 39.8023 | ETL.3190 | 40702269 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713868 | Not Scheduled | T2 EI CARIBOU-PALERMO :028/233 RPR STRT | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115713870 | Not Scheduled | T2 EI CARIBOU-PALERMO :028/232 RPR STRT | 44069597 | CARIBOU-PALERMO | :028/232 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450104 | 39.8023 | ETL.3190 | 40702269 | Structure-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115716122 | Not Scheduled | T3 DI DRM-GRSS VLLY WMR B17/386 RPL CRSW | 31431045 | DRUM-GRASS VALLEY-WEIMAR | B017/386 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-17 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9653 | 39.1328 | ETL.6760 | 40814230 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-04-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115716177 | Q2 | T2 EI BALCH-SANGER 000/002 RPR CONS | 43684626 | BALCH-SANGER | 000/002 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-19 | 2020-01-19 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.090382 | 36.9083 | ETL.1050 | 40682223 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115716181 | Q2 | T2 EI BALCH-SANGER 000/003 RPR CONS | 43684626 | BALCH-SANGER | 000/003 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-22 | 2020-01-22 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.091491 | 36.9082 | ETL.1050 | 40646819 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115716200 | Q2 | T2 EI BALCH-SANGER 000/001 REPL GYWS | 43684626 | BALCH-SANGER | 000/001 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-19 | 2020-01-19 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.088691 | 36.9085 | ETL.1050 | 40583096 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115716253 | Q2 | T2 EI BALCH-SANGER 002/014 FOND CVRD | 43709595 | BALCH-SANGER | 002/014 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-22 | 2020-01-22 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.1220496 | 36.8981 | ETL.1050 | 40946399 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718349 | Not Scheduled | T2 EI CARIBOU-PALERMO :28/229 RPR STUS | 44069801 | CARIBOU-PALERMO | :028/229 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.444868 | 39.8042 | ETL.3190 | 40867374 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718465 | Mar | T2 EI POE-RIO OSO 022/148 RPR INSS | 43737420 | POE-RIO OSO | 022/148 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.503661 | 39.6655 | ETL.5540 | 40873673 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718497 | Not Scheduled | T2 EI CARIBOU-PALERMO :027/221 RPL INSS |  | CARIBOU-PALERMO | :027/221 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718508 | Not Scheduled | T2 EI CARIBOU-PLERMO :027/221 RPR MEMBER | 44069454 | CARIBOU-PALERMO | :027/221 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718514 | Not Scheduled | T2 EI CARIBOU-PALERMO :29/237 RPR STRT | 44069801 | CARIBOU-PALERMO | :029/237 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.45426 | 39.7907 | ETL.3190 | 40826433 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115718520 | Not Scheduled | T2 EI CARIBOU-PALERMO :28/229 RPR FOND | 44069801 | CARIBOU-PALERMO | :028/229 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.444868 | 39.8042 | ETL.3190 | 40867374 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718523 | Not Scheduled | T2 EI CARIBOU-PALERMO :28/230 RPR STRT | 44069801 | CARIBOU-PALERMO | :028/230 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.447747 | 39.8034 | ETL.3190 | 40618605 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718536 | Not Scheduled | T2 EI CARIBOU-PALERMO :28/230 REPL INSS |  | CARIBOU-PALERMO | :028/230 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.447747 | 39.8034 | ETL.3190 | 40618605 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718628 | Not Scheduled | T2 EI CARIBOU-PALRMO :27/225 BURIED MEMB | 44069801 | CARIBOU-PALERMO | :027/225 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.437982 | 39.8092 | ETL.3190 | 40758496 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718679 | Not Scheduled | DI ATLANTIC-GOLD HILL 27/115 RPL HRDT | 43742041 | ATLANTIC-GOLD HILL | 027/115 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-17 | 2020-01-17 | [5 empty] | TLN/TLQ error |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.140216 | 38.6831 | ETL.4330 | 40750992 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718830 | Not Scheduled | T2 EI CARIBOU-PALERMO :27/227 RPL INSS |  | CARIBOU-PALERMO | :027/227 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.441037 | 39.8063 | ETL.3190 | 40853816 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115718941 | Not Scheduled | EI DRUM-HIGGINS 014/134 CANCEL | 43687142 | DRUM-HIGGINS | 014/134 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | [6 empty] | '-120.974288 | 39.1539 | ETL.4393 | 40597230 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719123 | Not Scheduled | T3 EI DRM-HGGNS 015/139 PNT STRT | 43687142 | DRUM-HIGGINS | 015/139 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2019-07-23 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.987124 | 39.1488 | ETL.4393 | 40814105 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719398 | Not Scheduled | T3 EI DRM-HGGNS 015/140 PNT STRT | 43687142 | DRUM-HIGGINS | 015/140 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2019-07-23 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.989908 | 39.1477 | ETL.4393 | 40809704 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719433 | Not Scheduled | T2 EI CORTINA-MEND #1 31/150 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 031/150 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.745575 | 39.0608 | ETL.1330 | 40608370 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719738 | Not Scheduled | T2 EI CORTINA-MENDO #1 31/149 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 031/149 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.744034 | 39.0585 | ETL.1330 | 40860981 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719837 | Not Scheduled | T3 EI DRM-HGGNS 016/141 RPR INSS | 43687117 | DRUM-HIGGINS | 016/141 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2019-07-23 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.992547 | 39.1467 | ETL.4393 | 40862213 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719851 | Q2 | T2 EI CTTNWD-DELEVAN #1 10/069 REPL DAMS | 43726632 | COTTONWOOD-DELEVAN #1 | 010/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 |  |  | 2021-04-02 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267785 | 40.2442 | ETL.4550 | 40870759 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719852 | Not Scheduled | T2 EI CORTINA-MENDO #1 031/148 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 031/148 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.742882 | 39.0568 | ETL.1330 | 40870421 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115719902 | Not Scheduled | T2 EI CORTINA-MENDO #1 32/155 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 032/155 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.753577 | 39.0725 | ETL.1330 | 40750577 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115720141 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/156 RPR FOND | 44069597 | CARIBOU-PALERMO | :018/156 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.340824 | 39.9089 | ETL.3190 | 40738360 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115720529 | Not Scheduled | EI DELEVAN-VACA #2 161/1223 INST HRDT | 43910525 | DELEVAN-VACA #2 | 161/1223 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.116488 | 38.949 | ETL.4231 | 40650665 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115720578 | Not Scheduled | T2 EI CARIBOU-PALERMO :006/051 REPL INSS |  | CARIBOU-PALERMO | :006/051 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.221517 | 40.0202 | ETL.3190 | 40910293 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115720617 | Not Scheduled | T2 EI CARIBOU-PALERMO :06/53 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :006/053 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.223574 | 40.0149 | ETL.3190 | 40910295 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115720646 | Not Scheduled | T2 EI CARIBOU-PALERMO :06/053 BENT MEMB | 44059014 | CARIBOU-PALERMO | :006/053 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.223574 | 40.0149 | ETL.3190 | 40910295 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115720648 | Q2 | T3 EI MORAGA-SAN LE #2 0/006 RPL SPLS | 43708450 | MORAGA-SAN LEANDRO #2 | 000/006 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2019-07-23 |  |  | 2021-05-27 | 2021-05-26 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.164492 | 37.8361 | ETL.2780 | 40850662 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1 | 2019-03-17 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115720668 | Mar | T2 EI HIGGINS-BELL 028/217 RPR SPLS | 43740275 | HIGGINS-BELL | 028/217 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2020-01-23 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08214 | 39.0318 | ETL.1412 | 40593236 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115720784 | Not Scheduled | T2 EI CORTINA-MENDO #1 32/157 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 032/157 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.756031 | 39.0761 | ETL.1330 | 40818158 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721009 | Q2 | T2 EI CSCD-BNTN-DSCHTS A7/155 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A007/155 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.260844 | 40.5657 | ETL.6310 | 40816322 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721021 | Not Scheduled | T2 EI CARIBOU-PALERMO :26/212 RPL INSS |  | CARIBOU-PALERMO | :026/212 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42118 | 39.8307 | ETL.3190 | 40674984 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721051 | Feb | DI PLACER-GOLD HILL #1 16/112 RMV DEBRIS | 43932211 | PLACER-GOLD HILL #1 | 016/112 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-22 | 2020-01-22 |  |  | 2021-02-19 | 2021-02-19 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.147436 | 38.6832 | ETL.3340 | 40906513 | Conductor-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721295 | Mar | T2 EI PIT#3-CARBERY SW ST 0/9 REPL SPLS | 43755519 | PIT #3-CARBERRY SW STA | 000/009 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.747005 | 40.9782 | ETL.5450 | 40870261 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721368 | Not Scheduled | T2NT EI CRESTA-RIO OSO 008/072A PAINT | 43708739 | CRESTA-RIO OSO | 008/072A | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421964 | 39.8293 | ETL.4590 | 41162726 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721609 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/156 INST HRDT | 44069597 | CARIBOU-PALERMO | :018/156 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.340824 | 39.9089 | ETL.3190 | 40738360 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115721736 | Not Scheduled | T2 EI CORTINA-MENDO #1 35/170 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 035/170 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.796553 | 39.1051 | ETL.1330 | 40587897 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115722109 | Not Scheduled | T2 DI PLACER-GOLD HILL #1 8/61 CANCEL | 43910532 | PLACER-GOLD HILL #1 | 008/061 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Internal Process |  | '-121.134416 | 38.7852 | ETL.3340 | 40911171 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115722178 | Q2 | T2 EI BALCH-SANGER 003/022 REPL DAMS | 43684626 | BALCH-SANGER | 003/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-23 | 2020-01-23 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.124367 | 36.8788 | ETL.1050 | 40652360 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115734569 | Not Scheduled | T2 EI CARIBOU-PALERMO :28/231 RPR STRT | 44069801 | CARIBOU-PALERMO | :028/231 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Structure-Tower | Anti-Climbing Guard | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115734822 | Not Scheduled | T2 EI CARIBOU-PALERMO :28/231 RPR GYWS | 44304495 | CARIBOU-PALERMO | :028/231 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115734967 | Q2 | T2 EI BALCH-SANGER 0/6 CVRD FOUNDATION | 43709595 | BALCH-SANGER | 000/006 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.0984223 | 36.9076 | ETL.1050 | 40954394 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115734970 | Not Scheduled | T2 EI CARIBOU-PALERMO :26/218 RPL SPLS | 44070463 | CARIBOU-PALERMO | :026/218 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.427709 | 39.8217 | ETL.3190 | 40867976 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115734971 | Not Scheduled | T2 EI CARIBOU-PALERMO :26/218 BENT MEMB | 44304495 | CARIBOU-PALERMO | :026/218 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.427709 | 39.8217 | ETL.3190 | 40867976 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735192 | Not Scheduled | T2 EI CARIBOU-PALERMO :026/220 RPR ST | 44069454 | CARIBOU-PALERMO | :026/220 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735194 | Not Scheduled | T2 EI CARIBOU-PALERMO :26/220 REPL INSS |  | CARIBOU-PALERMO | :026/220 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735242 | Q2 | T2 EI CRESTA-RIO OSO 008/072B RPR JUMP | 43708739 | CRESTA-RIO OSO | 008/072B | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2020-01-23 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421963 | 39.8294 | ETL.4590 | 41162727 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735555 | Feb | T3 EI DRUM-HIGGINS 016/142 CONS | 43738143 | DRUM-HIGGINS | 016/142 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2019-07-24 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735639 | Feb | T3 EI DRUM-HIGGINS 016/142 RPL SPLS | 43687142 | DRUM-HIGGINS | 016/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2019-07-24 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735747 | Feb | T3 EI DRUM-HIGGINS 016/142 RPR CONS | 43687142 | DRUM-HIGGINS | 016/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2019-07-24 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115735921 | Not Scheduled | T2 EI CORTINA-MENDO #1 33/159 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 033/159 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.761358 | 39.0803 | ETL.1330 | 40870087 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115736500 | Not Scheduled | T2 EI RND MTN-CTTNWD #3 R001/017 REPAINT | 43755803 | ROUND MTN-COTTONWOOD #3 | R001/017 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936067 | 40.797 | ETL.5650 | 40810238 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115736520 | Feb | T2 EI RND MTN-CTTNWD #3 R001/017 JUMS | 43755803 | ROUND MTN-COTTONWOOD #3 | R001/017 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936067 | 40.797 | ETL.5650 | 40810238 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115736566 | Not Scheduled | T2 EI VC-VCVLL-JAMESON-NTH TWR INST HRDT | 43740642 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/062 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2024-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.030828 | 38.3414 | ETL.4100 | 40650934 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115736630 | Not Scheduled | T2 EI CARIBOU-PALERMO :4/034 RPR STRT | 44059014 | CARIBOU-PALERMO | :004/034 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.210326 | 40.0495 | ETL.3190 | 40910278 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115736694 | Feb | T3 EI DRM-HGGNS 016/145 RPR CONS | 43687142 | DRUM-HIGGINS | 016/145 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2019-07-24 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.006557 | 39.1411 | ETL.4393 | 40913041 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737014 | Q4 | EI TRINITY-COTTONWOOD 11/87R REPL PL | 31455647 | TRINITY-COTTONWOOD | 011/087 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 |  |  | 2021-11-22 | 2021-08-23 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.420759 | 40.5099 | ETL.4040 | 44558225 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737186 | Not Scheduled | T2 EI CARIBOU-TABLE MTN 012/093 RPR STRT | 31454671 | CARIBOU-TABLE MTN | 012/093 | 70S | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2022-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  | REJECT: Crew reported work not needed. Please confirm(approve) or reject if disagree. |  |  | '-121.21733 | 40.0432 | ETL.4440 | 40662309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  | Reject |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737189 | Feb | T2 EI RND MTN-CTTNWD #3 27/222 RPL INSS | 31529415 | ROUND MTN-COTTONWOOD #3 | 027/222 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939278 | 40.7909 | ETL.5650 | 40668261 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737271 | Mar | EI DLVAN-VCA #2 162/1229 INS RPTR GRD | 31436101 | DELEVAN-VACA #2 | 162/1229 | 93R | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2022-01-24 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.109652 | 38.9377 | ETL.4231 | 40870217 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737403 | Not Scheduled | T2 EI CARIBOU-PALERMO :5/040 RPR CONS | 44070463 | CARIBOU-PALERMO | :005/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737441 | Not Scheduled | EI HIGGINS-BELL 035/263 RMV VEGN |  | HIGGINS-BELL | 035/263 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2020-01-24 |  |  |  | 2021-05-15 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.056345 | 38.9398 | ETL.1412 | 40816901 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737534 | Feb | T2 EI RND MTN-CTTNWD #3 R2/20 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | R002/020 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937705 | 40.7928 | ETL.5650 | 40604759 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737558 | Not Scheduled | T2 EI CORTINA-MENDO #1 36/173 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 036/173 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2022-01-24 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.80423 | 39.1092 | ETL.1330 | 40648767 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115737981 | Not Scheduled | T2 EI CARIBOU-PALERMO :25/208 BENT MEMB | 44069454 | CARIBOU-PALERMO | :025/208 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.419325 | 39.8395 | ETL.3190 | 40878271 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115738355 | Not Scheduled | T2 EI CARIBOU-PALERMO :24/204 REPAINT | 44302715 | CARIBOU-PALERMO | :024/204 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2025-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.414213 | 39.8445 | ETL.3190 | 40771768 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115738356 | Not Scheduled | T2 EI BALCH-SANGER 001/011 RUST REPAINT | 43848550 | BALCH-SANGER | 001/011 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.116429 | 36.903 | ETL.1050 | 40583098 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115738361 | Q2 | T2 EI BALCH-SANGER 001/009 RPR CONS | 43684626 | BALCH-SANGER | 001/009 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-24 | 2020-01-24 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.110094 | 36.9046 | ETL.1050 | 40859624 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115738406 | Not Scheduled | T2 EI CARIBOU-PALERMO :24/202 RPL INSS |  | CARIBOU-PALERMO | :024/202 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.409795 | 39.8476 | ETL.3190 | 40674980 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115738407 | Not Scheduled | T2 EI CARIBOU-PALRMO :024/201 RPR MEMBER | 44069454 | CARIBOU-PALERMO | :024/201 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-24 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.408343 | 39.8486 | ETL.3190 | 40591566 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115739270 | Not Scheduled | T2 EI CARIBOU-PALERMO :024/203 BENT MEMB | 44069454 | CARIBOU-PALERMO | :024/203 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2021-05-31 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.413518 | 39.8449 | ETL.3190 | 40651675 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739280 | Not Scheduled | T2 EI ROCK CREEK-POE 006/046 RPAINT STRT | 43724472 | ROCK CREEK-POE | 006/046 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2024-01-24 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.415344 | 39.8446 | ETL.5630 | 40820423 | Structure-Tower | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739295 | Mar | T2 EI HUMBOLDT-TRINITY 63/03C RPR GYWW | 43729542 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562966 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739302 | Mar | T2 EI HUMBOLDT-TRINITY 063/003 REPL SPLW | 43729542 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562966 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739518 | Before Feb | T3 EI DRUM-HIGGINS 016/143 PNT STRT | 43687142 | DRUM-HIGGINS | 016/143 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-25 | 2019-07-25 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.999826 | 39.1438 | ETL.4393 | 40604652 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739548 | Q2 | T2 EI CRESTA-RIO OSO 8/74 RPL SPLS | 43708739 | CRESTA-RIO OSO | 008/074 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2020-01-23 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.424997 | 39.8255 | ETL.4590 | 40907013 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739608 | Not Scheduled | T2 EI CARIBOU-PALERMO :27/226 RPR SPLS | 44304495 | CARIBOU-PALERMO | :027/226 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.438961 | 39.8082 | ETL.3190 | 40828380 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739640 | Q2 | T2 EI CRESTA-RIO OSO 8/74 RPR INSS | 43708739 | CRESTA-RIO OSO | 008/074 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2020-01-23 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4236839 | 39.8273 | ETL.4590 | 40916714 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739641 | Not Scheduled | T2 CARIBOU-PALERMO :24/197 RPR STRT | 44304495 | CARIBOU-PALERMO | :024/197 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.400639 | 39.8521 | ETL.3190 | 40815588 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739645 | Q2 | T2 EI CRESTA-RIO OSO 9/75 RPR INSS | 43708739 | CRESTA-RIO OSO | 009/075 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2020-01-23 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.425452 | 39.825 | ETL.4590 | 40907014 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739653 | Feb | T2 EI ROCK CREEK-POE 009/065 RPL HRDT | 43724474 | ROCK CREEK-POE | 009/065 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2020-01-22 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.438985 | 39.8092 | ETL.5630 | 40762480 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739654 | Q2 | T2 EI CRESTA-RIO OSO 9/75 RPL SPLS | 43708739 | CRESTA-RIO OSO | 009/075 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2020-01-23 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.425452 | 39.825 | ETL.4590 | 40907014 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115739868 | Mar | EI HIGGINS-BELL 035/260 SPLS | 43740275 | HIGGINS-BELL | 035/260 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-25 | 2020-01-25 |  |  | 2021-03-17 | 2021-03-14 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.052019 | 38.9444 | ETL.1412 | 40762907 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115740348 | Feb | T2 EI CORTINA-MENDO #1 38/182 RPL INSS | 31432492 | CORTINA-MENDOCINO #1 | 038/182 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | 2020-09-02 | 2020-09-04 | 2021-02-17 | 2021-02-08 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.832153 | 39.1232 | ETL.1330 | 40710766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115740641 | Not Scheduled | T2 EI CORTINA-MENDO #1 060/296 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 060/296 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.18768 | 39.2459 | ETL.1330 | 40809308 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115740854 | Mar | T2 EI HUMBOLDT-TRINITY 091/004 RPR GYWW | 43729543 | HUMBOLDT-TRINITY | 091/004 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-01-25 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.70711 | 40.7485 | ETL.1820 | 44560531 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-03-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-03-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115740916 | Feb | T3 EI RND MTN-CTTNWD #3 028/235 RPL INSS | 31424180 | ROUND MTN-COTTONWOOD #3 | 028/235 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2019-07-25 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9517036 | 40.7761 | ETL.5650 | 40792333 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115740942 | Not Scheduled | T2 EI METCALF-GREEN VLY 009/057 REPAINT | 44300668 | METCALF-GREEN VALLEY | 009/057 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-25 | 2024-01-25 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.666854 | 37.1338 | ETL.2540 | 40808555 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741211 | Not Scheduled | T2 EI CARIBOU-PALERMO :004/032 REPL INSS | 31426590 | CARIBOU-PALERMO | :004/032 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.206261 | 40.0532 | ETL.3190 | 40910276 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-02-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741219 | Not Scheduled | T2 EI VACA-SUISUN 10/078 REPAINT | 43740501 | VACA-SUISUN | 010/078 | ICD | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 | '-122.052407 | 38.307 | ETL.4070 | 40865461 | Structure-Tower | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense |  | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115741287 | Not Scheduled | T2 EI MEDOCNO-RDBD 60/295 RPL SPLS | 43721139 | MENDOCINO-REDBUD | 060/295 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | 2020-09-02 | 2020-09-04 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.185825 | 39.2447 | ETL.2410 | 40779105 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741288 | Not Scheduled | T2 EI CARIBOU-PALERMO :05/045 REPAINT | 44302715 | CARIBOU-PALERMO | :005/045 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-25 | 2021-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218992 | 40.0312 | ETL.3190 | 40910287 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741375 | Feb | T2 EI CORTINA-MENDO #1 59/294 RPR MEMBER | 43721181 | CORTINA-MENDOCINO #1 | 059/294 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | 2020-09-02 | 2020-09-04 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.184946 | 39.2442 | ETL.1330 | 40750616 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741402 | Mar | T2 EI HIGGINS-BELL 035/259 RPL SPLS | 43740275 | HIGGINS-BELL | 035/259 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-25 | 2020-01-25 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.049846 | 38.9467 | ETL.1412 | 40663157 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741530 | Q3 | T2 EI KRKHF-CLVS-SNGR #1 06/045 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 006/045 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.603319 | 36.972 | ETL.1890 | 40764698 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741588 | Q3 | T2 EI KRKHF-CLVS-SNGR #1 06/046 RPL RPTS | 43709695 | KERCKHOFF-CLOVIS-SANGER #1 | 006/046 | ICB | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.60245 | 36.97 | ETL.1890 | 40807006 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 593 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741598 | Not Scheduled | T2 CARIBOU-PALERMO :4/036 RPR HRDT | 44069455 | CARIBOU-PALERMO | :004/036 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2021-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21611 | 40.0461 | ETL.3190 | 40910280 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741762 | Not Scheduled | WEIMAR-HALSEY - 60 kV_003/072 | 31454601 | WEIMAR-HALSEY | 003/072 | 70Y | F | Pre-2020_(5) TD tag on other lines |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.00979 | 38.9916 | ETL.8340 | 40822754 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741900 | Not Scheduled | T2 EI MTCLF-MSS LNDNG #1 33/151 PNT STRT | 44300665 | METCALF-MOSS LANDING #1 | 033/151 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.680147 | 37.1433 | ETL.5100 | 40587032 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115741934 | Not Scheduled | T2 EI VACA-PARKWAY 14/77 INS HDWT | 43760159 | VACA-PARKWAY | 014/077 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2022-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.132055 | 38.2958 | ETL.5850 | 40821356 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115742010 | Not Scheduled | T2 EI CARIBOU-PALERMO :06/046 RPL HRDS | 44070463 | CARIBOU-PALERMO | :006/046 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219048 | 40.0305 | ETL.3190 | 40910288 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115742325 | Not Scheduled | T2 EI CORTINA-MENDO #1 059/293 RPR FOND | 43760958 | CORTINA-MENDOCINO #1 | 059/293 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.180753 | 39.2418 | ETL.1330 | 40659631 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115742589 | Not Scheduled | T2 EI CORTINA-MEND #1 59/287 RPL HRDT | 43721181 | CORTINA-MENDOCINO #1 | 059/287 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115742700 | Not Scheduled | T2 EI CORTINA-MEND #1 59/287 RPR STRT | 43721181 | CORTINA-MENDOCINO #1 | 059/287 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115742703 | Feb | T2 EI CORTINA-MEND #1 59/287 WASH INSS | 43720999 | CORTINA-MENDOCINO #1 | 059/287 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 |  |  | 2021-02-17 | 2021-02-08 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115742708 | Not Scheduled | T2 EI CTTNWD-DELEVN #2 067/591 STRT | 43730227 | COTTONWOOD-DELEVAN #2 | 067/591 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267862 | 40.2929 | ETL.4580 | 40597356 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754392 | Feb | T2 EI BCKS-RCK-CRSTA :0/6 INSTL MRKS | 43742056 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/006 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-23 | 2020-01-23 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.355287 | 39.9047 | ETL.4430 | 40816401 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754583 | Not Scheduled | T2 EI CARIBOU-PALERMO :016/131 RPR STRT | 44304495 | CARIBOU-PALERMO | :016/131 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318389 | 39.9316 | ETL.3190 | 40642565 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754585 | Feb | T2 EI BCKS CRK-RCK CRK-CRST 006/054 INSS | 31450543 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/054 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4182442 | 39.8411 | ETL.4430 | 40788518 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754597 | Not Scheduled | T2 EI CARIBOU-PALERMO :016/131 RPR STRT | 44069597 | CARIBOU-PALERMO | :016/131 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318389 | 39.9316 | ETL.3190 | 40642565 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754612 | Not Scheduled | T2 EI CARIBOU-PALERMO :021/181 RPR STRT | 44304495 | CARIBOU-PALERMO | :021/181 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37771 | 39.873 | ETL.3190 | 40642568 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115754656 | Not Scheduled | T2 EI CARIBOU-PALERMO :22/182 RPL HRDT | 44304495 | CARIBOU-PALERMO | :022/182 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37803 | 39.8724 | ETL.3190 | 40738807 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115754659 | Before Feb | T2 EI DRM-HGGNS 020/161 PNT TWR | 43687142 | DRUM-HIGGINS | 020/161 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-26 | 2020-01-26 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.056277 | 39.1196 | ETL.4393 | 40913057 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754697 | Not Scheduled | T2 EI CARIBOU-PALERMO :021/181 RPNT TWR | 44304495 | CARIBOU-PALERMO | :021/181 | ICS | E | Pre-2020_(3) On high spread structure |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37771 | 39.873 | ETL.3190 | 40642568 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115754794 | Not Scheduled | T2 Mendocino Red Bud_032/157 | 43919493 | MENDOCINO-REDBUD | 032/157 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.756226 | 39.0764 | ETL.2410 | 40844454 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754799 | Mar | T2 EI HIGGINS-BELL 031/232 RPR SPLS | 43740275 | HIGGINS-BELL | 031/232 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-26 | 2020-01-26 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061476 | 38.9999 | ETL.1412 | 40824195 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754802 | Feb | T2 EI DRM-HGGNS 020/162 RPR JUMS | 43687142 | DRUM-HIGGINS | 020/162 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.057427 | 39.1183 | ETL.4393 | 40913058 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115754863 | Feb | T3 EI RND MT-CTTNWD #3 33/281 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 033/281 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2019-07-26 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9989165 | 40.7191 | ETL.5650 | 40617505 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755025 | Feb | T2 EI DRM-HGGNS 020/164 RPL INSS | 31499112 | DRUM-HIGGINS | 020/164 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2021-05-31 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.0624766 | 39.116 | ETL.4393 | 40922904 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-06-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755063 | Not Scheduled | T2 EI BALCH-SANGER 001/012 RUST REPAINT | 43848550 | BALCH-SANGER | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.120545 | 36.902 | ETL.1050 | 40682227 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755066 | Not Scheduled | T2 EI CARIBOU-PALERMO :002/019 RPR STRT | 44070463 | CARIBOU-PALERMO | :002/019 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755085 | Not Scheduled | T2 EI CORTINA-MENDO #1 47/230 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 047/230 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2022-01-26 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.962089 | 39.1968 | ETL.1330 | 40608372 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755141 | Not Scheduled | T2 EI DRUM-HIGGINS 020/165 PNT TWR | 43687142 | DRUM-HIGGINS | 020/165 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2024-01-26 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.066296 | 39.1157 | ETL.4393 | 40913061 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755224 | Not Scheduled | T2 EI PT #5-RND MTN #1 3/32 PAINT STRT | 44322478 | PIT #5-ROUND MTN #1 | 003/032 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.946484 | 40.9497 | ETL.5420 | 40660954 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755232 | Not Scheduled | T2 EI PIT #5-RNDMTN #1 000/005 PNT TWR | 44322478 | PIT #5-ROUND MTN #1 | 000/005 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.968361 | 40.9803 | ETL.5420 | 40752302 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755246 | Feb | T2 EI CHC-SAL-SOL #2 :10/55 RPL CNDS | 31511873 | MOSS LANDING-SALINAS-SOLEDAD #2 | :010/055 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-18 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.475392 | 36.6263 | ETL.2910 | 40781230 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Moss Landing |  | Y - SS | 2019-04-17 | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755249 | Not Scheduled | T2 EI CORTINA-MENDO #1 048/235 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 048/235 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2022-01-26 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.979693 | 39.2025 | ETL.1330 | 40750593 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755361 | Feb | T2 EI CHC-SAL-SOL #2 :010/056 RPL CNDS | 31511873 | MOSS LANDING-SALINAS-SOLEDAD #2 | :010/056 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-18 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.4712728 | 36.6259 | ETL.2910 | 40838080 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Moss Landing |  | Y - SS | 2019-04-17 | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755449 | Not Scheduled | T2 EI CARIBOU-PALERMO :016/132 REPL INSS |  | CARIBOU-PALERMO | :016/132 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318489 | 39.9304 | ETL.3190 | 40738350 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755450 | Not Scheduled | T2 EI CARIBOU-PALERMO :016/132 REPL HRDT | 44304495 | CARIBOU-PALERMO | :016/132 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318489 | 39.9304 | ETL.3190 | 40738350 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755451 | Feb | T2 EI RO DLL JT-BRDGVLLE 33/06 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 033/006 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.896831 | 40.4848 | ETL.7850 | 40808722 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755516 | Not Scheduled | T2 EI BRIDGEVILLE-CTNWD 036/292 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 036/292 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.95442 | 40.3675 | ETL.1110 | 40762887 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755545 | Not Scheduled | T2 EI CARIBOU-PALRMO :16/135 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :016/135 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318466 | 39.9265 | ETL.3190 | 40753307 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115755687 | Not Scheduled | T2 EI CARIBOU-PALERMO :020/160 RPR STRT | 44069454 | CARIBOU-PALERMO | :020/160 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642284 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115756260 | Q2 | T2 EI BALCH-SANGER 003/023 RPR FOND | 43700488 | BALCH-SANGER | 003/023 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2020-01-24 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.127419 | 36.879 | ETL.1050 | 40657794 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-03-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756391 | Not Scheduled | T2 EI CARIBOU-PALERMO :21/177 INS HRDT | 44304495 | CARIBOU-PALERMO | :021/177 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.372498 | 39.8832 | ETL.3190 | 40738367 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756392 | Not Scheduled | T2 EI CARIBOU-PALERMO :21/177 PAINT STRT | 44302715 | CARIBOU-PALERMO | :021/177 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2021-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.372498 | 39.8832 | ETL.3190 | 40738367 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756460 | Mar | T2 EI HIGGINS-BELL 33/251 RPL SPLS | 43740275 | HIGGINS-BELL | 033/251 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-26 | 2020-01-26 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042373 | 38.9618 | ETL.1412 | 40762676 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756598 | Not Scheduled | T2 EI CARIBOU-PALERMO :2/021 RPL HRDT | 44062862 | CARIBOU-PALERMO | :002/021 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.189644 | 40.0629 | ETL.3190 | 40910265 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756680 | Q2 | T2 EI HMBLDT-BRDGVLL 113/7 RPR INSW | 43749687 | HUMBOLDT-BRIDGEVILLE | 113/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-124.073848 | 40.7722 | ETL.1810 | 40854183 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-04-03 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756799 | Feb | T2 EI VACA-SUISUN-JAMS 11/081 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 011/081 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-28 | 2020-01-28 |  |  | 2021-02-13 | 2021-02-11 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.057467 | 38.2989 | ETL.4080 | 40614350 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756813 | Not Scheduled | T2 EI VAC-VAC-JAM-N T 009/072 INST HRDT | 43740642 | VACA-VACAVILLE-JAMESON-NTH TWR | 009/072 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2024-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.044556 | 38.3201 | ETL.4100 | 40653589 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756942 | Not Scheduled | T2 EI STANISLAUS-MAN #2 10/64 INST MRKS | 43713081 | STANISLAUS-MANTECA #2 | 010/064 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.534547 | 38.0589 | ETL.3820 | 40744466 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115756947 | Mar | T2 EI HIGGINS-BELL 031/236 RPR JUMS | 43740275 | HIGGINS-BELL | 031/236 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-28 | 2020-01-28 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.056654 | 38.9925 | ETL.1412 | 40602396 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115757379 | Not Scheduled | T2 EI CORTINA-MENDO #1 54/266 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 054/266 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.081093 | 39.2201 | ETL.1330 | 40808943 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115757666 | Not Scheduled | T2 EI PIT#5-RUND MTN#2 12/121 REPAINT | 44343738 | PIT #5-ROUND MTN #2 | 012/121 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-28 | 2020-01-28 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938059 | 40.8092 | ETL.5430 | 40595120 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115757962 | Not Scheduled | T2 EI STAN-MEL S S-M #1 :007/041 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :007/041 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-28 | 2024-01-28 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.640332 | 37.9847 | ETL.3830 | 40579597 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-12-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115758143 | Not Scheduled | T2 EI CORTINA-MENDO #1 054/270 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 054/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.094164 | 39.224 | ETL.1330 | 40587921 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115758888 | Not Scheduled | T2 EI CARIBOU-PALERMO :002/017 RPR STRT | 44062862 | CARIBOU-PALERMO | :002/017 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.177753 | 40.0689 | ETL.3190 | 40910261 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115759055 | Feb | T2 EI ROUND MTN-COT #3 038/333 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 038/333 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0520811 | 40.6559 | ETL.5650 | 40686374 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115759184 | Q2 | T2 EI PT#5-RUND MTN#1 6/71 REPL DAM | 43758395 | PIT #5-ROUND MTN #1 | 006/071 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929593 | 40.8996 | ETL.5420 | 40677517 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115759210 | Feb | T2 EI DRUM-RIO OSO #1 020/157 RPL HRDT | 43685808 | DRUM-RIO OSO #1 | 020/157 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.081707 | 39.1116 | ETL.1420 | 40805287 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115759960 | Not Scheduled | T2 EI STANSLUS-MLNS-MNTC#1 3/19 INST MRK | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 003/019 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-28 | 2020-01-28 | [5 empty] | TLN/TLQ error - Move to TLQ |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.420247 | 38.1209 | ETL.3830 | 40872686 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115760352 | Not Scheduled | T2 EI CARIBOU-PALERMO :003/028 BIRD CAGI | 43659205 | CARIBOU-PALERMO | :003/028 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-02-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115760355 | Not Scheduled | T2 EI CARIBOU-PALERMO :3/28 LACING BENT | 44062862 | CARIBOU-PALERMO | :003/028 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115760392 | Not Scheduled | T2 EI CORTINA-MENDO #1 14/067 CANCEL | 44306522 | CORTINA-MENDOCINO #1 | 014/067 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.451374 | 39.0308 | ETL.1330 | 40808518 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115760452 | Not Scheduled | T2 EI BRIDGEVILLE-CTNWD 019/178 FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 019/178 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.634902 | 40.3783 | ETL.1110 | 40759346 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115760927 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/169 HANGER | 44304495 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115760954 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/169 RESAG CONS | 44304495 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115760958 | Mar | T2 EI HUMBOLDT-TRINITY 86/6 (L) RPL STRW | 31497850 | HUMBOLDT-TRINITY | 086/006 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-01-26 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.626189 | 40.7198 | ETL.1820 | 44560566 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-03-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115760960 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/169 RPR JUMP | 44304495 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115760981 | Mar | T2 EI HUMBOLDT-TRINITY 86/6 (R) RPL STRW | 31497850 | HUMBOLDT-TRINITY | 086/006 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-01-26 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.626189 | 40.7198 | ETL.1820 | 44560567 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-03-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115760989 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/154 RPR JUMS | 44304495 | CARIBOU-PALERMO | :018/154 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115760991 | Not Scheduled | T2 CARIBOU-PALERMO :23/196 RPL HRDT | 44304495 | CARIBOU-PALERMO | :023/196 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.399908 | 39.853 | ETL.3190 | 40828384 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761006 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/154 RPR STRT | 44304495 | CARIBOU-PALERMO | :018/154 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761013 | Not Scheduled | T2 EI CARIBOU-PALERMO :18/157 REPAINT | 44302715 | CARIBOU-PALERMO | :018/157 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2021-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.345372 | 39.9086 | ETL.3190 | 40810968 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761027 | Not Scheduled | T2 EI CARIBOU-PALERMO :17/139 RPR STUBS | 44069583 | CARIBOU-PALERMO | :017/139 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318496 | 39.9218 | ETL.3190 | 40738353 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761040 | Mar | T3 EI EGL-RCK CORTINA 17/083 RPL INSS | 31432492 | EAGLE ROCK-CORTINA | 017/083 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-26 | 2019-07-26 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5057491 | 39.0088 | ETL.1470 | 40676658 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761049 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/168 INST HRDT | 44069454 | CARIBOU-PALERMO | :020/168 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361944 | 39.8926 | ETL.3190 | 40858943 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115761053 | Not Scheduled | T2 EI CARIBOU-PALERMO :023/193 RPR CRST | 44069454 | CARIBOU-PALERMO | :023/193 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.395764 | 39.8578 | ETL.3190 | 40668938 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115761065 | Not Scheduled | T2 EI CARIBOU-PALERMO :023/193 RPR INST |  | CARIBOU-PALERMO | :023/193 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.395764 | 39.8578 | ETL.3190 | 40668938 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115761084 | Not Scheduled | T2 EI STNSLS-MS-MNTC #1 :6/35 RPR FOND | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | :006/035 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2022-01-29 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.624725 | 37.9743 | ETL.3830 | 40744455 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761102 | Not Scheduled | T2 EI DRUM-HIGGINS 021/174 RPR STRT | 43687117 | DRUM-HIGGINS | 021/174 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.089435 | 39.1084 | ETL.4393 | 40913070 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761152 | Feb | T2 EI RND MTN-CTNWD #3 40/344 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 040/344 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.074882 | 40.6285 | ETL.5650 | 40764770 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761211 | Q2 | T2 EI SBRNT-GRZL-CLRMT #2 7/51 RPR STRT | 44146666 | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.2282 | 37.8476 | ETL.3750 | 40804878 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 | 2019-04-25 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761216 | Not Scheduled | T2 EI DRUM-HIGGINS 022/175 PNT TWR | 43687142 | DRUM-HIGGINS | 022/175 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2024-01-29 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.093165 | 39.1069 | ETL.4393 | 40913071 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761291 | Not Scheduled | T3 EI RND MTN-CTNWD #3 34/293 INST HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 034/293 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.011598 | 40.7044 | ETL.5650 | 40656719 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761299 | Mar | T2 EI HIGGINS-BELL 32/244 RPR INSS | 43740275 | HIGGINS-BELL | 032/244 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-29 | 2020-01-29 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.045848 | 38.9759 | ETL.1412 | 40869245 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761340 | Not Scheduled | T2 EI CARIBOU-PALERMO :06/47 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :006/047 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219269 | 40.0274 | ETL.3190 | 40910289 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115761343 | Not Scheduled | T2 EI CARIBOU-PALERMO :002/020 RPR STRT | 44070463 | CARIBOU-PALERMO | :002/020 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.18454 | 40.065 | ETL.3190 | 40910264 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761389 | Feb | T2 EI RND MTN-CTTND #3 41/352 RPR SPLCT | 43755803 | ROUND MTN-COTTONWOOD #3 | 041/352 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.084637 | 40.6167 | ETL.5650 | 40675864 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761427 | Not Scheduled | T2 EI DRUM-HIGGINS 022/178 PNT TWR | 43687142 | DRUM-HIGGINS | 022/178 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2023-01-29 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.101735 | 39.1035 | ETL.4393 | 40913074 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115761507 | Not Scheduled | T3 EI GEYSERS #13 TAP 00/004 PNT TWR | 43693051 | GEYSERS #13 TAP | 000/004 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.73642 | 38.7741 | ETL.4781 | 40750673 | Structure-Steel | Paint/Coating | Other | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115762140 | Not Scheduled | T2 CARIBOU-PALERMO :20/170 INS HRDT | 44069454 | CARIBOU-PALERMO | :020/170 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.363578 | 39.8908 | ETL.3190 | 40642282 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763532 | Not Scheduled | T3 EI CARIBOU-PLERMO :030/245 RPR STRT | 43659208 | CARIBOU-PALERMO | :030/245 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763533 | Not Scheduled | T3 EI CARIBOU-PLERMO :030/245 RPR FOND | 44051417 | CARIBOU-PALERMO | :030/245 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763534 | Not Scheduled | T3 EI CARIBOU-PLERMO :030/245 INST HRDT | 44051417 | CARIBOU-PALERMO | :030/245 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763570 | Q2 | T2 EI PIT #7 TAP 1/12C RPR SHLW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-29 | 2020-01-29 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763573 | Q2 | T2 EI PIT #7 TAP 001/012A RPR GRWW | 43877044 | PIT #7 TAP | 001/012A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-29 | 2020-01-29 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971536 | 40.836 | ETL.5442 | 41162601 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763579 | Not Scheduled | T2 EI CARIBOU-PALERMO :1/11 RPR STUBS | 44062862 | CARIBOU-PALERMO | :001/011 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.165487 | 40.0733 | ETL.3190 | 40912340 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115763585 | Not Scheduled | T2 EI CARIBOU-PALERMO :1/011 INS HRDT | 44062862 | CARIBOU-PALERMO | :001/011 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.165487 | 40.0733 | ETL.3190 | 40912340 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115764020 | Q2 | T2 EI SBRNT-GRZL-CLRMT #2 7/51 RPR FOND | 44146666 | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/051 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.2282 | 37.8476 | ETL.3750 | 40804878 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 | 2019-04-25 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115764148 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/164 BENT MEMB | 44069454 | CARIBOU-PALERMO | :020/164 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361945 | 39.8992 | ETL.3190 | 40753366 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115764149 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/164 RPL HRDS | 44304495 | CARIBOU-PALERMO | :020/164 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361945 | 39.8992 | ETL.3190 | 40753366 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115764416 | Not Scheduled | T2 EI STANISLAUS-MNTCA #2 12/70 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 012/070 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2022-01-30 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.556368 | 38.0484 | ETL.3820 | 40607307 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-10-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115764562 | Feb | T2 EI DRUM-RIO OSO #1 021/166 RPR COND | 43685808 | DRUM-RIO OSO #1 | 021/166 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107424 | 39.1014 | ETL.1420 | 40805297 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115764947 | Not Scheduled | T2 EI STNSLS-MLNS-MNTCA 007/043 RPR STRT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 007/043 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2022-01-30 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.481878 | 38.0869 | ETL.3830 | 40642774 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765040 | Not Scheduled | T2 EI MENDOCINO-UKIAH 037/003 REGRADE | 44306674 | MENDOCINO-UKIAH | 037/003 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.159175 | 39.1564 | ETL.2420 | 40662784 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-05-01 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765066 | Q2 | T2 EI BRVILLE-CTNWD 045/353C RMV DBRS | 43862800 | BRIDGEVILLE-COTTONWOOD | 045/353C | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.108201 | 40.3967 | ETL.1110 | 42603429 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765166 | Not Scheduled | T2 EI STNSLS-MLNS-MNTCA 008/051 RPR STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 008/051 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2024-01-30 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.498942 | 38.0776 | ETL.3830 | 40594247 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765254 | Not Scheduled | T2 EI PLRM-CLGT C000/004 RPR SHLS | 43724331 | PALERMO-COLGATE | C000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.203441 | 39.3281 | ETL.5360 | 40757606 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765282 | Not Scheduled | T2 EI ROUND MTN-CO #3 44/377 RPL HRDT | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/377 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.109681 | 40.5866 | ETL.5650 | 40819296 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765304 | Not Scheduled | T2 EI PLRM-CLGT C000/004 RPR COND | 43724331 | PALERMO-COLGATE | C000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.203441 | 39.3281 | ETL.5360 | 40757606 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765437 | Not Scheduled | T2 EI RND MTN-CTTNWD #2 23/210 REM VEGT |  | ROUND MTN-COTTONWOOD #2 | 023/210 | HNA | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.049281 | 40.69 | ETL.5640 | 40605362 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-09-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765460 | Feb | T2 EI DRUM-RIO OSO #1 22/168 RPR CONS | 43685808 | DRUM-RIO OSO #1 | 022/168 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.113258 | 39.0991 | ETL.1420 | 40871377 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765504 | Feb | T2 EI PLRM-CLGTE 014/070 RPR COND | 43727762 | PALERMO-COLGATE | 014/070 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502239 | 39.4438 | ETL.5360 | 40605320 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765811 | Q2 | T2 EI SBRNT-GRZLY-CLRMT #1 1/13 RPR STRT | 44146666 | SOBRANTE-GRIZLY-CLARMNT #2+ | 001/013 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20084 | 37.8936 | ETL.3750 | 40857796 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765922 | Feb | T2 EI ROUND MTN-CO #3 45/391 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 045/391 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1235853 | 40.5699 | ETL.5650 | 40617514 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765944 | Not Scheduled | T2 EI PALERMO-COLGATE 015/071 RMV VEGN | 43727762 | PALERMO-COLGATE | 015/071 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-30 | 2020-01-30 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502196 | 39.4408 | ETL.5360 | 40590999 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115765988 | Mar | EI DELEVAN-VACA #1 017/109 RPL INSS | 31434839 | DELEVAN-VACA #1 | 017/109 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 |  |  | 2021-03-22 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.0851952 | 38.8969 | ETL.5010 | 40785859 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115766217 | Not Scheduled | T2 EI CARIBOU-PALERMO :1/13 INS HRDT | 44070463 | CARIBOU-PALERMO | :001/013 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.167509 | 40.072 | ETL.3190 | 40910258 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115766445 | Feb | T2 EI RND MTN-CTTNWD #3 40/342 RPL SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 040/342 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.069865 | 40.6345 | ETL.5650 | 40675860 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115766450 | Feb | T2 EI PALERMO-COLGATE 015/071 RPL INSS | 31438849 | PALERMO-COLGATE | 015/071 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5022092 | 39.4408 | ETL.5360 | 40616516 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115766497 | Before Feb | T2 EI DRUM-HIGGINS 023/180 PNT TWR | 43687142 | DRUM-HIGGINS | 023/180 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-30 | 2020-01-30 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107618 | 39.1012 | ETL.4393 | 40913076 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115766680 | Before Feb | T2 EI DRM-HGGNS 027/209 PNT TWR | 43687142 | DRUM-HIGGINS | 027/209 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-30 | 2020-01-30 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.090998 | 39.0454 | ETL.4393 | 40760630 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115766935 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/025 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/025 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.19718 | 40.0635 | ETL.3190 | 40910269 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115767493 | Q2 | T2 EI BRVILLE-CTNWD 045/353A RPL DMPS | 43742049 | BRIDGEVILLE-COTTONWOOD | 045/353A | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.108232 | 40.3966 | ETL.1110 | 40676657 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115767759 | Not Scheduled | T2 EI CARIBOU-PALERMO :0/8 INS HRDT | 44304495 | CARIBOU-PALERMO | :000/008 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115767926 | Not Scheduled | T2 EI STANISLAUS-MNTCA #2 13/77 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 013/077 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2022-01-30 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.574547 | 38.0372 | ETL.3820 | 40809198 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115768278 | Not Scheduled | T2 EI PALERMO-COL C001/007 RPR OPGW | 43724331 | PALERMO-COLGATE | C001/007 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.216462 | 39.3219 | ETL.5360 | 40814791 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115768402 | Not Scheduled | T2 EI DELTA-MTN GATE JCT 11/151 PNT TWR | 43708883 | DELTA-MOUNTAIN GATE JCT | 011/151 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-30 | 2020-01-30 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-122.317284 | 40.7991 | ETL.6750 | 40660676 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115769081 | Q2 | T2 EI BRDGVILLE-CTTONWD 050/380 RP DAM | 43862286 | BRIDGEVILLE-COTTONWOOD | 050/380 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 |  |  | 2021-04-30 | 2021-03-29 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.199218 | 40.4182 | ETL.1110 | 40676665 | Dampers | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115770555 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/151 RPR JUMP | 44304495 | CARIBOU-PALERMO | :018/151 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.331069 | 39.9114 | ETL.3190 | 40642500 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115770635 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/151 RPL INSS |  | CARIBOU-PALERMO | :018/151 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.331069 | 39.9114 | ETL.3190 | 40642500 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115770637 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/151 RPR FOND | 44069454 | CARIBOU-PALERMO | :018/151 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.331069 | 39.9114 | ETL.3190 | 40642500 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115770833 | Feb | T2 EI DRM-HGGNS 026/203 RPL SPLT | 43687142 | DRUM-HIGGINS | 026/203 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.09986 | 39.0591 | ETL.4393 | 40869575 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771016 | Feb | T2 EI ROUND MTN-CO #3 46/395 RPR CONS | 43755803 | ROUND MTN-COTTONWOOD #3 | 046/395 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126958 | 40.5658 | ETL.5650 | 40762510 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771185 | Not Scheduled | T2 EI STNISLS-MNTECA #2 013/078 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 013/078 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.576991 | 38.0357 | ETL.3820 | 40856498 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771187 | Not Scheduled | T2 EI STNISLS-MNTCA #2 013/078 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 013/078 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.576991 | 38.0357 | ETL.3820 | 40856498 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771188 | Not Scheduled | T2 EI STNISS-MNTEC #2 019/113 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 019/113 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.655182 | 37.9774 | ETL.3820 | 40651748 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771230 | Not Scheduled | T3 EI GEYSERS #16 TAP 01/005 PNT TWR | 43693047 | GEYSERS #16 TAP | 001/005 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.721515 | 38.7614 | ETL.4760 | 40761823 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771625 | Feb | T2 EI DRUM-RIO OSO #1 024/179 RPL INSS | 31426654 | DRUM-RIO OSO #1 | 024/179 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2021-05-31 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.1456915 | 39.0861 | ETL.1420 | 40888194 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-08-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771653 | Not Scheduled | T2 EI STANISLS-MNTC #2 019/111 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 019/111 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.651388 | 37.9802 | ETL.3820 | 40579603 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771658 | Not Scheduled | T2 EI STNSLS-MNTC #2 13/079 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 013/079 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.579216 | 38.0344 | ETL.3820 | 40856501 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771710 | Not Scheduled | T2 EI STNSLS-MNTC #2 13/079 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 013/079 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.579216 | 38.0344 | ETL.3820 | 40856501 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771767 | Not Scheduled | T2 EI CARIBOU-PALERMO :21/176 RPR STUBS | 44069454 | CARIBOU-PALERMO | :021/176 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.371524 | 39.8851 | ETL.3190 | 40811626 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771803 | Not Scheduled | T2 EI CARIBOU-PALERMO :21/175 BENT MEMB | 44069454 | CARIBOU-PALERMO | :021/175 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.370077 | 39.8867 | ETL.3190 | 40738366 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115771832 | Not Scheduled | T2 EI CARIBOU-PALERMO :21/176 PAINT STRT | 44302715 | CARIBOU-PALERMO | :021/176 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2021-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.371524 | 39.8851 | ETL.3190 | 40811626 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771889 | Feb | T2 EI ROUND MTN-CO #2 24/217 INST GUANO | 43877040 | ROUND MTN-COTTONWOOD #2 | 024/217 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-10 | 2021-02-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.05913 | 40.6769 | ETL.5640 | 40815315 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115771929 | Not Scheduled | EI DELEVAN-VACA #2 167/1258 REPAINT | 44305192 | DELEVAN-VACA #2 | 167/1258 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2024-01-31 | [8 empty] | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.071726 | 38.875 | ETL.4231 | 40868397 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772006 | Not Scheduled | T2 EI STNSLS-MNTC #2 14/083 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 014/083 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.590206 | 38.0276 | ETL.3820 | 40651746 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772017 | Feb | T2 EI ROUND MTN-CO #3 46/395 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 046/395 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126958 | 40.5658 | ETL.5650 | 40762510 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772165 | Not Scheduled | T2 EI PALERMO-COLG C009/041 RPR COND | 43724331 | PALERMO-COLGATE | C009/041 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.356287 | 39.3053 | ETL.5360 | 40581360 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772264 | Not Scheduled | T2 EI STISLS-MNTC#2 019/112 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 019/112 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.653289 | 37.9788 | ETL.3820 | 40658900 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772291 | Not Scheduled | T2 EI CARIBOU-PALERMO :000/007 RPR SPLS | 44070463 | CARIBOU-PALERMO | :000/007 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.159561 | 40.079 | ETL.3190 | 40910254 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772298 | Feb | T2 EI DRM-HGGNS 027/207 RPL SPLS | 43687142 | DRUM-HIGGINS | 027/207 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094618 | 39.051 | ETL.4393 | 40684239 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772340 | Not Scheduled | T2 EI STNL-MLN ST-MNT#1 013/081 RPL STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 013/081 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.583283 | 38.032 | ETL.3830 | 40585655 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772403 | Not Scheduled | T2 EI CARIBOU-PALERMO :000/007 RPR FOND | 44062862 | CARIBOU-PALERMO | :000/007 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.159561 | 40.079 | ETL.3190 | 40910254 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772416 | Feb | T2 EI DRM-HGGNS 027/207 RPL INSS | 31499112 | DRUM-HIGGINS | 027/207 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094618 | 39.051 | ETL.4393 | 40684239 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772457 | Before Feb | T2 EI DRM-HGGNS 027/207 PNT TWR | 43687142 | DRUM-HIGGINS | 027/207 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-31 | 2020-01-31 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094618 | 39.051 | ETL.4393 | 40684239 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772473 | Not Scheduled | T2 EI STNSLS-MNTC #2 13/080 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 013/080 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.583198 | 38.0319 | ETL.3820 | 40579640 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772525 | Not Scheduled | T2 EI CARIBOU-PALERMO :0/6 INS HRDT | 44062862 | CARIBOU-PALERMO | :000/006 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.157122 | 40.0804 | ETL.3190 | 40828375 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772584 | Not Scheduled | T2 EI STNSLS-MNTC #2 015/090 RPL HRDT | 43712838 | STANISLAUS-MANTECA #2 | 015/090 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.602797 | 38.0178 | ETL.3820 | 40587253 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772642 | Q4 | T3 DI MDLE FRK-GLD HLL 000/001 REPL STRW | 31421211 | MIDDLE FORK-GOLD HILL | 000/001 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2019-07-29 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 2021 - Micro pile vendor ([REDACTED]) unavailable in 2020 | '-120.597324 | 39.0239 | ETL.5140 | 44552336 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-07-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115772718 | Not Scheduled | T2 EI ROUND MTN-CO #3 43/368 RPL HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/368 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.100824 | 40.5973 | ETL.5650 | 40873484 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115772913 | Not Scheduled | T2 EI STANSLAUS-MNTC#2 20/118 RUSTD LADR | 43713081 | STANISLAUS-MANTECA #2 | 020/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.665353 | 37.9698 | ETL.3820 | 40856502 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773005 | Not Scheduled | T2 EI STNSLS-MNTC #2 027/159 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 027/159 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2020-01-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.768306 | 37.9235 | ETL.3820 | 40871571 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773031 | Not Scheduled | T2 EI STNSLS-MLNS SS-MNTC#1 20/125 LACNG | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/125 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-30 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.665458 | 37.9699 | ETL.3830 | 40744438 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773036 | Not Scheduled | T2 EI RND MTN-COTTN #3 043/369 INST HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/369 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.101727 | 40.5962 | ETL.5650 | 40862343 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773391 | Feb | T2 EI DRUM-RIO OSO #1 22/169 RPR CONS | 43685808 | DRUM-RIO OSO #1 | 022/169 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117202 | 39.0975 | ETL.1420 | 40858169 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773399 | Feb | T2 RND MTN-CTNWD #3 043/371 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 043/371 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.104095 | 40.5933 | ETL.5650 | 40595049 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773510 | Feb | T2 EI ROUND MTN-CO #3 43/370 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 043/370 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.102794 | 40.5949 | ETL.5650 | 40599924 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773558 | Not Scheduled | T2 EI STNSLS-MLNS SS-MNTC#1 20/124 LACNG | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/124 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.663785 | 37.9711 | ETL.3830 | 40649583 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773630 | Not Scheduled | T2 EI STN-MLNS S-MNTCA#1 26/167 RPL HRDT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/167 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2020-01-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.768366 | 37.9236 | ETL.3830 | 40751408 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773711 | Not Scheduled | T2 EI RND MTN-CTTON #3 043/372 INST HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/372 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.105156 | 40.5921 | ETL.5650 | 40675873 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773783 | Feb | T2 EI ROUND MTN-CO #3 44/373 RPL SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/373 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.10593 | 40.5911 | ETL.5650 | 40656727 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115773872 | Not Scheduled | T2 EI STNSLS-MNTC #2 020/116 RPL HRDT | 43712838 | STANISLAUS-MANTECA #2 | 020/117 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.66385 | 37.9709 | ETL.3820 | 40811286 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115774021 | Not Scheduled | T3 DI CARIBOU-PALERMO :037/301 RPR STRT | 44069801 | CARIBOU-PALERMO | :037/301 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.487314 | 39.6808 | ETL.3190 | 40913196 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115774097 | Feb | T2 EI ROUND MTN-CO #3 44/373 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/373 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.10593 | 40.5911 | ETL.5650 | 40656727 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115774149 | Not Scheduled | T2 EI PIT #4 TAP 000/006 HRDT | 43756947 | PIT #4 TAP | 000/006 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.86403 | 40.9852 | ETL.5432 | 40810520 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115774224 | Not Scheduled | T3 DI CARIBOU-PALERMO :11/86 RPR FOND | 44051417 | CARIBOU-PALERMO | :011/086 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115774226 | Not Scheduled | T3 DI CARIBOU-PALRMO-:11/086 RPAINT STRT | 44051417 | CARIBOU-PALERMO | :011/086 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115774228 | Not Scheduled | T3 DI CARIBOU-PALERMO-:11/086 RPL INSS | 31468828 | CARIBOU-PALERMO | :011/086 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115774412 | Not Scheduled | T2 EI STN MNTC 9/59 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 009/059 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2022-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.522145 | 38.0649 | ETL.3820 | 40861464 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115774492 | Not Scheduled | T3 DI CARIBOU-PALERMO-:11/086 RPL SPLS | 44070463 | CARIBOU-PALERMO | :011/086 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115775477 | Not Scheduled | T2 EI CARIBOU-PALERMO :18/150 RPR FOND | 44069454 | CARIBOU-PALERMO | :018/150 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.330456 | 39.9121 | ETL.3190 | 40642283 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115775478 | Not Scheduled | T2 EI CARIBOU-PALERMO :018/153 RPR FOND | 44069597 | CARIBOU-PALERMO | :018/153 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.334702 | 39.9097 | ETL.3190 | 40738358 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115776697 | Not Scheduled | T2 EI PTR VLY-MNDCN 000/002 RMV NEST | 43720856 | POTTER VALLEY-MENDOCINO | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-05-31 | [5 empty] | DLFL | CIRT needs more background on request | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.128962 | 39.3598 | ETL.7810 | 40698151 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115776740 | Not Scheduled | T2 EI CARIBOU-PALERMO :15/125 RPR CRSS | 44304495 | CARIBOU-PALERMO | :015/125 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.311915 | 39.9394 | ETL.3190 | 40753327 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115776741 | Not Scheduled | T2 EI CARIBOU-PALERMO :015/125 RPL SPLS | 44304495 | CARIBOU-PALERMO | :015/125 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.311915 | 39.9394 | ETL.3190 | 40753327 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115776827 | Feb | T2 EI BCK CRK-RCK CRK-CRST 4/41 RPL SPLS | 43742056 | BUCKS CREEK-ROCK CREEK-CRESTA | 004/041 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3995285 | 39.8542 | ETL.4430 | 40612544 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115777118 | Not Scheduled | T2 EI CARIBOU-PALRMO :17/142 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :017/142 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.321942 | 39.9192 | ETL.3190 | 40738354 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115777524 | Not Scheduled | T2 EI VACA-LAKEVILLE#1 4/23 INST HV | 43740456 | VACA-LAKEVILLE #1 | 004/023 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.999083 | 38.4069 | ETL.5840 | 40663082 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115777560 | Before Feb | T2 EI DRUM-HIGGINS 023/184 PNT TWR | 43687142 | DRUM-HIGGINS | 023/184 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-01 | 2020-02-01 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.120282 | 39.0961 | ETL.4393 | 40913080 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115777707 | Not Scheduled | T2 EI STNSLS-MNTC #2 21/121 BENT STEEL | 43712838 | STANISLAUS-MANTECA #2 | 021/121 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2022-02-01 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.673322 | 37.9639 | ETL.3820 | 40579604 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115777709 | Not Scheduled | T2 EI STNSLS-MLNS SS-MNTC 16/99 CANCEL | 43727720 | STANISLAUS-MELONES SS-MANTECA #1+ | 016/099 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.611253 | 38.0105 | ETL.3830 | 40871565 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778018 | Feb | T2 EI DRUM-HIGGINS 024/185B RPR INSS | 43687142 | DRUM-HIGGINS | 024/185B | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.121414 | 39.0955 | ETL.4393 | 41184219 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778392 | Not Scheduled | T2 EI CARIBOU-PALERMO :004/035 RPR STRT | 44059014 | CARIBOU-PALERMO | :004/035 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778428 | Not Scheduled | T2 EI CARIBOU-PALERMO :000/001 INST HRDT | 44062862 | CARIBOU-PALERMO | :000/001 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.147281 | 40.0864 | ETL.3190 | 41162785 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778485 | Not Scheduled | T2 EI CARIBOU-PALERMO :000/001 RPL GYWS | 44070463 | CARIBOU-PALERMO | :000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.147281 | 40.0864 | ETL.3190 | 41162785 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778517 | Not Scheduled | T2 EI BRIDGEVILLE-CTNWD 070/503 FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 070/503 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.504896 | 40.4571 | ETL.1110 | 40598650 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-04-05 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778891 | Not Scheduled | T2 EI CARIBOU-PALERMO :004/035 RPL INSS | 31425603 | CARIBOU-PALERMO | :004/035 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778900 | Feb | T2N EI PLRM-CLGT 017/083 INS MRKS | 43727762 | PALERMO-COLGATE | 017/083 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-01 | 2020-02-01 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.501889 | 39.4043 | ETL.5360 | 40660242 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778904 | Feb | T2 EI RND MTN-CTTNWD #3 52/462 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 052/462 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1908373 | 40.4888 | ETL.5650 | 40705901 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115778965 | Q2 | T2 EI HAT CRK #1-WESTWD 54/1050 REFRAME | 31459855 | HAT CREEK #1-WESTWOOD | 054/1050 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.000115 | 40.3133 | ETL.7030 | 40815904 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779092 | Not Scheduled | T2 EI CARIBOU-PALERMO :012/100 BENT MEMB | 44059014 | CARIBOU-PALERMO | :012/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275001 | 39.9644 | ETL.3190 | 40910339 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779094 | Not Scheduled | T2 EI CARIBOU-PALERMO :12/099 RPR STRT | 44059014 | CARIBOU-PALERMO | :012/099 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274973 | 39.9652 | ETL.3190 | 40910338 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779097 | Not Scheduled | T2 EI CARIBOU-PALERMO :012/100 RPL HRDT | 44059014 | CARIBOU-PALERMO | :012/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275001 | 39.9644 | ETL.3190 | 40910339 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779098 | Not Scheduled | T2 EI CARIBOU-PALERMO :012/100 RPR INSS | 44304495 | CARIBOU-PALERMO | :012/100 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.275001 | 39.9644 | ETL.3190 | 40920078 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779101 | Not Scheduled | T2 EI CARIBOU-PALERMO :13/102 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/102 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276601 | 39.9638 | ETL.3190 | 40738338 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779171 | Q2 | T2 EI HAT CRK#1-WSTWD 53/1038 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1038 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001793 | 40.3208 | ETL.7030 | 40751794 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779173 | Q2 | T2 EI HAT CRK #1-WSTWD 53/1040 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1040 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001067 | 40.3193 | ETL.7030 | 40827560 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779201 | Q2 | T2 EI HAT CRK #1-WESTWD 53/1040 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1040 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001067 | 40.3193 | ETL.7030 | 40827560 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779305 | Q2 | T2 EI HAT CRK #1-WSTWD 053/1041 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1041 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.000848 | 40.3185 | ETL.7030 | 40825645 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779316 | Q2 | T2 EI HAT CRK #1-WESTWD 53/1039 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1039 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001493 | 40.32 | ETL.7030 | 40770001 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115779795 | Not Scheduled | T2 DI SMARTVILLE TAP 000/000A RPR GYWW | 43910267 | SMARTVILLE TAP | 000/000A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.302657 | 39.2088 | ETL.6522 | 40576676 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115780144 | Not Scheduled | T2 EI CARIBOU-PALERMO :3/023 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/023 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40910267 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781622 | Feb | T2 EI RND MTN-CTTNWD #3 47/415 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 047/415 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.146685 | 40.5421 | ETL.5650 | 40762512 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781769 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/086 RPR SPLS | 44304495 | CARIBOU-PALERMO | 010/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523581 | 39.5954 | ETL.3190 | 40816572 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781771 | Not Scheduled | T2 EI CARIBOU-PALERMO 15/123 RPR FOND | 44069597 | CARIBOU-PALERMO | 015/123 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781772 | Not Scheduled | T2 EI CARIBOU-PALERMO 15/123 STRS PAINT | 44302715 | CARIBOU-PALERMO | 015/123 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-02 | 2021-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781778 | Feb | T2 EI PALERMO-COLG 018/085 INST MRKS | 43727762 | PALERMO-COLGATE | 018/085 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-02 | 2020-02-02 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50178 | 39.3981 | ETL.5360 | 40757847 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781895 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/87 RPR STRT | 44304495 | CARIBOU-PALERMO | 010/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.522843 | 39.598 | ETL.3190 | 40819278 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115781948 | Not Scheduled | T2 EI CRIBOU-TBLE MTN 007/056 RPR FOND | 43729340 | CARIBOU-TABLE MTN | 007/056 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.149342 | 40.0851 | ETL.4440 | 40815780 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782106 | Not Scheduled | T2 EI BRIDGEVILLE-CTNWD 059/431 FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 059/431 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.349751 | 40.3738 | ETL.1110 | 40657064 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-08-02 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782162 | Feb | T2 EI RND MTN-CTNWD #3 054/486 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 054/486 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.211829 | 40.4634 | ETL.5650 | 40819089 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782209 | Not Scheduled | T2 EI CARIBOU-PALERMO :1/16 RPR STRT | 44062862 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782213 | Not Scheduled | T2 EI CARIBOU-PALERMO :1/16 RPL HRDT | 44062862 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782221 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/172A INST HRDT | 44069455 | CARIBOU-PALERMO | :020/172A | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-02 | 2021-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.365436 | 39.8895 | ETL.3190 | 43203008 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782279 | Not Scheduled | T2 EI CARIBOU-PALERMO :18/149 RPL SPLS | 44304495 | CARIBOU-PALERMO | :018/149 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.330177 | 39.9125 | ETL.3190 | 40863125 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115782376 | Not Scheduled | T2 EI CARIBOU-PALERMO :18/148 RPR STUBS | 44069454 | CARIBOU-PALERMO | :018/148 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.329706 | 39.9131 | ETL.3190 | 44188831 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115782767 | Q2 | T2 EI TULE-SPRINGVILLE 011/010 RPL STRW | 31529263 | TULE-SPRINGVILLE | 011/010 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-02-02 | 2021-04-06 |  |  | 2021-04-06 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.939557 | 36.1091 | ETL.9040 | 40905728 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 115782786 | Not Scheduled | T2 EI CARIBOU-PALERMO :13/103A RPR CONS | 44304495 | CARIBOU-PALERMO | :013/103A | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278738 | 39.9631 | ETL.3190 | 41162770 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115783354 | Feb | T2 EI VACA-SUISUN 012/087 REPL INSS | 31435971 | VACA-SUISUN | 012/087 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 |  |  | 2021-02-15 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.066737 | 38.2839 | ETL.4070 | 40838458 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783373 | Not Scheduled | T2 EI CARIBOU-PALRMO :13/103 BURIED STUB | 44069583 | CARIBOU-PALERMO | :013/103 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278836 | 39.963 | ETL.3190 | 40738339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115783409 | Not Scheduled | T2 EI CARIBOU-PALERMO :18/147 RPR COND |  | CARIBOU-PALERMO | :018/147 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.3290391 | 39.9139 | ETL.3190 | 44549940 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115783671 | Not Scheduled | T2 EI CARIBOU-PALRMO :18/152 BURIED STUB | 44069454 | CARIBOU-PALERMO | :018/152 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.332107 | 39.9109 | ETL.3190 | 40738834 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783691 | Feb | T2 EI RND MTN-CTTNWD #3 054/489 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 054/489 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.214495 | 40.4601 | ETL.5650 | 40868134 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783698 | Feb | T2 EI DRUM-HIGGINS 026/199 REPL INSS | 31499112 | DRUM-HIGGINS | 026/199 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.1048066 | 39.0667 | ETL.4393 | 40793900 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783741 | Not Scheduled | EI CARIBOU-PALERMO 000/001 HRDT | 44304495 | CARIBOU-PALERMO | 000/001 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2020-02-04 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519606 | 39.4545 | ETL.3190 | 40589081 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783795 | Feb | T2 EI DRUM-RIO OSO #1 023/177 RPR COND | 43685808 | DRUM-RIO OSO #1 | 023/177 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.139728 | 39.0885 | ETL.1420 | 40821610 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783812 | Feb | T2 EI RND MTN-CTTNWD #3 052/464 INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 052/464 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1927051 | 40.4865 | ETL.5650 | 40789796 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783825 | Not Scheduled | T2 EI CRBU-PLRM 001/010 RPR FOND | 44069801 | CARIBOU-PALERMO | 001/010 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.542374 | 39.4642 | ETL.3190 | 40599223 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783837 | Not Scheduled | T2 EI CARIBOU-PALERMO 011/093 RPL SPLS | 44304495 | CARIBOU-PALERMO | 011/093 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783854 | Feb | T2 EI DRM-HGGNS 026/200 RPL SPLS | 43687142 | DRUM-HIGGINS | 026/200 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-09 | 2021-01-25 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.103517 | 39.0647 | ETL.4393 | 40760333 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783867 | Feb | T2 TRINITY-MAPLE CREEK 8/013 RELOCATE P | 31433769 | TRINITY-MAPLE CREEK | 008/013 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-04 | 2021-05-31 | 2020-12-13 | 2020-12-15 | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.069141 | 40.7619 | ETL.8170 | 40906374 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-03 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-09-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115783923 | Mar | T3 EI EAGLE ROCK-CORTINA :9/53 REPL INSL | 31437310 | EAGLE ROCK-CORTINA | :009/053 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2019-08-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.668401 | 38.888 | ETL.1470 | 40676867 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  |  | Released-Standard | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783941 | Not Scheduled | T2 EI CARIBOU-PALERMO 15/119 RPR FOND | 44069597 | CARIBOU-PALERMO | 015/119 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506565 | 39.6554 | ETL.3190 | 40913201 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115783996 | Feb | T2 EI RND MTN-CTNWD #3 052/471 RPR CONS | 43755803 | ROUND MTN-COTTONWOOD #3 | 052/471 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.197781 | 40.4803 | ETL.5650 | 40595104 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784006 | Feb | T2 EI RND MTN-CTTNWD #3 052/466 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 052/466 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1938781 | 40.4851 | ETL.5650 | 40845458 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784024 | Feb | T2 EI DRM-HGGNS 026/200 REPL INSS | 31426789 | DRUM-HIGGINS | 026/200 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.1035305 | 39.0647 | ETL.4393 | 40789827 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784135 | Feb | T2 EI RND MTN-CTNWD#3 059/534 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 059/534 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.259875 | 40.4052 | ETL.5650 | 40762838 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784136 | Not Scheduled | T2NT EI CRIBU-PLERM 9/83 RPR FOND | 44069597 | CARIBOU-PALERMO | 009/083 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525035 | 39.5903 | ETL.3190 | 40656341 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784217 | Not Scheduled | T2 EI CARIBOU-PALERMO 14/118 RPR FOND | 44069597 | CARIBOU-PALERMO | 014/118 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784228 | Not Scheduled | T2 EI COTTONWOOD #1 :003/028 RPL INSS | 31450547 | COTTONWOOD #1 | 003/028 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267857 | 40.3411 | ETL.6620 | 40920715 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784254 | Not Scheduled | T2 EI CARIBOU-PALERMO 009/082 RPR FOND | 44069597 | CARIBOU-PALERMO | 009/082 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784561 | Not Scheduled | T2 EI CARIBOU-PALERMO 009/082 RPR INST | 44304495 | CARIBOU-PALERMO | 009/082 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784568 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/091 REPL INSS |  | CARIBOU-PALERMO | 010/091 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520902 | 39.6048 | ETL.3190 | 40591547 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784596 | Not Scheduled | T2 EI CARIBOU-PALERMO 009/082 RPR STRT | 44304495 | CARIBOU-PALERMO | 009/082 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784600 | Not Scheduled | T2 EI PIT #1-COTTONWD 54/484 INST COTTER |  | PIT #1-COTTONWOOD | 054/484 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.209652 | 40.4657 | ETL.5390 | 40759701 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-21 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784606 | Not Scheduled | T2 EI CARIBOU-PALERMO 9/080 REPL INSS |  | CARIBOU-PALERMO | 009/080 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525656 | 39.5881 | ETL.3190 | 40599263 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784659 | Not Scheduled | T2 EI CARIBOU-PALERMO 9/83 RPR INSS | 44304495 | CARIBOU-PALERMO | 009/083 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525035 | 39.5903 | ETL.3190 | 40656341 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784751 | Not Scheduled | T2 EI CRIBU-PLERM 9/83 RPL HRDT | 43727174 | CARIBOU-PALERMO | 009/083 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525035 | 39.5903 | ETL.3190 | 40656341 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784764 | Not Scheduled | T2 CARIBOU-PALERMO 12/109 RPR INSS | 44304495 | CARIBOU-PALERMO | 012/109 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511691 | 39.6373 | ETL.3190 | 40864877 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784775 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/92 RPR SPLC | 44304495 | CARIBOU-PALERMO | 010/092 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784780 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/92 RPR FOND | 44069597 | CARIBOU-PALERMO | 010/092 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784791 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/92 RPR STRT | 44069597 | CARIBOU-PALERMO | 010/092 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784797 | Not Scheduled | T2 EI CARIBOU PALERMO 13/112 REPL SPLS | 43727174 | CARIBOU-PALERMO | 013/112 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.510109 | 39.6429 | ETL.3190 | 40668745 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115784806 | Mar | EI POE-RIO OSO 036/242 REPL INSS | 31431911 | POE-RIO OSO | 036/242 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.5255773 | 39.4652 | ETL.5540 | 40719834 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785011 | Not Scheduled | T2 EI CARIBOU-PALERMO 14/118 RPL HRDT |  | CARIBOU-PALERMO | 014/118 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785013 | Not Scheduled | T2 EI CARIBO-PALRMO 13/113 REPL SPLICE | 44304495 | CARIBOU-PALERMO | 013/113 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509591 | 39.6447 | ETL.3190 | 40656347 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785018 | Not Scheduled | T2 EI CARIBOU-PALERMO 1/8 INS HRDT | 44069801 | CARIBOU-PALERMO | 001/008 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536625 | 39.4611 | ETL.3190 | 40867924 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785042 | Mar | T2 EI POE-RIO OSO 037/245 REPL DAMS | 43737421 | POE-RIO OSO | 037/245 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.52412 | 39.458 | ETL.5540 | 40762421 | Damper-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785045 | Not Scheduled | T2 EI PIT #1-CTTNWD 55/495 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 055/495 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.22057 | 40.4525 | ETL.5390 | 40759493 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785204 | Not Scheduled | T2 EI PALERMO-WYANDOTTE 1/008 REPL DAMS | 43754988 | PALERMO-WYANDOTTE | 000/008 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2020-02-04 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536394 | 39.4612 | ETL.4315 | 40867155 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785282 | Q2 | T2 EI CRESTA-RIO OSO 30/243 RMV NEST | 43708739 | CRESTA-RIO OSO | 030/243 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-04 | 2020-02-04 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535087 | 39.5443 | ETL.4590 | 41083103 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785519 | Not Scheduled | T2 EI CARIBOU-PALERMO 8/72 RPR SPLC | 44304495 | CARIBOU-PALERMO | 008/072 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.529027 | 39.5771 | ETL.3190 | 40689950 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785631 | Not Scheduled | T2 EI PALERMO-WYANDOTTE 0/004 RPR INSS |  | PALERMO-WYANDOTTE | 000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process |  | '-121.525448 | 39.4555 | ETL.4315 | 40750691 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785646 | Not Scheduled | EI PALERMO-WYANDOTTE 0/7 INST HRDT | 43754988 | PALERMO-WYANDOTTE | 000/007 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2020-02-04 | [8 empty] | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-121.533336 | 39.4596 | ETL.4315 | 40819206 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785852 | Not Scheduled | T2 EI CARIBOU-PALERMO 8/071 INST HRDT | 44304495 | CARIBOU-PALERMO | 008/071 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52966 | 39.575 | ETL.3190 | 40595038 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115785931 | Not Scheduled | T3 EI ROUND MTN-COTTONWD #3 033/287 HRDT | 43755803 | ROUND MTN-COTTONWOOD #3 | 033/287 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.004973 | 40.7123 | ETL.5650 | 40810666 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786156 | Q2 | T2 EI TULE-SPRINGVILLE 24/006 RPL SPLW | 43708992 | TULE-SPRINGVILLE | 024/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.748093 | 36.1519 | ETL.9040 | 40823415 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786208 | Q2 | T2 EI TULE-SPRINGVILLE 24/006 RPR GYWW | 43708346 | TULE-SPRINGVILLE | 024/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.748093 | 36.1519 | ETL.9040 | 40823415 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786245 | Q2 | T2 EI TULE-SPRINGVILLE 17/005 RPL SPLW | 43708992 | TULE-SPRINGVILLE | 017/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.841934 | 36.1076 | ETL.9040 | 40765668 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786276 | Not Scheduled | T2 DI CARIBOU-PALERMO :002/019 RPR STRS | 44070463 | CARIBOU-PALERMO | :002/019 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786277 | Not Scheduled | T2 DI CARIBOU-PALERMO :002/019 RPR FOND | 44062862 | CARIBOU-PALERMO | :002/019 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786517 | Not Scheduled | T2 DI CARIBOU-PALERMO :13/108 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/108 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40858895 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786518 | Not Scheduled | T2 DI CARIBOU-PALERMO :13/108 RPL INSS |  | CARIBOU-PALERMO | :013/108 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40739402 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786600 | Not Scheduled | T2 DI CARIBOU-PALERMO :14/110A RPR FOND | 44069583 | CARIBOU-PALERMO | :014/110A | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.29189 | 39.9578 | ETL.3190 | 41162771 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115786601 | Not Scheduled | T2 DI CARIBOU-PALERMO :14/110A RPR SPLS | 44304495 | CARIBOU-PALERMO | :014/110A | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.29189 | 39.9578 | ETL.3190 | 41162771 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115786705 | Not Scheduled | T2 EI CARIBOU-PALERMO :14/112 BURID MEMB | 44069583 | CARIBOU-PALERMO | :014/112 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.295392 | 39.956 | ETL.3190 | 40738828 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115786868 | Q2 | T2 EI TL-SPRGVL 026/011 RPR CNDS | 43709292 | TULE-SPRINGVILLE | 026/011 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.710904 | 36.162 | ETL.9040 | 43604138 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-04-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115786878 | Q2 | T2 EI TULE-SPRINGVILLE 24/005 RPL SPLW | 43708992 | TULE-SPRINGVILLE | 024/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.750358 | 36.1508 | ETL.9040 | 40765682 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115787027 | Not Scheduled | T2 EI CARIBOU-PALERMO 8/72 RPR STRT | 44069597 | CARIBOU-PALERMO | 008/072 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.529027 | 39.5771 | ETL.3190 | 40689950 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115787278 | Not Scheduled | DISTRIBUTION MARKER |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 007/136 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-05 | 2020-02-05 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.553222 | 35.1847 | ETL.9100 | 42574213 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115787400 | Not Scheduled | T2 EI PIT #4 TAP 000/006 RPR STRT | 43756947 | PIT #4 TAP | 000/006 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.86403 | 40.9852 | ETL.5432 | 40810520 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115787592 | Feb | T2 EI ROUND MTN-CTNWD#3 58/529 REPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 058/529 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254431 | 40.4118 | ETL.5650 | 40891152 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115787642 | Not Scheduled | T2 EI VACA-PARKWAY 005/031 RPL HRDT | 43760159 | VACA-PARKWAY | 005/031 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.010778 | 38.3978 | ETL.5850 | 40589768 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115787892 | Not Scheduled | DISTRIBUTION RPR STRW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 009/166 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-05 | 2020-02-05 | [8 empty] | LATE | South | WSIP | FSRP | [5 empty] | '-120.525517 | 35.1673 | ETL.9100 | 42574216 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 115788129 | Feb | T2 EI RUND MTN-CTTNWD#3 58/532 REPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 058/532 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2574953 | 40.4081 | ETL.5650 | 40722092 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115788141 | Feb | T2 EI DRUM-HIGGINS 025/196 RPL INSS | 31499112 | DRUM-HIGGINS | 025/196 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.108772 | 39.0728 | ETL.4393 | 40592845 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115788211 | Not Scheduled | T2 EI RUND MTN-CTTNWD#3 58/532 RPR STRT | 43755801 | ROUND MTN-COTTONWOOD #3 | 058/532 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.257482 | 40.4081 | ETL.5650 | 40677349 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115788303 | Feb | T2 EI DRUM-HIGGINS 025/197 RPL INSS | 31499112 | DRUM-HIGGINS | 025/197 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107493 | 39.0709 | ETL.4393 | 40690102 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115788343 | Feb | T2 EI RUND MTN-CTTNWD#3 59/533 REPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 059/533 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2584617 | 40.4069 | ETL.5650 | 40687107 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115788368 | Not Scheduled | T2 EI VACA-PARKWAY 005/032 INS HRDT | 43760157 | VACA-PARKWAY | 005/032 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.012418 | 38.3961 | ETL.5850 | 40670590 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115789930 | Q3 | T2 EI TDWTR-SBRNTE 021/102 RPR FOND |  | TIDEWATER-SOBRANTE | 021/102 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-07-30 | 2021-07-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199442 | 37.9246 | ETL.5770 | 40661712 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115799835 | Not Scheduled | T2 EI VALLEY SPRINGS #1 A000/009 RPL PL | 31427931 | VALLEY SPRINGS #1 | A000/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.759075 | 38.2117 | ETL.8210 | 40907071 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Not Released | CalTrans | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115805225 | Feb | T2NT EI PALERMO-COLGATE 017/084 INS MRKS | 43727762 | PALERMO-COLGATE | 017/084 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.501832 | 39.401 | ETL.5360 | 40757913 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115817713 | Before Feb | T2 EI DRUM-HIGGINS 025/192 PNT TWR | 43687117 | DRUM-HIGGINS | 025/192 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-05 | 2020-02-05 |  |  | 2020-10-03 | 2020-09-08 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.114983 | 39.0824 | ETL.4393 | 40817267 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115817927 | Not Scheduled | EI ELECTRA-BELLOTA 19/137 CANCEL | 43727727 | ELECTRA-BELLOTA | 019/137 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-05 | 2020-02-05 | [6 empty] | CANCEL/CNCL |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.898999 | 38.1147 | ETL.4670 | 40658990 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115817990 | Mar | T2 EI TBL MTN-PLRMO 014/065 RPL INSS | 31452983 | TABLE MTN-PALERMO | 014/065 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-05 | 2020-02-05 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5025727 | 39.4566 | ETL.5690 | 40787140 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818074 | Before Feb | EI MOSS LNDNG-CBRN C027/105 RPR STRT | 43766044 | MOSS LANDING-COBURN | C027/105 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-05 | 2020-02-05 |  |  | 2020-05-31 | 2020-05-31 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.233921 | 36.39 | ETL.5330 | 40762040 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818208 | Feb | T2 DI SMRTVLE-NCOLUS #2 0/002 WASH INSS | 43852598 | SMARTVILLE-NICOLAUS #2 | 000/002 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.303527 | 39.2084 | ETL.8000 | 44177570 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 622 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818515 | Not Scheduled | T3 DI CARIBOU-PALERMO :037/299 RPL INSS | 31426499 | CARIBOU-PALERMO | :037/299 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486332 | 39.6826 | ETL.3190 | 40913194 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818519 | Not Scheduled | T3 DI CARIBOU-PALERMO :037/299 RPR STRT | 44051417 | CARIBOU-PALERMO | :037/299 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486332 | 39.6826 | ETL.3190 | 40913194 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818629 | Not Scheduled | T2 DI CARIBOU-PALERMO :0/6 RPR STUBS | 44062862 | CARIBOU-PALERMO | :000/006 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.157122 | 40.0804 | ETL.3190 | 40828375 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818669 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/089 RPL SPLS | 43735847 | CARIBOU-PALERMO | :011/089 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115818810 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/089 RPR FOND | 44051417 | CARIBOU-PALERMO | :011/089 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115818837 | Q3 | T2 EI TIDEWATER-SBRNTE 21/101 RPR STRT |  | TIDEWATER-SOBRANTE | 021/101 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-07-30 | 2021-07-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.19826 | 37.9263 | ETL.5770 | 40586685 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115818873 | Not Scheduled | DISTRIBUTION INSL | 43715793 | SPARE T-LINE RECORD | T098 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-02-05 | 2019-08-05 | [6 empty] | Midway-Santa Maria | TR3 | LATE | South | WSIP | [6 empty] | '-120.172272 | 35.0597 | ETL.9240 | 43249717 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115819082 | Not Scheduled | T3 DI CARIBOU-PALMERO 16/127 RPR FOND | 44051417 | CARIBOU-PALERMO | 016/127 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.495461 | 39.6739 | ETL.3190 | 41162781 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115819359 | Mar | T2 EI POE-RIO OSO 31/204 RPR JUMS | 43737420 | POE-RIO OSO | 031/204 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535652 | 39.5479 | ETL.5540 | 40762687 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115819539 | Not Scheduled | T2 DI CARIBOU-PALERMO :24/199 RPR FOND | 44069454 | CARIBOU-PALERMO | :024/199 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.402334 | 39.8505 | ETL.3190 | 40867369 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115819628 | Not Scheduled | T2 EI POE-RIO OSO 23/151 REPAINT | 43737420 | POE-RIO OSO | 023/151 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2024-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.506199 | 39.6588 | ETL.5540 | 40590429 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820077 | Not Scheduled | T2 CARIBOU-PALERMO 12/107 RPR SPLS | 44304495 | CARIBOU-PALERMO | 012/107 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511898 | 39.6366 | ETL.3190 | 40815581 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820161 | Not Scheduled | T2 EICOTTONWOOD #1 006/047 CANCEL | 43760649 | COTTONWOOD #1 | 006/047 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2020-02-06 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.267638 | 40.2988 | ETL.6620 | 40910988 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820269 | Not Scheduled | T2 EI PALERMO-COLGATE C005/026 RPR CONS | 43724331 | PALERMO-COLGATE | C005/026 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286576 | 39.3076 | ETL.5360 | 40815685 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820312 | Not Scheduled | T2 DI CARIBOU-PALERMO :001/12 RPR FOND | 44062862 | CARIBOU-PALERMO | :001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.166469 | 40.0723 | ETL.3190 | 40912339 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820329 | Not Scheduled | T2 EI ELECTRA-BELLOTA 15/110 RPR FOND | 43727727 | ELECTRA-BELLOTA | 015/110 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.848636 | 38.1635 | ETL.4670 | 40819238 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820565 | Not Scheduled | T2 EI PIT#1-CTNWD 045/394 RPR FOND | 43755354 | PIT #1-COTTONWOOD | 045/394 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2020-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.125884 | 40.5668 | ETL.5390 | 41107597 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820568 | Mar | T2 EI POE-RIO OSO 028/185 RPR INSS |  | POE-RIO OSO | 028/185 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2020-02-06 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.526702 | 39.5882 | ETL.5540 | 40757647 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-11 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820640 | Not Scheduled | T2 EI POE-RIO OSO 039/257 PAINT | 43737421 | POE-RIO OSO | 039/257 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-06 | 2020-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.518365 | 39.4294 | ETL.5540 | 40814853 | Structure-Steel | Paint/Coating | Other | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820689 | Mar | T2 EI TBLE MTN-PLRMO 10/47 INS MRKS | 43760152 | TABLE MTN-PALERMO | 010/047 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-06 | 2020-02-06 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502385 | 39.5124 | ETL.5690 | 40813461 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820721 | Feb | T2 EI OLEUM-MARTINEZ 4/029 REPL INSS | 31457825 | OLEUM-MARTINEZ | 004/029 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 |  |  | 2021-02-23 | 2021-02-23 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.1874362 | 38.0211 | ETL.3170 | 40830466 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820747 | Not Scheduled | EI HUMBOLDT BAY-HU #1 5/026 RPR FOND | 43720604 | HUMBOLDT BAY-HUMBOLDT #1 | 005/026 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2020-02-06 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-124.122675 | 40.771 | ETL.1800 | 40808915 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-09 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820774 | Mar | T2 EI POE-RIO OSO 28/184 RPR CONS | 43737420 | POE-RIO OSO | 028/184 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2020-02-06 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.526576 | 39.5899 | ETL.5540 | 40757650 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820791 | Not Scheduled | T2 EI DRUM-RIO OSO #1 20/158 RMV FENCE | 43685812 | DRUM-RIO OSO #1 | 020/158 | CHR | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-06 | 2021-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.083934 | 39.1107 | ETL.1420 | 40866022 | Right of Way | Encroachment | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLS | Land | Expense | 931 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820802 | Feb | T2 EI DRUM-RIO OSO #1 20/158 RPL SPLS | 43685808 | DRUM-RIO OSO #1 | 020/158 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2021-05-31 |  |  | 2021-02-23 | 2020-12-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.083934 | 39.1107 | ETL.1420 | 40866022 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115820973 | Mar | T2 EI POE-RIO OSO 027/181 RMV NEST | 43737420 | POE-RIO OSO | 027/181 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.524391 | 39.5947 | ETL.5540 | 40596655 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115821350 | Q2 | T2 EI EAGLE ROCK-RED :010/058 RPR FOND | 43730052 | EAGLE ROCK-REDBUD | :010/058 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.654685 | 38.892 | ETL.1480 | 40861253 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-05-15 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115821457 | Feb | DISTRIBUTION BENT MEMBER | 43715795 | SPARE T-LINE RECORD | T-124 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-06 | 2021-05-31 |  |  | 2021-02-25 | 2021-02-22 |  |  | Midway-Santa Maria | TR3 | LATE | South | WSIP | FSRP | [5 empty] | '-120.092924 | 35.1099 | ETL.9240 | 43249615 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 115826622 | Not Scheduled | T2 EI PITTSBURG-CLAY #3 004/023 REGRADE | 43753159 | PITTSBURG-CLAYTON #3 | 004/023 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.910066 | 37.9819 | ETL.3290 | 40648855 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115834266 | Not Scheduled | T2 EI CRESTA-RIO OSO 022/179 REPAINT | 43708739 | CRESTA-RIO OSO | 022/179 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2025-03-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.507798 | 39.6518 | ETL.4590 | 40910187 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115844527 | Q2 | T2 EI CRESTA-RIO OSO 27/220 REPL INSS | 31435732 | CRESTA-RIO OSO | 027/220 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5281191 | 39.5809 | ETL.4590 | 40921279 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115844556 | Not Scheduled | T2 EI PIT #1-COTTON 026/213 PAINT | 43879413 | PIT #1-COTTONWOOD | 026/213 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2024-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.923298 | 40.7957 | ETL.5390 | 40657405 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115844787 | Before Feb | T2NT EI PIT #1-COTTONWD 26/214 PNT TWR | 43755354 | PIT #1-COTTONWOOD | 026/214 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2021-02-06 |  |  | 2020-09-21 | 2020-09-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.925499 | 40.7951 | ETL.5390 | 40762975 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115852532 | Q2 | T2 EI PARADISE-TABLE MTN 24/188R RPL PL | 31453760 | PARADISE-TABLE MTN | 024/188 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.651841 | 39.7009 | ETL.4316 | 44383248 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858136 | Not Scheduled | T3 EI EAGLE ROCK-FUL-SIL 001/010 PAINT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 001/010 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2019-08-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800903 | 38.8166 | ETL.4392 | 40605188 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-05-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858431 | Not Scheduled | T2 DI CARIBOU-PALERMO :1/015 RPR STUB | 44062862 | CARIBOU-PALERMO | :001/015 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.172958 | 40.0703 | ETL.3190 | 40912341 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858438 | Not Scheduled | T2 DI CARIBOU-PALERMO :001/015 RPR STRT | 44062862 | CARIBOU-PALERMO | :001/015 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.172958 | 40.0703 | ETL.3190 | 40912341 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858632 | Feb | T2 DI SMRTVLLE-NICOLS #2 00/18 WASH INSS | 43852598 | SMARTVILLE-NICOLAUS #2 | 000/018 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.301104 | 39.1972 | ETL.8000 | 44177598 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 622 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858659 | Q2 | T2 EI CRESTA-RIO OSO 27/220 RMV NEST | 43708739 | CRESTA-RIO OSO | 027/220 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-06 | 2020-02-06 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.528106 | 39.5809 | ETL.4590 | 40911510 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858694 | Not Scheduled | T2 DI CARIBOU-PALERMO :026/215 RPLC HRPS | 44304495 | CARIBOU-PALERMO | :026/215 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42411 | 39.8261 | ETL.3190 | 40758494 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 115858744 | Not Scheduled | T2 DI CARIBOU-PALERMO :026/215 REPL GYWS | 44304495 | CARIBOU-PALERMO | :026/215 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42411 | 39.8261 | ETL.3190 | 40758494 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116153199 | Q2 | T2 EI COBURN-PANOCHE 44/191 RPR FOND | 43749766 | COBURN-PANOCHE | 044/191 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | [8 empty] | ETL.4460 | 40925417 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116153237 | Not Scheduled | EI PARKWAY-MORAGA 008/050 RPL HRDT | 43683430 | PARKWAY-MORAGA | 008/050 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.233688 | 38.0174 | ETL.5930 | 40758941 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116153239 | Q2 | T2 PALERMO-OROVILLE #2 A007/093 INSW | 31431545 | PALERMO-OROVILLE #2 | A007/093 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4936306 | 39.5304 | ETL.7740 | 41123112 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116153288 | Not Scheduled | T2 EI PALERMO-COLGATE C006/028 CONS | 43724331 | PALERMO-COLGATE | C006/028 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.294425 | 39.3075 | ETL.5360 | 40867219 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116153766 | Not Scheduled | T2 DI CARIBOU-PALRMO :001/016 RPR FOND | 44062862 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116153954 | Q2 | T2 EI HMBLDT-BRDGVLL 109/005L RPL PL | 31440336 | HUMBOLDT-BRIDGEVILLE | 109/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322613 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116155383 | Not Scheduled | T3 EI CARIBOU-PALERMO :033/265 INST HRDT | 44051418 | CARIBOU-PALERMO | :033/265 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-02-07 | 2019-08-07 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475991 | 39.7465 | ETL.3190 | 40770933 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116155760 | Mar | EI POE-RIO OSO 042/279 REPL INSS | 31431911 | POE-RIO OSO | 042/279 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 |  |  | 2021-03-19 | 2021-03-17 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.5090803 | 39.3801 | ETL.5540 | 40889566 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116155857 | Not Scheduled | T2 EI ELECTRA-BELLOTA 0/010 RPR HRDT | 43727727 | ELECTRA-BELLOTA | 001/011 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.672768 | 38.3166 | ETL.4670 | 40863018 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156059 | Not Scheduled | T2 EI NRTH TWR-MRTINZ JCT #1 :32/207 PNT | 43753295 | NORTH TOWER-MARTINEZ JCT #1 (21KV) | :032/207 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-07 | 2022-02-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203827 | 38.0292 | ETL.3130 | 40804760 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156070 | Not Scheduled | EI ELECTRA-BELLOTA 14/105 RPR STRT | 43727727 | ELECTRA-BELLOTA | 014/105 | ICQ | F | Pre-2020_(5) TD tag on other lines |  | 2019-02-07 | 2022-02-07 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-120.839334 | 38.1725 | ETL.4670 | 40593871 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156119 | Not Scheduled | T2 DI CARIBOU-PALERMO :5/39 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :005/039 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.217637 | 40.0409 | ETL.3190 | 40910282 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156299 | Not Scheduled | T3 EI DRUM-HIGGINS B009/088 REPAINT | 43738143 | DRUM-HIGGINS | B009/088 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2019-08-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.894598 | 39.1647 | ETL.4393 | 40867206 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156301 | Mar | T2 EI POE-RIO OSO 41/269 REPL HRDS | 31431911 | POE-RIO OSO | 041/269 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 |  |  | 2021-03-26 | 2021-03-22 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51312 | 39.4029 | ETL.5540 | 40870609 | Hardware-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156489 | Not Scheduled | T2 EI OLEUM-MARTINEZ 7/48 REPAINT | 43753565 | OLEUM-MARTINEZ | 007/048 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-07 | 2024-02-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.136149 | 37.993 | ETL.3170 | 40804606 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156508 | Not Scheduled | T2 DI CARIBOU-PALERMO :5/40 INSTL STRT | 44059014 | CARIBOU-PALERMO | :005/040 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156532 | Not Scheduled | T2 DI CARIBOU-PALERMO :5/40 RMV SRT |  | CARIBOU-PALERMO | :005/040 |  | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156552 | Mar | T2 EI POE-RIO OSO 42/276 RPR INSS | 43737421 | POE-RIO OSO | 042/276 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.510326 | 39.3872 | ETL.5540 | 40815741 | Insulator-Steel | No Good/Out of Stdrd | Repair | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156617 | Mar | T2 EI POE-RIO OSO 41/270 RPR INSS | 43737421 | POE-RIO OSO | 041/270 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.512926 | 39.4018 | ETL.5540 | 40598084 | Insulator-Steel | No Good/Out of Stdrd | Repair | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156642 | Not Scheduled | T2 DI CARIBOU-PALERMO :5/41 INSTL HRDT | 44059014 | CARIBOU-PALERMO | :005/041 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218194 | 40.0372 | ETL.3190 | 40910284 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156670 | Not Scheduled | T2 DI CARIBOU-PALERMO :5/41 RPR FOND | 44059014 | CARIBOU-PALERMO | :005/041 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218194 | 40.0372 | ETL.3190 | 40910284 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156801 | Feb | T2 EI DRUM-RIO OSO #1 32/235 WSH INSS | 43746397 | DRUM-RIO OSO #1 | 032/235 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.290097 | 39.0274 | ETL.1420 | 40762571 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156843 | Not Scheduled | T3 DI TGR CRK-VLLY SPRNG 3/025 RPNT STRT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 003/025 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-25 | 2020-01-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.543879 | 38.4337 | ETL.5790 | 40823048 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116156983 | Not Scheduled | EI ELECTRA-BELLOTA 14/107 RPR FOND | 43727727 | ELECTRA-BELLOTA | 014/107 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2022-02-07 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-120.843224 | 38.1687 | ETL.4670 | 40659318 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157031 | Not Scheduled | T2 EI TEMBLOR-SLO 26/160 REPL BIRD GARDS | 43740614 | TEMBLOR-SAN LUIS OBISPO | 026/160 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2024-02-07 | [7 empty] | TR2 | LATE | South | WSIP | FSRP |  |  |  | Clearance Cancelled - External | Aug clearance was cancelled, rescheduled for Nov | '-120.155757 | 35.3869 | ETL.3960 | 40604669 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Pismo Beach |  | Y - 4 | 2019-04-16 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157476 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/023 INS HRDT | 44062862 | CARIBOU-PALERMO | :003/023 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40910267 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157502 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/023 RPR FOND | 44062862 | CARIBOU-PALERMO | :003/023 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40910267 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157558 | Not Scheduled | T2 DI CARIBOU-PALERMO :002/017 INST HRDT | 44062862 | CARIBOU-PALERMO | :002/017 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.177753 | 40.0689 | ETL.3190 | 40910261 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157582 | Not Scheduled | T2 EI OLM-NRTH TWR-CHRSTI 3/22 PAINT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 003/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-07 | 2020-02-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203721 | 38.0286 | ETL.3180 | 40646332 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157631 | Not Scheduled | T2 DI CARIBOU-PALERMO :002/021 RPR FOND | 44062862 | CARIBOU-PALERMO | :002/021 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.189644 | 40.0629 | ETL.3190 | 40910265 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116157634 | Not Scheduled | T2 DI CARIBOU-PALERMO :002/018 RPR STRT | 44062862 | CARIBOU-PALERMO | :002/018 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.179456 | 40.0683 | ETL.3190 | 40910262 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116309697 | Mar | T2 EI HUMBOLDT-TRINITY 066/001C RPR GYWW | 43729542 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562793 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116309761 | Not Scheduled | T2 EI OLEUM-MARTINEZ 007/047 REPAINT | 43753565 | OLEUM-MARTINEZ | 007/047 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-07 | 2024-02-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.13698 | 37.9936 | ETL.3170 | 40857601 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319204 | Not Scheduled | T3 EI DRUM-HIGGINS 6/069 PNT TWR | 43738143 | DRUM-HIGGINS | 006/069 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.854985 | 39.1918 | ETL.4393 | 40865238 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319208 | Q2 | T2 EI NTH TWR-MRTNZ JCT 1 :32/204 RP DAM | 43753295 | NORTH TOWER-MARTINEZ JCT #1 (21KV) | :032/204 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-08 | 2020-02-08 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.205106 | 38.0367 | ETL.3130 | 40747004 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319495 | Q2 | T2 EI NRT TWR-MRTNZ JT 1 :32/204 RPL INS | 31455159 | NORTH TOWER-MARTINEZ JCT #1 (21KV) | :032/204 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-08 | 2021-05-31 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.205106 | 38.0367 | ETL.3130 | 40775615 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319619 | Not Scheduled | T3 EI DRUM-HIGGINS 6/067 PNT TWR | 43738143 | DRUM-HIGGINS | 006/067 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.850524 | 39.1935 | ETL.4393 | 40813294 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319776 | Not Scheduled | T2 EI OLEUM-MARTINEZ 007/046 RPR FOND | 43753569 | OLEUM-MARTINEZ | 007/046 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.13989 | 37.996 | ETL.3170 | 40857606 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319795 | Not Scheduled | T3 DI TIGR CRK-ELECTRA 5/043 REPAINT | 43691537 | TIGER CREEK-ELECTRA | 005/043 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-24 | 2019-07-24 | [7 empty] | TR3 | LATE | Central | WSIP |  |  |  |  | Clearance Denied by GCC | unable to take out line | '-120.581694 | 38.4245 | ETL.5780 | 40662764 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319921 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/30 RPR STUBS | 44059014 | CARIBOU-PALERMO | :003/030 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.205437 | 40.0561 | ETL.3190 | 40910274 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319924 | Not Scheduled | T2 DI CARIBOU-PALERMO :3/29 BURIED MEMB | 44062862 | CARIBOU-PALERMO | :003/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.202237 | 40.0585 | ETL.3190 | 40910273 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319941 | Not Scheduled | T2 EI CARIBOU-PALERMO :013/106 INST HRDT | 44069583 | CARIBOU-PALERMO | :013/106 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.283913 | 39.9602 | ETL.3190 | 40738342 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319944 | Feb | T2 EI PARKWAY-MORAGA 07/043 RPR OPGW | 43683436 | PARKWAY-MORAGA | 007/043 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 |  |  | 2021-02-02 | 2021-02-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233575 | 38.0337 | ETL.5930 | 40863055 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116319994 | Mar | T2 EI POE-RIO OSO 41/271 RPR INSS | 43737421 | POE-RIO OSO | 041/271 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.512201 | 39.3977 | ETL.5540 | 40590801 | Insulator-Steel | No Good/Out of Stdrd | Repair | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116321151 | Q2 | T2 HMBLDT-BRDGVLLE 99/06L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322423 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116321157 | Not Scheduled | T3 EI DRUM-HIGGINS 006/068 REPAINT | 43738143 | DRUM-HIGGINS | 006/068 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.852654 | 39.1926 | ETL.4393 | 40862207 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116322417 | Not Scheduled | T2 EI PIT #1-COTTON 037/318 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 037/318 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.034545 | 40.6766 | ETL.5390 | 40868299 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116322451 | Not Scheduled | T3 EI DRUM-HIGGINS 006/065 REPAINT | 43738143 | DRUM-HIGGINS | 006/065 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.846431 | 39.1953 | ETL.4393 | 40751949 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116324229 | Before Feb | T2 EI DRUM-HIGGINS B010/093 RPT TWR | 43738143 | DRUM-HIGGINS | B010/093 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-08 | 2020-02-08 |  |  | 2020-10-29 | 2020-10-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.910715 | 39.158 | ETL.4393 | 41196106 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116324828 | Not Scheduled | T3 EI DRUM-HIGGINS 6/066 PNT TWR | 43738143 | DRUM-HIGGINS | 006/066 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848575 | 39.1943 | ETL.4393 | 40822536 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116326609 | Not Scheduled | T3 EI DRUM-HIGGINS 6/064 PNT TWR | 43738143 | DRUM-HIGGINS | 006/064 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.845725 | 39.1968 | ETL.4393 | 40762134 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116327425 | Not Scheduled | T2 EI PIT #1-CTNWD 37/319 REPLUMB STRT | 43755354 | PIT #1-COTTONWOOD | 037/319 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.035637 | 40.6753 | ETL.5390 | 40867664 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116327631 | Not Scheduled | T2 DI CARIBOU-PALERMO :16/133 RPR FOND | 44069583 | CARIBOU-PALERMO | :016/133 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318623 | 39.9288 | ETL.3190 | 40738821 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116329924 | Not Scheduled | T2 EI PIT#1-CTNWD 040/345 RPNT TWR | 43879413 | PIT #1-COTTONWOOD | 041/345 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.077931 | 40.6245 | ETL.5390 | 40758862 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116330146 | Not Scheduled | T2 EI TIGR CRK-VAL SPR 013/101 RPR FOND | 43727746 | TIGER CREEK-VALLEY SPRINGS | 013/101 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2022-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.665017 | 38.34 | ETL.5790 | 40682058 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116332004 | Not Scheduled | T3 EI PIT #1-COTTONW 28/228 PNT TWR | 43735854 | PIT #1-COTTONWOOD | 028/228 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2023-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.944772 | 40.7841 | ETL.5390 | 40868810 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-03-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116340801 | Not Scheduled | T3 DRUM-HIGGINS 005/060 REPAINT STRT | 43738143 | DRUM-HIGGINS | 005/060 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.842668 | 39.2033 | ETL.4393 | 40595827 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116342755 | Not Scheduled | T2 EI TGR CRK-VAL SPR 012/099 PAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 012/099 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-08 | 2022-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.664014 | 38.3423 | ETL.5790 | 40582783 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116343050 | Not Scheduled | T2 EI TIGER CREEK-ELEC 012/099 PAINT | 43727728 | TIGER CREEK-ELECTRA | 012/099 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.663897 | 38.3432 | ETL.5780 | 40862695 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116347915 | Not Scheduled | T2 DI CARIBOU-PALERMO :005/042 RPR STUB | 44059014 | CARIBOU-PALERMO | :005/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218237 | 40.0358 | ETL.3190 | 40910285 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116348037 | Not Scheduled | T2 EI CRBU-TBL MTN 020/139B RPR GYWS | 43729346 | CARIBOU-TABLE MTN | 020/139B | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.277149 | 39.9655 | ETL.4440 | 44190879 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116348770 | Not Scheduled | T2 EI ELECTRA-BELLOTA 001/016 RPR FOND | 43727727 | ELECTRA-BELLOTA | 001/016 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.682611 | 38.3084 | ETL.4670 | 40659832 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116355588 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/022 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/022 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40910266 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116357902 | Not Scheduled | T2 DI CARIBOU-PALERMO :014/111 RPR FOND | 44069583 | CARIBOU-PALERMO | :014/111 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.293251 | 39.9571 | ETL.3190 | 40642567 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116357906 | Not Scheduled | T2 DI CARIBOU-PALERMO :014/112 INST HRDT | 44069583 | CARIBOU-PALERMO | :014/112 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.295392 | 39.956 | ETL.3190 | 40738828 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116360562 | Not Scheduled | T2 DI CARIBOU-PALERMO :014/113 BENT MEMB | 44069583 | CARIBOU-PALERMO | :014/113 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.297639 | 39.9554 | ETL.3190 | 40738825 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116360569 | Q2 | T3 DI CRESTA RIO OSO 014/114 RPR INSS | 43708739 | CRESTA-RIO OSO | 014/114 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2019-08-06 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.461694 | 39.7654 | ETL.4590 | 40910136 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116397299 | Q3 | T2 EI CARIBOU #2 20/022 RPL SPLW | 43742128 | CARIBOU #2 | 020/022 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.015388 | 40.032 | ETL.6280 | 40675452 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116416870 | Not Scheduled | T2 DI CARIBOU-PALRMO :14/116 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :014/116 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.301792 | 39.9518 | ETL.3190 | 40811629 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116457907 | Not Scheduled | T3 DI TIGER CREEK-ELECTRA 4/36 PNT STRT | 43691537 | TIGER CREEK-ELECTRA | 004/036 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-25 | 2019-07-25 | [7 empty] | TR3 | LATE | Central | WSIP |  |  |  |  | Clearance Denied by GCC | unable to take out line | '-120.568418 | 38.4278 | ETL.5780 | 40811159 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116459983 | Not Scheduled | T2 EI PIT #1-COTTON 040/344 REPAINT | 43930183 | PIT #1-COTTONWOOD | 040/344 | ICX | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-08 | 2020-02-08 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.074673 | 40.6284 | ETL.5390 | 40758994 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116459987 | Not Scheduled | T2 EI CARIBOU-PALERMO :015/121 RPR STRT | 44069583 | CARIBOU-PALERMO | :015/121 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.308198 | 39.9429 | ETL.3190 | 40642566 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116460026 | Not Scheduled | T3 EI DRUM-HIGGINS 005/062 REPAINT | 43738143 | DRUM-HIGGINS | 005/062 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.844544 | 39.1993 | ETL.4393 | 40660208 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460051 | Not Scheduled | T2 DI CARIBOU-PALERMO :26/216 BENT MEMB | 44069454 | CARIBOU-PALERMO | :026/216 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.425086 | 39.8249 | ETL.3190 | 40816589 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460053 | Not Scheduled | T2 DI CARIBOU-PALERMO :26/216 INST HRDS | 44302715 | CARIBOU-PALERMO | :026/216 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.425086 | 39.8249 | ETL.3190 | 40816589 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460057 | Not Scheduled | T2 DI CARBU-PALRM-TWR :26/217 RPR STUB | 44069454 | CARIBOU-PALERMO | :026/217 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.425857 | 39.8239 | ETL.3190 | 40815590 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460062 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/024 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/024 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.195411 | 40.0633 | ETL.3190 | 40910268 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460065 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/024 INST HRDT | 44062862 | CARIBOU-PALERMO | :003/024 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.195411 | 40.0633 | ETL.3190 | 40910268 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460066 | Not Scheduled | T2 DI CARIBOU-PALERMO :015/119 INST HRDT | 44069583 | CARIBOU-PALERMO | :015/119 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.305695 | 39.9478 | ETL.3190 | 40738346 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460099 | Not Scheduled | T2 DI CARIBOU-PALERMO :015/119 RPR STUBS | 44069583 | CARIBOU-PALERMO | :015/119 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.305695 | 39.9478 | ETL.3190 | 40738346 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460170 | Not Scheduled | T2 DI CARIBOU-PALERMO :003/027 RPR FOND | 44062862 | CARIBOU-PALERMO | :003/027 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.199707 | 40.0633 | ETL.3190 | 40910271 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460186 | Not Scheduled | T2 DI CARIBOU-PALERMO :027/223 RRP FOND | 44069801 | CARIBOU-PALERMO | :027/223 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.435652 | 39.8119 | ETL.3190 | 40668940 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460187 | Not Scheduled | T2 DI CARIBOU-PALERMO :27/223 RPR INSS | 44304495 | CARIBOU-PALERMO | :027/223 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.435652 | 39.8119 | ETL.3190 | 40668940 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460231 | Not Scheduled | T2 EI MIDDLE FORK-GOLD 036/26 PAINT | 44302265 | MIDDLE FORK-GOLD HILL | 036/262 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-09 | 2024-02-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.044457 | 38.6999 | ETL.5140 | 40683779 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-03-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460283 | Not Scheduled | T2 EI VALLEY SPRINGS-CL 005/077 RPR STRW | 43727736 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.83005 | 38.2007 | ETL.8264 | 44255306 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460304 | Not Scheduled | T2 DI CARIBOU-PALERMO :27/226 REPR FOND | 44069801 | CARIBOU-PALERMO | :027/226 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.438961 | 39.8082 | ETL.3190 | 40828380 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460315 | Not Scheduled | T2 EI VALLEY SPRINGS-CL 005/077 RPL SPLW | 43727736 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255307 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460334 | Not Scheduled | T2 EI OLEUM-MARTINEZ 006/042 RPR FOND | 43753569 | OLEUM-MARTINEZ | 006/042 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-09 | 2020-02-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.148856 | 38.0027 | ETL.3170 | 40644165 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460445 | Not Scheduled | T2 EI PARKWAY-MORAGA 009/053 RPL HRDT | 43683430 | PARKWAY-MORAGA | 009/053 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233747 | 38.0084 | ETL.5930 | 40868354 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460467 | Not Scheduled | T2 EI PLCR-GLD HLL#1 2/022 RPR STRT |  | PLACER-GOLD HILL #1 | 002/022 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-09 | 2020-02-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097404 | 38.8703 | ETL.3340 | 40911874 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460477 | Not Scheduled | T2 DI CARIBOU-PALERMO :4/33 RPL HRDT | 44059014 | CARIBOU-PALERMO | :004/033 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.208362 | 40.051 | ETL.3190 | 40910277 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460511 | Not Scheduled | EI PLACER-GOLD HILL #1 9/066 CANCEL | 43910271 | PLACER-GOLD HILL #1 | 009/066 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.141863 | 38.7729 | ETL.3340 | 40905619 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460571 | Not Scheduled | T2 DI CARIBOU-PALERMO :024/198 REGRADE | 44304495 | CARIBOU-PALERMO | :024/198 | ICS | E | Pre-2020_(3) On high spread structure |  | 2019-02-09 | 2020-02-09 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.401589 | 39.8512 | ETL.3190 | 40867974 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116460578 | Not Scheduled | T2 DI CARIBOU-PALERMO :024/200 REPAINT | 44302715 | CARIBOU-PALERMO | :024/200 | ICS | F | Pre-2020_(3) On high spread structure |  | 2019-02-05 | 2021-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.40384 | 39.85 | ETL.3190 | 40599288 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116460626 | Not Scheduled | T2 EI CARIBOU-PALERMO :024/202 RPR FOND | 44069454 | CARIBOU-PALERMO | :024/202 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.409795 | 39.8476 | ETL.3190 | 40674980 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460628 | Not Scheduled | T2 DI CARIBOU-PALERMO :024/202 RPR STRS | 44304495 | CARIBOU-PALERMO | :024/202 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.409795 | 39.8476 | ETL.3190 | 40674980 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460641 | Not Scheduled | T2 DI CARIBOU-PALERMO :024/203 RPR FOND | 44069454 | CARIBOU-PALERMO | :024/203 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.413518 | 39.8449 | ETL.3190 | 40651675 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460710 | Not Scheduled | T2 DI COLGATE SMRTVL#1 007/079 REGRADE | 44097455 | COLGATE-SMARTVILLE #1 | 007/079 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2024-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.284116 | 39.2647 | ETL.6510 | 40659535 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460715 | Not Scheduled | T2 DI CARIBOU-PALERMO :008/066 RPR INSS | 44304495 | CARIBOU-PALERMO | 008/066 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.24349 | 40.0068 | ETL.3190 | 40920047 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460778 | Q3 | T2 EI CARIBOU #2 23/021 RPL POLE | 31455203 | CARIBOU #2 | 023/021 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.968705 | 40.0406 | ETL.6280 | 40591777 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-04-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460893 | Not Scheduled | T3 DI CARIBOU PALERMO :033/270 INST HRDT | 44051417 | CARIBOU-PALERMO | :033/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.477905 | 39.7343 | ETL.3190 | 40599303 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460894 | Not Scheduled | T3 DI CARIBOU PALERMO :033/270 RPR FOND | 44051417 | CARIBOU-PALERMO | :033/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.477905 | 39.7343 | ETL.3190 | 40599303 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460900 | Not Scheduled | T2 DI CARIBOU-PALERMO :025/206 RPR STRT |  | CARIBOU-PALERMO | :025/206 |  | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.416443 | 39.8424 | ETL.3190 | 40828382 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460903 | Not Scheduled | T2 DI CRIBOU-PLERMO :025/210 RPR BURIED | 44069454 | CARIBOU-PALERMO | :025/210 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42085 | 39.8336 | ETL.3190 | 40599291 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460907 | Not Scheduled | T2 DI CARIBOU-PALERMO :25/211 BENT MEMB | 44069454 | CARIBOU-PALERMO | :025/211 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.421047 | 39.8318 | ETL.3190 | 40602486 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460923 | Q2 | T2 EI HAT CREEK #1-WES 28/546 RPL CRSW | 31471926 | HAT CREEK #1-WESTWOOD | 028/546 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.170675 | 40.6496 | ETL.7030 | 40868486 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460930 | Feb | T2 EI RO DLL JCT-BRDGVLLE 33/8 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 033/008 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.894189 | 40.4835 | ETL.7850 | 44360011 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-04-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-04-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460932 | Not Scheduled | T2 EI MESA-STA MARIA 21/102D REPL INSS | 31500464 | MESA-SANTA MARIA | 021/102D | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-09 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.4463564 | 35.0078 | ETL.2450 | 44283859 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 6 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-11-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460941 | Q2 | T2 EI HAT CREEK #1-WES 32/617 RPR INSW | 43736797 | HAT CREEK #1-WESTWOOD | 032/617 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.116032 | 40.6144 | ETL.7030 | 40656905 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460963 | Q2 | T2 EI HAT CREEK #1-WES 28/539 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 028/539 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.175737 | 40.6528 | ETL.7030 | 40601704 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460964 | Q2 | T2 EI HAT CREEK #1-WES 28/538 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 028/538 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.176543 | 40.6532 | ETL.7030 | 40616913 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460972 | Not Scheduled | T2 EI CARIBOU-TABLE MTN 21/145A PNT TWR | 43729346 | CARIBOU-TABLE MTN | 021/145A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-09 | 2020-02-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286625 | 39.959 | ETL.4440 | 40758277 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460976 | Q2 | T2 EI HAT CREEK #1-WEST 026/515 RPR INSW | 43736797 | HAT CREEK #1-WESTWOOD | 026/515 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191028 | 40.6667 | ETL.7030 | 40825588 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460977 | Q2 | T2 EI HAT CREEK #1-WE 26/514 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 026/514 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191597 | 40.6673 | ETL.7030 | 40817133 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460979 | Q2 | T2 EI HAT CREEK #1-WES 26/517 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 026/517 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.189843 | 40.6654 | ETL.7030 | 40876192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116460986 | Q2 | T2 EI HAT CREEK #1-WES 28/547 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 028/547 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.169887 | 40.6491 | ETL.7030 | 40876194 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116461105 | Not Scheduled | T2 DI CARIBOU-PALERMO :021/179 RPR FOND | 44069454 | CARIBOU-PALERMO | :021/179 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37491 | 39.8785 | ETL.3190 | 40738369 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116461108 | Not Scheduled | T2 DI CARIBOU-PALERMO :021/179 RPR INSS |  | CARIBOU-PALERMO | :021/179 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37491 | 39.8785 | ETL.3190 | 40738369 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116461109 | Not Scheduled | T2 DI CARIBOU-PALERMO :17/146 BURY MEMB | 44069583 | CARIBOU-PALERMO | :017/146 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.327474 | 39.9159 | ETL.3190 | 40811612 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469448 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/091 RPR FOND | 44051417 | CARIBOU-PALERMO | :011/091 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276852 | 39.9826 | ETL.3190 | 40912111 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469450 | Not Scheduled | T2 DI CARIBOU-PALERMO :020/162 RPL HRDT | 44069454 | CARIBOU-PALERMO | :020/162 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.357958 | 39.9029 | ETL.3190 | 40738811 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469456 | Not Scheduled | T2 DI CARIBOU-PALRMO :17/143 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :017/143 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40738355 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469459 | Not Scheduled | T2 DI CARIBOU-PALERMO :17/143 RPL INSS |  | CARIBOU-PALERMO | :017/143 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40739414 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116469471 | Not Scheduled | T2 DI CARIBOU-PALERMO :17/143 INST HRDT | 44069583 | CARIBOU-PALERMO | :017/143 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40738355 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469474 | Not Scheduled | T2 DI CARIBOU-PALERMO :17/140 RPR FOND | 44069583 | CARIBOU-PALERMO | :017/140 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.319376 | 39.9211 | ETL.3190 | 40642213 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469476 | Not Scheduled | T2 DI CARIBOU-PALERMO :17/141 RPR FOND | 44069583 | CARIBOU-PALERMO | :017/141 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.321058 | 39.9198 | ETL.3190 | 40642499 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116469488 | Not Scheduled | T2 DI CARIBOU-PALERMO :17/137 RPR STUB | 44069583 | CARIBOU-PALERMO | :017/137 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.317946 | 39.9235 | ETL.3190 | 40806063 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116469764 | Not Scheduled | T2 DI CARIBOU-PALERMO :013/104 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280354 | 39.9626 | ETL.3190 | 40747408 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116469765 | Not Scheduled | T2NT DI CARIBOU-PLRM :013/104 RPNT STRT |  | CARIBOU-PALERMO | :013/104 |  | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2021-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280354 | 39.9626 | ETL.3190 | 40747408 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116469911 | Not Scheduled | T2 DI CARIBOU-PALERMO :013/105 RPR STUBS | 44069583 | CARIBOU-PALERMO | :013/105 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.282785 | 39.961 | ETL.3190 | 40747389 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116469912 | Not Scheduled | T2 DI CARIBOU-PALERMO :013/105 RPR HRDT | 44069583 | CARIBOU-PALERMO | :013/105 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.282785 | 39.961 | ETL.3190 | 40747389 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116469919 | Not Scheduled | T2 DI CARIBOU-PALRMO :13/106 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :013/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.283913 | 39.9602 | ETL.3190 | 40738342 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116470379 | Not Scheduled | T2 DI CARIBOU-PALRMO :15/125 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :015/125 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.311915 | 39.9394 | ETL.3190 | 40753327 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116470380 | Not Scheduled | T2 DI CARIBOU-PALERMO :009/71 RPR FOND | 44059014 | CARIBOU-PALERMO | :009/071 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.257827 | 40.0052 | ETL.3190 | 40910313 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116470410 | Not Scheduled | T3 DI CARIBOU-PLRM :032/264 RPR JUMP | 43659205 | CARIBOU-PALERMO | :032/264 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475885 | 39.7472 | ETL.3190 | 40771771 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116470465 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/092 REPL CONN |  | CARIBOU-PALERMO | :011/092 | ICM | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27547 | 39.9808 | ETL.3190 | 40910331 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116470596 | Not Scheduled | T3 DI CARIBOU-PLRM :032/262 RPR FOND | 44051417 | CARIBOU-PALERMO | :032/262 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475245 | 39.7512 | ETL.3190 | 40702274 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116470618 | Not Scheduled | T2 DI CARIBOU-PALERMO :028/233 RPR HRDT | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116470643 | Not Scheduled | T3 DI CARIBOU-PLERMO :037/300B REPL CONN |  | CARIBOU-PALERMO | :037/300B | ICM | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486563 | 39.6812 | ETL.3190 | 41162692 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116470894 | Not Scheduled | T3 EI FULTON-PUEBLO 41/214 INS DAMS | 44306529 | FULTON-PUEBLO | 041/214 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2019-08-11 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.736557 | 38.4973 | ETL.1600 | 40762053 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-09-03 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471084 | Not Scheduled | T2 EI OLM-NRTH TWR-CHRST 1/10 PNT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 001/010 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-11 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.233799 | 38.0389 | ETL.3180 | 40580267 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471211 | Not Scheduled | T2 EI CARIBOU-PALERMO :013/109 RPL HRDT | 44069583 | CARIBOU-PALERMO | :013/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.288193 | 39.9584 | ETL.3190 | 40738826 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471213 | Not Scheduled | T2 CARIBOU-PALERMO :13/110 INS HRDT | 44069583 | CARIBOU-PALERMO | :013/110 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.290832 | 39.9582 | ETL.3190 | 40642211 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116471214 | Not Scheduled | T2 EI CARIBOU-PALERMO :014/111 RPR STRT | 44069583 | CARIBOU-PALERMO | :014/111 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-09 | 2020-02-09 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.293251 | 39.9571 | ETL.3190 | 40642567 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116471218 | Not Scheduled | T2 EI CARIBOU-PALERMO :013/109 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.288193 | 39.9584 | ETL.3190 | 40738826 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471227 | Not Scheduled | T2 EI CARIBOU-PALERMO :13/108 RPR JUMS | 44304495 | CARIBOU-PALERMO | :013/108 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2020-02-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40858895 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471265 | Not Scheduled | T2 EI PIT #1-COTTONWOOD 38/331 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 038/331 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.048237 | 40.6602 | ETL.5390 | 40579862 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471317 | Not Scheduled | T2 EI CARIBOU-TABLE MTN 20/144A PNT STRT | 43729346 | CARIBOU-TABLE MTN | 020/144A | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2024-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.28548 | 39.9599 | ETL.4440 | 40758423 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471357 | Not Scheduled | PLCR-GLD HILL#1 2/23 PAINT TOWER |  | PLACER-GOLD HILL #1 | 002/023 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-11 | 2020-02-11 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.097232 | 38.8664 | ETL.3340 | 40911183 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471432 | Not Scheduled | T3 DI CARIBOU-PLRM :030/248 RPR JUMS | 43659205 | CARIBOU-PALERMO | :030/248 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.455372 | 39.773 | ETL.3190 | 40878269 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471514 | Not Scheduled | T3 EI DRUM-HIGGINS B010/105 CANCEL | 43738143 | DRUM-HIGGINS | B010/105 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2019-08-11 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94385 | 39.1514 | ETL.4393 | 41162657 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471648 | Not Scheduled | T2 EI RND MTN-TBL MTN #2 81/328 INS MRKT | 44302501 | ROUND MTN-TABLE MTN #2 | 081/328 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701904 | 39.6591 | ETL.6070 | 40865961 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471845 | Not Scheduled | T3 DI CARIBOU-PALERMO :012/093 RMV FOND | 44051417 | CARIBOU-PALERMO | :012/093 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274659 | 39.9777 | ETL.3190 | 40912112 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116471848 | Not Scheduled | T3 DI CARIBOU-PALERMO :012/094 RPR FOND | 44051417 | CARIBOU-PALERMO | :012/094 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27516 | 39.9756 | ETL.3190 | 40912113 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116471874 | Not Scheduled | T2 EI PIT #1-COTTONWOOD 39/334 RPR FOND | 43879412 | PIT #1-COTTONWOOD | 039/334 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.055336 | 40.6516 | ETL.5390 | 40758992 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471883 | Not Scheduled | T3 EI DRUM-HIGGINS B010/106 REPAINT | 43738143 | DRUM-HIGGINS | B010/106 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2019-08-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.945249 | 39.153 | ETL.4393 | 41162660 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471943 | Q2 | T2 EI HTCRK#1-WSTWD 020/398 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 020/398 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.265607 | 40.7347 | ETL.7030 | 40770737 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471975 | Not Scheduled | T2 EI PIT #1-COTTONWOOD 39/335 | 43879412 | PIT #1-COTTONWOOD | 039/335 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.056317 | 40.6505 | ETL.5390 | 40762514 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116471987 | Not Scheduled | T3 EI ELDORADO-MISOR FLT#1 3/24 REPAINT | 44585955 | ELDORADO-MISSOURI FLAT #1 | 003/024 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2019-08-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.667428 | 38.7631 | ETL.1530 | 40751922 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472004 | Q2 | T2 EI RNDMTN-TBLMTN #2 079/322 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 079/322 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-11 | 2020-02-11 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.714977 | 39.6828 | ETL.6070 | 40670019 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472036 | Q2 | T2 EI HTCRK#1-WSTWD 020/400 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472073 | Not Scheduled | T2 EI PALERMO-WYANDOTTE 0/6 CANCEL | 44586169 | PALERMO-WYANDOTTE | 000/006 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2020-02-11 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.530622 | 39.4582 | ETL.4315 | 40815620 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472075 | Not Scheduled | T3 EI FULTON-PUEBLO 41/212 REPAINT | 43720980 | FULTON-PUEBLO | 041/212 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.729755 | 38.497 | ETL.1600 | 40648150 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-25 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472105 | Not Scheduled | T3 DI CARIBOU-PLERMO :12/095 BURIED MEMB | 44051418 | CARIBOU-PALERMO | :012/095 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274963 | 39.9723 | ETL.3190 | 40912114 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116472114 | Not Scheduled | T3 DI CARIBOU-PALERMO :012/096 RPR STRT | 44051417 | CARIBOU-PALERMO | :012/096 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274824 | 39.9695 | ETL.3190 | 40910335 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116472165 | Not Scheduled | T3 DI CARIBOU-PLRM :031/253 RPR FOND | 44051417 | CARIBOU-PALERMO | :031/253 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.463429 | 39.763 | ETL.3190 | 40668944 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472192 | Not Scheduled | T3 DI CARIBOU-PLRM :031/253 RPR STRT | 44051417 | CARIBOU-PALERMO | :031/253 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2019-07-29 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.463429 | 39.763 | ETL.3190 | 40668944 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472230 | Not Scheduled | T2 DI CARIBOU-PALERMO :28/231 REPL HRDT | 44069801 | CARIBOU-PALERMO | :028/231 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472232 | Not Scheduled | T2 DI CARIBOU-PALERMO :28/231 RMV FOOT |  | CARIBOU-PALERMO | :028/231 |  | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472375 | Not Scheduled | T2 EI PLACER-GOLD HILL 1/13 PNT STRT | 44586177 | PLACER-GOLD HILL #1 | 001/013 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2022-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.098103 | 38.8861 | ETL.3340 | 40906515 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472433 | Not Scheduled | T3 DI CARIBOU-PLRM :031/257 RPL HRDT | 44051418 | CARIBOU-PALERMO | :031/257 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.468506 | 39.759 | ETL.3190 | 40826429 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472461 | Not Scheduled | T2 DI CARIBOU-PALERMO :27/221 FOND | 44069454 | CARIBOU-PALERMO | :027/221 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472543 | Q2 | T2 EI HAT CRK #1-WSTWD 21/406 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 021/406 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.260183 | 40.7302 | ETL.7030 | 40667944 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472544 | Q2 | T2 EI HAT CRK #1-WSTWD 20/401 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 020/401 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.263613 | 40.733 | ETL.7030 | 40816134 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472574 | Not Scheduled | T2 DI CARIBOU-PALERMO :012/099 RPR FOND | 44059014 | CARIBOU-PALERMO | :012/099 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-22 | 2020-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274973 | 39.9652 | ETL.3190 | 40910338 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472586 | Not Scheduled | T2 EI ROUND MTN-TM #1 079/322 INST GMKS | 44305409 | ROUND MTN-TABLE MTN #1 | 079/322 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.715343 | 39.6824 | ETL.6060 | 40670052 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472622 | Not Scheduled | T2 DI CARIBOU PLERMO :28/234 BURIED MEMB | 44069801 | CARIBOU-PALERMO | :028/234 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451472 | 39.7995 | ETL.3190 | 40771764 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472634 | Not Scheduled | T2 EI OLM-NRTH TWR-CHRST 1/13 PNT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 001/013 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.228899 | 38.0353 | ETL.3180 | 40644346 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472683 | Not Scheduled | T3 DI CARIBOU-PLRM :031/256 REPNT STRT | 44051417 | CARIBOU-PALERMO | :031/256 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-22 | 2019-07-22 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472784 | Not Scheduled | T2 EI TGR CRK-ELECT 010/083 RPR STRT | 43727728 | TIGER CREEK-ELECTRA | 010/083 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.643348 | 38.369 | ETL.5780 | 40651017 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472792 | Not Scheduled | T2 DI CARIBOU-PALERMO :012/101 RPR STRT | 44069583 | CARIBOU-PALERMO | :012/101 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275177 | 39.9642 | ETL.3190 | 40910340 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472797 | Not Scheduled | T2 DI CARIBOU-PALERMO :012/101 RPR STUBS | 44069583 | CARIBOU-PALERMO | :012/101 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275177 | 39.9642 | ETL.3190 | 40910340 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472816 | Not Scheduled | T2 DI CRBOU PLRMO :28/235 STRT RMV SOIL |  | CARIBOU-PALERMO | :028/235 |  | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452416 | 39.7976 | ETL.3190 | 40758498 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472871 | Q2 | T2 EI RND MTN-TBL MTN #2 82/332 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 082/332 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-11 | 2020-02-11 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.695052 | 39.6471 | ETL.6070 | 40680197 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472940 | Not Scheduled | T2 EI PARKWAY-MORAGA 09/057 PNT TWR | 43683436 | PARKWAY-MORAGA | 009/057 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233292 | 38.0015 | ETL.5930 | 40676028 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116472960 | Not Scheduled | T2 DI CARIBOU-PALERMO :000/004 RPR FOND | 44062862 | CARIBOU-PALERMO | :000/004 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.153193 | 40.0836 | ETL.3190 | 41162787 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473048 | Not Scheduled | T2 EI OLM-NRTH TWR-CHRST 3/21 PNT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 003/021 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.204908 | 38.0291 | ETL.3180 | 40579964 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473137 | Q2 | T2 EI HAT CREEK #1-WSTWD 19/366 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 019/366 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.287155 | 40.752 | ETL.7030 | 40601707 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473243 | Q2 | T2 EI HAT CRK #1-WESTWD 33/636 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 033/636 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.104913 | 40.6024 | ETL.7030 | 40667962 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473298 | Q2 | T2 EI HAT CREEK #1-WSTWD 19/367 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 019/367 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286462 | 40.7515 | ETL.7030 | 40676303 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473335 | Q2 | T2 EI HAT CRK #1-WSTWD 19/365 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 019/365 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.287853 | 40.7526 | ETL.7030 | 40600214 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473517 | Q2 | T2 DI FORT ROSS-GUALALA 31/1 RPR GYWW | 43714438 | GUALALA-MONTE RIO | 031/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2020-02-11 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.253394 | 38.5527 | ETL.6980 | 40601533 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473545 | Q2 | T2 EI HT CRK #1-WESTWD 027/529 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 027/529 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.18311 | 40.6579 | ETL.7030 | 40600238 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473582 | Not Scheduled | T3 DI CARIBOU-PLRM :032/258 RPL HRDT | 44051417 | CARIBOU-PALERMO | :032/258 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.471155 | 39.7577 | ETL.3190 | 40867978 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473720 | Q2 | T2 EI HAT CRK #1-WSTWD 32/625 RPR GYWW | 31471926 | HAT CREEK #1-WESTWOOD | 032/625 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.111218 | 40.6092 | ETL.7030 | 40592108 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473726 | Q2 | T2 EI HT CRK #1-WSTWD 026/518 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 026/518 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.189327 | 40.6647 | ETL.7030 | 40600235 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473727 | Q2 | T2 EI HT CRK #1 WESTWD 027/525 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 027/525 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.185418 | 40.6604 | ETL.7030 | 40817135 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473741 | Not Scheduled | T3 DI CARIBOU-PLRM :009/074 RPR FON | 44051418 | CARIBOU-PALERMO | :009/074 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.264125 | 40.0035 | ETL.3190 | 40910316 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116473743 | Not Scheduled | T3 DI CARIBOU-PLRM :009/074 RPR STRT | 44059014 | CARIBOU-PALERMO | :009/074 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-31 | 2020-01-31 | [6 empty] | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.264125 | 40.0035 | ETL.3190 | 40910316 | Structure-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116473761 | Q2 | T2 EI HT CRK #1-WSTWD 028/554 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 028/554 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.164383 | 40.6457 | ETL.7030 | 40827489 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473793 | Q2 | T2 EI HT CRK #1-WSTWD 028/553 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 028/553 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.165163 | 40.6462 | ETL.7030 | 40759039 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473813 | Not Scheduled | T3 DI CARIBOU-PALERM :31/252 RPR FOND | 44051418 | CARIBOU-PALERMO | :031/252 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.461095 | 39.7655 | ETL.3190 | 40674989 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473821 | Not Scheduled | T3 DI CARIBOU-PLRM :009/73 RPR STRT | 44051417 | CARIBOU-PALERMO | :009/073 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.263216 | 40.0035 | ETL.3190 | 40910315 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116473823 | Not Scheduled | T3 DI CARIBOU-PLRM :009/73 RPL INSS | 31468828 | CARIBOU-PALERMO | :009/073 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.263216 | 40.0035 | ETL.3190 | 40910315 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116473829 | Not Scheduled | T2 DI CARIBOU-PALERMO :013/107 RPL SPLS | 44304495 | CARIBOU-PALERMO | :013/107 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.285231 | 39.9593 | ETL.3190 | 40810977 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473872 | Not Scheduled | T3 DI CARIBOU PALERMO :30/242 RPR FOND | 44051418 | CARIBOU-PALERMO | :030/242 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451805 | 39.7819 | ETL.3190 | 40702267 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473873 | Not Scheduled | T3 DI CARIBOU PALERMO :30/242 RPR INSS | 43659205 | CARIBOU-PALERMO | :030/242 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451805 | 39.7819 | ETL.3190 | 40702267 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473876 | Not Scheduled | T3 DI CRBOU PLRMO :30/245 RPL INSS | 31426498 | CARIBOU-PALERMO | :030/245 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116473999 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/163 PAINT STRT |  | CARIBOU-PALERMO | :020/163 | ICH | F | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2021-01-23 | [6 empty] | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.359437 | 39.9021 | ETL.3190 | 40738362 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 625 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474054 | Not Scheduled | T2 EI CARIBOU-PALERMO :20/162 RPR FOND | 44069455 | CARIBOU-PALERMO | :020/162 | ICQ | F | Pre-2020_(2) High fire spread TD |  | 2019-01-24 | 2021-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.357958 | 39.9029 | ETL.3190 | 40738811 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116474203 | Q2 | T2 EI HAT CRK #1-WSTWD 19/375 RPL PL | 31505374 | HAT CREEK #1-WESTWOOD | 019/375 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.280927 | 40.747 | ETL.7030 | 40616895 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474235 | Q2 | T2 EI HAT CRK #1-WESTWD 34/655 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 034/655 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.093897 | 40.5905 | ETL.7030 | 40667965 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474237 | Q2 | T2 EI HTCRK#1-WSTWD 031/613 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 031/613 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11826 | 40.6168 | ETL.7030 | 40877608 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474238 | Not Scheduled | T2 EI HTCRK#1-WSTWD 034/659 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 034/659 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.091532 | 40.5881 | ETL.7030 | 40816155 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474336 | Feb | T2 DI SMARTVLL NICLAUS # 2 0/4 WASH INSS | 43852598 | SMARTVILLE-NICOLAUS #2 | 000/004 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-21 | 2020-01-21 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3028 | 39.2071 | ETL.8000 | 44177580 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 622 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474594 | Not Scheduled | T3 DI CRBOU-PLRMO :035/286 REPL INSS | 31426498 | CARIBOU-PALERMO | :035/286 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.482382 | 39.7069 | ETL.3190 | 40813911 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116474700 | Not Scheduled | T3 DI CARIBOU-PALERMO :035/286 RPR FOND | 44051418 | CARIBOU-PALERMO | :035/286 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-08 | 2019-08-08 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.482382 | 39.7069 | ETL.3190 | 40813911 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475174 | Not Scheduled | T2 EI PARKWAY-MORAGA 009/058 REPAINT | 43683436 | PARKWAY-MORAGA | 009/058 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.232569 | 37.9998 | ETL.5930 | 40651053 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475178 | Mar | T2 POE-RIO OSO 037/248 RPR INSS |  | POE-RIO OSO | 037/248 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.522667 | 39.4508 | ETL.5540 | 40867267 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-11 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475235 | Not Scheduled | T2 EI MTCLF-L PT #1 003/018 RPR FOND | 44277393 | METCALF-EL PATIO #1 | 003/018 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.804171 | 37.223 | ETL.2500 | 40867596 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475328 | Q2 | T2 EI RND MTN-TBL MTN#2 079/321 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 079/321 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-12 | 2020-02-12 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.716734 | 39.6859 | ETL.6070 | 40589550 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475351 | Q2 | T2 EI HAT CRK #1-WESTWD 18/360 RPL PL | 31495723 | HAT CREEK #1-WESTWOOD | 018/360 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.29132 | 40.7555 | ETL.7030 | 40868466 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475371 | Q2 | T2 EI HTCRK #1-WSTWD 018/359 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 018/359 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.291997 | 40.756 | ETL.7030 | 40825575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475423 | Not Scheduled | T2 EI LM-NTH TWR-CHRST 002/014 RPR STRT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 002/014 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.224957 | 38.0347 | ETL.3180 | 40744890 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475633 | Q2 | T2 EI HAT CRK #1-WSTWD 18/355 RPL PL | 31426976 | HAT CREEK #1-WESTWOOD | 018/355 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.294783 | 40.7583 | ETL.7030 | 40667938 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475680 | Not Scheduled | T2 EI PIT#1-COTTONWD 039/336 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 039/336 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.057646 | 40.6489 | ETL.5390 | 40816946 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475688 | Not Scheduled | T3 EI DRUM-HIGGINS B010/107 CANCEL | 43738143 | DRUM-HIGGINS | B010/107 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-11 | 2019-08-11 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94692 | 39.155 | ETL.4393 | 41196118 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475713 | Not Scheduled | T3 EI EGL RCK-FTN-SLVRD 020/086 REPAINT | 43713428 | EAGLE ROCK-FULTON-SILVERADO | 020/086 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-12 | 2019-08-12 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.608562 | 38.4989 | ETL.4392 | 41129388 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475723 | Not Scheduled | T2 DRUM-RIO OSO #1 031/229 REPAINT STRT | 44304427 | DRUM-RIO OSO #1 | 031/229 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-12 | 2023-02-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.272175 | 39.0347 | ETL.1420 | 40864701 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475726 | Not Scheduled | T2 DI CARIBOU-PLRM :028/228 RPR JUMPER | 44070463 | CARIBOU-PALERMO | :028/228 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.442288 | 39.805 | ETL.3190 | 40878267 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475772 | Not Scheduled | T2 DI CARIBOU-PLRM :028/228RPR STUBS | 44069801 | CARIBOU-PALERMO | :028/228 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.442288 | 39.805 | ETL.3190 | 40878267 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475839 | Not Scheduled | T2 EI PIT#1-COTTONWD 039/337 RPR FOND | 43637398 | PIT #1-COTTONWOOD | 039/337 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.060957 | 40.6449 | ETL.5390 | 40817903 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475851 | Not Scheduled | T2 EI LKVL-GNC #1 IG002/009 RPR FOND | 43761675 | LAKEVILLE-IGNACIO #1 | IG002/009 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-12 | 2024-02-12 | [7 empty] | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.521366 | 38.1105 | ETL.4940 | 40868872 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475894 | Q2 | T2 EI LKVL-GNC IG002/010 RPR FOND | 43761675 | LAKEVILLE-IGNACIO #1 | IG002/010 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-12 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522131 | 38.1071 | ETL.4940 | 40602349 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475931 | Q2 | T2 EI LKVL-GNC #1 IG002/010 RPR STRT | 43761674 | LAKEVILLE-IGNACIO #1 | IG002/010 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-02-12 | 2021-05-31 |  |  | 2021-05-31 |  |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522131 | 38.1071 | ETL.4940 | 40602349 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-08-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116475967 | Not Scheduled | T2 EI MTCLF-DNVL #1 003/017D RPR FOND |  | METCALF-EDENVALE #1 | 003/017D | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-12 | 2024-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.803579 | 37.2225 | ETL.2480 | 40742457 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-02-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116476056 | Q2 | EI CORDELIA #2 TAP 003/066 RPR ANCW | 43743931 | CORDELIA #2 TAP | 003/066 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-12 | 2020-02-12 |  |  | 2021-05-04 | 2021-04-26 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.152884 | 38.2504 | ETL.8184 | 40612471 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116476211 | Not Scheduled | T2 EI PARKWAY-MORAGA 10/060 PNT TWR | 43683436 | PARKWAY-MORAGA | 010/060 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-12 | 2024-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.229498 | 37.9948 | ETL.5930 | 40758934 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116476465 | Not Scheduled | T2 EI CARIBOU-PALERMO :006/051 RPR STRT | 44059014 | CARIBOU-PALERMO | :006/051 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.221517 | 40.0202 | ETL.3190 | 40910293 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116480380 | Q2 | T2 EI HT CRK #1-WSTWD 031/600 RPR CRSW | 43736797 | HAT CREEK #1-WESTWOOD | 031/600 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.128433 | 40.6232 | ETL.7030 | 40759041 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116480390 | Q2 | T2 EI HT CRK #1-WSTWD 030/583 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 030/583 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.141767 | 40.6315 | ETL.7030 | 40825592 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481062 | Not Scheduled | T2 EI LM-NTH TWR-CHRST 002/018 RPR STRT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 002/018 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.213934 | 38.0325 | ETL.3180 | 40857757 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481119 | Q2 | T2 EI HT CRK #1-WSTWD 033/649 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 033/649 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.09734 | 40.5943 | ETL.7030 | 40827600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481180 | Q2 | T2 EI HT CRK #1-WSTWD 033/651 RPL HRDW | 43736797 | HAT CREEK #1-WESTWOOD | 033/651 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096175 | 40.5931 | ETL.7030 | 40868494 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481181 | Q2 | T2 EI HT CRK #1-WSTWD 033/650 RPL HRDW | 43736797 | HAT CREEK #1-WESTWOOD | 033/650 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096788 | 40.5936 | ETL.7030 | 40825597 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481187 | Not Scheduled | T2 EI LM-NTH TWR-CHRST 002/019 RPR STRT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 002/019 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.211346 | 38.0315 | ETL.3180 | 40856876 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481230 | Q3 | T2 EI CARIBOU-WESTWD 007/140B RPR GYWW | 43640851 | CARIBOU-WESTWOOD | 007/140 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08781 | 40.1717 | ETL.6300 | 42624246 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481348 | Not Scheduled | T2NT EI STNSLS-MLNS SW ST-MTC #1 REPAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 023/146 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-12 | 2021-02-12 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.708163 | 37.9415 | ETL.3830 | 40756196 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116481495 | Not Scheduled | T2 DI CARIBOU-PALERMO :018/154 RMV SOIL | 44069597 | CARIBOU-PALERMO | :018/154 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481750 | Not Scheduled | T2 EI STNSLS-MNTC#2 015/087 RPL HRDT | 43712838 | STANISLAUS-MANTECA #2 | 015/087 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  | REJECT: WV received email stating this tag was submit in error. Corrected submission has not yet been received. |  |  | '-120.595814 | 38.0239 | ETL.3820 | 40803363 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  | Reject | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481836 | Q2 | T2 EI HAT CRK #1-WSTWD 35/675 RPL PL | 31426976 | HAT CREEK #1-WESTWOOD | 035/675 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.082302 | 40.578 | ETL.7030 | 40770865 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481889 | Q2 | T2 EI HT CRK #1-WSTWD 026/503 RPR ANCW | 43736797 | HAT CREEK #1-WESTWOOD | 026/503 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.197668 | 40.6739 | ETL.7030 | 40759035 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481893 | Q2 | T2 EI HAT CRK #1-WESTWD 32/631 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 032/631 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-11 | 2020-02-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107808 | 40.6055 | ETL.7030 | 40825595 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481894 | Q2 | T2 EI HT CRK #1-WSTWD 034/665 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 034/665 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.088112 | 40.5843 | ETL.7030 | 40667967 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481897 | Q2 | T2 EI HT CRK #1-WSTWD 034/670 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 034/670 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.085213 | 40.5812 | ETL.7030 | 40877593 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481932 | Q2 | EI HTCRK#1-WSTWD 026/508 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 026/508 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.194835 | 40.6708 | ETL.7030 | 40616910 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481933 | Q2 | T2 EI HT CRK #1-WSTWD 026/503 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 026/503 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.197668 | 40.6739 | ETL.7030 | 40759035 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481935 | Q2 | EI HAT CRK #1-WSTWD 26/505 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 026/505 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.196537 | 40.6726 | ETL.7030 | 40816141 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116481999 | Not Scheduled | T3 DI CARIBOU PALERMO :034/279 RMV SOIL | 44051418 | CARIBOU-PALERMO | :034/279 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.480326 | 39.7195 | ETL.3190 | 40867378 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116482127 | Not Scheduled | T3 DI CARIBOU PALERMO :035/285 RPR FOND | 44051417 | CARIBOU-PALERMO | :035/285 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.482144 | 39.7083 | ETL.3190 | 40758502 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116482213 | Not Scheduled | T3 DI CARIBOU PALERMO :036/289 RPR STRT | 44051417 | CARIBOU-PALERMO | :036/289 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.483288 | 39.7013 | ETL.3190 | 40867380 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116482218 | Not Scheduled | T3 EI CARIBOU PALERMO :036/292 RPR FOND | 44051418 | CARIBOU-PALERMO | :036/292 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.483711 | 39.6987 | ETL.3190 | 40702278 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116482233 | Mar | T2 DI POE RIO OSO 39/257 INST RPTS | 43878128 | POE-RIO OSO | 039/257 | ICB | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-12 | 2020-02-12 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.518365 | 39.4294 | ETL.5540 | 40814853 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116482236 | Q2 | T2 EI HT CRK #1-WSTWD 022/423 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 022/423 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.248295 | 40.7206 | ETL.7030 | 40601613 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116482238 | Q2 | T2 EI HT CRK #1-WSTWD 022/422 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 022/422 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.249035 | 40.7213 | ETL.7030 | 40600217 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116483266 | Not Scheduled | T2 EI CRTNA MENDO #1 26/125 FOND RPR | 43760958 | CORTINA-MENDOCINO #1 | 026/125 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.661167 | 39.0292 | ETL.1330 | 40750575 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-05-08 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116483899 | Q2 | T2 EI HT CRK #1-WSTWD 027/532 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 027/532 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.181282 | 40.6562 | ETL.7030 | 40656896 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116484028 | Q2 | T2 EI HT CRK #1-WSTWD 027/531 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 027/531 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.181957 | 40.6566 | ETL.7030 | 40676354 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116486948 | Not Scheduled | T2 EI CHRISTIE-SOBRANTE 11/065 CANCEL | 44598163 | CHRISTIE-SOBRANTE | 011/065 | ICI | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP |  |  | REJECT: Crew reported work not needed. Please confirm(approve) or reject if disagree. Recommend : Wash all insulators. |  |  | '-122.194254 | 37.9792 | ETL.1260 | 40761571 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  | Reject | 2019-10-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116487342 | Q2 | T2 EI HTCRK #1-WSTWD 018/354 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 018/354 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.295552 | 40.7588 | ETL.7030 | 40701337 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116487343 | Not Scheduled | T2 EI HAT CRK #1-WESTWD 18/360 CANCEL | 43736796 | HAT CREEK #1-WESTWOOD | 018/360 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.29132 | 40.7555 | ETL.7030 | 40868466 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116487609 | Q2 | EI STAN-NEWARK #1 093/616 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 093/619 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-14 | 2020-02-14 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.88565 | 37.5729 | ETL.3850 | 40877299 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116487982 | Feb | T2 EI RVILL-THRMLIT-TBL #3 1/4 RPL DAMP | 43739693 | MTN #3 (CDWR) | 001/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-14 | 2020-02-14 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.507875 | 39.5359 | ETL.6622 | 42580949 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116488076 | Not Scheduled | T2 EI PALERMO-COLG C000/002 RPR COND | 43724331 | PALERMO-COLGATE | C000/002 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-14 | 2020-02-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.193937 | 39.3315 | ETL.5360 | 40683681 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116488109 | Not Scheduled | T2 EI PALERMO-COLG C000/002 COTTER KEY | 43724332 | PALERMO-COLGATE | C000/002 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-14 | 2020-02-14 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.193937 | 39.3315 | ETL.5360 | 40683681 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116488123 | Not Scheduled | T2 EI ROUND MTN-TM #1 077/314 RPR STRT | 44003357 | ROUND MTN-TABLE MTN #1 | 077/314 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-14 | 2020-02-14 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.729577 | 39.708 | ETL.6060 | 40761463 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116488142 | Q2 | T2 EI COLGATE-PALERMO 021/433 RPL SPLW | 43728970 | COLGATE-PALERMO | 021/433 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-14 | 2020-02-14 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.510802 | 39.4581 | ETL.6500 | 40822490 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116488314 | Not Scheduled | T2 ORO-TH-TA MT #1 2/12 CANCEL | 44630965 | MTN #1(CDWR) | 002/012 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-14 | 2020-02-14 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process |  | '-121.528307 | 39.5467 | ETL.6621 | 42580635 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116488831 | Not Scheduled | T2 DI CARIBOU-PALERMO :009/072 RPR FOND |  | CARIBOU-PALERMO | :009/072 |  | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.258867 | 40.0049 | ETL.3190 | 40910314 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116490031 | Not Scheduled | T3 EI CARIBOU-PALERMO :008/064 REPL HRDT | 44051418 | CARIBOU-PALERMO | :008/064 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.239441 | 40.0064 | ETL.3190 | 40910306 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116490032 | Not Scheduled | T3 EI CARIBOU-PALERMO :008/064 RPL HRDT | 44051418 | CARIBOU-PALERMO | :008/064 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.239441 | 40.0064 | ETL.3190 | 40910306 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116491927 | Not Scheduled | T2 EI OLM-NTH TWR-CHRST A03/027 PAINT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | A03/027 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-15 | 2020-02-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.201786 | 38.0173 | ETL.3180 | 40818337 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116492256 | Not Scheduled | T2 EI RND MTN-TBL M #2 077/314 RPR STRT | 43755806 | ROUND MTN-TABLE MTN #2 | 077/314 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-15 | 2020-02-15 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.729021 | 39.7081 | ETL.6070 | 40765458 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116492432 | Not Scheduled | T3 DI CARIBOU-PALERMO :008/063 RPR STRT | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116492438 | Not Scheduled | T3 DI CARIBOU-PALERMO :008/063 RPR STRT | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116492462 | Not Scheduled | T3 DI CARIBOU-PALERMO :008/063 REPL CONS |  | CARIBOU-PALERMO | :008/063 | 93C | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Conductor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 531 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116492467 | Not Scheduled | T3 DI CARBOU-PALERMO :008/063 REPNT STRS | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-14 | 2019-08-14 | [6 empty] | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116492551 | Q2 | T2 EI MILLBRAE-SNTH LNE 14/98 RPR STRT | 44278027 | MILLBRAE-SNEATH LANE | 014/098 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-15 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-05 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.445905 | 37.6219 | ETL.7570 | 41162747 | Structure-Tower | Anti-Climbing Guard | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | SFPUC | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-04-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116492575 | Not Scheduled | T2 EI PITTSBURG-TESLA #1 016/073 HRDT | 44238805 | PITTSBURG-TESLA #1 | 016/073 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-15 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.72794 | 37.8908 | ETL.5510 | 40650652 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116492817 | Q3 | T2 EI CARIBOU #2 17/025 RPR GYWW | 43742132 | CARIBOU #2 | 017/025 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-15 | 2020-02-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.062773 | 40.022 | ETL.6280 | 40768837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116492961 | Q3 | T2 EI CARIBOU #2 17/026 RPL SPLW | 43742136 | CARIBOU #2 | 017/026 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-15 | 2020-02-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.06235 | 40.0214 | ETL.6280 | 40826407 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116493267 | Not Scheduled | T2 EI OLM-NRTH TWR-CHRSTE A004/029 RPNT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | A04/029 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-15 | 2020-02-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20133 | 38.0146 | ETL.3180 | 40857608 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116493357 | Q3 | T2 EI CARIBOU #2 15/020 INST STEP | 43742127 | CARIBOU #2 | 015/020 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-15 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.102045 | 40.018 | ETL.6280 | 40614875 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116493735 | Not Scheduled | T2 EI POE-RIO OSO 027/174 RMV NEST | 43737420 | POE-RIO OSO | 027/174 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-15 | 2020-02-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519979 | 39.6103 | ETL.5540 | 40762685 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116493796 | Mar | T2 EI POE-RIO OSO 027/174 SPLS | 43737420 | POE-RIO OSO | 027/174 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-15 | 2020-02-15 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519979 | 39.6103 | ETL.5540 | 40762685 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116493799 | Not Scheduled | T2 EI OLM-NTH TWR-CHRST A03/026 PAINT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | A03/026 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-15 | 2020-02-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20233 | 38.0205 | ETL.3180 | 40804617 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116493893 | Not Scheduled | T3 DI CARIBOU-PALERMO :034/273 RPR STRS | 44051418 | CARIBOU-PALERMO | :034/273 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [6 empty] | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478516 | 39.7306 | ETL.3190 | 40668936 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116493937 | Not Scheduled | T2 EI OLM-N TWR-CH A3/26 HANGER GUEST | 44323394 | OLEUM-NORTH TOWER-CHRISTIE | A03/026 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-15 | 2020-02-15 | [5 empty] | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20233 | 38.0205 | ETL.3180 | 40804617 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116494207 | Not Scheduled | T3 DI CARIBOU PALERMO :33/272 RPR STRT | 44051418 | CARIBOU-PALERMO | :033/272 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478424 | 39.7311 | ETL.3190 | 40702276 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116494807 | Q3 | T2 DI CARIBOU #2 015/023 INS GYWW | 43742132 | CARIBOU #2 | 015/023 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-02-14 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.100345 | 40.017 | ETL.6280 | 40656556 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116494944 | Not Scheduled | T2 EI PITTSBURG-TESLA #1 017/079 HRDT |  | PITTSBURG-TESLA #1 | 017/079 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-15 | 2024-02-15 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.706942 | 37.8775 | ETL.5510 | 40862428 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116495010 | Not Scheduled | T2 EI PINE GROVE TAP 002/049 INS GYWW | 43687879 | PINE GROVE TAP | 002/049 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-14 | 2020-02-14 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.653296 | 38.4121 | ETL.8351 | 40596137 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-03-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116495826 | Not Scheduled | T2 EI METCALF-EL PATIO #1 003/015 REPAIN | 43753585 | METCALF-EL PATIO #1 | 003/015 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-15 | 2024-02-15 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.794203 | 37.2217 | ETL.2500 | 40757994 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116496057 | Not Scheduled | T2 EI BAHIA-MORAGA 12/071 PNT TWR | 43683412 | BAHIA-MORAGA | 012/071 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-16 | 2020-02-16 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233619 | 38.0051 | ETL.4340 | 40740004 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | 2019-03-22 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-03-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116496141 | Q3 | T2 EI CARIBOU #2 017/029 RPL SPLW | 43742127 | CARIBOU #2 | 017/029 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-15 | 2020-02-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061624 | 40.0201 | ETL.6280 | 40875420 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116496184 | Not Scheduled | T2 EI VASONA-METCALF 5/025 PRR FOND |  | VASONA-METCALF | 005/025 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-16 | 2020-02-16 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.838709 | 37.2274 | ETL.5932 | 40764929 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116496230 | Not Scheduled | T2 EI VASONA-METCALF 5/25 RPR STRT |  | VASONA-METCALF | 005/025 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-16 | 2020-02-16 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.838709 | 37.2274 | ETL.5932 | 40764929 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116496409 | Not Scheduled | T2 EI MRR BY-SN LS OBSP #1 0/3 REPAINT | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 000/003 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-16 | 2024-02-16 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.850948 | 35.3766 | ETL.2810 | 40650851 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 12 | 2019-04-08 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497177 | Q2 | T2 EI HAT CREEK #1-WSTWD 22/436 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 022/436 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-17 | 2020-02-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.239995 | 40.713 | ETL.7030 | 40770741 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497262 | Q2 | T2 EI HAT CRK #1-WSTWD 22/431 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 022/431 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-02-17 | 2020-02-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.243248 | 40.7159 | ETL.7030 | 40876186 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497263 | Q2 | T2 EI HT CRK #1-WSTWD 24/477 RPR CRSW | 43736797 | HAT CREEK #1-WESTWOOD | 024/477 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-17 | 2020-02-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.213393 | 40.6886 | ETL.7030 | 40825584 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497382 | Not Scheduled | T2NT EI RND MTN-TBL M #2 74/305 INS MRKS | 44302501 | ROUND MTN-TABLE MTN #2 | 074/305 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-17 | 2020-02-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.74984 | 39.7443 | ETL.6070 | 40765376 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497461 | Q2 | T2 EI OLEUM-G #2 0/9 RPL INSS | 31508069 | OLEUM-G #2 | 000/009 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-17 | 2021-05-31 | 2021-05-15 | 2021-05-15 | 2021-05-15 | 2021-05-15 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.2388294 | 38.0393 | ETL.3160 | 40893373 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497562 | Feb | T2 EI PITTSBURG-CLMB STL 3/19 REPL HRDS | 44609766 | PITTSBURG-COLUMBIA STEEL | 003/019 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-17 | 2020-02-17 |  |  | 2021-02-17 | 2021-02-17 |  | Hanger Plates Within Tag; separate |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.903161 | 37.9932 | ETL.3300 | 40872692 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116497841 | Q2 | T2 EI HT CRK #1-WSTWD 36/695 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 036/695 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-17 | 2020-02-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.07107 | 40.5659 | ETL.7030 | 40751788 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498015 | Q2 | T2 EI HAT CREEK #1-WSTWD 23/444 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/444 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.234585 | 40.708 | ETL.7030 | 40656890 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498023 | Q2 | T2 EI HAT CREEK #1-WSTWD 23/442 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/442 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.236194 | 40.7095 | ETL.7030 | 40592097 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498084 | Q2 | T2 EI HAT CREEK #1-WSTWD 23/445 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/445 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.233885 | 40.7074 | ETL.7030 | 40770862 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498091 | Q2 | T2 EI HAT CRK #1-WSTWD 17/328 RPR SPLC | 43736796 | HAT CREEK #1-WESTWOOD | 017/328 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.313593 | 40.7735 | ETL.7030 | 40676295 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498094 | Not Scheduled | T2 EI HAT CREEK #1-WSTWD 23/447 CANCEL | 43736797 | HAT CREEK #1-WESTWOOD | 023/447 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.232648 | 40.7062 | ETL.7030 | 40827485 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498129 | Q2 | T2 EI HAT CREEK #1-WSTWD 19/383 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 019/383 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.276137 | 40.7431 | ETL.7030 | 40816132 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498148 | Q2 | T2 EI RND MT-TBL MT #2 074/304 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 074/304 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-18 | 2020-02-18 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.751526 | 39.7474 | ETL.6070 | 40756244 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498207 | Q2 | T2 EI HAT CRK #1-WSTWD 23/454 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/454 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.22812 | 40.7021 | ETL.7030 | 40656892 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498208 | Q2 | T2 EI HAT CREEK #1-WSTWD 23/448 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/448 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.232052 | 40.7056 | ETL.7030 | 40816136 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498262 | Not Scheduled | T2 EI ROUND MTN-TM #1 74/304 RPL GYMK | 44305409 | ROUND MTN-TABLE MTN #1 | 074/304 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-18 | 2020-02-18 | [5 empty] | TLN/TLQ error |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.752028 | 39.7473 | ETL.6060 | 40764703 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498477 | Q2 | T2 EI HT CRK #1-WSTWD 35/685 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 035/685 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-17 | 2020-02-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.076825 | 40.5721 | ETL.7030 | 40758921 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498502 | Q2 | T2 EI HT CRK #1-WSTWD 26/512 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 026/512 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.192853 | 40.6685 | ETL.7030 | 40759206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498503 | Q2 | T2 EI HT CRK #1-WSTWD 26/511 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 026/511 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.19338 | 40.6692 | ETL.7030 | 40667950 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498621 | Q2 | T2 EI HAT CRK #1-WSTWD 23/447 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 023/447 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.232648 | 40.7062 | ETL.7030 | 40827485 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116498835 | Not Scheduled | T2 DI BAHIA-MORAGA 16/93 INS HRDT | 43683410 | BAHIA-MORAGA | 016/093 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-15 | 2020-02-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203898 | 37.9596 | ETL.4340 | 40740005 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116499456 | Not Scheduled | T2 EI JEFRSON-HLSDL JCT 0/3 RPR INSS | 43752125 | JEFFERSON-HILLSDALE JCT | 000/003 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.287319 | 37.4596 | ETL.7190 | 40653159 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116499660 | Not Scheduled | T2 EI JEFRSON-HLSDLE JCT 0/4 RPR INSS | 43752125 | JEFFERSON-HILLSDALE JCT | 000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.287928 | 37.4614 | ETL.7190 | 40755213 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116499786 | Not Scheduled | T2 EI JEFFRSON-HLLSDLE JCT 1/7 RPR INSS | 43752125 | JEFFERSON-HILLSDALE JCT | 001/007 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.291131 | 37.4703 | ETL.7190 | 40812553 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116499877 | Not Scheduled | T3 EI PIT #1-COTTONWOOD 028/234 PNT STRT | 43735854 | PIT #1-COTTONWOOD | 028/234 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-19 | 2023-02-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950614 | 40.7771 | ETL.5390 | 40759682 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-03-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116499936 | Q2 | EI HAT CRK #1-WESTWD 048/935 RPL POLE | 31426976 | HAT CREEK #1-WESTWOOD | 048/935 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-19 | 2020-02-19 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.018443 | 40.3973 | ETL.7030 | 40701262 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500139 | Not Scheduled | T2 EI JEFFERSON-STANFORD 0/05 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | 2020-08-26 | [6 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.280174 | 37.4598 | ETL.7220 | 40767172 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 | EPNP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500147 | Not Scheduled | T2 EI JEFFERSON-STANFORD 0/05 RPL ANCW | 31504281 | JEFFERSON-STANFORD (NO FLY) | 000/005 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | 2020-08-26 | [6 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.280174 | 37.4598 | ETL.7220 | 40767172 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 6 | EPNP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500328 | Not Scheduled | T2 EI JEFRSON-HLSDL JCT 0/5 REPL INSS | 31453027 | JEFFERSON-HILLSDALE JCT | 000/005 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2021-05-31 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.2887529 | 37.464 | ETL.7190 | 40783987 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 | SMCPD | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-05-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500338 | Not Scheduled | T2 EI JEFRSON-HLSDL JCT 0/5 REPL HRDS | 44218329 | JEFFERSON-HILLSDALE JCT | 000/005 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.28874 | 37.464 | ETL.7190 | 40755137 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500402 | Not Scheduled | T2 EI CRBRY S S-RND MTN 27/220A REPAINT | 43897848 | CARBERRY SW STA-ROUND MTN | 027/220A | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-19 | 2024-02-19 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.936552 | 40.7924 | ETL.5410 | 40577033 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500410 | Not Scheduled | T2 EI CHRISTIE-FRANKLIN #2 0/12 RPR GYWW | 43753117 | CHRISTIE-FRANKLIN #2 | 000/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-16 | 2020-02-16 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.225912 | 38.0041 | ETL.6360 | 40581068 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500450 | Feb | T2 EI SMRTVLLE-NICLS #2 1/25 RPR GYWS | 43760145 | SMARTVILLE-NICOLAUS #2 | 001/025 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-16 | 2020-02-16 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.301457 | 39.1925 | ETL.8000 | 44177820 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500563 | Not Scheduled | T2 EI ROUND MTN-TM #1 74/305 RPL GYMK | 44305409 | ROUND MTN-TABLE MTN #1 | 074/305 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-19 | 2020-02-19 | [5 empty] | TLN/TLQ error |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.750201 | 39.7439 | ETL.6060 | 40756160 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500583 | Not Scheduled | T2 EI MALIN-ROUND MTN#2 61/305 REPAINT | 43621093 | MALIN-ROUND MTN #2 | 061/305 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-02-19 | 2024-02-19 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.663711 | 41.1947 | ETL.6020 | 40759606 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500845 | Mar | T2 EI POE-RIO OSO 027/178 RPR INSS | 43737420 | POE-RIO OSO | 027/178 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-19 | 2020-02-19 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.522617 | 39.601 | ETL.5540 | 40867261 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116500940 | Not Scheduled | EI OLEUM-G #1 000/005 RPNT TWR | 43752220 | OLEUM-G #1 | 000/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-19 | 2025-02-19 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.249283 | 38.0411 | ETL.3150 | 40746013 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116501725 | Feb | T2 PF SMARTVILLE-NICLS #2 2/46 RPR GYWW | 43760146 | SMARTVILLE-NICOLAUS #2 | 002/046 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 |  |  | 2021-02-25 | 2021-02-24 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.308226 | 39.1787 | ETL.8000 | 44179467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116501853 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 61/306 REPAINT | 43621093 | MALIN-ROUND MTN #2 | 061/306 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-02-19 | 2024-02-19 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.665552 | 41.1924 | ETL.6020 | 40818808 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116502480 | Not Scheduled | T2 DI CARIBOU-PALERMO 006/054 RPL HRDT | 44069597 | CARIBOU-PALERMO | 006/054 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-13 | 2020-02-13 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540063 | 39.5414 | ETL.3190 | 40758611 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116502749 | Not Scheduled | T2 EI JEFFERSON-STNFRD 2/47 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/047 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-19 | 2020-02-19 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256905 | 37.465 | ETL.7220 | 40694686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116503045 | Q2 | T2 EI HAT CRK #1-WESTWD 040/780 RPL SPLW | 43736798 | HAT CREEK #1-WESTWOOD | 040/780 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-19 | 2020-02-19 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.030857 | 40.5095 | ETL.7030 | 40770769 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116503079 | Q2 | T2 EI HAT CRK #1-WESTWD 040/780 REFRAME | 31471926 | HAT CREEK #1-WESTWOOD | 040/780 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-19 | 2020-02-19 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.0308704 | 40.5095 | ETL.7030 | 40802346 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116503414 | Q2 | EI HAT CRK #1-WSTWD 048/925 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 048/925 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-20 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.019675 | 40.4042 | ETL.7030 | 40675746 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116503497 | Q2 | EI HAT CRK #1-WSTWD 048/924 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 048/924 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-02-20 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow. FSR 7/2020 | '-121.019768 | 40.405 | ETL.7030 | 40591894 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116503520 | Q2 | EI HAT CRK #1-WSTWD 048/924 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 048/924 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-02-20 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 7/2020 | '-121.019768 | 40.405 | ETL.7030 | 40591894 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116503581 | Not Scheduled | T2 EI LOS ESTEROS-MET 003/016 PAINT | 43753289 | LOS ESTEROS-METCALF | 003/016 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-20 | 2020-02-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.724722 | 37.27 | ETL.5353 | 40811285 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116503745 | Mar | T2 EI MONTA VISTA-J #1 06/24 RPL INSS | 31443073 | MONTA VISTA-JEFFERSON #1 | 006/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-20 | 2021-05-31 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.1760102 | 37.3307 | ETL.5220 | 40782415 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116503959 | Q2 | EI HAT CRK #1-WSTWD 049/944 COA | 43736798 | HAT CREEK #1-WESTWOOD | 049/944 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-02-20 | 2020-02-20 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020. Work is complete. Tag to be cancelled | '-121.017228 | 40.3902 | ETL.7030 | 40599863 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116504082 | Q2 | EI STNSLS-NWRK #1 092/613 RPR STR |  | STANISLAUS-NEWARK #1 (12KV) | 092/613 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-20 | 2020-02-20 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.87434 | 37.5814 | ETL.3850 | 40669429 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 | SFPUC | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  | Not Released | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116504154 | Mar | T2 EI BELDEN TAP 000/001C RPR CONS | 43742043 | BELDEN TAP | 000/001C | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-20 | 2020-02-20 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.250771 | 40.0077 | ETL.4441 | 43198034 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116504580 | Q2 | T2 EI OLEUM-G #1 001/012 RPR FOND | 43752139 | OLEUM-G #1 | 001/012 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-20 | 2024-02-20 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.234041 | 38.0362 | ETL.3150 | 40688523 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116504946 | Not Scheduled | T2 EI TESLA-METCALF 008/033 RPR SPLS | 43753282 | TESLA-METCALF | 008/033 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-20 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.593192 | 37.5918 | ETL.6110 | 40659433 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116504954 | Q2 | T2 EI CTNWD-BNTN #2 014/125 RPR GYWW | 43939217 | COTTONWOOD-BENTON #2 | 014/125 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-20 | 2020-02-20 |  |  | 2021-06-25 | 2021-06-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.39459 | 40.56 | ETL.6650 | 44560580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116505057 | Not Scheduled | HAMMER-COUNTRY CLUB C3/69 STUB POLE | 43691346 | HAMMER-COUNTRY CLUB (NO FLY) | C003/069 | GAR | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-28 | 2019-11-28 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.286381 | 37.9914 | ETL.7010 | 40652366 | Structure-Wood | Rotten | Stub | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 586 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  | 2019-11-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 116505059 | Not Scheduled | HAMMER-COUNTRY CLUB B3/76 STUB POLE | 43691346 | HAMMER-COUNTRY CLUB (NO FLY) | B003/076 | GAR | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-11-26 | 2019-11-26 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.27947 | 38.0307 | ETL.7010 | 42634555 | Structure-Wood | Rotten | Stub | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 586 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 116505376 | Q2 | EI HAT CRK #1-WSTWD 048/924 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 048/924 | 93E | E | Pre-2020_(2) High fire spread TD |  | 2019-02-20 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.0197813 | 40.405 | ETL.7030 | 40617470 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116577574 | Q2 | T2 EI PIT #7 TAP 003/026 RPR GYWW | 43877044 | PIT #7 TAP | 003/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-20 | 2020-02-20 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553659 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116577965 | Not Scheduled | T3 DI CRBOU PLRMO :32/260 RPR STRT | 43725390 | CARIBOU-PALERMO | :032/260 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.474651 | 39.7549 | ETL.3190 | 40599300 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578064 | Q2 | T2 EI KONOCTI-MIDDLETOWN 013/004 INSW | 43761672 | KONOCTI-MIDDLETOWN | 013/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.590443 | 38.7663 | ETL.6380 | 40769709 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578116 | Q2 | T2 EI KONOCTI-MIDDLETWN 015/009 RPR STRW | 43761672 | KONOCTI-MIDDLETOWN | 015/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.56713 | 38.7951 | ETL.6380 | 40875482 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578123 | Not Scheduled | T3 DI CRBOU PLRMO :034/274 SPLS RPL | 43659205 | CARIBOU-PALERMO | :034/274 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-14 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478839 | 39.7286 | ETL.3190 | 40758638 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578126 | Not Scheduled | T3 DI CRBOU PLRMO :034/274 STRT SOIL |  | CARIBOU-PALERMO | :034/274 |  | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-14 | 2019-08-14 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478839 | 39.7286 | ETL.3190 | 40758638 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578422 | Not Scheduled | T2 EI VLLY SPRINGS-CLAY 006/085 RPR GYWW | 43687883 | VALLEY SPRINGS-CLAY | 006/085 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833081 | 38.2099 | ETL.8264 | 40904721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578484 | Q2 | T2 EI TESLA-METCALF 032/133 RPR STRT |  | TESLA-METCALF | 032/133 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-30 | 2021-06-28 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.726393 | 37.2656 | ETL.6110 | 40651772 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578495 | Mar | T2 EI KONOCTI-MIDDLETOWN 016/013 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 016/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | 2021-03-01 | 2021-03-04 | 2021-03-03 | 2021-03-03 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573239 | 38.8077 | ETL.6380 | 40650686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578509 | Not Scheduled | T2 EI DRM-HGGNS 24/186 INSTL HRDT | 43687117 | DRUM-HIGGINS | 024/186 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.122275 | 39.0941 | ETL.4393 | 40594579 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578542 | Mar | T2 EI KONOCTI-MIDDLETOWN 016/014 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 016/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573231 | 38.8085 | ETL.6380 | 40752528 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578685 | Q2 | T2 EI BRY SW ST-RND MTN 26/211 RPL INSS | 31502961 | CARBERRY SW STA-ROUND MTN | 026/211 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2022-02-21 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.9189922 | 40.797 | ETL.5410 | 40621072 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578800 | Q2 | EI HAT CREEK #1-WESTWD 049/957 RPR SPLW | 43736798 | HAT CREEK #1-WESTWOOD | 049/957 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.015575 | 40.3804 | ETL.7030 | 40656682 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578809 | Q2 | EI HAT CREEK #1-WESTWD 049/956 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 049/956 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.01565 | 40.3809 | ETL.7030 | 40701264 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578908 | Not Scheduled | T2 EI CARIBOU-PALERMO :09/070 BENT MEMB | 44059014 | CARIBOU-PALERMO | :009/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.254842 | 40.0061 | ETL.3190 | 40910312 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578969 | Q2 | EI HAT CREEK #1-WESTWD 049/951 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 049/951 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.01634 | 40.3847 | ETL.7030 | 40825620 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578989 | Not Scheduled | T3 EI SAN RAMON-MORAGA 002/014 REPAINT | 43715783 | SAN RAMON-MORAGA | 002/014 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-21 | 2022-02-21 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-121.971073 | 37.7239 | ETL.5660 | 40857926 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116578995 | Mar | T2 EI PLACER-DEL MAR 002/058 RPL POLE | 31498224 | PLACER-DEL MAR | 002/058 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-18 | 2020-02-18 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117367 | 38.8744 | ETL.7800 | 40815283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116579007 | Q2 | T2 EI TESLA-METCALF 008/031 RPR STRT |  | TESLA-METCALF | 008/031 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.591356 | 37.5981 | ETL.6110 | 40581119 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116579112 | Not Scheduled | T2 EI CARIBOU-PALERMO :004/033 BENT MEMB | 44070463 | CARIBOU-PALERMO | :004/033 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.208362 | 40.051 | ETL.3190 | 40910277 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116579750 | Q2 | T2 EI BRY SW ST-RND MTN 25/204 RPL INSS | 31502961 | CARBERRY SW STA-ROUND MTN | 025/204 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2022-02-21 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.9028642 | 40.8013 | ETL.5410 | 40785136 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116579950 | Mar | T2 EI KONOCTI-MIDDLETOWN 014/004 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 014/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.580041 | 38.7774 | ETL.6380 | 44370572 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580010 | Q4 | T3 EI KESWICK-TRINITY 005/072 INST GYWW | 43661466 | KESWICK-TRINITY | 005/072 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-21 | 2019-08-21 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580455 | Q2 | T2 EI LAKEVILLE #1 009/000 RPR GYWW | 44310678 | LAKEVILLE #1 | 009/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-01 | 2021-05-28 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.551883 | 38.3676 | ETL.7360 | 40588835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580587 | Q2 | T2 EI MALIN-RND MTN #2 060/302 INST HRDT | 43754878 | MALIN-ROUND MTN #2 | 060/302 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.657825 | 41.2019 | ETL.6020 | 40677663 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580613 | Q2 | T2 EI MALIN-RND MTN #2 060/303 RPR COND | 43621093 | MALIN-ROUND MTN #2 | 060/303 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.65996 | 41.1993 | ETL.6020 | 40663113 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580712 | Q2 | EI HAT CREEK #1-WESTWD 049/952 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 049/952 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.016208 | 40.384 | ETL.7030 | 40868255 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580714 | Q2 | T2 EI MLIN-ROUND MTN #2 062/311 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 062/311 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.67461 | 41.1813 | ETL.6020 | 40619337 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116580717 | Q2 | EI HAT CREEK #1-WESTWD 047/912 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 047/912 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-21 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.021323 | 40.414 | ETL.7030 | 40877513 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116580811 | Q2 | T2 EI MALIN ROUND 060/301 RPL HRDT | 31439323 | MALIN-ROUND MTN #2 | 060/301 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-21 | 2020-02-21 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6561256 | 41.2041 | ETL.6020 | 40619336 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116581549 | Not Scheduled | T2 EI CARIBOU-PALERMO :09/070 RPR FOND | 44059014 | CARIBOU-PALERMO | :009/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.254842 | 40.0061 | ETL.3190 | 40910312 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116581610 | Q3 | T2 EI CARIBOU #2 018/000 RPL SPLW | 43742136 | CARIBOU #2 | 018/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061181 | 40.0195 | ETL.6280 | 40599711 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116582733 | Not Scheduled | T2 EI ROUND MTN-TM #1 33/160 RPR STRT | 43848514 | ROUND MTN-TABLE MTN #1 | 033/160 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.934379 | 40.3267 | ETL.6060 | 40601337 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116582818 | Not Scheduled | T3 EI FULTON-PUEBLO 30/147 REPAINT | 43720980 | FULTON-PUEBLO | 030/147 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-22 | 2022-02-22 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.537064 | 38.4876 | ETL.1600 | 40810374 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-25 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116582853 | Q2 | T2 EI KNCT-MDDLTWN 22/6 RPR GYWS | 43760955 | KONOCTI-MIDDLETOWN | 022/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.737662 | 38.9303 | ETL.6380 | 44244858 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116582859 | Not Scheduled | T2 EI DBL-MDWY #3 12/48 RPR INSS | 43756129 | DIABLO-MIDWAY #3 | 012/048 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.634937 | 35.1789 | ETL.5980 | 40863917 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116582881 | Not Scheduled | T2 EI GNC-LT-SSLT #1 6/47 PNT | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/047 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495152 | 37.9877 | ETL.7160 | 40601837 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116584028 | Not Scheduled | T2 EI GNC-LT-SSLT #1 6/48 PNT | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/048 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-22 | 2023-02-22 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495136 | 37.987 | ETL.7160 | 40701449 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116584972 | Feb | T2 EI DRUM-HIGGINS 17/150 REPL SPLS | 43738143 | DRUM-HIGGINS | 017/150 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.024284 | 39.1341 | ETL.4393 | 40913046 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116586307 | Not Scheduled | T2 EI DBL-MDWY #3 19/77 RPL INSS | 31456686 | DIABLO-MIDWAY #3 | 019/077 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.528026 | 35.174 | ETL.5980 | 40836750 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116586702 | Not Scheduled | T2 EI IGNCIO-ALT-SSLITO #1 6/44 PNT MEMB | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/044 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-22 | 2022-02-22 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495338 | 37.9969 | ETL.7160 | 40864746 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116586703 | Not Scheduled | EI NEWARK-LIVERMORE 005/040 PNT STRT | 43752137 | NEWARK-LIVERMORE | 005/040 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-22 | 2020-02-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.894996 | 37.5431 | ETL.7660 | 40613171 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116586937 | Not Scheduled | T2 EI RND MTN-TBL MTN #1 32/157 BENT STL | 43848514 | ROUND MTN-TABLE MTN #1 | 032/157 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.934125 | 40.3358 | ETL.6060 | 40813092 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587108 | Q2 | T2 EI RND MTN-TBL MTN#2 67/278 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 067/278 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-22 | 2020-02-22 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.798731 | 39.8518 | ETL.6070 | 40865966 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587174 | Not Scheduled | T2 EI TIGER CRK-VALY 12/97 SPRGS REPAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 012/097 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.662218 | 38.3464 | ETL.5790 | 40858494 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587255 | Not Scheduled | T2 EI RNDMTN-TBLMTN#1 067/278 INS GMKT | 43848514 | ROUND MTN-TABLE MTN #1 | 067/278 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-121.799305 | 39.8519 | ETL.6060 | 40865978 | Hardware-Tower | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587355 | Mar | T2 EI KNCT-MDDLTWN 15/8 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 015/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.566537 | 38.7943 | ETL.6380 | 44141955 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587410 | Not Scheduled | T2 EI IGNACIO-ALTO-SAUS #1 6/49 PNT TWR | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/049 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495096 | 37.9847 | ETL.7160 | 40668225 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587457 | Q2 | T2 EI KNCT-MDDLTWN 15/1 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 015/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573546 | 38.7841 | ETL.6380 | 44370574 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587513 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 14/055 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 014/055 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.607601 | 35.1675 | ETL.5970 | 40753809 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-05-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587715 | Not Scheduled | T2 EI RND MT-TBL MT #2 72/297 REPAINT | 44302501 | ROUND MTN-TABLE MTN #2 | 072/297 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.762773 | 39.7684 | ETL.6070 | 40813483 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587806 | Not Scheduled | T2 EI VINYRD-NEWRK 38/223A RPL HRDT |  | VINEYARD-NEWARK | 038/223A | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-22 | 2020-02-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.895761 | 37.5431 | ETL.4536 | 41196096 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116587817 | Not Scheduled | T2 EI VINYRD-NEWRK 38/223A PNT STRT | 43753288 | VINEYARD-NEWARK | 038/223A | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-22 | 2020-02-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.895761 | 37.5431 | ETL.4536 | 41196096 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116588326 | Not Scheduled | T2 EI TIGER CRK-ELECTRA 9/70 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 009/070 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.634276 | 38.3898 | ETL.5780 | 40591468 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116588515 | Feb | T2 EI RO DL JCT-BRDGE 027/004 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 027/004 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.9838 | 40.4935 | ETL.7850 | 40769406 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116588630 | Feb | T2 EI RO DLL JCT-BDGVLE 027/003 RPR ANCS | 43749702 | RIO DELL JCT-BRIDGEVILLE | 027/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.985802 | 40.4941 | ETL.7850 | 40648546 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-07-15 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116588698 | Feb | T2 EI RO DLL JCT-BRDGV027/ 005 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 027/005 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.982194 | 40.493 | ETL.7850 | 40750366 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116588744 | Feb | T2 EI RO DL JCT-BRDGVLE 027/007 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 027/007 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.97713 | 40.4914 | ETL.7850 | 40824509 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116588818 | Q2 | HAT CREEK #1-WESTWOOD 46/898 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 046/898 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.023102 | 40.4243 | ETL.7030 | 40758929 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116588903 | Q2 | EI HT CRK #1-WSTWD 46/903 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 046/903 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022455 | 40.4207 | ETL.7030 | 40876215 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116588904 | Q2 | EI HT CRK #1-WSTWD 47/906 RPL SPLW | 43736798 | HAT CREEK #1-WESTWOOD | 047/906 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 7/2020 | '-121.022087 | 40.4185 | ETL.7030 | 40675741 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116588910 | Q2 | DI HT CRK #1-WSTWD 47/904 REPL POLE | 31475080 | HAT CREEK #1-WESTWOOD | 047/904 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022305 | 40.4199 | ETL.7030 | 40617035 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116589420 | Not Scheduled | T2 EI PTSBRG-SN MTEO 020/081 RPR FOND | 44238800 | PITTSBURG-SAN MATEO | 020/081 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.925992 | 37.7526 | ETL.5463 | 40805085 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589508 | Not Scheduled | T2 EI LS ESTRS-MTCLF 013/061 RPR FOND |  | LOS ESTEROS-METCALF | 013/061 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.777067 | 37.399 | ETL.5353 | 40587062 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589589 | Not Scheduled | EI LAS POSITAS-NEWARK 14/092 REPAINT | 43753291 | LAS POSITAS-NEWARK | 014/092 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-23 | 2024-02-23 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.89351 | 37.5459 | ETL.4980 | 40593918 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589664 | Not Scheduled | T2 EI DIABLO-MIDWAY#2 18/071 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 018/071 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.54761 | 35.1746 | ETL.5970 | 40593632 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-05-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589702 | Not Scheduled | T2 EI RND MTN-TM #2 059/250 PAINT TWR | 44305720 | ROUND MTN-TABLE MTN #2 | 059/250 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.845287 | 39.9619 | ETL.6070 | 40601383 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589772 | Not Scheduled | EI NEWARK-LIVERMORE 5/041 REPAINT | 43752137 | NEWARK-LIVERMORE | 005/041 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-23 | 2020-02-23 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.892899 | 37.5455 | ETL.7660 | 40580687 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589965 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 021/088A RPL SPCS | 43756129 | DIABLO-MIDWAY #3 | 021/088A | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.477877 | 35.1638 | ETL.5980 | 40577051 | Spacer-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589966 | Not Scheduled | T2 EI RND MTN-TM #2 059/251 PAINT TWR | 44305720 | ROUND MTN-TABLE MTN #2 | 059/251 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.842922 | 39.9563 | ETL.6070 | 40592714 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116589985 | Not Scheduled | T2 EI QNTO SW STA-WSTLY 24/110 INST HRDT | 43727740 | LOS BANOS-WESTLEY | 024/110 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-23 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.215521 | 37.489 | ETL.5070 | 40591723 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590125 | Q2 | T2 EI COLGATE-PALERMO 17/341 RPL INSW | 43728970 | COLGATE-PALERMO | 017/341 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.434739 | 39.4361 | ETL.6500 | 40824128 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590199 | Q3 | T2 EI TESLA-NEWARK #1 022/115 RPR FOND | 43753786 | TESLA-NEWARK #1 | 022/115 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2020-02-23 |  |  | 2021-07-17 | 2021-07-12 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.892251 | 37.5459 | ETL.5720 | 40761984 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590252 | Mar | T3 EI DIABLO UNIT #2 005/006 RPR GYWS | 43921577 | DIABLO UNIT #2 (NF) | 005/006 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-23 | 2019-08-23 |  |  | 2021-03-15 | 2021-03-01 |  |  | Tower guy | TR3 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints; tag scheduled for 10/8-13 | '-120.85021 | 35.2134 | ETL.5950 | 40819287 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 1 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590298 | Not Scheduled | T2 EI RND MTN-TBLE MTN#1 33/159 INS GMKT | 43848514 | ROUND MTN-TABLE MTN #1 | 033/159 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-21 | 2020-02-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-121.934297 | 40.3297 | ETL.6060 | 40868413 | Hardware-Tower | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590352 | Not Scheduled | T2 EI QNTO SW STA-WSTLY 25/112 RPR FOND | 43727740 | LOS BANOS-WESTLEY | 025/112 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-23 | 2024-02-23 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.21049 | 37.4796 | ETL.5070 | 40662928 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590382 | Not Scheduled | T2 EI DIABLO-MIDWAY#2 17/70 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 017/070 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.549816 | 35.1746 | ETL.5970 | 40592838 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-05-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590396 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 29/118 RPR INSS | 43756129 | DIABLO-MIDWAY #3 | 029/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.348391 | 35.1675 | ETL.5980 | 40871725 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590429 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 29/119 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 029/119 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.343918 | 35.1673 | ETL.5970 | 40863567 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-05-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590472 | Not Scheduled | T2 EI PITTSBURG-TESLA #1 10/47 RPR FOND | 44238805 | PITTSBURG-TESLA #1 | 010/047 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-23 | 2020-02-23 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-121.815699 | 37.9248 | ETL.5510 | 40804252 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116590487 | Not Scheduled | T2 EI RND MTN-TBL MTN#2 70/288 RPR CONS | 44305720 | ROUND MTN-TABLE MTN #2 | 070/288 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.780121 | 39.8077 | ETL.6070 | 40871367 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116590528 | Not Scheduled | EI NEWARK-LIVERMORE 10/063 REPAINT | 43752137 | NEWARK-LIVERMORE | 010/063 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-23 | 2022-02-23 | [8 empty] | <15D | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.845808 | 37.5933 | ETL.7660 | 40644060 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116590695 | Not Scheduled | T2 EI DIABLO-MIDWAY#3 18/071 RPLC INSS | 43756129 | DIABLO-MIDWAY #3 | 018/071 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2020-02-23 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.546895 | 35.1752 | ETL.5980 | 40612740 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116591833 | Mar | EI KILARC-DESCHUTES A25/539 RPL STRW | 31440586 | KILARC-DESCHUTES | A025/539 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-22 | 2020-02-22 |  |  | 2021-03-26 | 2021-03-01 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.293359 | 40.5711 | ETL.7300 | 41118632 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 116591964 | Not Scheduled | T2 EI GNC-LT-SSLT #1 5/42 RPL HRDT | 43693608 | IGNACIO-ALTO-SAUSALITO #1 | 005/042 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.498316 | 38.0045 | ETL.7160 | 40827694 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592597 | Not Scheduled | T3 EI TGR CRK-LCTR 008/062 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 008/062 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-25 | 2019-08-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.617524 | 38.4018 | ETL.5780 | 40681643 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592628 | Feb | T2 EI RND MTN-CTTNWD #3 41/348 RPR INSS | 44624619 | ROUND MTN-COTTONWOOD #3 | 041/348 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.081169 | 40.6209 | ETL.5650 | 40873283 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592644 | Q2 | T2 EI KNCT-MDDLTWN 027/006 RPL PL | 31490901 | KONOCTI-MIDDLETOWN | 027/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.655546 | 38.9071 | ETL.6380 | 40826576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592661 | Not Scheduled | T3 EI TGR CRK-VLY SPG 007/061 REPAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 007/061 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-25 | 2019-08-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.617342 | 38.4016 | ETL.5790 | 40681626 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592913 | Not Scheduled | T3 EI TGR CRK-VLY SPG 008/063 REPAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 008/063 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-25 | 2019-08-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.621343 | 38.3988 | ETL.5790 | 40753070 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592932 | Not Scheduled | T3 EI TGR CRK-LCTR 008/064 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 008/064 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-25 | 2019-08-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.621524 | 38.3989 | ETL.5780 | 40752893 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592938 | Not Scheduled | EI JFFRSON-HLLSDLE JCT-007/044 RPL INSS | 31453027 | JEFFERSON-HILLSDALE JCT | 007/044 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-25 | 2021-05-31 | 2020-07-13 | 2020-07-17 | [6 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-122.3647585 | 37.5443 | ETL.7190 | 40793293 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 5 | SFPUC (4) | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116592958 | Not Scheduled | T3 EI TGR CRK-LCTR 008/063 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 008/063 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-25 | 2019-08-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.620505 | 38.3997 | ETL.5780 | 40651012 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593024 | Not Scheduled | T2 EI JEFFERSON-HILLSDLE J 6/35 RPL DAMP | 43752125 | JEFFERSON-HILLSDALE JCT | 006/035 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-25 | 2020-02-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.356591 | 37.5248 | ETL.7190 | 40755149 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 5 | SFPUC (4) | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593026 | Q2 | T2 EI KNCTI-MDDLTWN 28/08 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 028/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.632127 | 38.9123 | ETL.6380 | 40876780 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593074 | Q2 | T3 EI KNCTI-MDDLTWN 28/03L RPR GYWW | 43749609 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235467 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593253 | Q2 | T2 EI KNCT-MDDLTWN 024/012 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 024/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.617814 | 38.9108 | ETL.6380 | 40661672 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593360 | Not Scheduled | T2 EI JFFRSN-HILLSDL JCT 06/35E PNT STRS | 43752125 | JEFFERSON-HILLSDALE JCT | 006/035E | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-25 | 2020-02-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.35663 | 37.5251 | ETL.7190 | 44384034 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593816 | Not Scheduled | T2 EI TESLA-METCALF 032/136 INS HRDT |  | TESLA-METCALF | 032/136 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-23 | 2024-02-23 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.730295 | 37.2552 | ETL.6110 | 40818974 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116593822 | Q2 | T2 EI TESLA-METCALF 033/137 RPL HRDT |  | TESLA-METCALF | 033/137 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-23 | 2021-05-31 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.732281 | 37.2492 | ETL.6110 | 40817822 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116594053 | Feb | T2 EI RND MTN-CTTNWD #3 48/416 RPR INSS | 44624619 | ROUND MTN-COTTONWOOD #3 | 048/416 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147551 | 40.541 | ETL.5650 | 40816944 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116594366 | Feb | T2 EI RND MTN-CTTNWD #3 44/379 RPL HRDS | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/379 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-18 | 2020-02-18 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.111416 | 40.5845 | ETL.5650 | 40858192 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116594602 | Not Scheduled | T2 EI VLY SPRNGS-CLY 007/108 RPR GND | 43712679 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2020-02-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116594721 | Mar | DI POE-RIO OSO 36/241 INS HRDS | 43737421 | POE-RIO OSO | 036/241 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-14 | 2020-02-14 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.525947 | 39.4671 | ETL.5540 | 40596663 | Hardware-Steel | Missing | Install | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116595458 | Q2 | T2 EI HT CRK #1-WSTWD 046/884 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 046/884 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2020-02-22 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . | '-121.023065 | 40.4339 | ETL.7030 | 40589877 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116595578 | Not Scheduled | T3 EI DRM-HGGNS 008/084 PNT STRT | 43738143 | DRUM-HIGGINS | 008/084 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-25 | 2019-08-25 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.884168 | 39.1703 | ETL.4393 | 40751900 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116607344 | Not Scheduled | T2 EI VLLEY SPRNGS-CLY 7/106 RPL ANCH | 31426625 | VALLEY SPRINGS-CLAY | 007/106 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-26 | 2020-02-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8421 | 38.2282 | ETL.8264 | 40904739 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116607442 | Q2 | T2 EI HT CRK #1-WSTWD 045/874 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 045/874 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . | '-121.022883 | 40.4423 | ETL.7030 | 40876260 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116607744 | Not Scheduled | T2 ELECTRA-BELLOTA 000/001 INS GMKW | 43727726 | ELECTRA-BELLOTA | 000/001 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-26 | 2020-02-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.66894 | 38.3315 | ETL.4670 | 40911503 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116608191 | Mar | T2 EI EAGLE ROCK CORTINA :17/0 INS GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/000 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-02-22 | 2020-02-22 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609974 | 38.967 | ETL.1470 | 41176364 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116608356 | Q2 | T2 EI TESLA-METCALF 21/89 RPL ANCS |  | TESLA-METCALF | 021/089 |  | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-26 | 2020-02-26 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.659318 | 37.4123 | ETL.6110 | 40869059 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  | Y - 3 | 2019-06-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Q2 |  |  | 2019-06-04 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116608425 | Feb | T3 EI ORO FINO TAP 0/1 INS GYWW | 43758390 | ORO FINO TAP | 000/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-02-19 | 2019-08-19 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.62919 | 39.8652 | ETL.6721 | 40591915 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116609171 | Not Scheduled | T2 EI MLLBRE-SNTHLN 014/095 RPNT STRT | 43753781 | MILLBRAE-SNEATH LANE | 014/095 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-26 | 2024-02-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.44173 | 37.6175 | ETL.7570 | 44384516 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116609584 | Not Scheduled | T3 EI DRUM-RIO OSO #1 1/13 CANCEL | 43746396 | DRUM-RIO OSO #1 | 001/013 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-16 | 2019-08-16 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791076 | 39.2564 | ETL.1420 | 40654181 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116609858 | Not Scheduled | T2 EI JEFFERSON-STANFORD 1/28 ANTI-SPLIT | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/028 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-25 | 2020-02-25 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.266038 | 37.4618 | ETL.7220 | 40824885 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116609932 | Not Scheduled | T2 EI VLLY SPRINGS-CLAY 006/087 RPR GYWW | 43712893 | VALLEY SPRINGS-CLAY | 006/087 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833763 | 38.2121 | ETL.8264 | 40904722 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116611958 | Q2 | T2 EI CORDELIA #2 TAP 3/67 RPR GYWW | 43743931 | CORDELIA #2 TAP | 003/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-22 | 2020-02-22 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.154242 | 38.2508 | ETL.8184 | 40599323 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116614661 | Q2 | T2 EI KONOCTI-MIDDLE 025/005 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 025/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.689236 | 38.9149 | ETL.6380 | 40750138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116614807 | Feb | T2 EI PTTSBURG-SN MATEO 006/028 RPL INSS | 31457508 | PITTSBURG-SAN MATEO | 006/028 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-27 | 2020-02-27 |  |  | 2021-02-16 | 2021-02-16 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.8929165 | 37.9538 | ETL.5463 | 40671963 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116615248 | Q2 | T2 EI BALCH-SANGER 006/037 FOOTINGS | 43709595 | BALCH-SANGER | 006/037 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-13 | 2020-02-13 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.167301 | 36.8889 | ETL.1050 | 40806877 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116615901 | Q2 | T2 EI KNCTI-MDDLTWN 025/009 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 025/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.68291 | 38.9128 | ETL.6380 | 40875484 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616141 | Not Scheduled | T2 EI VLLY SPRNGS-CLY 8/121 RPR GYWW | 43712893 | VALLEY SPRINGS-CLAY | 008/121 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616163 | Not Scheduled | T2 EI PITT-TESLA #1 012/056 RPR FOND | 44238805 | PITTSBURG-TESLA #1 | 012/056 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-27 | 2020-02-27 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-121.786902 | 37.9139 | ETL.5510 | 40810772 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616177 | Not Scheduled | T3 EI CSTR VLY-NWRK -002/020 RPR FOND |  | CASTRO VALLEY-NEWARK | 002/020 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.027178 | 37.6745 | ETL.4450 | 40670684 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | 2018-04-17 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616202 | Q2 | T2 EI CSCDE-BNTN-DSCHTS A08/182 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/182 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-22 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.244996 | 40.5557 | ETL.6310 | 40600686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616290 | Not Scheduled | T2 EI IGNA-ALTO-SAU #1 011/077 RPR FOND | 43693608 | IGNACIO-ALTO-SAUSALITO #1 | 011/077 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.514491 | 37.9139 | ETL.7160 | 40601773 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-06-28 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616555 | Not Scheduled | T2 EI TESLA-RVNSWOOD 018/096 RPL INSS | 31454851 | TESLA-RAVENSWOOD | 018/096 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-27 | 2020-02-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.8471563 | 37.5922 | ETL.5730 | 40837846 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 | SFPUC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-05-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616694 | Mar | T2 EI NEWARK-LAW LAB 10/062 HANGER EYE | 44392611 | NEWARK-LAWRENCE LAB | 010/062 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-27 | 2020-02-27 |  |  | 2021-03-27 | 2021-03-22 |  | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.847264 | 37.5924 | ETL.3060 | 40732585 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 7 | SFPUC | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-05-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116616819 | Not Scheduled | T2 EI TESLA-NEWARK #2 017/118 REPAINT | 43753285 | TESLA-NEWARK #2 | 017/118 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-27 | 2020-02-27 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.847617 | 37.5924 | ETL.5354 | 41152664 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116616959 | Mar | T2 EI EGL RCK-CRTNA :020/003 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :020/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612153 | 39.0118 | ETL.1470 | 41176414 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617048 | Not Scheduled | T2 EI DRUM-RIO OSO #1 21/163 RPNT STRS | 43746398 | DRUM-RIO OSO #1 | 021/163 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-20 | 2024-02-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.097305 | 39.1054 | ETL.1420 | 40659461 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617095 | Not Scheduled | T2 EI VALLEY SPRINGS-CLY 11/160 RPL HRDD | 43712893 | VALLEY SPRINGS-CLAY | 011/160 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-20 | 2020-02-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.886319 | 38.2758 | ETL.8264 | 40904773 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617541 | Q3 | T2 EI CARIBOU #2 020/021 RPL PL | 31425844 | CARIBOU #2 | 020/021 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.018718 | 40.0319 | ETL.6280 | 40600626 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-04-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617542 | Q3 | T2 CARIBOU #2 020/019 RPL PL | 31455203 | CARIBOU #2 | 020/019 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.019303 | 40.0316 | ETL.6280 | 40867545 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-04-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617547 | Q3 | T2 EI CARIBOU #2 - 20/017 RPL ANCH | 31456236 | CARIBOU #2 | 020/017 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.020452 | 40.031 | ETL.6280 | 40824619 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617555 | Q3 | T2 EI CARIBOU #2 20/20 RPL SPLCW | 43742136 | CARIBOU #2 | 020/020 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.017555 | 40.032 | ETL.6280 | 40614863 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617613 | Not Scheduled | T3 EI FLTN-PBL 031/152 RPR FOND | 43720989 | FULTON-PUEBLO | 031/152 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5503 | 38.4856 | ETL.1600 | 40656848 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116617719 | Not Scheduled | T2 EI RND MTN-TM #2 032/157 RPR STRT | 43755806 | ROUND MTN-TABLE MTN #2 | 032/157 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-22 | 2020-02-22 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.933589 | 40.3358 | ETL.6070 | 40816747 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116618132 | Not Scheduled | T2 EI TESLA-NEWARK #2 018/121 PAINT | 43753285 | TESLA-NEWARK #2 | 018/121 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.855783 | 37.5875 | ETL.5354 | 41152667 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116618210 | Not Scheduled | T2 EI TESLA-NEWARK #2 018/119 PAINT | 43753285 | TESLA-NEWARK #2 | 018/119 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.85126 | 37.5903 | ETL.5354 | 41152665 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116618330 | Q2 | T2 EI MALIN-RND MTN #2 94/478 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 094/479 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-28 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.93149 | 40.8118 | ETL.6020 | 40870788 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116618551 | Before Feb | T2 EI RND MTN-TM # 055/238 PAINT TWR |  | ROUND MTN-TABLE MTN #2 | 055/238 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-28 | 2020-02-28 |  |  | 2020-12-30 | 2020-12-01 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.864177 | 40.0064 | ETL.6070 | 40869938 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2020-03-20 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116618555 | Not Scheduled | T2 EI IGNCO-ALTO-SSLTO #1 7/50 PNT MEMB | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 007/050 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-02-28 | 2022-02-28 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495047 | 37.9824 | ETL.7160 | 40770977 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116618670 | Not Scheduled | T2NT EI NEWARK-LIVERMORE 10/059 RPR STRT | 43752137 | NEWARK-LIVERMORE | 010/059 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-28 | 2021-02-28 | [7 empty] | TR2 | <15D | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-121.855598 | 37.5874 | ETL.7660 | 40857516 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116618718 | Not Scheduled | T2 EI MLN-RND MTN #2 093/478 PAINT | 43621093 | MALIN-ROUND MTN #2 | 094/478 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-28 | 2020-02-28 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.92932 | 40.8138 | ETL.6020 | 40816663 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116618832 | Not Scheduled | T2 EI TESLA-NEWARK #2 018/120 PAINT | 43753285 | TESLA-NEWARK #2 | 018/120 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.854345 | 37.5884 | ETL.5354 | 41152666 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116618861 | Before Feb | T2 EI ROUND MTN-TM #1 063/265 RPNT STRT | 44305409 | ROUND MTN-TABLE MTN #1 | 063/265 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-28 | 2020-02-28 |  |  | 2020-12-30 | 2020-12-01 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.821048 | 39.9034 | ETL.6060 | 40759748 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116619034 | Not Scheduled | T3 EI FLTN-IGNCO #1 007/041 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 007/041 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2020-02-28 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.628332 | 38.498 | ETL.4680 | 40597134 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619380 | Q2 | T2 EI FLTN-GNC #1 013/070 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 013/070 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.592307 | 38.4312 | ETL.4680 | 40592338 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619561 | Not Scheduled | T2 EI PITSBRG-SAN MATEO 007/032 RPR STRT | 44238800 | PITTSBURG-SAN MATEO | 007/032 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.892572 | 37.9403 | ETL.5463 | 40805051 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619611 | Not Scheduled | T2 EI CARBERRY SS-RO MTN 019/156 PNT TWR | 43897851 | CARBERRY SW STA-ROUND MTN | 019/156 | ICX | F | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2024-02-28 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.787667 | 40.8255 | ETL.5410 | 40811302 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619683 | Q2 | T2 EI SOBRANTE-R #1 004/029 REPL HRDT | 43727738 | SOBRANTE-R #1 | 004/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-26 | 2020-02-26 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.283829 | 37.9197 | ETL.3770 | 40857827 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619696 | Q2 | T2 EI HT CRK #1 WSTWD 012/249 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 012/249 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2020-01-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.368238 | 40.8175 | ETL.7030 | 40817101 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619798 | Not Scheduled | EI FULTON-IGNACIO #1 013/069 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 013/069 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2021-05-31 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.589229 | 38.4354 | ETL.4680 | 40863253 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619918 | Not Scheduled | T3 EI FLTN-GNC #1 007/044 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 007/044 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2020-02-28 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.618773 | 38.4975 | ETL.4680 | 40762364 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116619948 | Not Scheduled | T2 EI NEWARK-LIVER 009/058 REPAINT | 43752137 | NEWARK-LIVERMORE | 009/058 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.857195 | 37.5856 | ETL.7660 | 40875785 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116620007 | Q2 | T2 EI HT CRK #1 WSTWD 013/252 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 013/252 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-13 | 2020-01-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.366153 | 40.8159 | ETL.7030 | 40770721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116620008 | Q3 | T2 EI TESLA-NEWARK #1 018/100 RPR FOND |  | TESLA-NEWARK #1 | 018/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2020-02-28 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.857665 | 37.5847 | ETL.5720 | 40604780 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | SFPUC | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116620009 | Not Scheduled | T3 EI FLTN-IGNCO #1 006/035 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 006/035 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2020-02-28 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.647285 | 38.4973 | ETL.4680 | 40762100 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116620016 | Not Scheduled | T2 EI RND MTN-TM #2 056/242 RPR COND | 44305720 | ROUND MTN-TABLE MTN #2 | 056/242 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.858213 | 39.9923 | ETL.6070 | 40678044 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116620354 | Mar | T2 EI DIABLO-MIDWAY #3 35/143 RPL INSS | 31526449 | DIABLO-MIDWAY #3 | 035/143 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-02-28 | 2021-05-31 | 2021-03-11 | 2021-03-12 | 2021-03-11 | 2021-03-11 |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints | '-120.239079 | 35.1742 | ETL.5980 | 40680790 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-05-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116620439 | Q3 | T2 EI TESLA-NEWARK #1 018/100 RPL HRDT |  | TESLA-NEWARK #1 | 018/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2020-02-28 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.857665 | 37.5847 | ETL.5720 | 40604780 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | SFPUC | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116620463 | Q2 | EI NEWARK-LIVERMORE 17/110 RPR GYWW | 43752138 | NEWARK-LIVERMORE | 017/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.783096 | 37.6462 | ETL.7660 | 40580692 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622227 | Not Scheduled | T3 EI FLTN-GNC #1 008/046 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 008/046 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.610977 | 38.4975 | ETL.4680 | 40811753 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622390 | Feb | T2 EI BRENTWOOD-KELSO 06/034 RPL INSS | 31457314 | BRENTWOOD-KELSO | 006/034 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-01 | 2020-03-01 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.701857 | 37.8718 | ETL.4410 | 40781544 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622541 | Not Scheduled | T2 EI SANTA YNEZ TAP 03/029 RPL SPLW | 43763687 | SANTA YNEZ TAP | 003/029 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.135504 | 34.6315 | ETL.3701 | 40659083 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622623 | Not Scheduled | T3 EI FLTN-GNC #1 008/047 RPT STRT | 43720618 | FULTON-IGNACIO #1 | 008/047 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.607677 | 38.4975 | ETL.4680 | 40811138 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622693 | Not Scheduled | T2 EI TESLA-NEWARK #2 019/126 PAINT STRT | 43753285 | TESLA-NEWARK #2 | 019/126 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-01 | 2024-03-01 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.864475 | 37.5778 | ETL.5354 | 41152672 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622726 | Feb | T2 EI BRENTWOOD-KELSO 6/033 RPL INSS | 31457314 | BRENTWOOD-KELSO | 006/033 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-01 | 2020-03-01 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.704074 | 37.8744 | ETL.4410 | 40659787 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-09-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116622828 | Feb | T2 EI BRENTWOOD-KELSO 06/032 RPL INSS | 31452001 | BRENTWOOD-KELSO | 006/032 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-01 | 2020-03-01 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.7066892 | 37.8776 | ETL.4410 | 40713188 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-09-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623165 | Not Scheduled | T2 EI ROUND-TABLE #1 46/206 RPR FOND | 43848514 | ROUND MTN-TABLE MTN #1 | 046/206 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2022-03-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.912243 | 40.1304 | ETL.6060 | 40817835 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623408 | Not Scheduled | T2NT EI MALIN-RND MT #2 92/470 INST MRKS | 43621093 | MALIN-ROUND MTN #2 | 092/470 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-01 | 2022-03-01 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.910941 | 40.831 | ETL.6020 | 40868384 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623526 | Not Scheduled | T3NT EI CSTR VLY-NWK 005/031 RPR FOND |  | CASTRO VALLEY-NEWARK | 005/031 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-121.996988 | 37.6451 | ETL.4450 | 40654450 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623538 | Not Scheduled | T2 EI ROUND-TABLE #1 45/201 RPR FOND | 43848514 | ROUND MTN-TABLE MTN #1 | 045/201 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.917559 | 40.1508 | ETL.6060 | 40581219 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623614 | Not Scheduled | T2 EI VALLEY SPRINGS #1 007/137 RPR GYWW | 43727732 | VALLEY SPRINGS #1 | 007/137 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-15 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.856946 | 38.1519 | ETL.8210 | 40905600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623662 | Q2 | T2 EI OCEANO-CALLNDR SW 19/125 RPR GYWW | 43588178 | OCEANO-CALLENDAR SW STA | 019/125 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-28 | 2021-05-31 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-24 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.579929 | 35.1008 | ETL.2394 | 40752018 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623674 | Q2 | T2 EI MALIN-ROUND MTN#2 91/466 RPR OPGW | 43621093 | MALIN-ROUND MTN #2 | 091/466 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-01 | 2020-03-01 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91373 | 40.8436 | ETL.6020 | 40817798 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623883 | Q3 | T2 EI HMLTN BRNCH-CHSTR 0/004 RPR STRW | 31453005 | HAMILTON BRANCH-CHESTER | 000/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2020-02-28 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08705 | 40.2698 | ETL.7000 | 40675667 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623934 | Not Scheduled | T2 EI NRTH DBLN-VINEYARD 0/003 INS HRDS | 43753297 | NORTH DUBLIN-VINEYARD | 000/003 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.8474031 | 37.7449 | ETL.4501 | 42572237 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116623983 | Not Scheduled | T2 EI TESLA-LOS BANOS#1 27/125 INST ZENA | 44598405 | TESLA-LOS BANOS #1 | 027/125 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.193908 | 37.446 | ETL.6100 | 40753727 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116624072 | Not Scheduled | T2 EI TESLA-LOS BANOS #1 27/124 RPR STRT | 43727730 | TESLA-LOS BANOS #1 | 027/124 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-01 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.195786 | 37.4496 | ETL.6100 | 40762394 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116624166 | Not Scheduled | T2 EI RD MN-TBLE MN #2 056/241 RPR CONS | 44305720 | ROUND MTN-TABLE MTN #2 | 056/241 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.859275 | 39.9948 | ETL.6070 | 40592713 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116624408 | Q2 | T2 EI LAYTONVILLE-WIL 12/000 RPR JUMW | 43761787 | LAYTONVILLE-WILLITS | 012/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-01 | 2021-05-31 | 2020-10-14 | 2020-10-17 | 2021-05-28 | 2021-05-26 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.418734 | 39.5438 | ETL.8360 | 40614438 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116624636 | Not Scheduled | T2 EI CONTRA CSTA-LS PSTS 8/54 REPAINT | 43753151 | CONTRA COSTA-LAS POSITAS | 008/054 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-01 | 2024-03-01 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.740407 | 37.8965 | ETL.4510 | 40650444 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116624900 | Not Scheduled | T2 EI DIABLO-MDWY#3 38/153 REPL JUMS | 43756129 | DIABLO-MIDWAY #3 | 038/153 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.192643 | 35.1825 | ETL.5980 | 40651899 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116625067 | Not Scheduled | BELL-PLACER 004/035 RMV VEGN |  | BELL-PLACER | 004/035 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2020-02-27 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-121.087971 | 38.9033 | ETL.4395 | 40869585 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-01-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116626838 | Not Scheduled | T2 EI FULTON-PUEBLO 12/059A RPR GYWW | 43720985 | FULTON-PUEBLO | 012/059A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-02 | 2020-03-02 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.21417 | 38.5089 | ETL.1600 | 43249554 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-11 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116626921 | Q2 | T2 EI CBRY SW ST-RND MT 021/172 INS MRKS | 43742123 | CARBERRY SW STA-ROUND MTN | 021/172 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-02 | 2020-03-02 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.827346 | 40.8224 | ETL.5410 | 40668265 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627266 | Feb | T2 EI BRENTWOOD-KELSO 8/039 REPL INSS | 31452001 | BRENTWOOD-KELSO | 008/039 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-01 | 2020-03-01 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.688556 | 37.8557 | ETL.4410 | 40870203 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627314 | Not Scheduled | T2 EI DIABLO-MDWY#3 39/158 REPAINT | 43756129 | DIABLO-MIDWAY #3 | 039/158 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-01 | 2020-03-01 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.17316 | 35.1902 | ETL.5980 | 40870004 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627366 | Q2 | T2 EI TULE-SPRINGVILLE 17/013 REPL SPLW | 43709294 | TULE-SPRINGVILLE | 017/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-02 | 2020-03-02 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.836992 | 36.1117 | ETL.9040 | 40663638 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627408 | Q2 | T2 EI FULTON-PUEBLO 23/108 RPR FOND | 43720989 | FULTON-PUEBLO | 023/108 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-02 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.413403 | 38.5057 | ETL.1600 | 40858491 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-09-03 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627470 | Q2 | T2 EI TULE-SPRINGVILLE 17/012 RPL SPLW | 43709294 | TULE-SPRINGVILLE | 017/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-02 | 2020-03-02 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.837228 | 36.1115 | ETL.9040 | 40655023 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627524 | Not Scheduled | T2 EI TESLA-LOS BANS#1 27/123 REPL RPTS | 44598404 | TESLA-LOS BANOS #1 | 027/123 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-02 | 2020-03-02 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.197147 | 37.4521 | ETL.6100 | 40658774 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627636 | Q2 | T2 EI HAT CRK #1-WSTWD 009/175 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 009/175 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.407008 | 40.8648 | ETL.7030 | 40667929 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116627768 | Q2 | T2 EI RND MT-TB MT #2 030/147 REPL INSS | 31529255 | ROUND MTN-TABLE MTN #2 | 030/147 | 93K | F | Pre-2020_(9a) Other ignition related |  | 2019-03-02 | 2023-03-02 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.9353687 | 40.3663 | ETL.6070 | 40843696 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116628301 | Q2 | EI CHRISTIE-WILLOW PASS 3/43 RPL PL | 31431652 | CHRISTIE-WILLOW PASS | 003/043 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-26 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-09 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.147009 | 38.0206 | ETL.6370 | 40645283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116628302 | Q2 | EI CHRISTIE-WILLOW PASS 3/44 RPL STRW | 31431652 | CHRISTIE-WILLOW PASS | 003/044 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-26 | 2020-02-26 |  |  | 2021-04-10 | 2021-04-09 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.146351 | 38.0204 | ETL.6370 | 40643864 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116629662 | Not Scheduled | T2 EI IGNCIO-ALTO-SSLTO #1 015/109 STEPS | 43693608 | IGNACIO-ALTO-SAUSALITO #1 | 015/109 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-03 | 2022-03-03 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.50651 | 37.8544 | ETL.7160 | 40601775 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116630236 | Q2 | T2 EI TULE-SPRINGVILLE 13/4 RPR INSW | 43709222 | TULE-SPRINGVILLE | 013/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.913638 | 36.1096 | ETL.9040 | 40766132 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116630237 | Q2 | T2 EI TULE-SPRINGVILLE 013/004 RPL SPLW | 43709294 | TULE-SPRINGVILLE | 013/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.913638 | 36.1096 | ETL.9040 | 40766132 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116630632 | Q2 | T2 EI HAT CRK #1 WSTWD 018/363 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 018/363 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-26 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.28891 | 40.7535 | ETL.7030 | 40601610 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116630895 | Not Scheduled | T2 EI MRR BAY-SLR SW STA #1 0/4 REPAINT | 43760751 | MORRO BAY-SOLAR SW STA #1 | 000/004 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-04 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.847476 | 35.3758 | ETL.5300 | 40762339 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116631066 | Q2 | T2 EI COLGATE-PALERMO 17/342 RPL STRW | 31423185 | COLGATE-PALERMO | 017/342 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-21 | 2020-02-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.435171 | 39.4366 | ETL.6500 | 40814371 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116631682 | Not Scheduled | T2 EI BRDGVL-CTNWD 064/466 RPR FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 064/466 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-04 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.439682 | 40.4048 | ETL.1110 | 40764797 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116631926 | Not Scheduled | T2 EI OLEUM-G #1 006/042 RPNT TWR | 43752220 | OLEUM-G #1 | 006/042 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.258787 | 37.9713 | ETL.3150 | 40646300 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116631964 | Not Scheduled | T2 EI TSL-LS BNS #1 026/120 INST ZEENA | 44598403 | TESLA-LOS BANOS #1 | 026/120 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.203623 | 37.4642 | ETL.6100 | 40592674 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632198 | Q2 | T2 EI TULE-SPRINGVILLE 18/013 RPL INSS | 31430415 | TULE-SPRINGVILLE | 018/013 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-02 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.8254706 | 36.1184 | ETL.9040 | 40694902 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-04-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632265 | Q2 | T2 TSL-MTCLF 018/074 INS HRDT |  | TESLA-METCALF | 018/074 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-04 | 2020-03-04 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.63959 | 37.4526 | ETL.6110 | 40761170 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-04 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632501 | Q2 | T2 DI SOBRANTE R #1 4/29 RPR STRT | 43727738 | SOBRANTE-R #1 | 004/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-27 | 2020-02-27 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.283829 | 37.9197 | ETL.3770 | 40857827 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632525 | Not Scheduled | T2 EI RND MT-TBL MT #2 62/261 REPAINT | 44302501 | ROUND MTN-TABLE MTN #2 | 062/261 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.827893 | 39.921 | ETL.6070 | 40595252 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632535 | Q2 | T2 EI RND MT-TBL MT #2 62/261 RPL SPLS | 44305720 | ROUND MTN-TABLE MTN #2 | 062/261 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-04 | 2020-03-04 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.827893 | 39.921 | ETL.6070 | 40595252 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632538 | Q2 | T2 EI TULE-SPRINGV 026/005 RPR ANCHOR | 43795035 | TULE-SPRINGVILLE | 026/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  | CANCEL/CNCL | TR2 | LATE | South | WSIP | [6 empty] | '-118.71664 | 36.1602 | ETL.9040 | 40749766 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632539 | Q2 | T2 EI TULE-SPRINGVILLE 26/010 RPL POLE | 31429415 | TULE-SPRINGVILLE | 026/010 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.711853 | 36.1615 | ETL.9040 | 40586486 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116632593 | Q2 | T2 EI RND MT-TBL MT #2 40/183 RPL SPLS | 44305720 | ROUND MTN-TABLE MTN #2 | 040/183 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-04 | 2020-03-04 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.927069 | 40.2273 | ETL.6070 | 40658606 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116632903 | Q3 | T2 EI TESLA-NEWARK #1 11/063 RPR FOND |  | TESLA-NEWARK #1 | 011/063 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-04 | 2020-03-04 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.749816 | 37.6477 | ETL.5720 | 40650721 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116633187 | Not Scheduled | T2 EI RND MT-TBL MT #2 53/231 RPR CONS | 44305720 | ROUND MTN-TABLE MTN #2 | 053/231 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.876613 | 40.036 | ETL.6070 | 40595135 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116633216 | Q3 | T2 EI TESLA-NEWARK #2 11/076 RPR FOND |  | TESLA-NEWARK #2 | 011/076 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-04 | 2020-03-04 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.750427 | 37.6479 | ETL.5354 | 41152621 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116633254 | Q3 | EI TESLA-NEWARK #1 012/067 RPR FOND |  | TESLA-NEWARK #1 | 012/067 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-04 | 2020-03-04 |  |  | 2021-07-17 | 2021-07-12 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.76233 | 37.641 | ETL.5720 | 40810297 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116633336 | Not Scheduled | T2 EI RND MTN-TBL MTN#2 53/230 RPR CONS | 43790346 | ROUND MTN-TABLE MTN #2 | 053/230 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.877867 | 40.0394 | ETL.6070 | 40592104 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116633458 | Not Scheduled | T2 EI TESLA-NEWARK #2 11/076 PNT TWR | 43753285 | TESLA-NEWARK #2 | 011/076 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.750427 | 37.6479 | ETL.5354 | 41152621 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116634405 | Q2 | T2 EI TULE-SPRINGVILLE 25/010 RPR GYWW | 43708346 | TULE-SPRINGVILLE | 025/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.727579 | 36.1569 | ETL.9040 | 40609662 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116634411 | Q2 | T2 EI TULE-SPRINGVILLE 25/007 RPR GYWW | 43708346 | TULE-SPRINGVILLE | 025/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.730133 | 36.1563 | ETL.9040 | 40807811 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116634712 | Not Scheduled | T2 EI BRDGVL-CTNWD 060/435 RPR FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 060/435 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-02 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.361221 | 40.3718 | ETL.1110 | 40586445 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116634835 | Q2 | T2 EI TULE-SPRINGVILLE 25/002 RPL POLE | 31429415 | TULE-SPRINGVILLE | 025/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-04 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.73622 | 36.1544 | ETL.9040 | 40655176 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116635408 | Not Scheduled | T2 EI BRDGVLE-CTNWD 063/455 RPR FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 063/455 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.414395 | 40.3894 | ETL.1110 | 40586447 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116635652 | Not Scheduled | T2 EI RO MTN-T MTN #2 30/145 BENT STEEL | 44003390 | ROUND MTN-TABLE MTN #2 | 030/145 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.936194 | 40.374 | ETL.6070 | 40759760 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116635848 | Not Scheduled | T3 EI FULTON-IGNAC #1 011/062 PAINT | 43720618 | FULTON-IGNACIO #1 | 011/062 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-05 | 2019-09-05 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.586556 | 38.4527 | ETL.4680 | 40681566 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116635974 | Not Scheduled | T2 EI PITTS-TESLA #1 007/032 HANGER | 44238805 | PITTSBURG-TESLA #1 | 007/032 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-05 | 2020-03-05 | [5 empty] | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.86573 | 37.9503 | ETL.5510 | 40661559 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116636070 | Not Scheduled | T2 EI BRDGVLE-CTNWD 063/458 RPR FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 063/458 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.419145 | 40.3914 | ETL.1110 | 40759382 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116636118 | Q2 | T2 EI MLN-RND MT #2 059/294 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 059/294 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-05 | 2020-03-05 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6425341 | 41.2208 | ETL.6020 | 40792520 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116636427 | Not Scheduled | T2 EI MIDWAY-WHIRL 51/209 PNT MMBR | 44637106 | MIDWAY-WHIRLWIND | 051/209 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-05 | 2020-03-05 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-118.702835 | 35.0797 | ETL.6030 | 40871795 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637200 | Q3 | EI TESLA-NEWARK #1 012/066 RPR FOND |  | TESLA-NEWARK #1 | 012/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-07-17 | 2021-07-12 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.75969 | 37.6424 | ETL.5720 | 40810878 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637214 | Q3 | EI TESLA-NEWARK #1 012/066 RPL HRDT |  | TESLA-NEWARK #1 | 012/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-07-10 | 2021-07-05 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.75969 | 37.6424 | ETL.5720 | 40810878 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637408 | Q2 | T2 EI OLEUM-G 001/010 RPR STRT | 44229259 | OLEUM-G #1 | 001/010A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.23422 | 38.0385 | ETL.3150 | 40577230 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637461 | Q2 | T2 EI OLEUM-G 001/010 RPL ANCS |  | OLEUM-G #1 | 001/010A |  | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.23422 | 38.0385 | ETL.3150 | 40577230 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Q2 |  |  | 2019-06-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637623 | Not Scheduled | T2 EI NORTH DUBLIN-VNYD 2/013 RPR CONS | 43753297 | NORTH DUBLIN-VINEYARD | 002/013 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-05 | 2020-03-05 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.8049387 | 37.752 | ETL.4501 | 42572250 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637700 | Q3 | T2 EI TESLA-NEWARK #1 11/065 RPR FOND |  | TESLA-NEWARK #1 | 011/065 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.756349 | 37.6442 | ETL.5720 | 40761982 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637710 | Q2 | T2 EI OLEUM-G #1 1/010B REPLUMB STRT | 44103087 | OLEUM-G #1 | 001/010B | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.234157 | 38.0385 | ETL.3150 | 40740544 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637752 | Q3 | T2 EI TESLA-NEWARK #2 12/086 RPR FOND | 43753286 | TESLA-NEWARK #2 | 012/086 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.776642 | 37.6338 | ETL.5354 | 41152631 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116637958 | Before Feb | T2NT EI MALIN-RND MTN #2 090/460B CANCEL | 44305271 | MALIN-ROUND MTN #2 | 090/460B | ICS | F | Pre-2020_(1b) Lines with special commitments | Budget Owner (Paint) | 2019-03-05 | 2021-03-05 |  |  | 2020-09-14 | 2020-09-07 |  |  | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.91631 | 40.8563 | ETL.6020 | 41162773 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116638298 | Not Scheduled | EI TESLA-NEWARK #2 020/130 RPR FOND |  | TESLA-NEWARK #2 | 020/130 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-05 | 2020-03-05 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.874932 | 37.566 | ETL.5354 | 41152676 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116638323 | Q2 | T2 EI HAT CRK #1-WSTWD 033/643 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 033/643 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2020-02-28 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.100832 | 40.598 | ETL.7030 | 40600253 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116638553 | Not Scheduled | T2 EI LAS POSITAS-NEWARK 4/032 RPR FOND |  | LAS POSITAS-NEWARK | 004/032 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-05 | 2024-03-05 |  |  |  | 2020-12-09 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.754265 | 37.646 | ETL.4980 | 40595240 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116638800 | Not Scheduled | DISTRIBUTION | 43749776 | LONE STAR TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-27 | 2020-02-27 | 2020-03-18 | 2020-03-19 | [5 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-122.191842 | 37.0257 | ETL.6231 | 40770680 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116638911 | Not Scheduled | T2 DI CARIBOU-PALERMO :22/182 BURY MEMB | 44069454 | CARIBOU-PALERMO | :022/182 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-25 | 2020-02-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37803 | 39.8724 | ETL.3190 | 40738807 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116638983 | Not Scheduled | T2 DI SOBRANTE G #1 3/28 HRDD INST |  | SOBRANTE-"G" #1 | 003/028 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.283917 | 37.9199 | ETL.3720 | 40857869 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | 2019-05-15 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-15 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116639510 | Q2 | T2 EI TULE-SPRING 013/013 RPL SPLW | 43709294 | TULE-SPRINGVILLE | 013/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-05 | 2020-03-05 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.903194 | 36.1099 | ETL.9040 | 40663629 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116639744 | Q3 | T2 DI KRKHFF-CLVS-SNGER #1 4/28 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 004/028 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.576041 | 37.0105 | ETL.1890 | 40863764 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116639746 | Q3 | T2 DI KRKHFF-CLVS-SNGER #1 4/27 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 004/027 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.5752 | 37.0117 | ETL.1890 | 40806740 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116640876 | Q2 | T2 EI TULE-SPRINGVILLE 018/020 REPL STRW | 31429415 | TULE-SPRINGVILLE | 018/020 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-04 | 2020-03-04 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.822913 | 36.1184 | ETL.9040 | 40609654 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  |  | VRF (4-5 Months) | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116640928 | Q2 | T2 TULE-SPRINGVILLE 024/007 REPL STRW | 31429415 | TULE-SPRINGVILLE | 024/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-05 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.747395 | 36.152 | ETL.9040 | 40821823 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116640932 | Not Scheduled | T2 EI BRDGVLE-CTNWD 067/486 RPR FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 067/486 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-06 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.472681 | 40.4331 | ETL.1110 | 40765586 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116640964 | Q2 | T2 DI CLAY-MARTEL 32/488 RPL CRSW | 31429424 | CLAY-MARTEL | 032/488 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84163 | 38.4568 | ETL.8250 | 40904100 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116641832 | Q2 | T3 DI GOLD HILL #1 024/359 RPL STRW | 31494685 | GOLD HILL #1 | 024/359 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-26 | 2019-08-26 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848809 | 38.5855 | ETL.6950 | 40876097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-03-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116642749 | Q3 | T2 TESLA-NEWARK #2 013/087 REPL HRDT |  | TESLA-NEWARK #2 | 013/087 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.778911 | 37.6326 | ETL.5354 | 41152632 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116653026 | Not Scheduled | T3 DI CARIBOU-PALERMO :030/244 RPR FOND | 44051417 | CARIBOU-PALERMO | :030/244 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-22 | 2019-07-22 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452619 | 39.7784 | ETL.3190 | 40758634 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116654973 | Not Scheduled | T3NT DI CRIBU-PLERMO :030/244 PAINT STRT | 44304458 | CARIBOU-PALERMO | :030/244 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-22 | 2019-07-22 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452619 | 39.7784 | ETL.3190 | 40758634 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116671395 | Q3 | T2 EI TESLA-NEWARK #1 011/064 RPR FOND |  | TESLA-NEWARK #1 | 011/064 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.752542 | 37.6462 | ETL.5720 | 40761431 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116673129 | Feb | EI CRAZ CAN-SAL-SO #2 39/247 RPL SPLS | 43766021 | MOSS LANDING-SALINAS-SOLEDAD #2 | 039/247 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2021-05-31 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-121.6038721 | 36.7471 | ETL.2910 | 40843949 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 | 2019-07-15 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116673297 | Not Scheduled | T3 DI CARIBOU-PALERMO 034/276 RPL INSS |  | CARIBOU-PALERMO | :034/276 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-19 | 2019-08-19 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40856088 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116673325 | Not Scheduled | T3NT DI DISTRIBUTION |  | LIMESTONE TAP | 001/023 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-05 | 2020-03-05 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Distribution |  | '-120.981012 | 38.6394 | ETL.6951 | 40827787 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116673373 | Not Scheduled | T2 EI BRDGVLE-CTNWD 066/476 RPR FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 066/476 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-06 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.45757 | 40.4165 | ETL.1110 | 40592244 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116673392 | Not Scheduled | T3 DI CARIBOU-PLERMO :34/277 BURIED MEMB | 44051418 | CARIBOU-PALERMO | :034/277 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-26 | 2019-08-26 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.479702 | 39.7233 | ETL.3190 | 40815592 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116674182 | Mar | T2 EI TEJON-LEBEC 009/154 RPL POLE | 31469596 | TEJON-LEBEC | 009/154 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-06 | 2020-03-06 | 2019-09-19 | 2019-09-19 | 2021-03-07 | 2021-03-06 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.918712 | 34.8935 | ETL.9250 | 40654418 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116674269 | Q3 | T2 DI KRCKHOF-CLVS-SNGR #1 5/34 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 005/034 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-02-27 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.585899 | 36.997 | ETL.1890 | 40753732 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116674392 | Not Scheduled | T2 EI TRACY-LOS BANOS 31/148 RPL RPTS | 44651142 | TRACY-LOS BANOS | 031/148 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-06 | 2020-03-06 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.209138 | 37.4756 | ETL.6130 | 40873336 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116676006 | Q2 | DI CLAY-MARTEL 031/481 R INS GYW | 43727747 | CLAY-MARTEL | 031/481 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2021-05-31 |  |  | 2021-04-24 | 2021-04-19 |  |  |  |  | LATE | Central | WSIP | FSRP | [7 empty] | ETL.8250 | 44270320 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116676043 | Q3 | T2 EI TESLA-NEWARK #1 010/060 RPR FOND |  | TESLA-NEWARK #1 | 010/060 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.739044 | 37.6535 | ETL.5720 | 40591031 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116676340 | Q2 | DI CLAY-MARTEL 031/481C S GYWW | 43727747 | CLAY-MARTEL | 031/481 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-03-01 | 2021-05-31 |  |  | 2021-04-24 | 2021-04-19 |  |  |  |  | LATE | Central | WSIP | FSRP | [7 empty] | ETL.8250 | 44270319 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116678973 | Q2 | T2 EI TESLA-METCALF 26/108 INST HRDT |  | TESLA-METCALF | 026/108 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-06 | 2020-03-06 |  |  | 2021-06-30 | 2021-06-28 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.676142 | 37.3434 | ETL.6110 | 40863783 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116678974 | Q2 | T2 EI TESLA-METCALF 26/108 RPR FOND |  | TESLA-METCALF | 026/108 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.676142 | 37.3434 | ETL.6110 | 40863783 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116679131 | Q2 | T2 MALIN-ROUND MTN #2 64/322 RPR HRDS | 43621093 | MALIN-ROUND MTN #2 | 064/322 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-06 | 2020-03-06 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.697954 | 41.1566 | ETL.6020 | 40684085 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116679904 | Not Scheduled | T2 DI CARIBOU-PLRM :008/68 RPR FOND | 44059014 | CARIBOU-PALERMO | :008/068 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-04 | 2020-03-04 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.247789 | 40.0076 | ETL.3190 | 40910310 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116680308 | Not Scheduled | T3 DI DRUM-HIGGINS 17/148 PNT STRS | 43738143 | DRUM-HIGGINS | 017/148 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-28 | 2019-08-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.017625 | 39.1368 | ETL.4393 | 40913044 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116680648 | Q2 | T2 EI MALIN-RND MT #2 57/284 WASH INSS | 43754876 | MALIN-ROUND MTN #2 | 057/284 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.624443 | 41.2431 | ETL.6020 | 40759857 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116680671 | Not Scheduled | T3 DI CRSTA-RIO OSO 012/99 PNT TWR | 43708739 | CRESTA-RIO OSO | 012/099 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2019-09-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451302 | 39.7859 | ETL.4590 | 40910125 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116680913 | Q2 | T2 EI TSLA-MTCLF 016/068 RPR GYWS | 43753282 | TESLA-METCALF | 016/068 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-26 | 2021-06-21 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.629322 | 37.4785 | ETL.6110 | 40863776 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | 2019-06-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116681160 | Feb | SAN MATO-HILLSLE JCT 001/026 rmv splices | 44574935 | SAN MATEO-HILLSDALE JCT | 001/026 | ICK | B | Pre-2020_(0) A and B Tags |  | 2019-03-07 | 2021-03-03 |  |  | 2021-02-28 | 2021-02-28 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.318544 | 37.5659 | ETL.7950 | 40865014 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 515 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-03-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 116681164 | Mar | T2 HUMBOLDT-TRINITY 092/001L REPL STRW | 31433540 | HUMBOLDT-TRINITY | 092/001 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-03-07 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.725388 | 40.7504 | ETL.1820 | 44769615 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116681232 | Q2 | T2 EI MALIN-ROUND MTN#2 56/279 CLN INSS | 43754876 | MALIN-ROUND MTN #2 | 056/279 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.615265 | 41.2544 | ETL.6020 | 40870730 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116681396 | Not Scheduled | T2 EI CONTRA CST-LS PSTS 14/91 INST HRDT |  | CONTRA COSTA-LAS POSITAS | 014/091 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2024-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.725024 | 37.792 | ETL.4510 | 40590632 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116681465 | Not Scheduled | T2 EI TRCY-LS BNS 031/146 RPL ANMS | 43844594 | TRACY-LOS BANOS | 031/146 | ICB | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-07 | 2024-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.211204 | 37.4791 | ETL.6130 | 40812029 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116681904 | Q2 | EI STNSLUS-NWRK#1(12KV)92/611 INST ATCG | 31454925 | STANISLAUS-NEWARK #1 (12KV) | 092/611 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.872223 | 37.5855 | ETL.3850 | 40602897 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116681935 | Not Scheduled | T3 EI MNT VT-JFRSN #1 014/060 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 014/060 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2021-05-31 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.290554 | 37.3945 | ETL.5220 | 40602700 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682008 | Q2 | T2 DI CLAY-MARTEL 32/490 RPL STRW | 31430278 | CLAY-MARTEL | 032/490 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.842238 | 38.4581 | ETL.8250 | 40904098 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-05-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682310 | Q2 | T2 DI CLAY-MARTEL 32/493 RPL STRW | 31498114 | CLAY-MARTEL | 032/493 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 |  |  | 2021-05-01 | 2021-04-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843471 | 38.4608 | ETL.8250 | 40904095 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682464 | Q2 | T2 DI BALCH SANGER 6/40 INS HRDT | 43709727 | BALCH-SANGER | 006/040 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-25 | 2020-02-25 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.17294 | 36.886 | ETL.1050 | 40585030 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682552 | Q2 | T2 EI MALIN-RND MTN#2 064/321 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 064/321 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.696342 | 41.1579 | ETL.6020 | 40592575 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682646 | Not Scheduled | T2 DI CARIBOU-PLRM :022/185 RPR INSS | 44304495 | CARIBOU-PALERMO | :022/185 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-19 | 2020-02-19 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.380738 | 39.8706 | ETL.3190 | 40757284 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682750 | Not Scheduled | T2 DI CARIBOU-PLRM :022/186 RPR STRT | 44069454 | CARIBOU-PALERMO | :022/186 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-02-18 | 2020-02-18 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.385577 | 39.8688 | ETL.3190 | 40806164 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116682767 | Q2 | T2 EI MALIN-ROUND MTN #2 65/326 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 065/326 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.708607 | 41.1482 | ETL.6020 | 40822888 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116682815 | Not Scheduled | T2 DI CARIBOU-PLRM :022/186 RPR FOND | 44069454 | CARIBOU-PALERMO | :022/186 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-02-18 | 2020-02-18 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.385577 | 39.8688 | ETL.3190 | 40806164 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116683111 | Not Scheduled | T2 DI CLAY-MARTEL 18/263 STRW REPLACE | 31460367 | CLAY-MARTEL | 018/263 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.919062 | 38.3409 | ETL.8250 | 40663970 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116683171 | Not Scheduled | T2 EI MALIN-ROUND MTN#2 89/453 COMPLETE | 43621093 | MALIN-ROUND MTN #2 | 089/453 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913202 | 40.8756 | ETL.6020 | 40657564 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116683191 | Not Scheduled | T2 EI MALIN-ROUND MTN#2 89/453 CANCEL | 43754876 | MALIN-ROUND MTN #2 | 089/453 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913202 | 40.8756 | ETL.6020 | 40657564 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116683302 | Mar | T2 DI CLAY-MARTEL 024/346 RPL STRW | 31422461 | CLAY-MARTEL | 024/346 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-03-20 | 2021-03-17 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.814502 | 38.3602 | ETL.8250 | 40691770 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116683309 | Q2 | T2 DI CLAY-MARTEL 27/408 RPL POLE | 31460367 | CLAY-MARTEL | 027/408 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2020-02-28 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 | LATE | Central | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-120.81329 | 38.394 | ETL.8250 | 40904047 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  | Reject | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116683867 | Not Scheduled | T2 EI OLEUM-G #1 10/066 REPAINT | 43752220 | OLEUM-G #1 | 010/066 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-07 | 2020-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.284407 | 37.92 | ETL.3150 | 40804791 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116684126 | Not Scheduled | T3 EI TGR CRK-VLLY SPRNGS 12/98 PNT STRS | 43708739 | CRESTA-RIO OSO | 012/098 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-06 | 2019-09-06 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451798 | 39.7874 | ETL.4590 | 40910124 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116684136 | Not Scheduled | T3 EI SBRNT-G #2 003/019 WSH INSS | 43895436 | SOBRANTE-"G" #2 | 003/019 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2019-09-07 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.259498 | 37.9137 | ETL.3730 | 40878764 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116685114 | Q2 | DI IONE TAP 3/12 RPR STRW | 43844198 | IONE TAP | 003/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.952317 | 38.3746 | ETL.8253 | 40644753 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116685590 | Q2 | T2 EI MALIN-RND MT #2 65/325 WASH INSS | 43754876 | MALIN-ROUND MTN #2 | 065/325 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-07 | 2020-03-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705665 | 41.1505 | ETL.6020 | 40759608 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116685829 | Not Scheduled | T2 DI PLACER-DEL MAR 4/90 RMV VEGN |  | PLACER-DEL MAR | 004/090 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.136978 | 38.8621 | ETL.7800 | 40809982 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-07-16 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686117 | Mar | T2 VOLTA-SOUTH 001/040 REFRAME | 31471616 | VOLTA-SOUTH | 001/040 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-06 | 2020-03-06 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.8726 | 40.4359 | ETL.8300 | 40826968 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-06-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686163 | Mar | T2 DI VOLTA-SOUTH 4/100 REFRAME | 31453744 | VOLTA-SOUTH | 004/100 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-06 | 2020-03-06 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878295 | 40.399 | ETL.8300 | 40667414 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686173 | Feb | T2 COLEMAN-SOUTH 005/108 RPL POLE | 31515568 | COLEMAN-SOUTH | 005/108 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.967732 | 40.4031 | ETL.6450 | 40817388 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686272 | Not Scheduled | T3 DI TIGR CREK-VLLY SPRNG 8/62 PAINT | 43830095 | TIGER CREEK-VALLEY SPRINGS | 008/062 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-07 | 2019-09-07 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.620443 | 38.3994 | ETL.5790 | 40651153 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686377 | Feb | T2 EI ROCK CREEK-POE 1/11 RPL INSS | 31431457 | ROCK CREEK-POE | 001/011 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2020-01-28 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3628 | 39.8992 | ETL.5630 | 40616276 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686380 | Not Scheduled | T2NT EI MTCLF-GRN VLLY 8/055 REPAINT | 44300678 | METCALF-GREEN VALLEY | 008/055 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-04 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.673354 | 37.1399 | ETL.2540 | 40761851 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686386 | Not Scheduled | EI MORAGA-LAKEWOOD 008/063 REPR FOND |  | MORAGA-LAKEWOOD | 008/063 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.107483 | 37.8796 | ETL.3741 | 40659422 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116686760 | Q2 | T2 EI MLIN-RND MTN #2 048/236 RPL HRDS | 43621093 | MALIN-ROUND MTN #2 | 048/236 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-08 | 2020-03-08 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.529495 | 41.3597 | ETL.6020 | 40817693 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116687073 | Not Scheduled | T3 EI MNT VST-JFFRSN #1 15/64 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 015/064 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-08 | 2021-05-31 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.293752 | 37.4037 | ETL.5220 | 40760857 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116687201 | Not Scheduled | T2 EI RND MTN-TBL MTN #1 33/161 RPR STRT | 43848514 | ROUND MTN-TABLE MTN #1 | 033/161 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.934487 | 40.3228 | ETL.6060 | 40581216 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116687486 | Not Scheduled | EI TESLA-LOS BANOS #1 24/109 RPR FOND | 43844591 | TESLA-LOS BANOS #1 | 024/109 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-08 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.22292 | 37.4941 | ETL.6100 | 40863461 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116687579 | Not Scheduled | T2 EI RND MN-TBLE MTN #2 000/006 RMV VEG |  | ROUND MTN-TABLE MTN #2 | 000/006 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-08 | 2020-03-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.928734 | 40.7936 | ETL.6070 | 40817840 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-05-30 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116687671 | Not Scheduled | T2 EI OLEUM-G #1 010/068 RPNT TWR | 43752220 | OLEUM-G #1 | 010/068 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-08 | 2020-03-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.288972 | 37.9192 | ETL.3150 | 40857750 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116687779 | Not Scheduled | T2 EI VACA-SUISUN 11/082 PNT/COATNG STRS | 43740515 | VACA-SUISUN | 011/082 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-28 | 2020-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.058581 | 38.2971 | ETL.4070 | 40668976 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116688254 | Not Scheduled | T3 EI OLEUM-G #1 010/065 RPNT STRT | 43726138 | OLEUM-G #1 | 010/065 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-08 | 2019-09-08 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.283518 | 37.9207 | ETL.3150 | 40746019 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8 | 2019-04-24 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116688441 | Not Scheduled | T2 DI SOBRANTE-MORAGA 000/008 RPR FOND | 44261935 | SOBRANTE-MORAGA | 000/008 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.202084 | 37.9027 | ETL.3742 | 41135450 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116688650 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 89/455 COMPLETE | 43621093 | MALIN-ROUND MTN #2 | 089/455 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-08 | 2020-03-08 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.914529 | 40.8672 | ETL.6020 | 40752315 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116688801 | Q2 | T2 DI IONE TAP 0/005 RPR CRSW | 43844195 | IONE TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.918855 | 38.3446 | ETL.8253 | 40765829 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116688826 | Q2 | T2 DI PARKWAY-MORAGA 010/059 RPR STRT | 43753156 | PARKWAY-MORAGA | 010/059 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-04-02 | 2021-03-29 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.23148 | 37.9973 | ETL.5930 | 40763001 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116689190 | Not Scheduled | DI VALLEY SPRINGS #1 3/057 RPR STRW | 43831016 | VALLEY SPRINGS #1 | 003/057 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.813024 | 38.1959 | ETL.8210 | 40909217 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116689191 | Not Scheduled | DI VALLEY SPRINGS #1 3/058 RPR STRW | 43831082 | VALLEY SPRINGS #1 | 003/058 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.813671 | 38.1953 | ETL.8210 | 40909218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116689194 | Not Scheduled | T2 DI METCALF-HICKS 5/027 RPL CONN | 43753590 | METCALF-HICKS 1 & 2 (IDLE) | 005/027 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.830672 | 37.2261 | ETL.4317 | 41167702 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116689197 | Feb | T2 EI RND MTN-CTTNWD#3 046/397 RPR CONS | 43755803 | ROUND MTN-COTTONWOOD #3 | 046/397 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.128712 | 40.5637 | ETL.5650 | 40815940 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116689214 | Not Scheduled | T3 EI TEMBLOR-SLO+ 42/241 REPA STUCTURE | 43763689 | TEMBLOR-SAN LUIS OBISPO | 042/241 | ICQ | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-08 | 2019-09-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.411638 | 35.3687 | ETL.3960 | 40585711 | Structure-Tower | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116689348 | Not Scheduled | T2 EI MLN-RND MTN #2 078/395B INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 078/395B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-08 | 2022-03-08 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890339 | 41.0353 | ETL.6020 | 41162682 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690543 | Not Scheduled | T2 EI MLN-RND MTN #2 078/395A INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 078/395A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-08 | 2022-03-08 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890182 | 41.0353 | ETL.6020 | 41162685 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690545 | Q2 | T2 EI TESLA-METCALF 023/099 RPR GYWS | 43753282 | TESLA-METCALF | 023/099 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 |  |  | 2021-06-26 | 2021-06-21 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.674756 | 37.3789 | ETL.6110 | 40863439 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690554 | Q2 | T2 EI TESLA-METCALF 023/099 BENT MEMBER |  | TESLA-METCALF | 023/099 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.674756 | 37.3789 | ETL.6110 | 40863439 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690568 | Not Scheduled | T2 EI CRESTA-RIO OSO 23/182 PNT STRT | 43708739 | CRESTA-RIO OSO | 023/182 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2025-03-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.509488 | 39.6459 | ETL.4590 | 40910190 | Structure-Steel | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690606 | Q2 | T2 DI MORAGA-LAKEWOOD 10/078 RPL SPLS | 43752130 | MORAGA-LAKEWOOD | 010/078 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-08 | 2020-03-08 |  |  | 2021-04-06 | 2021-04-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.134703 | 37.8653 | ETL.3741 | 40857633 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690607 | Q2 | T2 DI MORAGA-LAKEWOOD 10/078 RPL INSS | 31451424 | MORAGA-LAKEWOOD | 010/078 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-08 | 2020-03-08 |  |  | 2021-04-06 | 2021-04-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.134703 | 37.8653 | ETL.3741 | 40880140 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690608 | Q2 | T2 DI MORAGA-LAKEWOOD 10/078 RPR CONS | 43752130 | MORAGA-LAKEWOOD | 010/078 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-08 | 2020-03-08 |  |  | 2021-04-06 | 2021-04-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.134703 | 37.8653 | ETL.3741 | 40857633 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690749 | Mar | T2 EI HIGGINS-BELL 33/251 RPR INSS | 43740275 | HIGGINS-BELL | 033/251 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-06 | 2020-03-06 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042373 | 38.9618 | ETL.1412 | 40762676 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690786 | Q3 | EI TSL-NWRK #1 013/074 RPR FOND | 43753786 | TESLA-NEWARK #1 | 013/074 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 |  |  | 2021-07-17 | 2021-07-12 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.785225 | 37.6287 | ETL.5720 | 40761433 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-01-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690799 | Not Scheduled | T2 DI PKWY-MORAGA 8/046 RPR HRDT | 43683430 | PARKWAY-MORAGA | 008/046 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233619 | 38.0277 | ETL.5930 | 40592005 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116690926 | Mar | T2 EI HIGGINS-BELL 34/254 RPR INSS | 43740275 | HIGGINS-BELL | 034/254 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-06 | 2020-03-06 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.04283 | 38.9542 | ETL.1412 | 40869579 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691031 | Not Scheduled | T2 DI SBRNT-GRZLY-CLRMT #1 1/14 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 001/014 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.20099 | 37.8935 | ETL.3740 | 40857132 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | 2019-04-09 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-05 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691256 | Mar | T2 DI MORAGA-SN LEANDRO #1 8/58 RPR STRT | 44294404 | MORAGA-SAN LEANDRO #1 | 008/058 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.11931 | 37.7372 | ETL.2770 | 40857652 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691324 | Q2 | T2 EI MLN-RD MTN #2 047/234 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 047/234 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-08 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5259319 | 41.3641 | ETL.6020 | 40789955 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691357 | Q2 | T2 DI IONE TAP 2/1 CRWS RPR | 43844195 | IONE TAP | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-08 | 2020-03-08 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.927115 | 38.3689 | ETL.8253 | 40580314 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691359 | Q2 | DI IONE TAP 3/14 INSW RPLC | 31430408 | IONE TAP | 003/014 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.95451 | 38.3741 | ETL.8253 | 40773360 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691493 | Q2 | T2 DI IONE TAP 1/7 RPR GYWW | 43844195 | IONE TAP | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925828 | 38.3617 | ETL.8253 | 40804110 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691495 | Q2 | T2 DI IONE TAP 1/7 RPR GWSW | 43844195 | IONE TAP | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925828 | 38.3617 | ETL.8253 | 40804110 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691496 | Q2 | T2 DI IONE TAP 1/7 RPR STRW | 43844195 | IONE TAP | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925828 | 38.3617 | ETL.8253 | 40804110 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691570 | Q2 | DI IONE TAP 1/9 RPR STRW | 43796670 | IONE TAP | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-08 | 2021-05-31 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.926922 | 38.3645 | ETL.8253 | 40857174 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691837 | Not Scheduled | T2 DI PARKWAY-MORAGA 009/055 RPL HRDT | 43683430 | PARKWAY-MORAGA | 009/055 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-09 | 2020-03-09 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233796 | 38.0051 | ETL.5930 | 40576197 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691870 | Q2 | T2 EI MALIN-RD MTN #2 066/330 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 066/330 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7173586 | 41.1412 | ETL.6020 | 40635012 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116691930 | Mar | T2 EI ATSCDRO-SLO 014/174 INST HRDT | 43766560 | ATASCADERO-SAN LUIS OBISPO | 014/174 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-09 | 2021-05-31 |  |  | 2021-03-01 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.630444 | 35.2813 | ETL.8490 | 40668420 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692006 | Q2 | T2 DI IONE TAP 2/002 RPL INSS | 31430408 | IONE TAP | 002/002 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-08 | 2020-03-08 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.92712 | 38.3694 | ETL.8253 | 40704123 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-04-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692019 | Feb | T2 EI BCKS CRKRCK CRKC :000/001 RPR JUMS | 43742056 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.346983 | 39.9057 | ETL.4430 | 40595003 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692175 | Not Scheduled | T2 EI TRACY-LOS BAN 30/143 INST CORONA | 43844596 | TRACY-LOS BANOS | 030/143 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-09 | 2020-03-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.218474 | 37.4895 | ETL.6130 | 40651827 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692383 | Not Scheduled | T3 EI SOBRANTE-R #1 002/016 PAINT | 43727737 | SOBRANTE-R #1 | 002/016 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-09 | 2019-09-09 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249227 | 37.9104 | ETL.3770 | 40804940 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692486 | Not Scheduled | T2 EI MLIN-ROUND MTN #2 66/333 COMPLETE | 43754876 | MALIN-ROUND MTN #2 | 066/333 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2020-03-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.724272 | 41.1358 | ETL.6020 | 40660397 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692522 | Q2 | T2 EI MALIN-RD MTN #2 067/336 RPL HRDT | 43621093 | MALIN-ROUND MTN #2 | 067/336 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.731535 | 41.13 | ETL.6020 | 40817705 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692525 | Q2 | T2 EI MALIN-ROUND MTN #2 66/334 RPR STRT | 44110806 | MALIN-ROUND MTN #2 | 066/334 | ICS | E | 2020_(1b) Lines with special commitments |  | 2019-03-09 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.726216 | 41.1342 | ETL.6020 | 40762173 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116692559 | Q2 | T2 EI MLN-RND MTN #2 050/250 RPR OPGW | 44305271 | MALIN-ROUND MTN #2 | 050/250 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2020-03-09 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.557085 | 41.3259 | ETL.6020 | 40605576 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693063 | Not Scheduled | T2 DI DVDE-VNDNBRG #1 2/018 RMV DBRW | 43769296 | DIVIDE-VANDENBERG #1 | 002/018 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-03-08 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.478655 | 34.8005 | ETL.8620 | 40576372 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693274 | Mar | T2 EI POE-RIO OSO 38/252 RPL INSS | 31431911 | POE-RIO OSO | 038/252 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.520605 | 39.4406 | ETL.5540 | 40729675 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693330 | Mar | T2 EI POE-RIO OSO 38/253 RPL INSS | 31431911 | POE-RIO OSO | 038/253 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.520329 | 39.4392 | ETL.5540 | 40685030 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693373 | Feb | T2 EI RUND MTN-CTTNWD #3 58/531 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 058/531 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-05 | 2020-02-05 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.256284 | 40.4095 | ETL.5650 | 40619627 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693378 | Q2 | T2 EI CRESTA-RIO OSO 38/254 RPL INSS | 31435732 | CRESTA-RIO OSO | 038/254 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-05 | 2020-02-05 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519716 | 39.4361 | ETL.4590 | 40787727 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693677 | Not Scheduled | T2 DI CTRA CSTA-MRGA #1 26/124 PAINT | 43753199 | CONTRA COSTA-MORAGA #1 | 026/124 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-07 | 2024-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.155519 | 37.8538 | ETL.5452 | 40804949 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-16 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116693678 | Not Scheduled | T2 DI CTRA CSTA-MRGA #1 26/125 RPR FOND |  | CONTRA COSTA-MORAGA #1 | 026/125 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2024-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.157489 | 37.852 | ETL.5452 | 40857894 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | 2019-04-16 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116694303 | Not Scheduled | T2 EI RND MTN-TBL MTN #1 18/98 RMV VEGN | 44305409 | ROUND MTN-TABLE MTN #1 | 018/098 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-09 | 2024-03-09 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.943992 | 40.5342 | ETL.6060 | 40871647 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116704821 | Not Scheduled | T2 DI SBRNTE-GRZZLY-CLRMNT 1/15 REPAINT | 43752392 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 001/015 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-07 | 2020-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199121 | 37.8919 | ETL.3740 | 40580680 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-09 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116704830 | Q2 | T2 DI CLAY-MARTEL 33/497 RPL STRW | 31498114 | CLAY-MARTEL | 033/497 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-05-01 | 2021-04-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844528 | 38.464 | ETL.8250 | 40912854 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116704833 | Q2 | T2 DI CLAY-MARTEL 33/499 RPR STRW | 43793351 | CLAY-MARTEL | 033/499 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-05-01 | 2021-04-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844892 | 38.4659 | ETL.8250 | 40912852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116704838 | Q2 | T2 DI CLAY-MARTEL 33/500 RPR STRW | 43793354 | CLAY-MARTEL | 033/500 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845091 | 38.4667 | ETL.8250 | 40912851 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116704839 | Q2 | T2 DI CLAY-MARTEL 33/513 RPL STRW | 31430278 | CLAY-MARTEL | 033/513 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2020-03-06 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844917 | 38.4759 | ETL.8250 | 40908884 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705040 | Q2 | T2 DI CLAY-MARTEL 33/515 RPL PL | 31430278 | CLAY-MARTEL | 033/515 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84474 | 38.4768 | ETL.8250 | 40908882 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705042 | Q2 | T2 DI CLAY-MARTEL 33/516 RPL STRW | 31430278 | CLAY-MARTEL | 033/516 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844608 | 38.4771 | ETL.8250 | 40908881 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705094 | Not Scheduled | T3 EI MRAGA-SN LNDRO 004/036 RPR FOND | 43753783 | MORAGA-SAN LEANDRO #1 | 004/036 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2020-03-07 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.126399 | 37.7877 | ETL.2770 | 40804654 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705301 | Q2 | DI CRESTA-RIO OSO 40/262 RPL INSS | 31435732 | CRESTA-RIO OSO | 040/262 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 |  |  | 2021-04-02 | 2021-03-29 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.516195 | 39.4186 | ETL.4590 | 40719840 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705307 | Mar | DI POE-RIO OSO 040/264 WASH INSS | 43724322 | POE-RIO OSO | 040/264 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.515393 | 39.4147 | ETL.5540 | 40761322 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705371 | Feb | T3 DI ROCK CREEK-POE 11/79 RPR INSS | 43724474 | ROCK CREEK-POE | 011/079 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2019-09-07 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451784 | 39.784 | ETL.5630 | 40866645 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705376 | Not Scheduled | T2 DI PARKWAY-MORAGA 10/63 RPL HRDT | 43683430 | PARKWAY-MORAGA | 010/063 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2020-03-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.224315 | 37.9882 | ETL.5930 | 40871592 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116705789 | Not Scheduled | T2 DI VALLEY SPRINGS #1 7/134 STRW REPAI | 43831014 | VALLEY SPRINGS #1 | 007/134 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-06 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.855017 | 38.1536 | ETL.8210 | 40905597 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116706970 | Q2 | T2NT EI MALIN-RD MTN #2 067/338 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 067/338 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7368133 | 41.1258 | ETL.6020 | 40893466 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116706971 | Not Scheduled | T2 EI MALIN-RD MTN #2 066/332 COMPLETE | 31439323 | MALIN-ROUND MTN #2 | 066/332 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2020-03-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7222803 | 41.1373 | ETL.6020 | 40722246 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116706996 | Q2 | T2 EI TESLA-MET 027/114 INST HRDT |  | TESLA-METCALF | 027/114 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-09 | 2020-03-09 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.686896 | 37.3239 | ETL.6110 | 40753750 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116707001 | Not Scheduled | T3 EI DIABLO-GATES #1 1/012 RPR STUB | 43756059 | DIABLO-GATES #1 | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-09 | 2019-09-09 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.821032 | 35.2256 | ETL.5960 | 40664670 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116707154 | Not Scheduled | T3 EI RD MN-TBL MN #2 021/106 CANCEL | 43740169 | ROUND MTN-TABLE MTN #2 | 021/106 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2019-09-08 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.945532 | 40.5037 | ETL.6070 | 40818832 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116707947 | Q2 | T2 DI OLEUM-G #1 3/025 RPR FOND |  | OLEUM-G #1 | 003/025 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.234233 | 38.0074 | ETL.3150 | 40761585 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116707948 | Q2 | T2 DI OLEUM-G #1 3/027 RPR FOND |  | OLEUM-G #1 | 003/027 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-08 | 2024-03-08 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.234251 | 38.0048 | ETL.3150 | 40820388 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116708507 | Not Scheduled | T3 EI RND MTN-TBL MTN #1 21/109 CANCEL | 31440201 | ROUND MTN-TABLE MTN #1 | 021/109 | 93Z | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-09 | 2019-09-09 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.946912 | 40.4936 | ETL.6060 | 40868406 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116708580 | Q2 | DI IONE TAP 001/011 RPL STRW | 31425589 | IONE TAP | 001/011 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-09 | 2020-03-09 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.927073 | 38.3671 | ETL.8253 | 40596264 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116709406 | Not Scheduled | T2 DI CNTR COSTA-MORAGA #1 6/33 RPR FOND |  | CONTRA COSTA-MORAGA #1 | 006/033 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-08 | 2024-03-08 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.854426 | 37.977 | ETL.5452 | 40659436 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | 2019-04-16 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116709487 | Q2 | T2 EI MLN-RND MTN #2 051/255 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 051/255 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2020-03-11 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.567116 | 41.3136 | ETL.6020 | 40746557 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116709571 | Not Scheduled | T2 EI MALIN-RD MTN #2 066/335 COMPLETE | 31439323 | MALIN-ROUND MTN #2 | 066/335 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2020-03-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7290863 | 41.132 | ETL.6020 | 40782045 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116709807 | Not Scheduled | T2NT EI MLN-RND MTN #2 087/444B INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 087/444B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2024-03-11 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919367 | 40.8987 | ETL.6020 | 41162673 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116709969 | Q4 | EI KESWICK-TRINITY 22/160 RPL DAMP | 43740171 | KESWICK-TRINITY | 022/160 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-11 | 2021-05-31 |  |  | 2021-10-11 | 2021-10-04 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.5547142 | 40.6339 | ETL.7270 | 40699794 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116710129 | Not Scheduled | T2 DI TGR CRK-VLY SPRNGS 14/113 RPR FOND | 43830086 | TIGER CREEK-VALLEY SPRINGS | 014/113 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2024-03-11 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.670384 | 38.3246 | ETL.5790 | 40581567 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116710537 | Q2 | T2 EI PARADISE-TBL MTN 9/80 HELIWSH INSU | 43724324 | PARADISE-TABLE MTN | 009/080 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-06 | 2020-02-06 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.524229 | 39.5924 | ETL.4316 | 40608928 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116710636 | Not Scheduled | NEWARK-LIVERMORE 013/082 REPAINT MEMB |  | NEWARK-LIVERMORE | 013/082 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-11 | 2024-03-11 |  |  |  | 2020-12-02 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.805195 | 37.6177 | ETL.7660 | 40696213 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711231 | Not Scheduled | T2 EI RND MTN-TBL MT #1 016/084 RPR STRT | 43848514 | ROUND MTN-TABLE MTN #1 | 016/084 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2020-03-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.944979 | 40.5715 | ETL.6060 | 40759982 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711649 | Not Scheduled | T3 DI ROCK CREEK-POE 015/102 PAINT | 43724474 | ROCK CREEK-POE | 015/102 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-07 | 2019-09-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.478783 | 39.734 | ETL.5630 | 40674525 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711686 | Not Scheduled | T2 EI STNSLS-MLNS-MNTC#1 18/112 PNT STRS | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 018/112 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-07 | 2020-02-07 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.638792 | 37.9897 | ETL.3830 | 40669923 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711752 | Q2 | T2 DI IONE TAP 001/004 RPL STRW | 31499906 | IONE TAP | 001/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-11 | 2020-03-11 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.924383 | 38.3582 | ETL.8253 | 40745287 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-04-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711754 | Not Scheduled | T2 DI VALLEY SPRINGS #1 5/93 RPR STRW | 43831084 | VALLEY SPRINGS #1 | 005/093 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833271 | 38.1756 | ETL.8210 | 40905508 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711788 | Not Scheduled | T2 DI VALLEY SPRINGS #1 007/151 RPR GYWW | 43831083 | VALLEY SPRINGS #1 | 007/151 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.862603 | 38.144 | ETL.8210 | 40908234 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116711876 | Feb | T3 DI POE-RIO OSO 16/112 RPR INSS | 43724474 | ROCK CREEK-POE | 016/112 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-07 | 2019-09-07 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.48222 | 39.7127 | ETL.5630 | 40723992 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116712066 | Not Scheduled | T2 DI CHRISTIE SOBRANTE 9/53 RPL INSL | 31446629 | CHRISTIE-SOBRANTE | 009/053 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199235 | 38.0024 | ETL.1260 | 40669433 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Land |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116712072 | Not Scheduled | T2NT EI MLN-RND MTN #2 087/444A INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 087/444A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2024-03-11 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919147 | 40.8987 | ETL.6020 | 41162672 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116712303 | Q2 | T2 DI PARKWAY MORAGA 9/54 HRDT INST | 43683430 | PARKWAY-MORAGA | 009/054 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-09 | 2020-03-09 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233759 | 38.0065 | ETL.5930 | 40867736 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116713023 | Not Scheduled | T2 DI ELECTRA-BELLOTA 18/132 RPR FOND | 43844906 | ELECTRA-BELLOTA | 018/132 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-11 | 2020-03-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.889431 | 38.1257 | ETL.4670 | 40863029 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116713046 | Mar | T2 DI PLACER-DEL MAR 5/115 RPL STRW | 31454612 | PLACER-DEL MAR | 005/115 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-07 | 2020-03-07 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.158216 | 38.8504 | ETL.7800 | 40747059 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116713592 | Not Scheduled | T2 DI TIGER CREEK-VLY SP 15/124 RPR FOND | 43830085 | TIGER CREEK-VALLEY SPRINGS | 015/124 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2024-03-11 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.680275 | 38.31 | ETL.5790 | 40648161 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116713596 | Not Scheduled | T2 DI ELECTRA-BELLOTA 18/133 CANCEL | 43844906 | ELECTRA-BELLOTA | 018/133 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-11 | 2020-03-11 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.891218 | 38.1237 | ETL.4670 | 40862711 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116713874 | Q2 | EI COTTON-DELE #2 061/555 RPL INSS | 31450548 | COTTONWOOD-DELEVAN #2 | 061/555 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-04-02 | 2021-03-30 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.2683139 | 40.3685 | ETL.4580 | 40789122 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116713996 | Not Scheduled | T2 EI MALIN-RND MTN#2 67/341 COMPLETE | 43754876 | MALIN-ROUND MTN #2 | 067/341 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2020-03-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.742692 | 41.1212 | ETL.6020 | 40597344 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714036 | Q3 | T2 CRAG VIEW-CASCADE 000/009 REPL INSS | 31462721 | CRAG VIEW-CASCADE | 000/009 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-12 | 2021-05-31 |  |  | 2021-09-28 | 2021-09-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.412241 | 40.9212 | ETL.1350 | 41166982 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714290 | Q2 | EI MELONES-CURTIS 14/000L RPL POLE | 31485152 | MELONES-CURTIS | 014/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-04-02 | 2021-03-02 |  |  |  |  | LATE | Central | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-120.329469 | 37.9718 | ETL.2390 | 44391011 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  | Reject | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714308 | Not Scheduled | T2 EI MLIN-RND MTN #2 078/398A INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 078/398A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2022-03-11 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890795 | 41.0251 | ETL.6020 | 41162694 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714346 | Q2 | EI COTTONWOOD-DEL #2 61/556 RPL INSS | 31450548 | COTTONWOOD-DELEVAN #2 | 061/556 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-04-02 | 2021-03-30 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.2683017 | 40.3667 | ETL.4580 | 40845800 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714363 | Q2 | EI MELONES-CURTIS 14/000R RPL POLE | 31485152 | MELONES-CURTIS | 014/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-04-02 | 2021-03-02 |  |  |  |  | LATE | Central | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-120.329469 | 37.9718 | ETL.2390 | 44391012 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  | Reject | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714447 | Not Scheduled | T2 DI PARKWAY-MORAGA 7/44 RPL SHLS | 43753156 | PARKWAY-MORAGA | 007/044 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233594 | 38.0313 | ETL.5930 | 40872756 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714461 | Q2 | T2 EI MLN-RND MTN #2 080/406 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 080/406 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8952165 | 41.0042 | ETL.6020 | 40852031 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714835 | Not Scheduled | EI NEWARK-LAWRENCE LAB 14/088 RPR FOND |  | NEWARK-LIVERMORE | 014/088 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-12 | 2020-03-12 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.789525 | 37.6266 | ETL.7660 | 40875752 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714904 | Q2 | T2 EI MALIN-RND MTN#2 82/416 RPR OPGW | 43621093 | MALIN-ROUND MTN #2 | 082/416 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.909489 | 40.9783 | ETL.6020 | 40817711 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116714963 | Not Scheduled | EI STANIS-NEW #1 088/583 PAINT | 43753192 | STANISLAUS-NEWARK #1 (12KV) | 088/583 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-12 | 2020-03-12 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.809238 | 37.6187 | ETL.3850 | 41196254 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715215 | Not Scheduled | T2 EI DIABLO-GATES #1 58/239A REPAINT | 43756059 | DIABLO-GATES #1 | 058/239A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-12 | 2020-03-12 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.300477 | 35.8934 | ETL.5960 | 41130203 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715248 | Not Scheduled | T2 EI RND MT-TBL MT #1 15/080 RMV VEGN | 43877023 | ROUND MTN-TABLE MTN #1 | 015/080 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-12 | 2020-03-12 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.945298 | 40.5827 | ETL.6060 | 40601327 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715320 | Not Scheduled | EI TSLA-RVNSWD 017/092 REPL INSS | 31454851 | TESLA-RAVENSWOOD | 017/092 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-12 | 2020-03-12 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.8359257 | 37.599 | ETL.5730 | 40704316 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715353 | Not Scheduled | T2 EI MALIN-RND MTN#2 82/419A INST MRKS | 43621093 | MALIN-ROUND MTN #2 | 082/419A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2023-03-12 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913876 | 40.9704 | ETL.6020 | 41162607 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715433 | Not Scheduled | T2 DI VALLEY SPRINGS #1 7/147 RPR SPLW | 43831019 | VALLEY SPRINGS #1 | 007/147 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.860995 | 38.1462 | ETL.8210 | 40908230 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715488 | Q2 | T2 EI RND MT-TBL MT #1 16/87 RPL SPLS | 44305409 | ROUND MTN-TABLE MTN #1 | 016/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.944718 | 40.5628 | ETL.6060 | 40816705 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715669 | Not Scheduled | T2 EI TEMPLETON-GATES 48/204A REPAINT | 43923645 | TEMPLETON-GATES | 048/204A | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-12 | 2024-03-12 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.295703 | 35.8973 | ETL.5934 | 40911555 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116715725 | Not Scheduled | T2 DI PARKWAY-MORAGA 9/56 RPR STRT | 43753156 | PARKWAY-MORAGA | 009/056 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-11 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.233783 | 38.0027 | ETL.5930 | 40587012 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116716039 | Not Scheduled | T2 EI ROCK CREEK-POE 007/052 PAINT | 43724473 | ROCK CREEK-POE | 007/052 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-12 | 2024-03-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.422719 | 39.8302 | ETL.5630 | 40683788 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116716062 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 72/368 RPL HRDT |  | MALIN-ROUND MTN #2 | 072/368 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.81068 | 41.0702 | ETL.6020 | 40868974 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116716068 | Q2 | T2 EI MALIN-RND MTN#2 86/438 RPR OPGW | 43621093 | MALIN-ROUND MTN #2 | 086/438 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2020-03-12 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.918181 | 40.913 | ETL.6020 | 40871639 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116716300 | Q2 | EI COTTONWOOD-GLENN 61/554 RPL INSS | 31451261 | COTTONWOOD-GLENN | 061/554 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-12 | 2020-03-12 |  |  | 2021-06-04 | 2021-06-01 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.2683097 | 40.3703 | ETL.4560 | 40796993 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116716557 | Q2 | T2 EI MALIN-ROUND MTN#2 68/343 RPLC INSS | 43754876 | MALIN-ROUND MTN #2 | 068/343 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7465291 | 41.1182 | ETL.6020 | 40680148 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718001 | Not Scheduled | T2 DI MRGA-SN LNDRO #3 8/057 RPR FOND | 43753784 | MORAGA-SAN LEANDRO #3 | 008/057 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-12 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.119193 | 37.737 | ETL.2790 | 40804673 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718601 | Not Scheduled | T2 DI CHRISTIE-SOBRNTE 10/054 RPL HRDS | 43751914 | CHRISTIE-SOBRANTE | 010/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2020-03-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199192 | 38.0017 | ETL.1260 | 40745844 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Land |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718782 | Feb | T2 DI CC-MORAGA #1 24/113 RPR STRT | 44358165 | CONTRA COSTA-MORAGA #1 | 024/113 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-02-20 | 2021-02-15 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.120888 | 37.8621 | ETL.5452 | 40822239 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | 2019-04-16 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-04-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718842 | Q2 | T2 EI TESLA-MET 027/114 BENT MBR |  | TESLA-METCALF | 027/114 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2020-03-11 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.686896 | 37.3239 | ETL.6110 | 40753750 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718880 | Not Scheduled | T2 DI TGR CRK-VLY SPRNGS 15/125 RPR FOND | 43830091 | TIGER CREEK-VALLEY SPRINGS | 015/125 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2024-03-11 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.682415 | 38.3082 | ETL.5790 | 40645140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718884 | Not Scheduled | T2 DI TGR CRK-ELCTR 13/102 RPR FOND | 43830099 | TIGER CREEK-ELECTRA | 013/102 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-12 | 2022-03-12 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.665266 | 38.3401 | ETL.5780 | 40662458 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-12-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116718933 | Q2 | T2 EI HAT CRK #1-WESTWD 026/514 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 026/514 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-09 | 2020-02-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191597 | 40.6673 | ETL.7030 | 40817133 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116719413 | Q2 | T2 EI TESLA-METCALF 25/105 RPR GYWS | 43753282 | TESLA-METCALF | 025/105 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-09 | 2020-03-09 |  |  | 2021-06-26 | 2021-06-21 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.679879 | 37.3551 | ETL.6110 | 40753703 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116719414 | Q2 | T2 EI TESLA-METCALF 029/119 RPR GYWS | 43753282 | TESLA-METCALF | 029/119 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-06-26 | 2021-06-21 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.699665 | 37.3098 | ETL.6110 | 40870373 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116719415 | Q2 | T2 EI TESLA-METCALF 28/118 RPR GYWS | 43753282 | TESLA-METCALF | 028/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2020-03-12 |  |  | 2021-06-26 | 2021-06-21 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.697323 | 37.3124 | ETL.6110 | 40863785 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116719427 | Q2 | T2 EI TESLA-METCALF 026/109 RPR FOND |  | TESLA-METCALF | 026/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2020-03-11 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.676346 | 37.3394 | ETL.6110 | 40863441 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116719479 | Q2 | T2 EI MALIN-RND MTN #2 74/376 RPLC INSS | 43754876 | MALIN-ROUND MTN #2 | 074/376 | ICD | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-12 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8422022 | 41.0674 | ETL.6020 | 40837368 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116719494 | Mar | CORCORAN GUERNSEY 03/009 RPL TIED | 31430405 | CORCORAN-GUERNSEY | 003/009 | 93I | B | Pre-2020_(0) A and B Tags |  | 2019-03-12 | 2021-03-22 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.6220034 | 36.1088 | ETL.9360 | 40895352 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 116719572 | Q2 | T2 EI TULE-SPRINGVLLE 021/010A RPR SPLS | 43709294 | TULE-SPRINGVILLE | 021/010A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-12 | 2020-03-12 |  |  | 2021-04-30 | 2021-03-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | [8 empty] | ETL.9040 | 44264400 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116720048 | Not Scheduled | DI VALLEY SPRINGS #1 5/099 RPR STRW | 43831086 | VALLEY SPRINGS #1 | 005/099 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-08 | 2020-03-08 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.836202 | 38.1723 | ETL.8210 | 40905514 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721200 | Not Scheduled | T3 QC MORAGA SN LEANDRO#1 4/33 STRT PNT | 43708450 | MORAGA-SAN LEANDRO #1 | 004/033 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-13 | 2019-08-13 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.127977 | 37.7936 | ETL.2770 | 40644209 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721226 | Mar | EI CLR LKE-HPLND 000/014 RPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 000/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.067538 | 38.9699 | ETL.6390 | 40769721 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721481 | Not Scheduled | EI TESLA-NEWARK #2 015/100 RPR FOND |  | TESLA-NEWARK #2 | 015/100 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-13 | 2020-03-13 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.80855 | 37.6159 | ETL.5354 | 41152645 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721496 | Not Scheduled | T2 EI CARIBOU PALERMO :5/40 SPLS RPR | 44070463 | CARIBOU-PALERMO | :005/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721719 | Not Scheduled | T2 EI RND MTN-TBL MTN #2 9/52 REPL GYWS | 44156943 | ROUND MTN-TABLE MTN #2 | 009/052 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2020-03-13 | [6 empty] | Tower guy | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939259 | 40.6665 | ETL.6070 | 40663401 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721744 | Q2 | T2 EI TESLA-METCALF 034/142 RPR FOND |  | TESLA-METCALF | 034/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2021-05-31 |  |  | 2021-06-30 | 2021-06-28 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.737798 | 37.2324 | ETL.6110 | 40664359 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721826 | Q2 | T2 EI TESLA-METCALF 034/142 ZENA GRD |  | TESLA-METCALF | 034/142 | ICB | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-13 | 2022-03-13 |  |  | 2021-06-26 | 2021-06-21 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.737798 | 37.2324 | ETL.6110 | 40664359 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 593 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116721862 | Not Scheduled | T3 EI RND MT-TBL MT #2 008/047 RPR STRT | 43755806 | ROUND MTN-TABLE MTN #2 | 008/047 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2019-09-13 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Scheduling by circuit based. | '-121.939766 | 40.6829 | ETL.6070 | 40816729 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116722144 | Q2 | T2 EI MLN-RND MTN #2 72/367A RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 072/367A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-13 | 2020-03-13 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.809236 | 41.0711 | ETL.6020 | 40576756 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116722146 | Q2 | T2 EI MLN-RND MT #2 072/367 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 072/367 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-13 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8081859 | 41.0716 | ETL.6020 | 40846155 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116722318 | Not Scheduled | T2 SANTA YNEZ TAP 115KV 0/3 REPL INSULS | 31434029 | SANTA YNEZ TAP | 000/003 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2020-03-13 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.181979 | 34.6468 | ETL.3701 | 40711948 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116722522 | Not Scheduled | T2 DI TIDEWATER-SOBRANTE 16/80 RMV NEST | 43753287 | TIDEWATER-SOBRANTE | 016/080 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-13 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.118018 | 37.9627 | ETL.5770 | 40609117 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116722933 | Q2 | T2 EI MLN-RND MT #2 072/365 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 072/365 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-13 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8033481 | 41.0743 | ETL.6020 | 40782037 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116722963 | Feb | EI COALINGA #1-SAN MIGUEL 19/1 RMV SOIL | 44300672 | COALINGA #1-SAN MIGUEL | 019/001 | ICY | E | Pre-2020_(9a) Other ignition related |  | 2019-03-13 | 2020-03-13 |  |  | 2021-02-26 | 2021-02-15 |  |  | Likely MAT error - delink to correct |  | LATE | South | WSIP | [6 empty] | '-120.59577 | 35.9967 | ETL.8580 | 40597698 | Structure-Tower | Soil | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Pismo Beach |  |  | BLM | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116723165 | Not Scheduled | T2 SANTA YNEZ TAP 115KV 1/10 RPR INSW |  | SANTA YNEZ TAP | 001/010 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.167932 | 34.6422 | ETL.3701 | 40712630 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116723290 | Not Scheduled | T2 EI MLN-RND MT #2 072/364B INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 072/364B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-13 | 2022-03-13 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.801869 | 41.0751 | ETL.6020 | 41162772 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116723379 | Q2 | T2 EI CRESTA-RIO OSO 9/76 RPR SPLCS |  | CRESTA-RIO OSO | 009/076 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-13 | 2020-03-13 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.426171 | 39.8241 | ETL.4590 | 40910105 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116723413 | Mar | EI CLR LKE-HPLND 002/001 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 002/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.045335 | 38.9674 | ETL.6390 | 40584491 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116723421 | Not Scheduled | T2NT EI BCKS CRK-RCK CRK-CRST 5/50 REPNT | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 005/050 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-13 | 2020-03-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.410283 | 39.8477 | ETL.4430 | 40608902 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116723560 | Mar | EI CLR LKE-HPLND 002/002 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 002/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.043967 | 38.9675 | ETL.6390 | 40699137 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116725980 | Not Scheduled | T2 EI RD MTN-TBL MTN #2 77/313 REPL ANCS | 31474558 | ROUND MTN-TABLE MTN #2 | 077/313 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-14 | 2020-02-14 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.731925 | 39.713 | ETL.6070 | 40660100 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116727675 | Not Scheduled | T2 EI MLIN-RND MT #2 068/345A COMPLETE | 43621093 | MALIN-ROUND MTN #2 | 068/345A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-13 | 2020-03-13 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.754181 | 41.1121 | ETL.6020 | 40576895 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116731426 | Not Scheduled | T2 MALIN-ROUND MTN #2 -76/385 RPR GYWS | 43621093 | MALIN-ROUND MTN #2 | 076/385 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2021-05-31 | [6 empty] | Tower guy | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.86893 | 41.0574 | ETL.6020 | 40765410 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116731428 | Q2 | T2 EI MLN-ROUND MTN #2 76/385A RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 076/385A | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.869056 | 41.0575 | ETL.6020 | 41162684 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116731500 | Q2 | T2 EI MALIN-ROUND MTN #2 76/386 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 076/386 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871248 | 41.0554 | ETL.6020 | 40817709 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116731501 | Q2 | T2 EI MALIN-RND MTN #2 76/385B RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 076/385B | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-11 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8692 | 41.0576 | ETL.6020 | 41162686 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116731616 | Q2 | T2 EI MLN-RND MT #2 068/347 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 068/347 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-13 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7574349 | 41.1095 | ETL.6020 | 40843690 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116732149 | Not Scheduled | T2 DI TGR CRK-VLLY SPRGS 14/112 RPR FOND | 43836755 | TIGER CREEK-VALLEY SPRINGS | 014/112 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-11 | 2024-03-11 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.669879 | 38.3267 | ETL.5790 | 40582785 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116732725 | Not Scheduled | T2 EI CARB SW ST-RD MT R000/001 PAINT | 43897849 | CARBERRY SW STA-ROUND MTN | R000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-14 | 2024-03-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.937479 | 40.7918 | ETL.5410 | 40586641 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116732886 | Not Scheduled | T2 EI MB-CALIF FLATS SS 40/167B RPR INSU | 43763692 | MORRO BAY-GATES #2 | 040/167B | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-14 | 2020-03-14 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.394973 | 35.8059 | ETL.5280 | 40740430 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 1 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116732964 | Not Scheduled | T2 EI CARB SW ST-RO MT R000/002 PAINT | 43897849 | CARBERRY SW STA-ROUND MTN | R000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-14 | 2020-03-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937428 | 40.7929 | ETL.5410 | 40661608 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733071 | Not Scheduled | T2 EI VOLTA-DESCHUTES-014/312 RMV VEG | 43939089 | VOLTA-DESCHUTES | 014/312 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-03-14 | 2024-03-14 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.133119 | 40.5284 | ETL.8290 | 44186906 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733110 | Not Scheduled | T2 SPAULDING #3-SPAULDING #1 - 60 kV_000 | 31445624 | SPAULDING #3-SPAULDING #1 | 000/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-28 | 2020-02-28 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.642653 | 39.3294 | ETL.8050 | 40861958 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733243 | Not Scheduled | T2 EI CARB SW ST-RO MT R000/002 RMV VEGN |  | CARBERRY SW STA-ROUND MTN | R000/002 | HNA | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-14 | 2020-03-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937428 | 40.7929 | ETL.5410 | 40661608 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-06-14 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733549 | Not Scheduled | T2 EI PLRMO-COLGATE C008/036 INST DAMS | 43724331 | PALERMO-COLGATE | C008/036 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.333546 | 39.3066 | ETL.5360 | 40822161 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733618 | Q2 | T2 EI CARBERRY SS-R MTN R0/3 RPL INSS | 31450544 | CARBERRY SW STA-ROUND MTN | R000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-14 | 2020-03-14 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937014 | 40.7944 | ETL.5410 | 40693159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733782 | Not Scheduled | T3NT EI RUND MTN-T MTN #1 5/031 RPL GYMK | 43740167 | ROUND MTN-TABLE MTN #1 | 005/031 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-14 | 2020-03-14 | [5 empty] | TLN/TLQ error |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.942109 | 40.7275 | ETL.6060 | 40592679 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733787 | Not Scheduled | T2 EI MALIN-RND MTN #2 079/401 RPL HRDT | 43621093 | MALIN-ROUND MTN #2 | 079/401 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2020-03-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.891762 | 41.0179 | ETL.6020 | 40587306 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733828 | Q2 | T2 EI MALIN-RND MTN #2 079/401 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 079/401 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8917754 | 41.0179 | ETL.6020 | 40612253 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116733829 | Q2 | T2 EI MALIN-RND MTN #2 079/400 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 079/400 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-09 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8913259 | 41.0203 | ETL.6020 | 40635018 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734004 | Not Scheduled | EI TESLA-NEWARK #2 014/097 REPAINT | 43753285 | TESLA-NEWARK #2 | 014/097 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-14 | 2020-03-14 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.802733 | 37.6194 | ETL.5354 | 41152642 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734035 | Mar | EI DIABLO-GATES #1 54/220 INST STEPS | 43756059 | DIABLO-GATES #1 | 054/220 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-14 | 2021-05-31 |  |  | 2021-03-31 | 2021-03-03 |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.3536 | 35.844 | ETL.5960 | 40603335 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734038 | Not Scheduled | EI LAS POSITAS-NEWARK 7/050 PNT LADDER | 43753291 | LAS POSITAS-NEWARK | 007/050 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-14 | 2022-03-14 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.799276 | 37.6218 | ETL.4980 | 40862260 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734569 | Q2 | T2 EI MALIN-ROUND MTN #2 69/349A COTTER | 43621093 | MALIN-ROUND MTN #2 | 069/349A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2020-03-14 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.76361 | 41.1046 | ETL.6020 | 40576896 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734588 | Not Scheduled | T2 EI RND MT-TBL MT #2 011/063 RPL ANCS | 31488209 | ROUND MTN-TABLE MTN #2 | 011/063 | 93Z | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2020-03-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939001 | 40.6349 | ETL.6070 | 40651392 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734599 | Not Scheduled | T3 EI ROUND MTN-T MTN #1 8/45 RPL BOLT | 43790345 | ROUND MTN-TABLE MTN #1 | 008/045 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-14 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940575 | 40.6894 | ETL.6060 | 40746375 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734695 | Q2 | T2 EI MALIN-RND MTN #2 69/351 RPL INSS | 31527915 | MALIN-ROUND MTN #2 | 069/351 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7674293 | 41.1016 | ETL.6020 | 40610988 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734738 | Q2 | T2 EI MALIN-RND MTN #2 069/348 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 069/348 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2020-03-14 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7602167 | 41.1073 | ETL.6020 | 40893468 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734760 | Q2 | T2 EI MALIN-ROUND MTN #2 69/350 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 069/350 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7653229 | 41.1033 | ETL.6020 | 40635014 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734967 | Not Scheduled | T3 EI RND MTN-T M #1 008/044 INST HRDT | 43790345 | ROUND MTN-TABLE MTN #1 | 008/044 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-14 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940651 | 40.6913 | ETL.6060 | 40762867 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116734977 | Q2 | T2 EI MALIN-RND MTN #2 070/352 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 070/352 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7702866 | 41.0994 | ETL.6020 | 40722250 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116735272 | Q2 | T2 SANTA YNEZ TAP 115KV 2/21 REPL POLE | 31435800 | SANTA YNEZ TAP | 002/021 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-14 | 2020-03-14 |  |  | 2021-05-01 | 2021-05-01 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.146922 | 34.6354 | ETL.3701 | 40765581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116735568 | Not Scheduled | T2 DI TIGER CRK-VLY SPRG 15/123 RPR FOND | 43836745 | TIGER CREEK-VALLEY SPRINGS | 015/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2024-03-12 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.679707 | 38.3105 | ETL.5790 | 40590026 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116736170 | Not Scheduled | EI DIABLO-GATES #1 008/036 PAINT | 43756059 | DIABLO-GATES #1 | 008/036 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-14 | 2021-05-31 | [8 empty] | LATE | South | WSIP | FSRP | [5 empty] | '-120.798075 | 35.3088 | ETL.5960 | 40820161 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116736287 | Q2 | T2 SANTA YNEZ TAP 115KV 3/32 REPL POLE | 31435800 | SANTA YNEZ TAP | 003/032 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-14 | 2020-03-14 |  |  | 2021-05-01 | 2021-05-01 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.130278 | 34.6294 | ETL.3701 | 40751453 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116737553 | Q2 | T2 EI MALIN-RND MTN #2 69/350A RPL HRDT | 43621093 | MALIN-ROUND MTN #2 | 069/350A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.766673 | 41.1022 | ETL.6020 | 41111833 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116737554 | Q2 | T2 EI MALIN-ROUND MTN #2 69/350A COTTER | 43621093 | MALIN-ROUND MTN #2 | 069/350A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2020-03-14 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.766673 | 41.1022 | ETL.6020 | 41111833 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116737566 | Not Scheduled | T2 EI MALIN-RD MTN #2 071/358B INST MRKS | 43621093 | MALIN-ROUND MTN #2 | 071/358B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2022-03-14 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.787573 | 41.0856 | ETL.6020 | 41191648 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116739774 | Q2 | T2 EI MALIN-RND MTN #2 71/362B RPL SPLS | 43621093 | MALIN-ROUND MTN #2 | 071/362B | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.797676 | 41.0777 | ETL.6020 | 40740258 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116739805 | Q2 | T2 EI MALIN-RND MTN #2 70/356 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 070/356 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-14 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7792949 | 41.0922 | ETL.6020 | 40837366 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2020-02-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116740440 | Not Scheduled | T2 DI TGR CRK-VLLY SPRNG 13/111 RPL HRDT | 43836757 | TIGER CREEK-VALLEY SPRINGS | 013/111 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2024-03-12 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.669424 | 38.3286 | ETL.5790 | 40858406 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116740642 | Not Scheduled | T2 DI TGR CRK-VLLY SPRNG 13/111 RPR FOND | 43836758 | TIGER CREEK-VALLEY SPRINGS | 013/111 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-12 | 2024-03-12 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.669424 | 38.3286 | ETL.5790 | 40858406 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116741423 | Not Scheduled | T2 DI CARIBOU-PALERMO :9/70 RMV SOIL | 44070463 | CARIBOU-PALERMO | :009/070 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.254842 | 40.0061 | ETL.3190 | 40910312 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116741438 | Not Scheduled | EI LAS POSITAS-NEWARK 7/049 PNT TWR | 43753291 | LAS POSITAS-NEWARK | 007/049 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-15 | 2023-03-15 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.797571 | 37.6228 | ETL.4980 | 40872287 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116741512 | Mar | T2 EI PARADISE-BUTTE 9/89L RPR GYWS | 43881381 | PARADISE-BUTTE | 009/089 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-15 | 2020-03-15 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4396 | 44382927 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116741792 | Not Scheduled | T3 EI CARIBOU-PALERMO :012/096 RPL GYWS | 44304491 | CARIBOU-PALERMO | :012/096 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274824 | 39.9695 | ETL.3190 | 40910335 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116741872 | Not Scheduled | T3 EI CRIBOU-PLRMO :11/92 RPL BENT MMBER | 44304491 | CARIBOU-PALERMO | :011/092 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27547 | 39.9808 | ETL.3190 | 40910331 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116741890 | Not Scheduled | T3 EI CARIBOU-PALERMO :11/092 RPR JUMPER | 44304491 | CARIBOU-PALERMO | :011/092 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27547 | 39.9808 | ETL.3190 | 40910331 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116742120 | Not Scheduled | T3 EI CARIBOU-PALERMO :012/097 BENT MEMB | 44051418 | CARIBOU-PALERMO | :012/097 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274864 | 39.9683 | ETL.3190 | 40910336 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116742489 | Not Scheduled | EI NEWARK-LIVERMORE 012/075 RPR FOND |  | NEWARK-LIVERMORE | 012/075 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-15 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.819147 | 37.6093 | ETL.7660 | 40767814 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116742683 | Not Scheduled | T3 EI CARIBOU-PALERMO :10/084 RPR CONS | 44304491 | CARIBOU-PALERMO | :010/084 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116742904 | Not Scheduled | T3 EI CRIBOU-PALERMO :10/84 RPR BENT MEM | 44051418 | CARIBOU-PALERMO | :010/084 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116742933 | Not Scheduled | T3NT EI CARIBOU-PALERMO :10/82 RPNT MEMB | 44302715 | CARIBOU-PALERMO | :010/082 | ICS | F | Pre-2020_(3) On high spread structure |  | 2019-03-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272037 | 39.994 | ETL.3190 | 40910323 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116742951 | Not Scheduled | T3 EI CARIBOU-PALERMO :010/082 RPL INSS |  | CARIBOU-PALERMO | :010/082 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272037 | 39.994 | ETL.3190 | 40920062 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116743221 | Not Scheduled | T3 EI CARIBOU-PALERMO :010/078 RPL HRDS | 44304491 | CARIBOU-PALERMO | :010/078 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.267244 | 40.0011 | ETL.3190 | 40907020 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116743258 | Not Scheduled | T2 EI CTNWD-DLVN #2 070/614 RPNT TWR | 43730227 | COTTONWOOD-DELEVAN #2 | 070/614 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-07 | 2020-01-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267538 | 40.2386 | ETL.4580 | 40762881 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116743385 | Not Scheduled | T3 EI SNTH LN-HLF MN BY?010/8 WASH INSW |  | SNEATH LANE-HALF MOON BAY | ?010/008 | ICI | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.419356 | 37.4821 | ETL.7212 | 40901218 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116743470 | Not Scheduled | T3NT EI CARIBOU-PALERMO :10/079 REPAINT | 44302715 | CARIBOU-PALERMO | :010/079 | ICS | F | Pre-2020_(3) On high spread structure |  | 2019-03-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.268442 | 39.9988 | ETL.3190 | 40910320 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744475 | Not Scheduled | T2 EI HT CRK #1-PT #1 000/003 PNT STRT | 43749468 | HAT CREEK #1-PIT #1 | 000/003 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.501721 | 40.9872 | ETL.7020 | 40657262 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744477 | Not Scheduled | T3NT EI CARIBOU-PALERMO :32/263 REPAINT | 44304495 | CARIBOU-PALERMO | :032/263 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744487 | Not Scheduled | T3 EI RNDMTN-CTNWD#3 029/239 RPNT TWR | 43755803 | ROUND MTN-COTTONWOOD #3 | 029/239 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2019-07-25 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.955659 | 40.7713 | ETL.5650 | 40870436 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744503 | Not Scheduled | T2 EI CARIBOU-PALERMO 005/045 REPAINT | 44302715 | CARIBOU-PALERMO | 005/045 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-12 | 2021-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540407 | 39.526 | ETL.3190 | 40755507 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744508 | Not Scheduled | T2 EI SNTH LN-HLFMNBY ?011/8 RPNT STRS | 43752382 | SNEATH LANE-HALF MOON BAY | ?011/008 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-11 | 2024-01-11 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.424086 | 37.4718 | ETL.7212 | 40591479 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 30 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744510 | Not Scheduled | T2 EI HT CRK #1-PT #1 000/005 PNT STRT | 43749468 | HAT CREEK #1-PIT #1 | 000/005 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) | 2019-01-11 | 2020-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50641 | 40.9834 | ETL.7020 | 40769927 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744514 | Not Scheduled | T3 EI CRST-RO OSO 017/139 PNT STRT | 43708860 | CRESTA-RIO OSO | 017/139 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) | 2019-01-12 | 2019-07-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.479492 | 39.7275 | ETL.4590 | 40910155 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744515 | Not Scheduled | T2 EI PT #1-CTTNWD 009/075 RPR FOND | 43930183 | PIT #1-COTTONWOOD | 009/075 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-01-12 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.640715 | 40.9151 | ETL.5390 | 40759514 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744518 | Not Scheduled | T2 EI CARIBOU-PALERMO 6/53 PAINT STRT |  | CARIBOU-PALERMO | 006/053 |  | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-15 | 2021-01-15 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540497 | 39.5401 | ETL.3190 | 40660305 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744524 | Not Scheduled | T3 EI POE-RIO OSO 020/139 RPNT TWR | 43737420 | POE-RIO OSO | 020/139 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-11 | 2019-07-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.486317 | 39.6878 | ETL.5540 | 40870586 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744527 | Not Scheduled | T2 EI PRDS-TBL MTN 005/049 PNT STRT | 43727174 | PARADISE-TABLE MTN | 005/049 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54028 | 39.5358 | ETL.4316 | 40867305 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744532 | Not Scheduled | T2 EI HT CRK #1-PT #1 001/008 PNT STRT | 43749468 | HAT CREEK #1-PIT #1 | 001/008 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) | 2019-01-12 | 2020-01-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51109 | 40.9794 | ETL.7020 | 40877442 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744538 | Not Scheduled | T2 EI CARIBOU-PALERMO 004/044 REPAINT | 44302715 | CARIBOU-PALERMO | 004/044 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-11 | 2021-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540274 | 39.5245 | ETL.3190 | 40758609 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744553 | Not Scheduled | T2 EI CLINGA#1-SAN MIGUEL 30/03 RPNT TWR | 43763703 | COALINGA #1-SAN MIGUEL | 030/003 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-16 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.63867 | 35.8507 | ETL.8580 | 40663679 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744561 | Not Scheduled | T3 EI DRUM-HIGGINS 005/055 RPNT TWR | 43738143 | DRUM-HIGGINS | 005/055 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-18 | 2019-07-18 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839155 | 39.2099 | ETL.4393 | 40751947 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744573 | Not Scheduled | T2 EI DRM-HGGNS 15/135 PNT STRT | 43738143 | DRUM-HIGGINS | 015/135 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-22 | 2024-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.976913 | 39.1528 | ETL.4393 | 40690223 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744576 | Not Scheduled | T2 EI CORTINA-VACA 011/076 RPNT TWR | 44304829 | CORTINA-VACA | 011/076 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-22 | 2024-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.126187 | 38.9646 | ETL.4540 | 40689900 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744579 | Not Scheduled | T2 EI CORTINA-VACA 012/077 PAINT | 44304829 | CORTINA-VACA | 012/077 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-22 | 2024-01-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.125102 | 38.9628 | ETL.4540 | 40655809 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744584 | Not Scheduled | T2 EI CORTINA-VACA 012/079 PAINT | 44304829 | CORTINA-VACA | 012/079 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2024-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.121487 | 38.9568 | ETL.4540 | 40757914 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744586 | Before Feb | T3 EI DRM-HGGNS 016/141 PNT STRT | 43738143 | DRUM-HIGGINS | 016/141 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-23 | 2019-07-23 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.992547 | 39.1467 | ETL.4393 | 40862213 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744589 | Not Scheduled | T2 EI CARIBOU-PALERMO :6/051 PAINT STRT |  | CARIBOU-PALERMO | :006/051 |  | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-23 | 2021-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.221517 | 40.0202 | ETL.3190 | 40910293 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744594 | Not Scheduled | T3 EI MRGA-OAKLND#3 000/004 RPNT TWR | 43725286 | MORAGA-OAKLAND #3 | 000/004 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-22 | 2019-07-22 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.169892 | 37.8468 | ETL.2740 | 40745871 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744601 | Not Scheduled | T2 EI CARIBOU-PALEMO :26/220 BURIED MEMB | 44069454 | CARIBOU-PALERMO | :026/220 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-23 | 2020-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744603 | Not Scheduled | T2 EI CRIBOU-PALRMO :27/222 PAINT STRT |  | CARIBOU-PALERMO | :027/222 |  | F | Pre-2020_(3) On high spread structure |  | 2019-01-23 | 2021-01-23 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.433688 | 39.8145 | ETL.3190 | 40702271 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744606 | Not Scheduled | EI CORTINA-VACA 013/085 CANCEL | 44304829 | CORTINA-VACA | 013/085 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2020-01-24 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.114486 | 38.9453 | ETL.4540 | 40591070 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744608 | Not Scheduled | EI CORTINA-VACA 013/084 CANCEL | 43729335 | CORTINA-VACA | 013/084 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-23 | 2020-01-23 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.115552 | 38.947 | ETL.4540 | 40598512 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744616 | Not Scheduled | T2 EI CORTNA-MNDCINO #1 025/122 RPNT STR | 43721139 | CORTINA-MENDOCINO #1 | 025/122 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2020-01-24 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.654517 | 39.0287 | ETL.1330 | 40657052 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-05-08 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744617 | Not Scheduled | T3 EI DRUM-HIGGINS 016/144 PNT STRT | 43738143 | DRUM-HIGGINS | 016/144 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2019-07-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.002818 | 39.1426 | ETL.4393 | 40913040 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744625 | Not Scheduled | T3 EI RND MTN-CTNWD #3 028/234 CANCEL | 43755803 | ROUND MTN-COTTONWOOD #3 | 028/234 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2019-07-25 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950791 | 40.7772 | ETL.5650 | 40755449 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744638 | Not Scheduled | T3 EI RCK CRK-PE 011/082 PNT STRT | 43724473 | ROCK CREEK-POE | 011/082 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2019-07-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.453946 | 39.7785 | ETL.5630 | 40690317 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744645 | Before Feb | T3 EI DRM-HGGNS 016/145 PNT STRT | 43738143 | DRUM-HIGGINS | 016/145 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-24 | 2019-07-24 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.006557 | 39.1411 | ETL.4393 | 40913041 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744646 | Not Scheduled | T2 EI MTCLF-GRN VLLY 007/048 PNT STRT | 44300700 | METCALF-GREEN VALLEY | 007/048 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2024-01-24 | [8 empty] | LATE | South | WSIP | FSRP | [5 empty] | '-121.682866 | 37.1535 | ETL.2540 | 40861181 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744649 | Not Scheduled | T2 EI CARIBOU-PALERMO :25/208 REPAINT | 44302715 | CARIBOU-PALERMO | :025/208 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-24 | 2021-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.419325 | 39.8395 | ETL.3190 | 40878271 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744650 | Not Scheduled | T3 RNDMTN-CTNWD#3 28/232 CANCEL | 43900105 | ROUND MTN-COTTONWOOD #3 | 028/232 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2019-07-25 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.948693 | 40.7797 | ETL.5650 | 40662733 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744651 | Not Scheduled | T3 EI RND MTN-CTTNWD #3 028/233 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 028/233 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2019-07-25 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.949661 | 40.7785 | ETL.5650 | 40653356 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744660 | Not Scheduled | T2 EI MTCLF-MSSLNDING #1 33/150 RPNT TWR | 44300679 | METCALF-MOSS LANDING #1 | 033/150 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.681472 | 37.1455 | ETL.5100 | 40596466 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744661 | Not Scheduled | EI DLVN-VC #2 163/1239 PNT STRT | 44452822 | DELEVAN-VACA #2 | 163/1239 | ICX | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2024-01-26 | [6 empty] | Likely MAT error - delink to correct |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.097185 | 38.9171 | ETL.4231 | 40869552 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744664 | Not Scheduled | T2 EI DRM-HGGNS 019/159 PNT STRT | 43738143 | DRUM-HIGGINS | 019/159 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2024-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.053528 | 39.1226 | ETL.4393 | 40913055 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744674 | Not Scheduled | T2 EI CARIBOU-PALERMO :05/38 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :005/038 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.216968 | 40.0432 | ETL.3190 | 40910281 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744675 | Not Scheduled | T3 EI RND MTN-CTTNWD #3 029/240 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 029/240 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-25 | 2019-07-25 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.957067 | 40.7696 | ETL.5650 | 40594999 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744677 | Not Scheduled | EI CORTINA-VACA 015/096 PAINT | 44304830 | CORTINA-VACA | 015/096 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-25 | 2021-01-25 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.100678 | 38.9225 | ETL.4540 | 40670968 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744680 | Before Feb | T2 EI DRUM-HIGGINS 020/162 RPNT TWR | 43738143 | DRUM-HIGGINS | 020/162 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-26 | 2020-01-26 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.057427 | 39.1183 | ETL.4393 | 40913058 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744681 | Not Scheduled | T2 EI DRUM-RIO OSO #1 018/149 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 018/149 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2024-01-26 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.060911 | 39.1198 | ETL.1420 | 40865480 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744682 | Not Scheduled | EI DLVN-VC #2 164/1240 PNT STRT | 44452824 | DELEVAN-VACA #2 | 164/1240 | ICX | F | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2024-01-26 | [6 empty] | Likely MAT error - delink to correct |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.096088 | 38.9153 | ETL.4231 | 40608953 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744685 | Not Scheduled | T3 EI RNDMTN-CTNWD#3 032/271 CANCEL | 43755803 | ROUND MTN-COTTONWOOD #3 | 032/271 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2019-07-26 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98802 | 40.7326 | ETL.5650 | 40594853 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744687 | Before Feb | T2NT EI PT #6 JCT-RND MTN14/129 PNT STRT | 43854766 | PIT #6 JCT-ROUND MTN | 014/129 | ICQ | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-26 | 2023-01-26 |  |  | 2020-09-21 | 2020-09-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938408 | 40.8088 | ETL.5440 | 40868192 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Before Feb | IC | Before Feb |  |  | 2019-08-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744688 | Not Scheduled | T3 EI RND MTN-CTTNWD #3 032/270 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 032/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2019-07-26 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.986851 | 40.734 | ETL.5650 | 40605780 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744691 | Not Scheduled | T2 EI MRR BY-MS 020/091 PNT STRT | 43769287 | MORRO BAY-MESA | 020/091 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-26 | 2020-01-26 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.592536 | 35.1733 | ETL.5290 | 40587104 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  | 2019-04-08 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744699 | Not Scheduled | T2 CARIBOU-PALERMO :4/37 RPR FOND | 44059014 | CARIBOU-PALERMO | :004/037 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.216388 | 40.0451 | ETL.3190 | 40907002 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744701 | Not Scheduled | T2 EI PIT #5-ROUND MTN #1 0/002 RPNT TWR | 44322478 | PIT #5-ROUND MTN #1 | 000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.973862 | 40.9838 | ETL.5420 | 40660950 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744703 | Not Scheduled | T2 CARIBOU-PALERMO :4/32 RPR FOND | 44059014 | CARIBOU-PALERMO | :004/032 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-25 | 2020-01-25 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.206261 | 40.0532 | ETL.3190 | 40910276 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744717 | Not Scheduled | T2 EI PT #5-RND MTN #2 000/006 PNT STRT | 43755669 | PIT #5-ROUND MTN #2 | 000/006 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.966566 | 40.9795 | ETL.5430 | 40810526 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744723 | Not Scheduled | T3 EI RNDMTN-CTNWD #3 032/268 RPNT TWR | 43755803 | ROUND MTN-COTTONWOOD #3 | 032/268 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2019-07-26 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984819 | 40.7364 | ETL.5650 | 40863128 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744727 | Not Scheduled | T2 EI PIT #5-ROUND MTN #2 0/004 RPNT TWR | 43755672 | PIT #5-ROUND MTN #2 | 000/004 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-26 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.969026 | 40.9809 | ETL.5430 | 40752235 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744745 | Not Scheduled | T2 STAN MELONES SS :007/040 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :007/040 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-28 | 2024-01-28 |  |  |  | 2020-12-01 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.6377616 | 37.9827 | ETL.3830 | 40639678 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744751 | Not Scheduled | T2NT EI PT #5-RND MTN #1 8/082 PNT STRT | 43758397 | PIT #5-ROUND MTN #1 | 008/082 | ICQ | F | Pre-2020_(2) High fire spread TD | Budget Owner (Paint) | 2019-01-28 | 2021-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 | '-121.93003 | 40.878 | ETL.5420 | 40657422 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744755 | Not Scheduled | EI CORTINA-VACA 016/104 RPR PAINT CANCEL | 44304829 | CORTINA-VACA | 016/104 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.09058 | 38.9058 | ETL.4540 | 40596757 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744756 | Before Feb | T2 EI DRUM-HIGGINS 022/176 RPNT TWR | 43738143 | DRUM-HIGGINS | 022/176 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-29 | 2020-01-29 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Per email from [REDACTED], crew submit to wrong notification. This submission was intended for 115761236. |  |  | '-121.094955 | 39.1062 | ETL.4393 | 40913072 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  | Reject | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744763 | Not Scheduled | T2NT EI PT #5-RND MTN #1 9/091 PNT STRT | 43758397 | PIT #5-ROUND MTN #1 | 009/091 | ICQ | F | Pre-2020_(4) TD tag on high spread line | Budget Owner (Paint) | 2019-01-28 | 2021-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.931538 | 40.8615 | ETL.5420 | 40660391 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744775 | Not Scheduled | T2 CARIBOU-PALERMO :23/196 REPAINT | 44302715 | CARIBOU-PALERMO | :023/196 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-24 | 2021-01-24 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.399908 | 39.853 | ETL.3190 | 40828384 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744781 | Not Scheduled | T2 EI BCKS CRK-RCK CRK-CRST 1/11 PAINT | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 001/011 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-28 | 2024-01-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.345489 | 39.9088 | ETL.4430 | 40586032 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744782 | Not Scheduled | EI DELEVAN-VACA #2 164/1243 PAINT CANCEL | 44305192 | DELEVAN-VACA #2 | 164/1243 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.091479 | 38.9076 | ETL.4231 | 40656796 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744783 | Not Scheduled | EI CORTINA-VACA 016/105 RPR PAINT | 44304830 | CORTINA-VACA | 016/105 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-29 | 2021-01-29 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.089838 | 38.9045 | ETL.4540 | 40589935 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744785 | Not Scheduled | EI DELEVAN-VACA #2 164/1244 PAINT CANCEL | 44305192 | DELEVAN-VACA #2 | 164/1244 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.090391 | 38.9058 | ETL.4231 | 40759070 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744791 | Not Scheduled | T2 EI RND MTN-CTTNWD #2 022/206 PNT STRT | 43691533 | ROUND MTN-COTTONWOOD #2 | 022/206 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.042248 | 40.6993 | ETL.5640 | 40816295 | Structure-Tower | No Good/Out of Stdrd | Repair | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744795 | Not Scheduled | T2 EI STNL-MLN SW ST-MTC#1 :5/29PNT STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | :005/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.607476 | 37.9675 | ETL.3830 | 40856491 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744797 | Before Feb | T2 EI DRM-HGGNS 022/177 PNT STRT | 43738143 | DRUM-HIGGINS | 022/177 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-29 | 2020-01-29 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097356 | 39.1052 | ETL.4393 | 40913073 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744800 | Not Scheduled | EI CORTINA-VACA -016/107 PAINT | 44304830 | CORTINA-VACA | 016/107 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-29 | 2021-01-29 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.08668 | 38.8993 | ETL.4540 | 40654590 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744806 | Not Scheduled | T2 EI DRUM-RIO OSO #1 020/162 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 020/162 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.094698 | 39.1064 | ETL.1420 | 40670155 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744807 | Not Scheduled | T2 EI STNSLS-MLNS SW-MNTCA #1 :4/28 RPNT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :004/028 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.605922 | 37.9669 | ETL.3830 | 40875487 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744808 | Not Scheduled | T2 EI STNSLS-MLN SW ST-MTC #1 PNT STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | :003/022 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-29 | 2020-01-29 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-120.589068 | 37.9602 | ETL.3830 | 40642906 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744811 | Not Scheduled | T2NT EI CARIBOU-PLRMO :20/170 PAINT STRT |  | CARIBOU-PALERMO | :020/170 |  | F | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2021-01-29 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.363578 | 39.8908 | ETL.3190 | 40642282 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744814 | Not Scheduled | T3 EI MSRIFLT-GLDHLL#1 19/158 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 019/158 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892042 | 38.6645 | ETL.2660 | 40862234 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744816 | Before Feb | T2 EI DRUM-HIGGINS 027/208 RPNT TWR | 43738143 | DRUM-HIGGINS | 027/208 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-30 | 2020-01-30 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.092139 | 39.0472 | ETL.4393 | 40658224 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744818 | Not Scheduled | T2 EI PIT #4 TAP 000/005 RPNT TWR | 43756947 | PIT #4 TAP | 000/005 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2024-01-30 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.862076 | 40.9854 | ETL.5432 | 40752299 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744819 | Not Scheduled | EI CORTINA-VACA -017/113 PAINT | 44304829 | CORTINA-VACA | 017/113 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2024-01-30 | [8 empty] | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.079737 | 38.8878 | ETL.4540 | 40865836 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744820 | Not Scheduled | EI CORTINA-VACA -017/109 PAINT | 44304829 | CORTINA-VACA | 017/109 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-122.085182 | 38.8968 | ETL.4540 | 40756643 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744824 | Not Scheduled | T3 EI GYSRS #13 TP 000/005 PNT STRT | 43761567 | GEYSERS #13 TAP | 000/005 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.73934 | 38.775 | ETL.4781 | 40746212 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744825 | Not Scheduled | T2 EI DRUM-RIO OSO #1 021/166 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 021/166 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2024-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.107424 | 39.1014 | ETL.1420 | 40805297 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744834 | Not Scheduled | T2 EI CNTRA CSTA-MRG#1 024/111 PAINT | 43753199 | CONTRA COSTA-MORAGA #1 | 024/111 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-30 | 2024-01-30 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.117104 | 37.8602 | ETL.5452 | 40746201 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744835 | Not Scheduled | T3 EI SNTAFEGTHERMAL TAP 0/3 RPNT TWR | 43729334 | SANTA FE GEOTHERMAL TAP | 000/003 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.746969 | 38.7871 | ETL.4782 | 40659183 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744836 | Not Scheduled | T3 EI MRG-SN LNDR #1 000/004 PNT STRT | 43715763 | MORAGA-SAN LEANDRO #1 | 000/004 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-30 | 2019-07-30 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.164395 | 37.8407 | ETL.2770 | 40764851 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744837 | Not Scheduled | EI CORTINA-VACA 017/110 CANCEL | 44304829 | CORTINA-VACA | 017/110 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2020-01-30 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.083906 | 38.8947 | ETL.4540 | 40814753 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2020-07-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744844 | Not Scheduled | EI CORTINA-VACA 018/118 CANCEL | 44304829 | CORTINA-VACA | 018/118 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2020-01-31 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.071843 | 38.8748 | ETL.4540 | 40756707 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744847 | Not Scheduled | T2 EI STNSLS-MNS-MNTCA#1 20/125 RPNT TWR | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/125 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.665458 | 37.9699 | ETL.3830 | 40744438 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744848 | Not Scheduled | T3 EI MSRIFLT-GLDHLL#1 18/155 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 018/155 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2019-08-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.880254 | 38.6669 | ETL.2660 | 40761892 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744852 | Not Scheduled | T3 EI MSSRIFLT-GLDHILL#1 18/154 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 018/154 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.875671 | 38.6678 | ETL.2660 | 40753623 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744853 | Not Scheduled | T2 EI PT #4 TP 000/001 PNT STRT | 43756947 | PIT #4 TAP | 000/001 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.849746 | 40.987 | ETL.5432 | 40592506 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744855 | Not Scheduled | T2 EI BCK CR-RK CR-CR 007/063 PAINT | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 007/063 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2024-01-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.419304 | 39.8293 | ETL.4430 | 40656157 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744860 | Not Scheduled | T2 EI STNSLS-MLNSSW-MNTC#1 :0/1 RPNT TWR | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :000/001 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-31 | 2020-01-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.528009 | 37.9459 | ETL.3830 | 40599421 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744861 | Not Scheduled | EI CORTINA-VACA -018/117 PAINT | 44304830 | CORTINA-VACA | 018/117 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-31 | 2021-01-31 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.073865 | 38.8781 | ETL.4540 | 40654591 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744864 | Not Scheduled | EI CORTINA-VACA 18/116 PAINT | 44304830 | CORTINA-VACA | 018/116 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-31 | 2021-01-31 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.074727 | 38.8795 | ETL.4540 | 40670976 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744865 | Not Scheduled | T3 EI MSRIFLT-GLDHLL#1 17/148 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 017/148 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.860207 | 38.6752 | ETL.2660 | 40873254 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744866 | Not Scheduled | EI MORAGA-SAN LEANDRO #3 009/064 PAINT | 43728142 | MORAGA-SAN LEANDRO #3 | 009/064 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-31 | 2022-01-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-122.133778 | 37.7251 | ETL.2790 | 40745897 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744869 | Not Scheduled | T2 DRUM-RIO OSO #1 024/180 PNT STRT | 44304427 | DRUM-RIO OSO #1 | 024/180 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2024-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.148176 | 39.0851 | ETL.1420 | 40596161 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744872 | Not Scheduled | EI STANISLAUS-MANTECA#2 027/158 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 027/158 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-01-31 | 2021-01-31 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.766736 | 37.9239 | ETL.3820 | 40856504 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744876 | Not Scheduled | EI STAN-MEL SW ST-MA #1 026/166 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/166 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-31 | 2020-01-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.766791 | 37.924 | ETL.3830 | 40744440 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744881 | Before Feb | T2 EI DRM-HGGNS 027/205 PNT STRT | 43738143 | DRUM-HIGGINS | 027/205 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-01-31 | 2020-01-31 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096126 | 39.0533 | ETL.4393 | 40602393 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744882 | Not Scheduled | T3 EI GYSRS #13 TP 001/009 PNT STRT | 43761567 | GEYSERS #13 TAP | 001/009 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.755376 | 38.7783 | ETL.4781 | 40869699 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744883 | Not Scheduled | EI STAN-MEL SW ST-MA #1 026/167 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/167 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-01-31 | 2020-01-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.768366 | 37.9236 | ETL.3830 | 40751408 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744892 | Not Scheduled | T2 EI DRUM-RIO OSO #1 025/186 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 025/186 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2023-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.163684 | 39.0789 | ETL.1420 | 40814362 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744893 | Not Scheduled | T2 EI DRM-RIO OSO #1 025/187 PNT STRT | 44304427 | DRUM-RIO OSO #1 | 025/187 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2023-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.165884 | 39.078 | ETL.1420 | 40813555 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744894 | Not Scheduled | T2 EI CARIBOU-PALERMO :23/195 REPAINT | 44302715 | CARIBOU-PALERMO | :023/195 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2021-01-31 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.399102 | 39.8539 | ETL.3190 | 40758490 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744898 | Not Scheduled | T3 EI GEYSERS #13 TAP 001/010 RPNT TWR | 43693054 | GEYSERS #13 TAP | 001/010 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2019-07-31 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.759345 | 38.7788 | ETL.4781 | 40588014 | Structure-Steel | Paint/Coating | Other | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744904 | Not Scheduled | T2 EI BALCH-SANGER 016/084 PAINT | 43709727 | BALCH-SANGER | 016/084 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.319731 | 36.8237 | ETL.1050 | 40748595 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744905 | Not Scheduled | T2 EI HS-MCCLL 019/103 PNT STRT | 43709743 | HAAS-MCCALL | 019/103 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2024-02-01 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.319818 | 36.8239 | ETL.4850 | 40657755 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744911 | Not Scheduled | T2 EI VCA-PRKWY 004/027 RPNT TWR | 44305724 | VACA-PARKWAY | 004/027 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.001644 | 38.4046 | ETL.5850 | 40813753 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744913 | Not Scheduled | T2 EI DRUM-RIO OSO #1 024/181 RPNT STRT | 43746398 | DRUM-RIO OSO #1 | 024/181 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2024-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.151287 | 39.0839 | ETL.1420 | 40587527 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744918 | Not Scheduled | T2 EI DRM-RIO OSO #1 024/183 PNT STRT | 44304427 | DRUM-RIO OSO #1 | 024/183 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.156721 | 39.0817 | ETL.1420 | 40654198 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744919 | Not Scheduled | EI STANISLAUS-MANTECA#2 026/156 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/156 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-02-01 | 2021-02-01 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.759524 | 37.9261 | ETL.3820 | 40803378 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116744920 | Not Scheduled | EI STANISLAUS-MANTECA#2 026/153 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/153 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-01 | 2020-02-01 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.751638 | 37.9284 | ETL.3820 | 40651750 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744921 | Not Scheduled | T2 CARIBOU-PALERMO :4/35 REPAINT STRT |  | CARIBOU-PALERMO | :004/035 |  | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-01 | 2020-02-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744922 | Not Scheduled | T2 EI STNSLS-MLS-MNTC#1 20/131 CANCEL | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/131 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-01 | 2020-02-01 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.677445 | 37.961 | ETL.3830 | 40604620 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744926 | Not Scheduled | EI STANISLAUS-MANTECA #2 026/154 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/154 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-01 | 2020-02-01 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.753705 | 37.9278 | ETL.3820 | 40750272 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744929 | Not Scheduled | EI STANISLAUS-MANTECA #2 028/168 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 028/168 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-01 | 2020-02-01 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.791685 | 37.9165 | ETL.3820 | 40861754 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2018-10-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744930 | Not Scheduled | EI STAN-MANTECA #2 026/155 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/155 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-01 | 2020-02-01 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.756662 | 37.9269 | ETL.3820 | 40744469 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2018-10-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744931 | Not Scheduled | T2NT EI STNSLS-MNTC #2 021/125 PNT STRT | 43712838 | STANISLAUS-MANTECA #2 | 021/125 | ICQ | F | Pre-2020_(4) TD tag on high spread line | Budget Owner (Paint) | 2019-02-01 | 2021-02-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.682195 | 37.9573 | ETL.3820 | 40753678 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744933 | Not Scheduled | T2 EI CRBU PALERMO :00/002 BENT STEEL | 43742125 | CARIBOU-PALERMO | :000/002 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-02 | 2020-02-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.149439 | 40.0846 | ETL.3190 | 44188832 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744935 | Not Scheduled | T2 EI HAAS-MCCALL 021/114 RPNT TWR | 43709744 | HAAS-MCCALL | 021/114 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-01 | 2024-02-01 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.360659 | 36.8153 | ETL.4850 | 40760132 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744938 | Not Scheduled | T2 EI BALCH-SANGER 007/044 PAINT | 43709727 | BALCH-SANGER | 007/044 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.186531 | 36.8777 | ETL.1050 | 44307581 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744952 | Not Scheduled | T2 EI CTTNWD #1 005/034 CANCEL | 44585953 | COTTONWOOD #1 | 005/034 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2020-02-04 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.267813 | 40.3261 | ETL.6620 | 40910978 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744953 | Not Scheduled | T2NT EI PIT #1-CTTNWD 53/481 REPAINT | 43879363 | PIT #1-COTTONWOOD | 053/481 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-04 | 2020-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.206769 | 40.4692 | ETL.5390 | 40592475 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744954 | Not Scheduled | T3 EI EGL RCK-FLTN-SLVRD 4/18 REPAINT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 004/018 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2019-08-04 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.764133 | 38.671 | ETL.4392 | 41129321 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744955 | Not Scheduled | T2 EI CTTNWD #1 :005/036 CANCEL | 44585953 | COTTONWOOD #1 | 005/036 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2020-02-04 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.267779 | 40.3221 | ETL.6620 | 40910979 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744960 | Not Scheduled | T2 EI BALCH-SANGER 007/043 PAINT | 43709727 | BALCH-SANGER | 007/043 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-29 | 2020-01-29 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.184727 | 36.878 | ETL.1050 | 40646826 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744961 | Not Scheduled | T2 EI DRUM-RIO OS #1 24/185 REPAINT STRT | 44304427 | DRUM-RIO OSO #1 | 024/185 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2022-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.162231 | 39.0794 | ETL.1420 | 40746548 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744962 | Not Scheduled | T3 EI EAGLE ROCK-REDBUD :8/048 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :008/048 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2019-08-04 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.685011 | 38.8871 | ETL.1480 | 40861251 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-06-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744973 | Not Scheduled | T2 EI DRUM-RIO OSO #1 26/194 REPNT STRT | 44304427 | DRUM-RIO OSO #1 | 026/194 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-04 | 2024-02-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.185517 | 39.07 | ETL.1420 | 40764902 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744974 | Not Scheduled | T2 EI PT #4 TP 000/004 PNT STRT | 43756947 | PIT #4 TAP | 000/004 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-30 | 2020-01-30 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.859918 | 40.9857 | ETL.5432 | 40765746 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744976 | Not Scheduled | T2 EI PIT #4 TAP 001/010 RPNT TWR | 43756947 | PIT #4 TAP | 001/010 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-31 | 2024-01-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.875509 | 40.982 | ETL.5432 | 40601048 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744977 | Not Scheduled | T2 EI PIT #4 TAP 000/002 RPNT TWR | 43756947 | PIT #4 TAP | 000/002 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-01-30 | 2024-01-30 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.85332 | 40.9866 | ETL.5432 | 40688058 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744978 | Not Scheduled | T2 EI DRUM-RIO OSO #1 26/195 REPAINT | 44304427 | DRUM-RIO OSO #1 | 026/195 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2024-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.188222 | 39.0689 | ETL.1420 | 40762307 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744979 | Before Feb | T2 EI DRUM-HIGGINS 025/194 REPAINT | 43738143 | DRUM-HIGGINS | 025/194 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-05 | 2020-02-05 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11171 | 39.0774 | ETL.4393 | 40868884 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-09-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744981 | Not Scheduled | T2 EI VACA-LAKEVILLE #1 005/029 RPNT TWR | 43740456 | VACA-LAKEVILLE #1 | 005/029 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-05 | 2020-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.012795 | 38.3963 | ETL.5840 | 40867684 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744982 | Before Feb | T2NT EI DRUM-HIGGINS 25/196 REPAINT | 43738143 | DRUM-HIGGINS | 025/196 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-05 | 2020-02-05 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.108772 | 39.0728 | ETL.4393 | 40592845 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-09-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744983 | Not Scheduled | T3 EI MSSR FLT-GLD #1 17/151 REPAINT | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 017/151 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.867462 | 38.6708 | ETL.2660 | 40913117 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744984 | Not Scheduled | T3 EI POE-RIO OSO 19/131A REPAINT | 43737420 | POE-RIO OSO | 019/131A | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.482894 | 39.7089 | ETL.5540 | 43202197 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744985 | Not Scheduled | T3 EI EAGLE ROCK-REDBUD :5/30 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :005/030 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.743442 | 38.8779 | ETL.1480 | 40604567 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-06-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744987 | Not Scheduled | T3 EI EAGLE ROCK-REDBUD :04/27 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :004/027 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.752407 | 38.8754 | ETL.1480 | 40808633 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | Yes | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744992 | Before Feb | T2 EI DRUM-HIGGINS 025/197 REPAINT | 43738143 | DRUM-HIGGINS | 025/197 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-05 | 2020-02-05 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107493 | 39.0709 | ETL.4393 | 40690102 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-09-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744993 | Not Scheduled | T3 EI EAGLE ROCK-FN-SO 13/58 REPAINT | 43713428 | EAGLE ROCK-FULTON-SILVERADO | 013/058 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.696251 | 38.5642 | ETL.4392 | 41129360 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116744995 | Not Scheduled | T3NT EI POE-RIO OSO 19/129 REPAINT | 43737420 | POE-RIO OSO | 019/129 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2019-08-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.481635 | 39.716 | ETL.5540 | 40866272 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745003 | Before Feb | T2 EI DRUM-HIGGINS 024/191 REPAINT | 43738143 | DRUM-HIGGINS | 024/191 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-05 | 2020-02-05 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.116017 | 39.084 | ETL.4393 | 40818401 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745005 | Not Scheduled | T2 EI DRUM-RIO OSO #1 27/199 REPANT STRT | 44304427 | DRUM-RIO OSO #1 | 027/199 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2024-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.197637 | 39.0651 | ETL.1420 | 40865486 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745006 | Not Scheduled | T2 EI DRUM-RIO OSO #1 027/198 REPAINT | 44304427 | DRUM-RIO OSO #1 | 027/198 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-05 | 2024-02-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.195289 | 39.066 | ETL.1420 | 40858245 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745008 | Not Scheduled | T2 EI DRUM-RIO OSO #1 27/204 REPNT STRT | 44304427 | DRUM-RIO OSO #1 | 027/204 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2023-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.208088 | 39.0608 | ETL.1420 | 40746585 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745016 | Not Scheduled | T3NT EI GEYSERS #12-FLTN 1/6 REPAINT | 43749452 | GEYSERS #12-FULTON | 001/006 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2024-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.767206 | 38.7958 | ETL.4750 | 41129171 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-03 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745018 | Not Scheduled | EI CRAG VIEW-CASCADE 11/96 CANCEL | 44406337 | CRAG VIEW-CASCADE | 011/096 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2020-02-06 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | [6 empty] | '-122.317514 | 40.7996 | ETL.1350 | 40808603 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745021 | Before Feb | T2NT EI DRUM-HIGGINS 24/188 REPAINT | 43738143 | DRUM-HIGGINS | 024/188 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-02-06 | 2020-02-06 |  |  | 2020-10-03 | 2020-09-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.119279 | 39.089 | ETL.4393 | 40658220 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745023 | Not Scheduled | T2 EI DRUM-HIGGINS 021/172 REPAINT | 43738143 | DRUM-HIGGINS | 021/172 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2024-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.083852 | 39.1106 | ETL.4393 | 40913068 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745025 | Not Scheduled | T3 EI EGLE ROCK-REDBUD :06/38 REPNT STRT | 43730053 | EAGLE ROCK-REDBUD | :006/038 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2019-08-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.721842 | 38.8817 | ETL.1480 | 40861249 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-01 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745027 | Not Scheduled | T2 EI ELECTRA-BELLOTA 016/120 REPAINT | 43727726 | ELECTRA-BELLOTA | 016/120 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-06 | 2024-02-06 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.86647 | 38.1461 | ETL.4670 | 40822055 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-10-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745028 | Not Scheduled | T2 EI DRUM-HIGGINS B010/101 REPAINT | 43738143 | DRUM-HIGGINS | B010/101 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2024-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.928987 | 39.1487 | ETL.4393 | 41196114 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745040 | Not Scheduled | T2 EI OLEUM-MARTINEZ 4/032 REPAINT | 43753565 | OLEUM-MARTINEZ | 004/032 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-02-06 | 2020-02-06 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.1795 | 38.0173 | ETL.3170 | 40644167 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745042 | Not Scheduled | T3NT EI EAGL RCK-FLTN-SLVRD 03/16 REPANT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 003/016 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2019-08-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802137 | 38.8015 | ETL.4392 | 40814648 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745044 | Not Scheduled | T2 EI CNTR CST-MRG #1 14/70 REPAINT | 43753199 | CONTRA COSTA-MORAGA #1 | 014/070 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-02-06 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.977795 | 37.9161 | ETL.5452 | 40746195 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-16 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745045 | Not Scheduled | T2 EI VC-LKVLL #1 008/043 REPAINT | 43705009 | VACA-LAKEVILLE #1 | 008/043 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-02-07 | 2020-02-07 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.037092 | 38.3617 | ETL.5840 | 40656087 | Structure-Steel | Paint/Coating | Other | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745049 | Not Scheduled | T3 EI DRUM-HIGGINS 006/070 REPAINT | 43738143 | DRUM-HIGGINS | 006/070 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2019-08-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856996 | 39.191 | ETL.4393 | 40590064 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745052 | Not Scheduled | T2 EI TIGER CREEK-ELCTRA 13/105 RPR FOND | 43713222 | TIGER CREEK-ELECTRA | 013/105 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2022-02-07 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.667127 | 38.3359 | ETL.5780 | 40752892 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745055 | Not Scheduled | T3 EI DRUM-HIGGINS B09/87 REPAINT | 43738143 | DRUM-HIGGINS | B009/087 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2019-08-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.893645 | 39.1652 | ETL.4393 | 40809702 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745056 | Not Scheduled | T3 EI DRUM-HIGGINS 07/72 REPAINT | 43738143 | DRUM-HIGGINS | 007/072 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2019-08-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.859746 | 39.1897 | ETL.4393 | 40682540 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745057 | Not Scheduled | T3 EI EGL RCK-FLTN-SLVRD 2/14 REPAINT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 002/014 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2019-08-07 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.797954 | 38.8065 | ETL.4392 | 40756573 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745059 | Not Scheduled | T2 EI VACA-LAKEVILLE #1 10/051A RPNT TWR | 43740456 | VACA-LAKEVILLE #1 | 010/051A | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2020-02-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.052995 | 38.3397 | ETL.5840 | 40576568 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745062 | Not Scheduled | T2 EI DRUM-RIO OSO #1 028/208 REPAINT | 44304427 | DRUM-RIO OSO #1 | 028/208 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2023-02-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.219334 | 39.0563 | ETL.1420 | 40866026 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745067 | Not Scheduled | T2 EI DRUM-RIO OSO #1 28/209 REPNT STRT | 44304427 | DRUM-RIO OSO #1 | 028/209 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2023-02-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.222266 | 39.0551 | ETL.1420 | 40870513 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116745077 | Not Scheduled | T2 EI PIT#1-COTTONWD 42/358 REPAINT | 43879413 | PIT #1-COTTONWOOD | 042/358 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-02-07 | 2024-02-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.089058 | 40.6111 | ETL.5390 | 40868303 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116746860 | Not Scheduled | T3 EI CARIBOU-PALERMO :10/83 RPL JUMPERS | 44304491 | CARIBOU-PALERMO | :010/083 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272689 | 39.9931 | ETL.3190 | 40910324 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116746976 | Feb | T2 DI CLNGA #1-SAN MGL 032/001 REPL GYWS | 43763703 | COALINGA #1-SAN MIGUEL | 032/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-13 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-15 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.635677 | 35.8254 | ETL.8580 | 40592554 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-06-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747078 | Not Scheduled | T3 EI CRBRY SW ST-RND MT 24/198 PNT STRS | 43742123 | CARBERRY SW STA-ROUND MTN | 024/198 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-22 | 2019-08-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.887973 | 40.8052 | ETL.5410 | 40865167 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747134 | Q2 | T3 EI KNCTI-MDDLTWN 28/003C RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2019-08-25 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235468 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747181 | Q2 | T3 EI KNCTI-MDDLTWN 28/003R RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-25 | 2019-08-25 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-05-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747242 | Not Scheduled | T2 DI OLEUM-MARTINEZ 4/29 REPAINT | 43753565 | OLEUM-MARTINEZ | 004/029 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-03-15 | 2020-03-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.187423 | 38.0211 | ETL.3170 | 40804609 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747380 | Q2 | T2 EI PIT #1-COTTONWOOD 018/143 RPR SPLS |  | PIT #1-COTTONWOOD | 018/143 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-01 | 2020-03-01 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 | '-121.769035 | 40.8356 | ETL.5390 | 40657389 | Splice-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116747392 | Not Scheduled | T2 METCALF-MOSS LANDNG #1 34/157 REPAINT | 44300674 | METCALF-MOSS LANDING #1 | 035/157 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-16 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.670918 | 37.1264 | ETL.5100 | 40810613 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747612 | Not Scheduled | EI MB-CALIF FLATS SS 33/142 REPL INSULS | 31439887 | MORRO BAY-GATES #2 | 033/142 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-16 | 2020-03-16 | [8 empty] | LATE | South | WSIP | [6 empty] | '-120.4716251 | 35.7433 | ETL.5280 | 40714275 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - MCF |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116747842 | Not Scheduled | T2 METCALF-MOSS LANDNG #1 34/156 REPAINT | 44300677 | METCALF-MOSS LANDING #1 | 034/156 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-16 | 2024-03-16 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.670806 | 37.1291 | ETL.5100 | 40822603 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116748174 | Q2 | T2 EI HT CRK #1-WSTWD 046/887 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 046/887 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-02-22 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow. | '-121.02308 | 40.4324 | ETL.7030 | 40656677 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116748212 | Q2 | T2 EI MALIN-ROUND MTN #2 61/304 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 061/304 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-02-19 | 2020-02-19 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.661637 | 41.1972 | ETL.6020 | 40793838 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116748618 | Before Feb | T2 EI MOSS LANDING-COBURN C07/31 REPAINT | 44300676 | MOSS LANDING-COBURN | C007/031 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-16 | 2020-03-16 |  |  | 2020-05-31 | 2020-05-31 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.276613 | 36.6223 | ETL.5330 | 40587144 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116748699 | Not Scheduled | T3 EI EAGLE ROCK-REDBD :01/10 PAINT STRS | 43730053 | EAGLE ROCK-REDBUD | :001/010 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-02-06 | 2019-08-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.785141 | 38.8386 | ETL.1480 | 40588081 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116748815 | Before Feb | T2 EI MOSS LANDING-COBURN C08/32 REPAINT | 44300675 | MOSS LANDING-COBURN | C008/032 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-16 | 2020-03-16 |  |  | 2020-05-31 | 2020-05-31 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.275795 | 36.6209 | ETL.5330 | 40689404 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116748864 | Not Scheduled | T2 EI MORRO BAY-TEMPLETN 13/55 RMV DBRS | 43735698 | MORRO BAY-TEMPLETON | 013/055 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-16 | 2024-03-16 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.709847 | 35.5225 | ETL.5933 | 40762765 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116748931 | Not Scheduled | T2 EI CARIBOU-PALERMO :3/030 INS HRDT | 44070463 | CARIBOU-PALERMO | :003/030 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-16 | 2020-03-16 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.205437 | 40.0561 | ETL.3190 | 40910274 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116749686 | Not Scheduled | T3 EI CARIBOU-PALERMO :10/081 RPR HRDT | 44304491 | CARIBOU-PALERMO | :010/081 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.271411 | 39.9963 | ETL.3190 | 40910322 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116749687 | Not Scheduled | T3 EI CARIBOU-PALERMO :10/081 RPR CONDS | 44304491 | CARIBOU-PALERMO | :010/081 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-15 | 2019-09-15 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.271411 | 39.9963 | ETL.3190 | 40910322 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116749915 | Q2 | T2 EI PIT #1-COTTONWOOD 49/426 RMV NEST | 43735854 | PIT #1-COTTONWOOD | 049/426 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-16 | 2021-05-31 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.156454 | 40.53 | ETL.5390 | 40819063 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116750089 | Not Scheduled | T2 DI CHRSTIE-SBRNTE 11/059 PNT STRS | 43751914 | CHRISTIE-SOBRANTE | 011/059 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-14 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.197314 | 37.9898 | ETL.1260 | 40857610 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116753201 | Not Scheduled | T2 EI BLACK TAP 000/003 RPR ANCS | 44070470 | BLACK TAP | 000/003 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-17 | 2020-03-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.978299 | 40.9876 | ETL.5431 | 44188817 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116753918 | Mar | DI SAN RAMON-MORAGA 20/88 RPL INSS | 31459455 | SAN RAMON-MORAGA | 020/088 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-16 | 2020-03-16 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.134955 | 37.8478 | ETL.5660 | 40633222 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116753919 | Not Scheduled | T3NT CARIBOU-PALERMO :30/248 PAINT STRT | 44302715 | CARIBOU-PALERMO | :030/248 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.455372 | 39.773 | ETL.3190 | 40878269 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116754581 | Not Scheduled | EI FULTON-PUEBLO 040/208 RPR FOND | 43720989 | FULTON-PUEBLO | 040/208 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-18 | 2024-03-18 | [8 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.719875 | 38.4968 | ETL.1600 | 40870811 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-25 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116755505 | Q2 | T2 EI MS LNDNG-CBRN C006/026A RPR FOND | 44102662 | MOSS LANDING-COBURN | C006/026A | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-18 | 2024-03-18 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.285723 | 36.6388 | ETL.5330 | 44149207 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 1 | 2019-04-15 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116756134 | Q2 | T2 EI MS LNDNG-CBRN C006/026 RPR FOND | 44102662 | MOSS LANDING-COBURN | C006/026 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-18 | 2024-03-18 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.28701 | 36.6437 | ETL.5330 | 40819514 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 1 | 2019-04-15 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-04-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116756249 | Q2 | EI SBRNTE-GRZLY-CLRMNT #1 A3/18 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A003/018 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-18 | 2020-03-18 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-122.245297 | 37.876 | ETL.3740 | 40857836 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 | 2019-04-08 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-04-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116757531 | Before Feb | T2NT EI PIT#1-COTTONWD 17/137 REPAINT | 43879413 | PIT #1-COTTONWOOD | 017/137 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-03-18 | 2021-03-18 |  |  | 2020-12-30 | 2020-12-01 |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.762685 | 40.8439 | ETL.5390 | 40816505 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116757726 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 41/168 REPL INSS | 31443715 | DIABLO-MIDWAY #3 | 041/168 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-18 | 2020-03-18 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.136018 | 35.2052 | ETL.5980 | 44668416 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116761592 | Not Scheduled | T3 DI PINE GROVE TAP 0/2 REPL PL | 31430351 | PINE GROVE TAP | 000/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-18 | 2019-09-18 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.629911 | 38.3933 | ETL.8351 | 40665504 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116762128 | Not Scheduled | EI FITCH MTN #1 TAP 00/04 RPR GYWW | 43761311 | FITCH MTN #1 TAP | 000/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-19 | 2020-03-19 | 2020-08-17 | 2020-08-23 | [6 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.845202 | 38.606 | ETL.6891 | 40750566 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116762247 | Not Scheduled | EI FITCH MTN #1 TAP 00/05 RPR GYWW | 43761311 | FITCH MTN #1 TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-19 | 2020-03-19 | 2020-08-17 | 2020-08-23 | [6 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.845713 | 38.6054 | ETL.6891 | 40750532 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116763686 | Not Scheduled | DI VLY SPRNGS #1 10/207 REPL SPLW | 43780878 | VALLEY SPRINGS #1 | 010/207 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-18 | 2020-03-18 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.894428 | 38.1155 | ETL.8210 | 40908292 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116764336 | Feb | T2 MORROBAY-SLO#2 4/26 RPL FLASHD INSULS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 004/026 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-18 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.790436 | 35.3418 | ETL.2820 | 40835553 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  | 2019-04-08 | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-05-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116764620 | Q2 | T2 EI RND MTN-T MTN #1 19/99 RPL INSS | 31455288 | ROUND MTN-TABLE MTN #1 | 019/099 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-03-19 | 2020-03-19 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.9439225 | 40.5248 | ETL.6060 | 40893009 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116764720 | Not Scheduled | T2 DI VLY SPRNGS #1 9/180 RPR STRW | 43831092 | VALLEY SPRINGS #1 | 009/180 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.87651 | 38.1266 | ETL.8210 | 40908265 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116765400 | Not Scheduled | T2 DI CNTRA CSTA-MRAGA 024/114 RPR FOND |  | CONTRA COSTA-MORAGA #1 | 024/114 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-13 | 2024-03-13 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.123696 | 37.8634 | ETL.5452 | 40818035 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | 2019-04-16 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116766299 | Not Scheduled | T2 DI VALLY SPRINGS #1 7/146 RPR GYWW | 43831087 | VALLEY SPRINGS #1 | 007/146 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.860587 | 38.1468 | ETL.8210 | 40908229 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116766368 | Not Scheduled | T3 EI TEMBLOR-SLO+51/288 REPAINT MEMBERS | 43740614 | TEMBLOR-SAN LUIS OBISPO | 051/288 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-19 | 2019-09-19 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.550032 | 35.3151 | ETL.3960 | 40856740 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116766767 | Not Scheduled | T3 EI PT #1-CTTNWD 029/245 RPR FOND | 43930183 | PIT #1-COTTONWOOD | 029/245 | ICX | F | Pre-2020_(9a) Other ignition related |  | 2019-03-19 | 2022-03-19 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.962249 | 40.7631 | ETL.5390 | 40744729 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116766838 | Not Scheduled | EI MORR BY-SAN LUS OBSP #1 1/7 REPAINT | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 001/007 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-19 | 2020-03-19 | [8 empty] | LATE | South | WSIP | [6 empty] | '-120.839462 | 35.3738 | ETL.2810 | 40810411 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4 | 2019-04-08 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116766905 | Not Scheduled | DI VALLEY SPRINGS #1 12/241 RPL SPLW | 43831565 | VALLEY SPRINGS #1 | 012/241 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-18 | 2020-03-18 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.919877 | 38.1037 | ETL.8210 | 40904216 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116767246 | Not Scheduled | T2 DI MELONES-WILSON 000/001 INS GMKS | 43844901 | MELONES-WILSON | 000/001 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-19 | 2020-03-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537403 | 37.9443 | ETL.5080 | 40586992 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116767314 | Not Scheduled | EI LKVLE-IGNACIO #1 IG002/011 RPNT STRS | 43761676 | LAKEVILLE-IGNACIO #1 | IG002/011 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-19 | 2024-03-19 | [8 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522675 | 38.1054 | ETL.4940 | 40593209 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116767448 | Not Scheduled | T2 EI JFFRSN-HLLSDLE J 6/35 CANCEL | 44598165 | JEFFERSON-HILLSDALE JCT | 006/035 | ICI | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-18 | 2020-03-18 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-122.356591 | 37.5248 | ETL.7190 | 40755149 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116767714 | Not Scheduled | T2 DI PNE GRV TAP 2/59 RPR GYWW | 43749302 | PINE GROVE TAP | 002/059 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-19 | 2020-03-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.659255 | 38.4133 | ETL.8351 | 40587998 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116767794 | Not Scheduled | T2 DI STANISLAUS-MNTC 9/56 BENT STEEL | 43842120 | STANISLAUS-MANTECA #2 | 009/056 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.516414 | 38.068 | ETL.3820 | 40809563 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116767807 | Not Scheduled | EI MR BY-SN LS BSP #1 000/006 PAINT | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 000/006 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-19 | 2020-03-19 | [8 empty] | LATE | South | WSIP | [6 empty] | '-120.841416 | 35.3744 | ETL.2810 | 40811024 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 12 | 2019-04-08 | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116788698 | Not Scheduled | T2 DI PN GRV TAP 2/55 RPR GYWW | 43749302 | PINE GROVE TAP | 002/055 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-19 | 2020-03-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.656532 | 38.4132 | ETL.8351 | 40811754 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116788722 | Not Scheduled | T2 DI OLEUM-MRTNZ 5/36 PNT STRT | 43753565 | OLEUM-MARTINEZ | 005/036 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-03-18 | 2020-03-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.166232 | 38.0109 | ETL.3170 | 40868916 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116788877 | Not Scheduled | DI VALLEY SPRINGS #1 000/003 RPR STRW | 43831323 | VALLEY SPRINGS #1 | 000/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.763949 | 38.2144 | ETL.8210 | 40904179 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789057 | Q2 | T2 EI OLEUM-G #1 001/010 RPL INSS HRD | 44103166 | OLEUM-G #1 | 001/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-05 | 2020-03-05 | 2021-05-13 | 2021-05-14 | 2021-05-14 | 2021-05-13 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.234025 | 38.0385 | ETL.3150 | 40622200 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789270 | Not Scheduled | DI VLLY SPRNGS-CLAY 5/77 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [8 empty] | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255307 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789343 | Not Scheduled | DI VALLEY SPRINGS #1 0/9 RPR GYWW | 43831326 | VALLEY SPRINGS #1 | 000/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.769115 | 38.2106 | ETL.8210 | 40904185 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789361 | Not Scheduled | DI VLLY SPRNGS-CLAY 5/77 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [8 empty] | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255308 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789392 | Not Scheduled | DI VLLY SPRNGS-CLAY 5/77 RPR STRW | 43844012 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [8 empty] | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255308 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789396 | Not Scheduled | T2 DI VLY SPRNGS 6/86 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/086 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833612 | 38.2116 | ETL.8264 | 40905033 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789501 | Not Scheduled | T2 DI VLLY SPRNGS-CLAY 5/78 RPL STRW | 31501102 | VALLEY SPRINGS-CLAY | 005/078 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-18 | 2020-03-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.830224 | 38.201 | ETL.8264 | 40904716 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789651 | Not Scheduled | T2 DI VLLY SPRNGS-CLAY 5/79 RPR STRW | 43844012 | VALLEY SPRINGS-CLAY | 005/079 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.830564 | 38.2022 | ETL.8264 | 40905031 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789809 | Not Scheduled | T2 DI VLY SPRNGS-CLY 6/88 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/088 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834348 | 38.2139 | ETL.8264 | 40904723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789827 | Mar | EI KILARC-DESCHUTES A026/547 RPL STRW | 31431892 | KILARC-DESCHUTES | A026/547 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-20 | 2020-03-20 |  |  | 2021-03-26 | 2021-03-01 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.30127 | 40.5711 | ETL.7300 | 40828782 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 116789842 | Not Scheduled | EI IGNACIO-STAFFORD A005/104 REPL STRW | 31469870 | ETL.1042.POLE.WOOD | A005/104 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-20 | 2020-03-20 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.608792 | 38.1177 | ETL.1042 | 40585464 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789947 | Mar | EI KILARC-DESCHUTES A026/548 REPL STRW | 31431892 | KILARC-DESCHUTES | A026/548 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-20 | 2020-03-20 |  |  | 2021-03-26 | 2021-03-01 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.302175 | 40.5711 | ETL.7300 | 40826841 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 116789960 | Not Scheduled | T2 DI PINE GRV TAP 2/57 RPL STRW | 31430351 | PINE GROVE TAP | 002/057 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.658161 | 38.4132 | ETL.8351 | 40863882 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | 2020-09-24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789964 | Not Scheduled | T2 DI PINE GROVE TAP 2/60 RPR GYWW | 43749302 | PINE GROVE TAP | 002/060 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.659412 | 38.4129 | ETL.8351 | 40754205 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116789980 | Not Scheduled | T2 DI VLY SPRNGS-CLY 6/88 RPR GRWW | 43844012 | VALLEY SPRINGS-CLAY | 006/088 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834348 | 38.2139 | ETL.8264 | 40904723 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790114 | Not Scheduled | T2 DI VLY SPRNGS-CLY 6/85 RPR STRW | 43844012 | VALLEY SPRINGS-CLAY | 006/085 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833081 | 38.2099 | ETL.8264 | 40904721 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790295 | Not Scheduled | T2 DI VALLEY SPRINGS 006/090 RPL STRW | 31426450 | VALLEY SPRINGS-CLAY | 006/090 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834766 | 38.2154 | ETL.8264 | 40904724 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790447 | Not Scheduled | T3 DI GROVE TAP 001/029 RPR STRW | 43749302 | PINE GROVE TAP | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-20 | 2019-09-20 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.644002 | 38.4053 | ETL.8351 | 40812438 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790570 | Q3 | EI TESLA-NEWARK #2 9/68 RPR STRT |  | TESLA-NEWARK #2 | 009/068 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 |  |  | 2021-07-17 | 2021-07-12 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.732718 | 37.6573 | ETL.5354 | 41152613 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790672 | Feb | T2 DI OLEUM-MARTINEZ 6/42 RPR INSS HRD | 44326132 | OLEUM-MARTINEZ | 006/042 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-18 | 2020-03-18 |  |  | 2021-02-23 | 2021-02-23 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.148856 | 38.0027 | ETL.3170 | 40671259 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-03-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790835 | Not Scheduled | T2 DI VLLY SPRNGS 7/106 RPR STRW | 43844187 | VALLEY SPRINGS-CLAY | 007/106 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-19 | 2020-03-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8421 | 38.2282 | ETL.8264 | 40904739 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116790836 | Not Scheduled | T2 DI VALLEY SPRINGS #1 8/164 RPR STRW | 43831090 | VALLEY SPRINGS #1 | 008/164 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-18 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.868271 | 38.1361 | ETL.8210 | 40908247 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116791051 | Not Scheduled | EI TESLA-NEWARK #2 010/070 PAINT STRS | 43753285 | TESLA-NEWARK #2 | 010/070 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-06 | 2020-03-06 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.735992 | 37.6556 | ETL.5354 | 41152615 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116791510 | Not Scheduled | T2 EI TRCY-LS BANOS 31/148 RPR GYWS | 43844596 | TRACY-LOS BANOS | 031/148 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-19 | 2020-03-19 | [6 empty] | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.209138 | 37.4756 | ETL.6130 | 40873336 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116791848 | Not Scheduled | T2 DI SOBRANTE-STD OIL 003/019 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 003/019 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-18 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.205863 | 37.9483 | ETL.3800 | 40857808 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-13 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116791955 | Not Scheduled | T2 EI PIT #3-PIT #1 000/000B RPR GYWS | 43877630 | PIT #3-PIT #1 | 000/000B | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.498067 | 40.9916 | ETL.5400 | 41184138 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116792115 | Not Scheduled | T3 DI MORAGA-CASTRO VLLEY 10/46 CANCEL | 43744386 | MORAGA-CASTRO VALLEY | 010/046 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-18 | 2019-09-18 | [6 empty] | CANCEL/CNCL | TR3 | LATE | Central | WSIP | [6 empty] | '-122.066475 | 37.7321 | ETL.5250 | 40816974 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116792381 | Not Scheduled | T2 DI VALLEY SPRINGS-CLAY 6/84 RPL GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/084 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.832294 | 38.2077 | ETL.8264 | 40904720 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116792653 | Not Scheduled | T2 DI STNSLS-MANTECA #2 8/50 CANCEL | 43842120 | STANISLAUS-MANTECA #2 | 008/050 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.498855 | 38.0775 | ETL.3820 | 40579634 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116792855 | Not Scheduled | T2 EI FULTON-PUEBLO 14/068 PAINT STRS | 43720980 | FULTON-PUEBLO | 014/068 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-18 | 2020-03-18 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.252392 | 38.5068 | ETL.1600 | 40870813 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-04-25 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116793208 | Not Scheduled | T2 DI VLLEY SPRNGS-CLY 007/110 RPR GWSW | 43844187 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116794356 | Not Scheduled | EI TESLA-NEWARK #2 19/129 PAINT STRS | 43753285 | TESLA-NEWARK #2 | 019/129 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-06 | 2020-03-06 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.872042 | 37.5693 | ETL.5354 | 41152675 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116802155 | Not Scheduled | T2 DI OLEUM-MRTNZ 005/037 RPNT STRT | 43753565 | OLEUM-MARTINEZ | 005/037 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-20 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.163536 | 38.0096 | ETL.3170 | 40857603 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116802386 | Q2 | T2 DI MTCLF-GRN VLY 007/051 RPR STRT | 44140745 | METCALF-GREEN VALLEY | 007/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.679262 | 37.1472 | ETL.2540 | 40585522 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116802626 | Not Scheduled | T2 DI VLLY SPRNGS-CLAY 7/104 RPR GYWW | 43844187 | VALLEY SPRINGS-CLAY | 007/104 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.840996 | 38.2269 | ETL.8264 | 40904737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116802673 | Not Scheduled | T2 DI VALLEY SPRINGS #1 009/189 RPR GYWW | 43831094 | VALLEY SPRINGS #1 | 009/189 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.881616 | 38.1209 | ETL.8210 | 40908274 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116803110 | Q2 | EI KONOCTI-MIDDLETOWN_;023/006 REPL GUY | 43760955 | KONOCTI-MIDDLETOWN | ;023/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2021-05-31 |  |  | 2021-05-31 |  |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.609077 | 38.8978 | ETL.6380 | 40810828 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 637 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116803343 | Not Scheduled | T2 EI OLEUM-G #1 6/43 REPAINT | 44586166 | OLEUM-G #1 | 006/043 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-18 | 2020-03-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.260076 | 37.9695 | ETL.3150 | 40659401 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116803523 | Not Scheduled | T2 FULTON-HOPLAND 037/005 RPL POLE | 31510603 | FULTON-HOPLAND | 037/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | 2020-08-17 | 2020-08-23 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.063025 | 38.9428 | ETL.6890 | 40769687 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-18 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116803566 | Not Scheduled | T2NT EI OLEUM-G #1 7/45 PAINT STRS | 43752220 | OLEUM-G #1 | 007/045 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-03-16 | 2021-03-16 | [7 empty] | TR2 | <30D | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.263942 | 37.9641 | ETL.3150 | 40746017 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116803721 | Q2 | T3 EI RND MTN-TBL MTN #1 5/29 RPL SPLS | 43790345 | ROUND MTN-TABLE MTN #1 | 005/029 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-20 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.941773 | 40.7323 | ETL.6060 | 40868400 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116803923 | Q2 | T2 EI SMARTVILLE-MARY 8/156 RPR GYWW | 43760141 | SMARTVILLE-MARYSVILLE | 008/156 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 |  |  | 2021-04-13 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.422903 | 39.2262 | ETL.7980 | 40767569 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | CalTrans | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116803934 | Mar | EI KONOCTI-MIDDLETOWN_012/005 RPR INSW | 43761672 | KONOCTI-MIDDLETOWN | 012/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2021-05-31 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.608451 | 38.7563 | ETL.6380 | 40768995 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116804088 | Not Scheduled | EI KONOCTI-MIDDLETOWN_012/008 CANCEL | 43761672 | KONOCTI-MIDDLETOWN | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | 2020-10-26 | 2020-10-30 |  |  |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.605367 | 38.7579 | ETL.6380 | 40876752 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116804501 | Not Scheduled | T3 EI SOBRANTE-R 2/019 #1 PAINT STRS | 43727737 | SOBRANTE-R #1 | 002/019 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-07 | 2019-09-07 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.258062 | 37.9131 | ETL.3770 | 40857825 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116804818 | Not Scheduled | EI BRDGVLL-CTTNWD 45/355 CANCEL COA | 43742049 | BRIDGEVILLE-COTTONWOOD | 045/355 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-21 | 2020-03-21 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | [5 empty] | 2021 - Snow . FSR 12/2020. Work is complete. Tag to be Cancelled. |  |  | ETL.1110 | 44424624 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116804987 | Not Scheduled | T2 EI SOBRANTE-MORAGA 000/004 INSW | 44388405 | SOBRANTE-MORAGA | 000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2020-03-21 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.206472 | 37.9045 | ETL.3742 | 41135445 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116805069 | Not Scheduled | T2 DI VLLEY SPRINGS-CLAY 13/172 RPL STRW | 31426450 | VALLEY SPRINGS-CLAY | 013/172 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.897389 | 38.2816 | ETL.8264 | 40904778 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116805120 | Not Scheduled | T2 DI VLLEY SPRNGS-CLAY 6/91 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/091 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.835072 | 38.2161 | ETL.8264 | 40904725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116805131 | Mar | EI KONOCTI-MIDDLETOWN_016/001 RPL STRW | 31456914 | KONOCTI-MIDDLETOWN | 016/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2021-05-31 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.568817 | 38.7975 | ETL.6380 | 40600741 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-05-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116805216 | Not Scheduled | EI BRDGVLL-CTTNWD 45/355C CANCEL COA | 44143775 | BRIDGEVILLE-COTTONWOOD | 045/355 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-21 | 2020-03-21 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | [5 empty] | 2021 - Snow . FSR 12/2020. Work is complete. Tag to be Cancelled. |  |  | ETL.1110 | 44424623 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116805609 | Mar | EI KONOCTI-MIDDLETOWN_016/012 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 016/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2021-05-31 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.572714 | 38.8069 | ETL.6380 | 40699007 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116805697 | Q2 | T3 DI MSSR FLT-GLD HL #1 19/160 RPL INSS | 31451775 | MISSOURI FLAT-GOLD HILL #1 | 019/160 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-20 | 2019-09-20 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.900523 | 38.6629 | ETL.2660 | 40636540 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116805824 | Not Scheduled | T2 DI VLLY SPRNGS-CLAY 007/105 RPR HRDD | 43844187 | VALLEY SPRINGS-CLAY | 007/105 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.841288 | 38.2273 | ETL.8264 | 40904738 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116806126 | Not Scheduled | T2 DI VLLY SPRNGS-CLAY 013/179 RPR STRW | 43844187 | VALLEY SPRINGS-CLAY | 013/179 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.903365 | 38.2847 | ETL.8264 | 41167566 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116808495 | Not Scheduled | T2 DI VLLEY SPRGS-CLAY 12/171 RPR GYWW | 43844187 | VALLEY SPRINGS-CLAY | 012/171 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.896517 | 38.2811 | ETL.8264 | 40904777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116808505 | Mar | T2 DI CLAY-MARTEL 23/327 RPL STRW | 31422461 | CLAY-MARTEL | 023/327 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 |  |  | 2021-03-20 | 2021-03-16 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.835885 | 38.3523 | ETL.8250 | 40812116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116808704 | Feb | T2 EI RND MTN-CTTNWD #3 35/296 RPR INSS | 44624619 | ROUND MTN-COTTONWOOD #3 | 035/296 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-31 | 2020-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.015054 | 40.7002 | ETL.5650 | 40816921 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116810212 | Mar | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T095 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-03-21 | 2019-09-21 |  |  | 2021-03-05 | 2021-03-01 |  |  | Midway-Santa Maria | TR3 | LATE | South | WSIP | [6 empty] | '-120.17661 | 35.0542 | ETL.9240 | 43249571 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116810592 | Not Scheduled | T2 DI VLLY SPRNGS-CLY 17/247 STP BLT | 43844010 | VALLEY SPRINGS-CLAY | 017/247 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.935049 | 38.3395 | ETL.8264 | 40904838 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116810756 | Mar | T2 DI PLACER-DEL MAR 0/21 RPR GYWW | 43755677 | PLACER-DEL MAR | 000/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-20 | 2020-03-20 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097344 | 38.8904 | ETL.7800 | 40758278 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116811515 | Not Scheduled | EI IGNACIO-SAN RAFAEL #1 002/014 FOND | 43715549 | IGNACIO-SAN RAFAEL #1 | 002/014 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-22 | 2024-03-22 | [8 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.533646 | 38.0488 | ETL.1850 | 40753422 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-29 | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116813128 | Not Scheduled | DI VLLY SPRNGS-CLY 013/178 RPR GYWW | 43844187 | VALLEY SPRINGS-CLAY | 013/178 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.902332 | 38.2843 | ETL.8264 | 40904784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116813186 | Q2 | EI KONOCTI-MIDDLETOWN 029/002 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 029/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.626008 | 38.9122 | ETL.6380 | 40656001 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116813198 | Q2 | EI KONOCTI-MIDDLETOWN 29/2 RPL STRW | 43761672 | KONOCTI-MIDDLETOWN | 029/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.626008 | 38.9122 | ETL.6380 | 40656001 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814498 | Not Scheduled | T3 EI GRIZZLY TAP 3/12 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2019-09-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322423 | 39.9075 | ETL.2395 | 44551439 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814647 | Not Scheduled | T3 EI GRIZZLY TAP 003/017L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551421 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814648 | Not Scheduled | T3 EI GRIZZLY TAP 004/001L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551404 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814672 | Not Scheduled | T3 EI GRIZZLY TAP 003/020L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/020 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.325883 | 39.9106 | ETL.2395 | 44551441 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814748 | Not Scheduled | T3 EI GRIZZLY TAP 003/016 (L) RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2022-03-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3233411 | 39.9089 | ETL.2395 | 44551359 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814749 | Not Scheduled | T3 EI GRIZZLY TAP 3/15 RPR CONW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2022-03-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323076 | 39.9087 | ETL.2395 | 40782201 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814753 | Not Scheduled | T3NT EI GRIZZLY TAP 3/16 INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-22 | 2022-03-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3233411 | 39.9089 | ETL.2395 | 44551359 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116814806 | Not Scheduled | T2 DI VLLY SPRGS-CLAY 9/125 RPL SPLW | 43844187 | VALLEY SPRINGS-CLAY | 009/125 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2020-03-22 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850969 | 38.2495 | ETL.8264 | 40904752 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815113 | Feb | T2 DI OLEUM-MARTINEZ 004/031 RPL SPLS | 43753565 | OLEUM-MARTINEZ | 004/031 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-19 | 2020-03-19 |  |  | 2021-02-23 | 2021-02-23 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.18146 | 38.0182 | ETL.3170 | 40745836 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815141 | Not Scheduled | DISTRIBUTION INSL | 31431489 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/173 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-19 | 2020-03-19 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.526441 | 35.1615 | ETL.9100 | 44188919 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815208 | Not Scheduled | T3 DI CNTR CST-MRG #1 20/96 RPNT STRT | 43744389 | CONTRA COSTA-MORAGA #1 | 020/096 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-19 | 2019-09-19 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.057676 | 37.8593 | ETL.5452 | 40604247 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-16 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815221 | Not Scheduled | T2 DI VLLY SPRNGS 010/193 RPR STRW | 43831093 | VALLEY SPRINGS #1 | 010/193 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.884174 | 38.119 | ETL.8210 | 40908278 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815826 | Not Scheduled | T2 DI STNSLS-MNTCA #2 014/084 RPR FND | 43842120 | STANISLAUS-MANTECA #2 | 014/084 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.592282 | 38.0263 | ETL.3820 | 40764248 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815828 | Not Scheduled | T2 DI STNSLS-MNTCA #2 014/082 RPR FOND | 43842120 | STANISLAUS-MANTECA #2 | 014/082 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.588337 | 38.0288 | ETL.3820 | 40642926 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116815861 | Not Scheduled | T2 DI VLY SPRNGS-CLY 13/180 GRD/WSH INSU | 43844009 | VALLEY SPRINGS-CLAY | 013/180 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.904357 | 38.2851 | ETL.8264 | 40904785 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116816365 | Not Scheduled | EI PTTR VLLY-MNDCNO 000/006 RPL STRT |  | POTTER VALLEY-MENDOCINO | 000/006 | 70S | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2020-03-22 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-123.131392 | 39.3527 | ETL.7810 | 40826196 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-04-29 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116816552 | Not Scheduled | T2 DI STNSLS-MANTECA #2 014/082 RPR FOND | 43842120 | STANISLAUS-MANTECA #2 | 015/087 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-20 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.595814 | 38.0239 | ETL.3820 | 40803363 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116816725 | Not Scheduled | EI MONTE RIO-FULTON 007/009 RPL SPLW | 43762371 | MONTE RIO-FULTON | :007/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-23 | 2020-03-23 | 2020-11-10 | 2020-11-10 | [6 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.894206 | 38.4897 | ETL.7630 | 40863278 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116816733 | Not Scheduled | EI MONTE RIO-FULTON 007/009 RPR GYWW | 43762371 | MONTE RIO-FULTON | :007/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-23 | 2020-03-23 | 2020-11-10 | 2020-11-10 | [6 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.894206 | 38.4897 | ETL.7630 | 40863278 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116817008 | Not Scheduled | T2 DI STNSLS-MLS MNTCA 011/070 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.553433 | 38.0499 | ETL.3830 | 40604155 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116817152 | Not Scheduled | T2 DI STNS-MLN MTC #1 011/067 RPNT STRT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/067 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-22 | 2023-03-22 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.541885 | 38.0558 | ETL.3830 | 40803318 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116817319 | Q2 | EI UKIAH-HPLND-CLVRDLE 03/30 INST GUY | 43737337 | UKIAH-HOPLAND-CLOVERDALE | 003/030 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-03-23 | 2021-05-31 |  |  | 2021-04-16 | 2021-04-13 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.15001 | 39.1396 | ETL.4050 | 40772250 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-10 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116817752 | Mar | EI CLEAR LAKE-HOPLAND 009/008 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 009/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-23 | 2021-05-31 |  |  | 2021-03-30 | 2021-03-30 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.915678 | 38.9959 | ETL.6390 | 40860816 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-04-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116818178 | Q2 | DI MELONES-CURTIS 9/3 RPR GYWW CMPLTD | 44623078 | MELONES-CURTIS | 009/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2019-03-22 | 2020-03-22 |  |  | 2021-04-02 | 2021-03-02 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391060 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116818396 | Not Scheduled | DISTRIBUTION RPL INSS |  | SPARE T-LINE RECORD | T-139 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-23 | 2020-03-23 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.050759 | 35.1133 | ETL.9240 | 43249651 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116818401 | Q2 | DI MELONES-CURTIS 9/3 SPLW RPR | 43842664 | MELONES-CURTIS | 009/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2020-03-22 |  |  | 2021-04-02 | 2021-03-02 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391060 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116818598 | Not Scheduled | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T-144 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-23 | 2020-03-23 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.036975 | 35.1199 | ETL.9240 | 43249807 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116819432 | Not Scheduled | EI FITCH MTN #1 TAP 00/05 REMOVE STRW | 31470929 | FITCH MTN #1 TAP | 000/005 | 93J | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2020-03-22 | 2020-08-17 | 2020-08-23 | [6 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.845713 | 38.6054 | ETL.6891 | 40750532 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116819460 | Not Scheduled | EI FITCH MTN #1 TAP 00/007 RPR GYWW | 43761311 | FITCH MTN #1 TAP | 000/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2020-03-22 | 2020-08-17 | 2020-08-23 | [6 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.848043 | 38.6047 | ETL.6891 | 40808480 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116819621 | Not Scheduled | T2 EI SLT SPRNGS-TGR CRK 3/31 RPR FOND | 43842263 | SALT SPRINGS-TIGER CREEK | 003/031 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-03-23 | 2022-03-23 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.274897 | 38.4781 | ETL.3500 | 40579794 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116821597 | Not Scheduled | EI KONOCTI-MIDDLETOWN 012/008 CANCEL | 43761672 | KONOCTI-MIDDLETOWN | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | 2020-10-26 | 2020-10-30 |  |  |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.605367 | 38.7579 | ETL.6380 | 40876752 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116822571 | Not Scheduled | T2 DI VLLY SPRINGS-CLAY 005/081 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 005/081 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-20 | 2020-03-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.831266 | 38.2045 | ETL.8264 | 40904718 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116823557 | Not Scheduled | T2 EI SALT SPRNGS-TGR CRK 04/36 RPR FOND | 43842263 | SALT SPRINGS-TIGER CREEK | 004/036 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-24 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.284185 | 38.477 | ETL.3500 | 40803565 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116824112 | Not Scheduled | T2 DI VLLY SPRNGS-CLY 008/121 REFRAME | 31501104 | VALLEY SPRINGS-CLAY | 008/121 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-21 | 2020-03-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825033 | Q2 | EI LAYTONVILLE-WILLITS 4/4 RPL STRW | 31434842 | LAYTONVILLE-WILLITS | 004/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2021-05-31 | 2020-10-14 | 2020-10-17 | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.338624 | 39.4587 | ETL.8360 | 40750488 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825209 | Not Scheduled | T2 EI SALT SPRINGS-TGR CRK 6/51 REPAINT | 43842276 | SALT SPRINGS-TIGER CREEK | 006/051 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-24 | 2020-03-24 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825220 | Not Scheduled | T2 EI SALT SPRINGS-TGR CRK 6/51 INST HRD | 43842265 | SALT SPRINGS-TIGER CREEK | 006/051 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-24 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825231 | Not Scheduled | T2 EI SALT SPRINGS-TGR CRK 6/51 BENT STL | 43842265 | SALT SPRINGS-TIGER CREEK | 006/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-24 | 2020-03-24 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825232 | Not Scheduled | T2 EI SALT SPRINGS-TGR CRK 6/51 RPR FOND | 43842265 | SALT SPRINGS-TIGER CREEK | 006/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-24 | 2020-03-24 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825551 | Not Scheduled | EI MENDOCINO-UKIAH 39/007 RPR FOND | 43762362 | MENDOCINO-UKIAH | 039/007 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2020-03-25 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-123.18243 | 39.1447 | ETL.2420 | 40810781 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825725 | Not Scheduled | T2 DI PINE GROVE TAP 1/38 INST HRDD | 43749302 | PINE GROVE TAP | 001/038 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.650316 | 38.4067 | ETL.8351 | 40754201 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116825813 | Not Scheduled | DISTRIBUTION BIRD GUARD | 31432273 | SPARE T-LINE RECORD | T-147 | 93R | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.029612 | 35.1253 | ETL.9240 | 43249723 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826231 | Q2 | T2 EI HT CRK #1-WSTWD 025/480 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 025/480 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-12 | 2020-02-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.211493 | 40.6868 | ETL.7030 | 40592100 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826385 | Not Scheduled | T3 EI MORRO BAY-TEMPLETON 10/41 REPAINT | 43735698 | MORRO BAY-TEMPLETON | 010/041 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2022-03-25 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.74269 | 35.4771 | ETL.5933 | 40593891 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826431 | Not Scheduled | T3 DI MORAGA-OKALAND 1/12 PNT STRS | 43744382 | MORAGA-OAKLAND #1 | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-25 | 2019-09-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189143 | 37.8371 | ETL.2720 | 40648544 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826450 | Not Scheduled | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T-148 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.027986 | 35.1266 | ETL.9240 | 43249581 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826880 | Not Scheduled | T3 EI MORRO BAY-TEMPLETON 9/40 REPAINT | 43735698 | MORRO BAY-TEMPLETON | 009/040 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2019-09-25 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.743958 | 35.4741 | ETL.5933 | 40591874 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826892 | Not Scheduled | T2 DI PINE GROVE TAP 1/42 RPR GYWW | 43749302 | PINE GROVE TAP | 001/042 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651409 | 38.4082 | ETL.8351 | 40874901 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826982 | Not Scheduled | T2 DI PINE GROVE TAP 1/44 RPR GYWW | 43749302 | PINE GROVE TAP | 001/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651468 | 38.4098 | ETL.8351 | 40587997 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116826983 | Not Scheduled | T2 DI PINE GROVE TAP 1/44 RPR STRW | 43749302 | PINE GROVE TAP | 001/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651468 | 38.4098 | ETL.8351 | 40587997 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116827281 | Not Scheduled | T3 EI MRRO BY-TMPLTN 09/39 RPNT MEMB | 43735698 | MORRO BAY-TEMPLETON | 009/039 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2019-09-25 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.745533 | 35.4704 | ETL.5933 | 40862971 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116827888 | Not Scheduled | DISTRIBUTION MARKER |  | SPARE T-LINE RECORD | T-163 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | [6 empty] | '-119.993002 | 35.1575 | ETL.9240 | 43249693 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116827928 | Not Scheduled | DISTRIBUTION BIRD GUARD |  | SPARE T-LINE RECORD | T-151 | ICB | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.020557 | 35.1329 | ETL.9240 | 43249813 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116828058 | Not Scheduled | DISTRIBUTION INSL |  | SPARE T-LINE RECORD | T-167 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.984147 | 35.1655 | ETL.9240 | 43249773 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116828222 | Not Scheduled | DISTRIBUTION HARDWARE |  | SPARE T-LINE RECORD | T-162 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.994769 | 35.156 | ETL.9240 | 43249695 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116828257 | Not Scheduled | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T-164 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.990449 | 35.1598 | ETL.9240 | 43249593 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116829652 | Not Scheduled | T2 EI ELECT-BELLOTA 00/006 PAINT STRS | 43844907 | ELECTRA-BELLOTA | 000/006 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.670029 | 38.3219 | ETL.4670 | 40659003 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116833055 | Not Scheduled | T2 EI SALT SPRNGS-TGR CRK 4/037 RPR FOND | 43842263 | SALT SPRINGS-TIGER CREEK | 004/037 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.286165 | 38.4775 | ETL.3500 | 40803566 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116833392 | Not Scheduled | DI VALLEY SPRINGS #1 005/101 RPR GYWW | 43831339 | VALLEY SPRINGS #1 | 005/101 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-22 | 2020-03-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.837009 | 38.1715 | ETL.8210 | 40905516 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116833552 | Not Scheduled | T3 EI MORRO BAY-TEMPLETON 9/38 REPAINT | 43735698 | MORRO BAY-TEMPLETON | 009/038 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2019-09-25 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.747245 | 35.4665 | ETL.5933 | 40863323 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116836120 | Not Scheduled | T2 DI PINE GROVE TAP 001/045 RPR GYWW | 43749302 | PINE GROVE TAP | 001/045 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651712 | 38.4101 | ETL.8351 | 40697081 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116837954 | Not Scheduled | T2 EI SALT SPRNGS-TGER CRK 6/53 INS MRKS | 43842276 | SALT SPRINGS-TIGER CREEK | 006/053 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.324482 | 38.4771 | ETL.3500 | 40643018 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116838418 | Q2 | EI BELL-PLACER 002/022 RPL INSS | 31434830 | BELL-PLACER | 002/022 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 |  |  | 2021-04-07 | 2021-04-07 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.068137 | 38.9272 | ETL.4395 | 44139230 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116839961 | Not Scheduled | T2 DI PINE GROVE TAP 001/027 RPR GYWW | 43749302 | PINE GROVE TAP | 001/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.642614 | 38.4043 | ETL.8351 | 40754253 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116840529 | Not Scheduled | T3 DI CNTR CSTA-MRG #1 22/104 RPR STRT | 43744389 | CONTRA COSTA-MORAGA #1 | 022/104 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-25 | 2019-09-25 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.08189 | 37.8566 | ETL.5452 | 40804947 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116841024 | Not Scheduled | T2 DI VALLEY SPRINGS #1 3/69 RPL SPLW | 43831099 | VALLEY SPRINGS #1 | 003/069 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-26 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.819224 | 38.1901 | ETL.8210 | 40903830 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116841025 | Not Scheduled | T2 DI VALLEY SPRINGS #1 3/69 RPL CRSW | 31431490 | VALLEY SPRINGS #1 | 003/069 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-26 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.819224 | 38.1901 | ETL.8210 | 40903830 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116842078 | Not Scheduled | T2 EI FULTON-PUEBLO 009/044 RPNT TWR | 43761418 | FULTON-PUEBLO | 009/044 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-26 | 2020-03-26 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.159755 | 38.5183 | ETL.1600 | 40765287 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116846448 | Not Scheduled | T2 DI BUELL TON TAP 000/001 RPL STRW | 31508010 | BUELLTON TAP | 000/001 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-27 | 2020-03-27 | [7 empty] | TR2 | LATE | South | WSIP |  |  |  |  | Estimating | LC rtn'd to CIRT for pole replacement | '-120.184809 | 34.6476 | ETL.1201 | 40588594 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 2 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116846685 | Before Feb | DI EXCHEQUER-YOSEMITE 000/012 PAINT | 43825051 | EXCHEQUER-YOSEMITE | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-03-26 | 2020-03-26 | 2020-11-03 | 2020-12-16 | 2020-12-16 | 2020-11-03 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.243402 | 37.5757 | ETL.8650 | 40651165 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 38 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116847018 | Not Scheduled | T2 DI PINE GROVE TAP 002/053 RPR GYWW | 43749302 | PINE GROVE TAP | 002/053 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-26 | 2020-03-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.655617 | 38.4132 | ETL.8351 | 40754203 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116847089 | Not Scheduled | T2 DI WST PNT-VLLY SPRNGS 6/69 RPL POLE | 31519841 | WEST POINT-VALLEY SPRINGS | 006/069 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-26 | 2020-03-26 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  | REJECT: Could not complete work due to Scope Change Required. No work to verify. |  |  | '-120.636063 | 38.3842 | ETL.8350 | 40579957 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  | Reject | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116847304 | Not Scheduled | T2 DI PINE GROVE TAP 002/053 RPL HRDD | 43749302 | PINE GROVE TAP | 002/049 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.653296 | 38.4121 | ETL.8351 | 40596137 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116847602 | Q2 | DI IONE TAP 003/009 RPR STRW | 43844198 | IONE TAP | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-27 | 2020-03-27 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.949885 | 38.3745 | ETL.8253 | 40871541 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116847622 | Feb | T2 EI DRUM-RIO OSO #2 023/176 RPR CONDS | 43746398 | DRUM-RIO OSO #2 | 023/176 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-03-27 | 2022-03-27 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Project | 2021 - Drum Rio Oso Project | '-121.1363757 | 39.0899 | ETL.1430 | 40851887 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116848127 | Not Scheduled | T2 DI PINE GROVE TAP 001/046 REPR GYWW | 43749302 | PINE GROVE TAP | 001/046 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-25 | 2020-03-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.652218 | 38.4106 | ETL.8351 | 40661588 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116848560 | Not Scheduled | T2 DI STNSLS-MNTC #2 012/075 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 012/075 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2024-03-27 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.569779 | 38.0402 | ETL.3820 | 40744463 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116848617 | Not Scheduled | T2 DI STNSLS-MNTC #2 009/054 CANCEL | 43842132 | STANISLAUS-MANTECA #2 | 009/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2020-03-27 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.510481 | 38.0713 | ETL.3820 | 40744464 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116848925 | Q2 | T2 DI CHRISTI-WIL PS 3/042 RPL STRW | 31431652 | CHRISTIE-WILLOW PASS | 003/042 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-27 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-09 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.147667 | 38.0208 | ETL.6370 | 40599513 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 3 | 2019-08-05 | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116849532 | Mar | T2 PLACER-DEL MAR 000/007 RPL POLE | 31478099 | PLACER-DEL MAR | 000/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-27 | 2020-03-27 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.089297 | 38.8979 | ETL.7800 | 40583103 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116850302 | Not Scheduled | T2 DI STNSLAS-MNTCA #2 9/52 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 009/052 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2024-03-27 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.505766 | 38.0738 | ETL.3820 | 40642922 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116852182 | Not Scheduled | T3 EI GRIZZLY TAP 3/12 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2019-09-22 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.322423 | 39.9075 | ETL.2395 | 44551471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116852541 | Not Scheduled | T3 EI GRIZZLY TAP 3/16 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2019-09-22 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.323328 | 39.9089 | ETL.2395 | 44551420 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116852661 | Not Scheduled | T2 DI STNSLS-MNTCA #2 12/74 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 012/074 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2024-03-27 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.568207 | 38.0411 | ETL.3820 | 40751359 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116852759 | Mar | T2 PLACER-DEL MAR 000/018 RPL POLE | 31478099 | PLACER-DEL MAR | 000/018 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-27 | 2020-03-27 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.095685 | 38.892 | ETL.7800 | 40591283 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116853487 | Not Scheduled | T3 EI GRIZZLY TAP 3/16 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-22 | 2019-09-22 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.323328 | 39.9089 | ETL.2395 | 44551472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116854043 | Not Scheduled | T2 EI SLT SPRNGS-TGR CRK 2/25 BENT STEEL | 43842263 | SALT SPRINGS-TIGER CREEK | 002/025 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-26 | 2024-03-26 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.26242 | 38.4856 | ETL.3500 | 40744655 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116854127 | Q2 | T2 EI CRESTA-RIO OSO 40/265 RPR INSS |  | CRESTA-RIO OSO | 040/265 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2020-03-25 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51486 | 39.412 | ETL.4590 | 40786932 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-23 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116854278 | Not Scheduled | T2 EI SLT SPRNGS-TGR CRK 02/024 RPNT TWR | 43842275 | SALT SPRINGS-TIGER CREEK | 002/024 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-03-26 | 2020-03-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.261269 | 38.4866 | ETL.3500 | 40744661 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116854449 | Not Scheduled | T2 DI STNSLAUS-MNTCA #2 20/116 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 020/116 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2020-03-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.66317 | 37.9715 | ETL.3820 | 40803372 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116854603 | Not Scheduled | DI BRIONES TAP 2/37 GRD WASH |  | BRIONES TAP | 002/037 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-27 | 2020-03-27 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.752 | 37.9043 | ETL.7055 | 40695869 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-31 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116855000 | Not Scheduled | T2 EI VCA-VVL-JMSN-NRTHTWR 8/63 CANCEL | 43740701 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/063 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-03-28 | 2021-03-28 | [6 empty] | CANCEL/CNCL | TR2 | <60D | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.032541 | 38.3394 | ETL.4100 | 40765438 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116855641 | Not Scheduled | T2 EI MTCLF-GRN VLY 07/051 PAINT STRS | 44300701 | METCALF-GREEN VALLEY | 007/051 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-26 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.679262 | 37.1472 | ETL.2540 | 40585522 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116856263 | Not Scheduled | DI VLLY SPRNGS-MRTL #1 003/013 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 003/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2020-03-28 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.775375 | 38.2517 | ETL.8240 | 40644751 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116856780 | Not Scheduled | T2 DI STNSLS-MANTCA #2 009/053 BNT MEM | 43842132 | STANISLAUS-MANTECA #2 | 009/053 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.507839 | 38.0727 | ETL.3820 | 40663252 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116856926 | Not Scheduled | T2 EI SALT SPGS-TGR CRK 11/90 PAINT STRS | 43842278 | SALT SPRINGS-TIGER CREEK | 011/090 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-03-26 | 2021-03-26 | [7 empty] | TR2 | <60D | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-120.406127 | 38.4796 | ETL.3500 | 40579974 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116857329 | Q2 | T2 DI MELONES-CURTIS 9/2A RMV NEST | 43842416 | MELONES-CURTIS | 009/002A | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.404871 | 37.9422 | ETL.2390 | 40575680 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 18 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116858371 | Not Scheduled | T2 DI VLLY SPRNGS-MRTLL #1 8/11 RPR GYWW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 008/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2020-03-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.768549 | 38.3124 | ETL.8240 | 40600041 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116858631 | Q2 | EI T2 GARCIA TAP -002/007 RPR GYWW | 43761564 | GARCIA TAP | 002/007 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-03-27 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.55612 | 38.8908 | ETL.8411 | 40825504 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-10 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116858641 | Not Scheduled | T2 DI VLY SPRNG-MRTL #1 005/006 RPR SPLW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 005/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-27 | 2020-03-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.76161 | 38.2685 | ETL.8240 | 40813064 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116860956 | Not Scheduled | T2 DI CNTRA CSTA-LS PSTS 17/108 RPR SHLS | 43753328 | CONTRA COSTA-LAS POSITAS | 017/108 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-25 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.73308 | 37.7511 | ETL.4510 | 40818780 | Ground Wire-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116861088 | Not Scheduled | T2 DI STNSLS-MANTEC 20/119 RPL HRDT | 43842120 | STANISLAUS-MANTECA #2 | 020/119 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2023-03-28 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.667927 | 37.9679 | ETL.3820 | 40860787 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116861200 | Not Scheduled | T2 DI STNSLS-MANTEC 20/119 BNT MEM | 43842120 | STANISLAUS-MANTECA #2 | 020/119 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2023-03-28 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.667927 | 37.9679 | ETL.3820 | 40860787 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116861356 | Not Scheduled | T2 DI CRESTA-RIO OSO 27/220 PAINT | 43708739 | CRESTA-RIO OSO | 027/220 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-03-28 | 2020-03-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.528106 | 39.5809 | ETL.4590 | 40911510 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116861685 | Not Scheduled | T2 EI TEMBLOR-SLO 056/310 RPNT TWR | 43740614 | TEMBLOR-SAN LUIS OBISPO | 056/310 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-29 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.608084 | 35.2686 | ETL.3960 | 40580080 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116861893 | Not Scheduled | DI VLLY SPGS-MRTLL #1 3/013A RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 003/013A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2020-03-28 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.77474 | 38.2524 | ETL.8240 | 44183841 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116862153 | Not Scheduled | T3 EI GROVE TAP 001/029 RPR GYWW | 43736449 | PINE GROVE TAP | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2018-12-29 | 2019-06-29 | [7 empty] | TR3 | LATE | Central | WSIP |  |  |  |  | Clearance Delayed | Clearance in September on section not able to take out due to summer loading and West Point Valley Springs shoo fly. | '-120.644002 | 38.4053 | ETL.8351 | 40812438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116862252 | Not Scheduled | T2 DI VLY SPRGS MRTL#1 9/4 STRW RPR | 43740949 | VALLEY SPRINGS-MARTELL #1 | 009/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2020-03-28 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.772084 | 38.3195 | ETL.8240 | 40753696 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116862379 | Q2 | T2 DI CRESTA-RIO OSO 28/225 INS DAMS | 43729877 | CRESTA-RIO OSO | 028/225 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-27 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.530592 | 39.5728 | ETL.4590 | 40911511 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116862640 | Not Scheduled | T3 EI TEMBLOR-SLO 054/301 RPNT TWR | 43740614 | TEMBLOR-SAN LUIS OBISPO | 054/301 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-29 | 2019-09-29 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.58198 | 35.283 | ETL.3960 | 40585669 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116863145 | Not Scheduled | T2 DI BRCEBURG JCT-MRPS 005/013 RPR IBWW | 43825046 | BRICEBURG JCT-MARIPOSA TAP | 005/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-28 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.986205 | 37.5216 | ETL.8651 | 40660791 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116866950 | Not Scheduled | T2 DI VLY SPRNGS-MRTL #1 12/6 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.793235 | 38.3636 | ETL.8240 | 40805072 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116867200 | Not Scheduled | T2 DI VLY SPRNG-MRTL #1 012/004 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.792255 | 38.3626 | ETL.8240 | 40755069 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116867228 | Not Scheduled | T2 DI DUNLAP TAP 7/4 RPR GWSS | 43709735 | DUNLAP TAP | 007/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-28 | 2020-03-28 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.158766 | 36.6458 | ETL.9061 | 40763449 | Auto Guy Wire Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116867330 | Not Scheduled | T2 DI VLLY SPRGS-MRT #1 10/010 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 010/010 | ICW | E | 2020_(1a) PSPS |  | 2019-03-29 | 2020-03-29 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.781872 | 38.3412 | ETL.8240 | 40599122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 116868486 | Not Scheduled | T2 DI CHRISTIE-SOBRNTE 012/069 RPR JMPS | 44621446 | CHRISTIE-SOBRANTE | 012/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-26 | 2020-03-26 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.195397 | 37.9695 | ETL.1260 | 40871959 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Land |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116870394 | Q2 | T2 EI KONOCTI-MIDDLETOWN 23/011 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 023/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.614309 | 38.9027 | ETL.6380 | 40586668 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116870752 | Not Scheduled | DI STNSLS-MNTC #2 027/163 PNT TWR | 43842132 | STANISLAUS-MANTECA #2 | 027/163 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-03-29 | 2020-03-29 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.778921 | 37.9203 | ETL.3820 | 40642820 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116871007 | Mar | PLACER-DEL MAR 1/042 RPL POLE | 31502069 | PLACER-DEL MAR | 001/042 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-30 | 2020-03-30 |  |  | 2021-03-31 | 2021-03-27 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.111263 | 38.8821 | ETL.7800 | 40660920 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116871562 | Not Scheduled | T3 EI DRUM-RIO OSO #1 000/001 PNT STRT | 43746398 | DRUM-RIO OSO #1 | 000/001 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-03-30 | 2023-03-30 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.769665 | 39.2571 | ETL.1420 | 40594929 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116873540 | Not Scheduled | T2 DI VLY SPNGS-MRTL #1 12/3 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.791702 | 38.3621 | ETL.8240 | 40666222 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116873586 | Not Scheduled | T2 DI VLY SPNGS-MRTL #1 12/1 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-28 | 2020-03-28 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.790336 | 38.3608 | ETL.8240 | 40600035 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116876142 | Mar | T3 EI DRUM-HIGGINS 009/092L RPL STRW | 31432822 | DRUM-HIGGINS | 009/092 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892639 | 39.1723 | ETL.4393 | 44172126 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116876143 | Mar | T3 EI DRUM-HIGGINS 009/092C RPL STRW | 31432822 | DRUM-HIGGINS | 009/092 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892639 | 39.1723 | ETL.4393 | 44172127 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-04-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116876728 | Feb | LAYTONVILLE-COVELO 13/04 REPL NG POLE | 31451876 | LAYTONVILLE-COVELO | 013/004 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-03-28 | 2021-03-07 |  |  | 2021-02-24 | 2021-02-22 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.266864 | 39.7573 | ETL.7390 | 40750461 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 116878160 | Q2 | T2 Mendocino/Redbud_030/145 RPLC INSS | 31478190 | MENDOCINO-REDBUD | 030/145 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-31 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.735888 | 39.0466 | ETL.2410 | 40791768 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116880142 | Not Scheduled | T2 DI CHRISTIE-FRNKLIN #2 0/12 REPL POLE | 31499910 | CHRISTIE-FRANKLIN #2 | 000/012 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-01 | 2020-04-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.225912 | 38.0041 | ETL.6360 | 40581068 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-04-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116880732 | Not Scheduled | EI PALERMO-WYANDOTTE 001/015 RPR STRS | 43754992 | PALERMO-WYANDOTTE | 001/015 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-10 | 2020-01-10 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.539609 | 39.4733 | ETL.4315 | 40757544 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116882290 | Not Scheduled | EI DRUM-RIO OSO #1 33/236 PAINT STRS | 43746398 | DRUM-RIO OSO #1 | 033/236 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-03-23 | 2024-03-23 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.291893 | 39.0266 | ETL.1420 | 40817486 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116883769 | Mar | T2 DI MRG-SN LNDR 008/057 BENT STEEL | 44294404 | MORAGA-SAN LEANDRO #1 | 008/057 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-01 | 2020-04-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.117419 | 37.7394 | ETL.2770 | 40804655 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116883826 | Not Scheduled | DISTRIBUTION JUMPER |  | SPARE T-LINE RECORD | T-165 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-25 | 2020-03-25 | [6 empty] | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.989252 | 35.1609 | ETL.9240 | 43249631 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116884682 | Mar | T2 DI MORAGA-OAKLAND #1 3/27 RMV SOIL | 43752132 | MORAGA-OAKLAND #1 | 003/027 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-01 | 2021-05-31 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.210798 | 37.816 | ETL.2720 | 40804633 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-06-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116884688 | Not Scheduled | T2 DI CLEAR LAKE-HOPLAND 1/0 CANCEL | 43734956 | CLEAR LAKE-HOPLAND | 001/000 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-01 | 2020-04-01 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.064436 | 38.9695 | ETL.6390 | 40587013 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116885043 | Not Scheduled | T2 DI PITTSBURG-EASTSHORE 5/22 RPR FOND | 44238518 | PITTSBURG-EASTSHORE | 005/022 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-01 | 2020-04-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.90117 | 37.9749 | ETL.5462 | 40680966 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116885142 | Not Scheduled | T2 DI PITTSBURG-SN MTO 006/029 INS HRDT |  | PITTSBURG-SAN MATEO | 006/029 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-04-01 | 2024-04-01 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.893848 | 37.9515 | ETL.5463 | 40761887 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-11-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116885233 | Not Scheduled | T2 DI PTTSBRG-SN MTEO 008/034 INS HRDT |  | PITTSBURG-SAN MATEO | 008/034 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-04-01 | 2024-04-01 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.888931 | 37.9278 | ETL.5463 | 40862985 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-11-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116899610 | Not Scheduled | T2 TW DI PTTSBG-TSL #1 021/093 RPR FOND | 43753186 | PITTSBURG-TESLA #1 | 021/093 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-01 | 2020-04-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.667467 | 37.8298 | ETL.5510 | 40658971 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116899611 | Not Scheduled | T2 DI PITTSBUG-EASTSHORE 21/082 RPR JUMS | 43753182 | PITTSBURG-EASTSHORE | 021/082 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-01 | 2020-04-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.927405 | 37.7487 | ETL.5462 | 41135612 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116899721 | Mar | T2 DI CLR LAKE-HOPLAND 0/15 RPL POLE | 31501678 | CLEAR LAKE-HOPLAND | 000/015 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-01 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.066037 | 38.9697 | ETL.6390 | 40750112 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116903296 | Q2 | T2 HAT CREEK #1-WESTWD 13/251 REFRAME | 31471576 | HAT CREEK #1-WESTWOOD | 013/251 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-03-30 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.366886 | 40.8165 | ETL.7030 | 40735035 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116905339 | Q3 | T2 DELTA-MTN GATE JCT 13/171 REPL INSS | 31454737 | DELTA-MOUNTAIN GATE JCT | 013/171 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-30 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.310277 | 40.7722 | ETL.6750 | 41115165 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q3 |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116920659 | Not Scheduled | DISTRIBUTION RPL POLE | 31383233 | SPARE T-LINE RECORD | T018 | 70Y | F | Pre-2020_(2) High fire spread TD |  | 2019-04-02 | 2021-04-02 | [6 empty] | Midway-Santa Maria |  | <60D | South | Non-WSIP | [6 empty] | '-120.335532 | 34.9327 | ETL.9240 | 43250119 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116922941 | Q2 | T2 DI NEWARK-VLECITOS 95/620 BNT MEM | 43753293 | NEWARK-VALLECITOS | 095/620 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-01 | 2020-04-01 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.894258 | 37.5681 | ETL.7670 | 40613250 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116927011 | Q2 | T3 EI PARADISE-TABLE MTN 16/134 RPR GYWW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 44552318 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116927013 | Q2 | T3 EI PARADISE-TABLE MTN 16/134 RPR GYWW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-08 | 2019-07-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 44552501 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116937011 | Mar | T2 MENDOCINO-WLTS-FT BRG 23/7 RMV VEG |  | MENDOCINO-WILLITS-FORT BRAGG | 023/007 | HNA | E | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-03-26 | 2021-05-31 |  |  | 2021-03-16 | 2021-03-16 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.7550 | 44211135 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | HNA | Mar |  |  | 2019-09-10 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116937655 | Q2 | EI CTTNWD-DLEVN #1 30/207A RPLC DAMS | 43726632 | COTTONWOOD-DELEVAN #1 | 030/207A | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-03-19 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-30 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.266328 | 39.9558 | ETL.4550 | 40577001 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116939014 | Q2 | T2 DI CRZY HRS CYN SL SL#1 :13/70 STRT | 43775531 | CRZY HORSE CYN-SALNS-SOLDAD#1 | :013/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-02 | 2020-04-02 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.432541 | 36.5952 | ETL.2900 | 40591359 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 8 | 2019-07-15 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116939245 | Not Scheduled | DI LAS POSITAS NEWARK 13/89 STRS PAINT | 43753291 | LAS POSITAS-NEWARK | 013/089 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-02 | 2024-04-02 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.889356 | 37.5504 | ETL.4980 | 40862566 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116939362 | Not Scheduled | T2 EI CRESTA-RIO OSO 29/235 PAINT STRS | 43729877 | CRESTA-RIO OSO | 029/235 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-01-11 | 2024-01-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.535578 | 39.5565 | ETL.4590 | 41083096 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116939533 | Not Scheduled | T2 EI STNSLS-MNTCA #2 014/084 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 014/084 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-03-27 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.592282 | 38.0263 | ETL.3820 | 40764248 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116939545 | Not Scheduled | T3 DI SLT SPRGS-TGR CRK 15/118 PNT STRT | 43842402 | SALT SPRINGS-TIGER CREEK | 015/118 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-01 | 2019-10-01 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.477709 | 38.4532 | ETL.3500 | 40856680 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116950347 | Q2 | T2 EI MALIN-ROUND MTN #2 50/251 RPR SHLS | 43621093 | MALIN-ROUND MTN #2 | 050/251 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-03-20 | 2020-03-20 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.559088 | 41.3234 | ETL.6020 | 40587309 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116952426 | Q2 | T2 EI CBRN-LS AGLS SW ST 41/177 RPL CONN | 43749765 | COBURN-PANOCHE | 041/177 | ICM | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-02 | 2020-04-02 | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2021-04-29 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.069279 | 36.6644 | ETL.4460 | 40809321 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Moss Landing |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116953844 | Not Scheduled | EI GREEN VALLY-LLAGS :12/076 PAINT STRS | 43766025 | GREEN VALLEY-LLAGAS | :012/076 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-01-25 | 2020-01-25 | [8 empty] | LATE | South | WSIP | [6 empty] | '-121.644717 | 37.0923 | ETL.1720 | 40819873 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116954236 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 16/119 RPR GYWW | 43753055 | CAYUCOS-CAMBRIA | 016/119 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-02 | 2020-04-02 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-121.087542 | 35.5891 | ETL.8560 | 40819707 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 1 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116957168 | Mar | POE-RIO OSO 032/216 RPR JUMS | 43875009 | POE-RIO OSO | 032/216 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-04 | 2020-04-04 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.536668 | 39.524 | ETL.5540 | 40843579 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116958507 | Not Scheduled | T2 DI CASTRO VLY-NWK 10/54 RPR STRT PNT | 43751913 | CASTRO VALLEY-NEWARK | 010/054 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-04-02 | 2020-04-02 | [7 empty] | TR2 | LATE | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-121.9237 | 37.5914 | ETL.4450 | 40819387 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116959302 | Q2 | T2 DI WISHON COPPERMINE 0/1 RPL ANCS | 31433444 | WISHON-COPPERMINE | 000/001 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2021-05-31 |  |  | 2021-06-15 | 2021-06-02 |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.505707 | 37.147 | ETL.9330 | 40591637 | Anchor-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116959303 | Q2 | T2 DI WISHON COPPERMINE 0/1 RPL GYWS | 43711388 | WISHON-COPPERMINE | 000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2021-05-31 |  |  | 2021-06-15 | 2021-06-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.505707 | 37.147 | ETL.9330 | 40591637 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116960675 | Not Scheduled | DI CLR LK HOPELAND 0/13 CANCEL | 43734956 | CLEAR LAKE-HOPLAND | 000/013 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-01 | 2020-04-01 | [6 empty] | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.0691 | 38.9701 | ETL.6390 | 40667038 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116960679 | Q2 | T2 EI CRESTA-RIO OSO 008/072A RPL CONN | 43844645 | CRESTA-RIO OSO | 008/072A | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-02 | 2020-04-02 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421964 | 39.8293 | ETL.4590 | 41162726 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116960915 | Not Scheduled | T3 EI DRUM-RIO OSO #1 08/88 PAINT STRS | 43746398 | DRUM-RIO OSO #1 | 008/088 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-19 | 2019-07-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.889062 | 39.1876 | ETL.1420 | 40873409 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116967225 | Q3 | T2 DI WISHON-COPPERMNE 007/050 REPR FOND | 43711311 | WISHON-COPPERMINE | 007/050 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-04-03 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.540751 | 37.0606 | ETL.9330 | 40606324 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-08-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116967637 | Q2 | T2 EI OLEUM-G #1 001/013 RPL HRDT | 43752139 | OLEUM-G #1 | 001/013 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-05 | 2020-04-05 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.234061 | 38.0334 | ETL.3150 | 40644329 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116968968 | Not Scheduled | T2 DI STS-MLNS SS MTCA #1 4/29 RPR FOND | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 004/029 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-04 | 2020-04-04 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.443839 | 38.1079 | ETL.3830 | 40856453 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-04-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116970741 | Before Feb | T2 DI MERCED FALLS-EXQR 3/4 STRT RPR | 44300846 | MERCED FALLS-EXCHEQUER | 003/004 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-05 | 2020-04-05 | 2020-09-01 | 2020-10-31 | 2020-10-31 | 2020-09-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.319222 | 37.5726 | ETL.8990 | 40748141 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116970995 | Mar | T2 DI EAGLE RCK-CRTINA :15/001 CANCEL |  | EAGLE ROCK-CORTINA | :015/001 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2020-04-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608649 | 38.9383 | ETL.1470 | 40629350 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-06 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116971051 | Q3 | T2 DI WISHON-COPPERMINE 9/71 RPR FOND | 43711311 | WISHON-COPPERMINE | 009/071 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-04-06 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.566407 | 37.0243 | ETL.9330 | 40595600 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116971811 | Not Scheduled | T2 DI HELMS-GREGG #1 022/150 REMOVE NEST | 43825460 | HELMS-GREGG #1 | 022/150 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-04 | 2024-04-04 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.33215 | 36.947 | ETL.4870 | 40602723 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116972003 | Not Scheduled | T2 DI VLLY SPRG-MRTL #1 010/004 RPR SPLW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 010/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-02 | 2020-04-02 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.778439 | 38.3358 | ETL.8240 | 40758491 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116972119 | Not Scheduled | DI STNSLS-MLNS-MNTCA #2 26/152 RPR SPLS | 43842132 | STANISLAUS-MANTECA #2 | 026/152 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-02 | 2020-04-02 | [5 empty] | TLN/TLQ error |  |  | LATE | Central | WSIP | [6 empty] | '-120.748745 | 37.9293 | ETL.3820 | 40642939 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116976706 | Q3 | T2 DI WISHON-COPPERMINE 11/85 RPR FOND | 44571732 | WISHON-COPPERMINE | 011/085 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-04-04 | 2024-04-04 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.586578 | 36.9968 | ETL.9330 | 40765443 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116977523 | Not Scheduled | T2 DI STNLS-MLNS SS-MNTCA 2/17 PNT STRT | 43841832 | STANISLAUS-MELONES SS-MANTECA #1+ | 002/017 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-04 | 2024-04-04 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.414321 | 38.1241 | ETL.3830 | 40803312 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116978773 | Q2 | T2 VOLTA-DESCHUTES 20/445 REFRAME | 31475775 | VOLTA-DESCHUTES | 020/445 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-08 | 2020-04-08 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.227783 | 40.5521 | ETL.8290 | 40676458 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-06-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116979755 | Q2 | T2 DI IONE TAP 001/005 REPL CRSW | 31434028 | IONE TAP | 001/005 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-03 | 2020-04-03 | 2021-03-29 |  | 2021-04-03 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925042 | 38.3598 | ETL.8253 | 40745286 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116981376 | Not Scheduled | T2 DI STSL-MNS SS-MTCA #1 10/61 CANCEL | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 010/061 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-05 | 2020-04-05 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.524244 | 38.0639 | ETL.3830 | 40594248 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116982050 | Not Scheduled | T2 DI STSL-MNS SS-MTCA #1 07/45 PNT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 007/045 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-05 | 2023-04-05 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.485992 | 38.0846 | ETL.3830 | 40745910 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116982474 | Feb | T2 DI EAGLE ROCK-REDBUD :18/001 RPR GYWW | 43760959 | EAGLE ROCK-REDBUD | :018/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2020-04-03 | 2020-11-11 | 2020-11-12 | 2021-02-27 | 2021-02-22 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612467 | 38.9824 | ETL.1480 | 40602600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116983334 | Feb | T2 DI EAGLE ROCK-REDBUD :18/000 RPR GYWW | 43760959 | EAGLE ROCK-REDBUD | :018/000 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2020-04-03 | 2020-11-11 | 2020-11-12 | 2021-02-27 | 2021-02-22 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612459 | 38.9816 | ETL.1480 | 40618884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116984351 | Not Scheduled | T2 DI STN-MLN SW ST-MNT#1 11/69 RPR STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-08 | 2020-04-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.549164 | 38.0521 | ETL.3830 | 40871563 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116984398 | Q2 | T2 VOLTA-DESCHUTES 019/427 RPL POLE | 35163206 | VOLTA-DESCHUTES | 019/427 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-09 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.214873 | 40.5493 | ETL.8290 | 40615948 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116984689 | Mar | T3 EI BRUNSWICK #2 TAP 000/007 RPL INSS | 31453336 | BRUNSWICK #2 TAP | 000/007 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-19 | 2019-07-19 |  |  | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.013336 | 39.1521 | ETL.1431 | 40834391 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-06-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116985048 | Not Scheduled | T3 DI CARIBOU-PALERMO :008/063 REPR FOND | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-03-16 | 2019-09-16 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 116985801 | Before Feb | T2 DI EXCHEQUER-YSMITE 01/07 PNT/CT STRS | 43709741 | EXCHEQUER-YOSEMITE | 001/007 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-01-18 | 2020-01-18 | 2020-11-03 | 2020-12-16 | 2020-12-16 | 2020-11-03 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.258318 | 37.5758 | ETL.8650 | 40806452 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116986060 | Not Scheduled | T2 DI STN-MLN SW -MNT#1 18/114 PNT STRT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 018/114 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-04-08 | 2020-04-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.642037 | 37.9873 | ETL.3830 | 40744436 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116986189 | Mar | T2 DI CLEAR LAKE-HOPLND 9/2 RPR GYWS | 43734957 | CLEAR LAKE-HOPLAND | 009/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-08 | 2021-05-31 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.923367 | 38.9937 | ETL.6390 | 44639194 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116986500 | Mar | T2 DI EAGLE ROCK-CORTINA :15/14 RPR GYWW | 43761301 | EAGLE ROCK-CORTINA | :015/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-08 | 2020-04-08 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607779 | 38.9472 | ETL.1470 | 41176339 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116986504 | Mar | T2 DI EAGLE ROCK-CORTINA :15/14 RPL INSW | 31469921 | EAGLE ROCK-CORTINA | :015/014 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-08 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607779 | 38.9472 | ETL.1470 | 40779607 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116986869 | Not Scheduled | T2 DI IGNACIO-SN RFAEL #1 7/38 PNT STRS | 43761667 | IGNACIO-SAN RAFAEL #1 | 007/038 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-08 | 2020-04-08 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.494925 | 37.9868 | ETL.1850 | 40858036 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116991107 | Not Scheduled | T2 DI STN-MLN SW STA-MNT#1 6/38 PNT STRS | 43841832 | STANISLAUS-MELONES SS-MANTECA #1+ | 006/038 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-04-05 | 2020-04-05 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.469087 | 38.0939 | ETL.3830 | 40856452 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 116991476 | Not Scheduled | T2 DI HELMS-GREGG #1 22/148 RMV NEST | 43825460 | HELMS-GREGG #1 | 022/148 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-05 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.32174 | 36.9503 | ETL.4870 | 40858331 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117000185 | Not Scheduled | HEINZ TAP - 115 KV 000/014 | 43846573 | HEINZ TAP IDLE | 000/014 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-10 | 2020-04-10 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.412231 | 37.7449 | ETL.2193 | 40758883 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117000638 | Not Scheduled | HEINZ TAP 000/006 INST MRKW | 43846573 | HEINZ TAP IDLE | 000/006 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-04-10 | 2024-04-10 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.415472 | 37.7479 | ETL.2193 | 40828533 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117000670 | Not Scheduled | HEINZ TAP 000/006 RMV IDLE SWITCH | 43853810 | HEINZ TAP IDLE | 000/006 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-04-10 | 2024-04-10 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.415472 | 37.7479 | ETL.2193 | 40828533 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117001123 | Not Scheduled | T2 DI STNS-MELN SW MANT 3/24 PNT STRT | 43841832 | STANISLAUS-MELONES SS-MANTECA #1+ | 003/024 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-04-09 | 2020-04-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.432942 | 38.1139 | ETL.3830 | 40756401 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117005727 | Not Scheduled | T2 DI IGNACIO-ALTO 016/157 RPL STRW | 31492618 | IGNACIO-ALTO | 016/157 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-05 | 2020-04-05 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.51668 | 37.9168 | ETL.7150 | 40770115 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117006596 | Feb | T2 DI EAGLE ROCK-REDBD :15/11 RPL HRDD | 43760959 | EAGLE ROCK-REDBUD | :015/011 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2020-04-10 | 2020-11-11 | 2020-11-12 | 2021-02-27 | 2021-02-22 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607986 | 38.9446 | ETL.1480 | 40585046 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117006648 | Feb | T2 DI EAGLE ROCK-REDBD :15/11 RPL SWIW | 31472116 | EAGLE ROCK-REDBUD | :015/011 | 93H | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2020-04-10 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607986 | 38.9446 | ETL.1480 | 40585046 | Switch-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-06-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117006683 | Not Scheduled | DI LAS POSITAS-NEWRK 015/097 RPNT STRS | 43753291 | LAS POSITAS-NEWARK | 015/097 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-04-09 | 2020-04-09 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.902364 | 37.5355 | ETL.4980 | 40819290 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117007683 | Not Scheduled | T2 DI STNSLS-MANTECA #2 015/094 RPR FOND | 44460414 | STANISLAUS-MANTECA #2 | 015/094 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-10 | 2020-04-10 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.611092 | 38.0105 | ETL.3820 | 40744468 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117007708 | Not Scheduled | T2 DI STNSLS-MNTCA #2 15/94 PAINT | 43842132 | STANISLAUS-MANTECA #2 | 015/094 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-04-10 | 2020-04-10 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.611092 | 38.0105 | ETL.3820 | 40744468 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117008010 | Not Scheduled | T2 DI VLLY SPRNG-MRTL #1 12/7 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.793805 | 38.3643 | ETL.8240 | 40805044 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117008204 | Q4 | T2 DI SALINAS-LAURELES 08/186 RMV VEGN |  | SALINAS-LAURELES | 008/186 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-04-04 | 2020-04-04 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.707892 | 36.5908 | ETL.7930 | 40666632 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117008414 | Q2 | T2 DI COLGATE-PALERMO 017/340 RPL STRW | 31495724 | COLGATE-PALERMO | 017/340 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-09 | 2020-04-09 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.434258 | 39.4356 | ETL.6500 | 40766440 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117008583 | Not Scheduled | T2 DI STANISLS-MANTECA #2 15/94 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 015/094 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2020-04-10 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.611092 | 38.0105 | ETL.3820 | 40744468 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117009591 | Not Scheduled | T2 DI EAGLE ROCK-REDBUD :15/04 REMV ROW1 |  | EAGLE ROCK-REDBUD | :015/004 | CHR | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-10 | 2020-04-10 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608031 | 38.9403 | ETL.1480 | 40750731 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117013071 | Not Scheduled | T2 DI CLGTE-SMRTVILE #2 002/026 RPL SPLW | 43851744 | COLGATE-SMARTVILLE #2 | 002/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-09 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.223185 | 39.3183 | ETL.6520 | 40594294 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117013092 | Mar | T3 DI PARADISE-BUTTE 001/015 RPR GRWS | 43758389 | PARADISE-BUTTE | 001/015 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-10 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.62906 | 39.7507 | ETL.4396 | 41127211 | Ground Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117014198 | Not Scheduled | T2 DI JFFERSON-STNFORD 001/032 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/032 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.263139 | 37.4614 | ETL.7220 | 40612107 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117014201 | Not Scheduled | DI JEFFERSON-STANFORD 002/064 RPL STRW | 31434138 | JEFFERSON-STANFORD (NO FLY) | 002/064 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-11 | 2020-04-11 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.248261 | 37.4641 | ETL.7220 | 40874147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-04-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117014673 | Not Scheduled | T2 DI STNS-MNS SS MTCA #1 14/84 INS HRDT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 014/084 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-04-05 | 2022-04-05 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.587666 | 38.0293 | ETL.3830 | 40744435 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117015686 | Mar | T2 DI EAGLE ROCK-CORTINA :14/7 GYWW RPR | 43761301 | EAGLE ROCK-CORTINA | :014/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608519 | 38.9279 | ETL.1470 | 41176310 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117016775 | Q2 | T3 EI DRUM-HIGGINS 3/32R REPLACE POLE | 31453426 | DRUM-HIGGINS | 003/032 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.799724 | 39.2229 | ETL.4393 | 44172143 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-04-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117017109 | Not Scheduled | T2 DI JEFFERSON-STANFORD 1/25 RPR STRW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.268239 | 37.462 | ETL.7220 | 40653218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117017484 | Not Scheduled | T2 DI JEFFERSON-STANFORD 1/30 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/030 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.264748 | 37.4617 | ETL.7220 | 40875244 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117017489 | Not Scheduled | T2 DI JEFFERSON-STANFORD 1/23 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/023 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.269243 | 37.4614 | ETL.7220 | 40599123 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117017751 | Not Scheduled | T2 DI JEFFERSON-STANFORD 1/39 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/039 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.259769 | 37.4623 | ETL.7220 | 40812607 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117018623 | Not Scheduled | T2 DI JEFFERSON-STANFORD 2/61 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/061 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.250489 | 37.4639 | ETL.7220 | 40813364 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117018860 | Q2 | DI LAYTONVILLE-WILLITS 4/2 WASH INSU | 43761785 | LAYTONVILLE-WILLITS | 004/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2021-05-31 | 2020-10-14 | 2020-10-17 | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.336224 | 39.4567 | ETL.8360 | 40733598 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117019218 | Not Scheduled | T2 DI BRCBRG JCT MRPOSA 4/18 RPR STRW | 43825046 | BRICEBURG JCT-MARIPOSA TAP | 004/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.985987 | 37.532 | ETL.8651 | 40872665 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117023770 | Q2 | T2 RINCON #2 00/02 REPL FLSH INSUL | 31447732 | RINCON #2 TAP | 000/002 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-13 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.667734 | 38.4939 | ETL.1611 | 40710645 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117023813 | Not Scheduled | T2 DI JEFFERSON-STANDFORD 1/43 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/043 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.259104 | 37.4636 | ETL.7220 | 40599124 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117023877 | Not Scheduled | T2 DI JEFFERSON-STNFRD 2/46 RPR GYWW | 43744381 | JEFFERSON-STANFORD (NO FLY) | 002/046 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.257373 | 37.4645 | ETL.7220 | 40588808 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117023956 | Not Scheduled | T2 DI JEFFERSON-STAND 2/063 RPR GYWW | 43744381 | JEFFERSON-STANFORD (NO FLY) | 002/063 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.248805 | 37.4636 | ETL.7220 | 40865046 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117024006 | Not Scheduled | T2 DI JEFFERSON-STANDFORD 2/60 RPL GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/060 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.251591 | 37.4641 | ETL.7220 | 40767166 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117024017 | Not Scheduled | T2 DI JEFFERSON-STANDFORD 2/45 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/045 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.257687 | 37.4642 | ETL.7220 | 40612133 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117024149 | Not Scheduled | T2 DI JEFFERSON-STANFORD 1/28 RPR GYWW | 43744381 | JEFFERSON-STANFORD (NO FLY) | 001/028 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.266038 | 37.4618 | ETL.7220 | 40824885 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117024366 | Not Scheduled | T2 DI STSLS-MNS SS-MTC #1 9/60 REPAINT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 009/060 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-05 | 2024-04-05 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.522057 | 38.0651 | ETL.3830 | 40581586 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117025363 | Not Scheduled | T3 EI MDDL FRK-GLD HLL 008/072 RPNT STRT | 44302263 | MIDDLE FORK-GOLD HILL | 008/072 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-13 | 2024-04-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.729152 | 38.9963 | ETL.5140 | 40681075 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117028282 | Feb | T2 EI BCKS CRK-RCK CRK-CRST :001/013 RPL | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :001/013 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-14 | 2020-04-14 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.362328 | 39.895 | ETL.4430 | 40656150 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117030161 | Q2 | T2 DI EXCHQUER-YOSEMITE 021/078 PNT STRS | 44300705 | EXCHEQUER-YOSEMITE | 021/078 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-03 | 2020-04-03 |  |  | 2021-06-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.009093 | 37.5832 | ETL.8650 | 40859318 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 42 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117030406 | Not Scheduled | T2 DI STNSLS-MANTECA #2 24/141 PNT STRS | 43842132 | STANISLAUS-MANTECA #2 | 024/141 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-03 | 2022-04-03 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.719798 | 37.9379 | ETL.3820 | 40584588 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117031770 | Mar | T2 DI EAGLE RCK-CRTNA :18/000 RPR HRDD | 43761301 | EAGLE ROCK-CORTINA | :018/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-03 | 2020-04-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613115 | 38.981 | ETL.1470 | 41176383 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117033850 | Mar | DI CLEAR LAKE-HOPLAND 001/010 REPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 001/010 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2021-05-31 | 2021-03-30 | 2021-04-02 | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.052193 | 38.9667 | ETL.6390 | 40587016 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117034416 | Not Scheduled | T2 DI JFFERSON-STNFORD 001/040 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/040 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.260037 | 37.4626 | ETL.7220 | 40875242 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117034784 | Not Scheduled | T2 DI JEFFERSON-STANFORD 01/35 REPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/035 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.261461 | 37.4621 | ETL.7220 | 40653216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117034968 | Q2 | T2 EI CHOWCHILLA-KERCKHOFF 0/4 RPR FOND | 43795032 | CHOWCHILLA-KERCKHOFF | 000/004 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-15 | 2021-05-31 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.559507 | 37.0915 | ETL.1250 | 40748514 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | BLM | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-05-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117035238 | Not Scheduled | T3 DI CNTRVLLE-TBLE MTN 02/35 RPL STRW | 31495727 | CENTERVILLE-TABLE MTN | 002/035 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-13 | 2019-10-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.677948 | 39.7628 | ETL.6320 | 40598384 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117035485 | Not Scheduled | T2 DI JEFFERSON-STANFORD 2/50 REPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/050 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-12 | 2020-04-12 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.255614 | 37.4656 | ETL.7220 | 40767168 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117035538 | Mar | T2 DI KONOCTI-MIDDLETOWN 17/01 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 017/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2020-04-12 | 2021-03-01 | 2021-03-04 | 2021-03-03 | 2021-03-03 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573671 | 38.812 | ETL.6380 | 40600743 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117035609 | Not Scheduled | T2 DI SPAULDING-SUMMIT 004/149 INS MRKW | 43947948 | SPAULDING-SUMMIT | 004/149 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2020-04-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.576488 | 39.3073 | ETL.8060 | 40586084 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117036603 | Not Scheduled | T2 EI LKVLL-IGNC #1 IG002/012 RPNT STRS | 43761676 | LAKEVILLE-IGNACIO #1 | IG002/012 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-16 | 2024-04-16 | [8 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522296 | 38.1032 | ETL.4940 | 40679207 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117038746 | Mar | T2 DI CLEAR LAKE-HOPLAND 01/03 REPL STRW | 31434604 | CLEAR LAKE-HOPLAND | 001/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-13 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.059435 | 38.9693 | ETL.6390 | 40667033 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117039552 | Not Scheduled | T2 DI CRYSTAL SPRINGS TAP 0/03 RPR GYWW | 43751917 | CRYSTAL SPRINGS TAP (NO FLY) | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.361887 | 37.5325 | ETL.7211 | 40653176 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | CalTrans, SFPUC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117044116 | Not Scheduled | T2 DI CPPRMN-TIVY VLLY 22/09 RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2020-04-12 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117044600 | Not Scheduled | DI STNLS-MLNS SS-MNT#1 28/175 PAINT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 028/175 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-04-15 | 2020-04-15 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.78929 | 37.9173 | ETL.3830 | 40654076 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117044794 | Q2 | T2 DI CNTRVL TM ORVIL 5/105 SPLW RPL | 43903760 | CENTERVILLE-TABLE MTN-OROVILLE | 005/105 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-10 | 2020-04-10 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.645877 | 39.7187 | ETL.6330 | 40692711 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117044922 | Mar | T2NT DI TBLE MTN-PLRM 010/045 INST MRKS | 43760152 | TABLE MTN-PALERMO | 010/045 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-15 | 2020-04-15 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502379 | 39.517 | ETL.5690 | 40756130 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117047443 | Not Scheduled | T2 DI COLGATE-PALERMO 09/185 CANCEL | 43910644 | COLGATE-PALERMO | 009/185 | ICW | F | 2020_(1a) PSPS |  | 2019-04-11 | 2020-04-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.350666 | 39.3602 | ETL.6500 | 40873587 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117047597 | Feb | GOLD HILL-BELLOTA-LCKFRD 43/262 REPL INS | 31457033 | GOLD HILL-BELLOTA-LOCKEFORD | 043/262 | 93K | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-17 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-17 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.142969 | 38.5429 | ETL.1690 | 44596104 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2020-03-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117048028 | Not Scheduled | T2 DI CRYSTL SPRNGS TAP 000/002 RPL POLE | 31507608 | CRYSTAL SPRINGS TAP (NO FLY) | 000/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.361106 | 37.533 | ETL.7211 | 40667847 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117049106 | Not Scheduled | T3 DI GRIZZLY TAP 002/001L REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550829 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117049107 | Not Scheduled | T3 DI GRIZZLY TAP 002/001C REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550813 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117049108 | Not Scheduled | T3 DI GRIZZLY TAP 002/001R REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550741 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117049400 | Not Scheduled | T3 DI GRIZZLY TAP 002/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117049402 | Not Scheduled | T3 DI GRIZZLY TAP 002/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2019-10-15 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117049404 | Not Scheduled | T3 DI GRIZZLY TAP 002/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050486 | Not Scheduled | T3 DI GRIZZLY TAP 002/009 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.316036 | 39.8978 | ETL.2395 | 44550784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050539 | Q2 | T2 EI CHOWCHILLA-KERCKHOFF 0/2 RPR FOND | 43795032 | CHOWCHILLA-KERCKHOFF | 000/002 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-16 | 2021-05-31 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.556809 | 37.0916 | ETL.1250 | 40652116 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | BLM | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-05-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050553 | Not Scheduled | T3 DI GRIZZLY TAP 002/009 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.316036 | 39.8978 | ETL.2395 | 44550836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050574 | Not Scheduled | T3 DI GRIZZLY TAP 002/009 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2019-10-15 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.316036 | 39.8978 | ETL.2395 | 44550816 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050576 | Not Scheduled | T3 DI GRIZZLY TAP 002/010 REPR GYWW |  | TAP (CITY OF SANTA CLARA) | 002/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-14 | 2020-04-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.317667 | 39.8978 | ETL.2395 | 44550769 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050577 | Not Scheduled | T3 DI GRIZZLY TAP 002/010 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-14 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.317667 | 39.8978 | ETL.2395 | 44550744 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050579 | Not Scheduled | T3 DI GRIZZLY TAP 002/010 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-14 | 2019-10-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.317667 | 39.8978 | ETL.2395 | 44550770 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050904 | Not Scheduled | T2 DI JEFFERSON-STANFORD 02/49 REPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/049 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256033 | 37.4656 | ETL.7220 | 40755288 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050907 | Not Scheduled | T2 DI JEFFERSON-STANFORD 2/49 INS HRDW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/049 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256033 | 37.4656 | ETL.7220 | 40755288 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117050908 | Not Scheduled | T2 DI JEFFERSON-STANFORD 2/49 REPL INSW | 31435407 | JEFFERSON-STANFORD (NO FLY) | 002/049 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256033 | 37.4656 | ETL.7220 | 40755288 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117052163 | Mar | T2 DI VLY SPRNGS-MRTL#1 010/014 RPL POLE |  | VALLEY SPRINGS-MARTELL #1 | 010/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-16 | 2020-04-16 |  |  | 2021-03-12 | 2021-03-11 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.783152 | 38.3432 | ETL.8240 | 40768889 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-08-20 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117052200 | Mar | T2 DI VEDDER TAP 8/93 RPR GYWW | 43860163 | VEDDER TAP | 008/093 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-12 | 2021-05-31 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-118.960257 | 35.5598 | ETL.2141 | 40669197 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117052915 | Not Scheduled | T3 DI GRIZZLY TAP 002/005 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2019-10-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.309307 | 39.8969 | ETL.2395 | 44550834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117052930 | Not Scheduled | T3 DI GRIZZLY TAP 002/005 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2019-10-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.309307 | 39.8969 | ETL.2395 | 44550751 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117052940 | Not Scheduled | T3 DI GRIZZLY TAP 002/005 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2019-10-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.309307 | 39.8969 | ETL.2395 | 44550792 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117053049 | Not Scheduled | T3 DI GRIZZLY TAP 002/008 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.314116 | 39.8975 | ETL.2395 | 44550743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117053240 | Not Scheduled | T3 DI GRIZZLY TAP 002/008 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.314116 | 39.8975 | ETL.2395 | 44550783 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117054182 | Not Scheduled | EI LAKEVILLE-IGNACIO#1 IG002/013 REPAINT | 43761676 | LAKEVILLE-IGNACIO #1 | IG002/013 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-18 | 2020-04-18 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.521914 | 38.101 | ETL.4940 | 40663153 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117054477 | Q2 | DI CNTRVL-TBLMTN-ORVL 010/200 RPR CRSW | 43903760 | CENTERVILLE-TABLE MTN-OROVILLE | 010/200 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-17 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.633663 | 39.6467 | ETL.6330 | 40767069 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117055166 | Not Scheduled | T2 DI JEFFERSON-STANFORD 2/53 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/053 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-17 | 2020-04-17 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.254149 | 37.4651 | ETL.7220 | 40875257 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117055786 | Not Scheduled | T2 DI SPAULDING-SUMMIT 013/435 RPR GYWW | 43876247 | SPAULDING-SUMMIT | 013/435 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.426063 | 39.327 | ETL.8060 | 40771515 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117055936 | Not Scheduled | T3 EI CLGTE ALLGHNY 21/591 RMV VEG | 43881184 | COLGATE-ALLEGHANY | 021/591 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-01-04 | 2019-07-04 | [6 empty] | Likely veg | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876021 | 39.4713 | ETL.6470 | 40760454 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117060352 | Q2 | EI CRESTA-RIO OSO 42/279 REPL INSS | 31435732 | CRESTA-RIO OSO | 042/279 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-07 | 2020-02-07 |  |  | 2021-04-02 | 2021-03-29 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.5087 | 39.3776 | ETL.4590 | 40889564 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117062729 | Q2 | DI STANISLS-NEWARK #1 092/611 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 092/611 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2020-04-12 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.872223 | 37.5855 | ETL.3850 | 40602897 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | SFPUC | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117063042 | Feb | T2 EI DRUM-RIO OSO #2 20/158 RPL INSS | 31453342 | DRUM-RIO OSO #2 | 020/158 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-06 | 2021-05-31 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.083934 | 39.1107 | ETL.1430 | 40890248 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | CalTrans | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-05-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117063389 | Mar | T3 EI EGL-RCK CORTINA 20/095 RPL INSS | 31437310 | EAGLE ROCK-CORTINA | 020/095 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2019-07-28 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40795319 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117063475 | Mar | T3 EI EAGLE ROCK-CORTINA 14/68 RPL INSS | 31437310 | EAGLE ROCK-CORTINA | 014/068 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-28 | 2019-07-28 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62768 | 38.9028 | ETL.1470 | 40884478 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117063963 | Mar | T3 DI EAGLE ROCK-CORTINA :6/039 RPR SPLS | 43762411 | EAGLE ROCK-CORTINA | :006/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2019-10-10 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-120.268619 | 34.7995 | ETL.1470 | 40878317 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-05-20 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117064150 | Not Scheduled | T2 DI DRUM-SUMMIT #1 21/250 RPL POLE | 31453474 | DRUM-SUMMIT #1 | 021/250 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.428095 | 39.3169 | ETL.1440 | 40663004 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117066097 | Not Scheduled | T2 DI STS-MNS SS-RB JT SS 11/65 PNT STRS | 43841480 | STAN MEL SW STA-RVERBNK JCT SW STA | 011/065 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537881 | 38.0574 | ETL.3840 | 41196636 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117066287 | Feb | T2 EI VACA-SUISUN JAM 3/031 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 003/031 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-18 | 2020-01-18 |  |  | 2021-02-13 | 2021-02-11 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.990026 | 38.4012 | ETL.4080 | 40614338 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117066420 | Feb | T2 EI VACA-SUISUN JAM 04/032 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 004/032 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-18 | 2020-01-18 |  |  | 2021-02-13 | 2021-02-11 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.99012 | 38.3991 | ETL.4080 | 40717502 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117066658 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/484 RPLC STRW | 31518243 | SPAULDING-SUMMIT | 015/484 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.388553 | 39.3287 | ETL.8060 | 40828181 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117069255 | Q2 | T2 EI BALCH-SANGER 009/054 RPR FOND | 43867621 | BALCH-SANGER | 009/054 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-04-20 | 2020-04-20 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.216836 | 36.8724 | ETL.1050 | 40760187 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117075091 | Q2 | DI LAKEVLLE-IGNCIO #1 IG01/005 INST MRKS | 43761676 | LAKEVILLE-IGNACIO #1 | IG001/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-12 | 2020-04-12 |  |  | 2021-05-27 | 2021-05-26 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.511705 | 38.1196 | ETL.4940 | 40760307 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117075167 | Mar | T2 POE-RIO OSO 029/192 RPL INSS | 31434829 | POE-RIO OSO | 029/192 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-19 | 2020-04-19 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.531131 | 39.5723 | ETL.5540 | 40719817 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117075240 | Mar | T2 POE-RIO OSO 029/197 RPL INSS | 31434829 | POE-RIO OSO | 029/197 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-22 | 2020-04-22 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.534783 | 39.5606 | ETL.5540 | 40840546 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117077277 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/482 RPL INSW | 31463883 | SPAULDING-SUMMIT | 015/482 | 93I | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.390021 | 39.329 | ETL.8060 | 40771519 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117077333 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/482 REPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/482 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.390021 | 39.329 | ETL.8060 | 40771519 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117077534 | Mar | T2 POE-RIO OSO 28/186 REPL INSS | 31434829 | POE-RIO OSO | 028/186 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-22 | 2020-04-22 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.526797 | 39.5865 | ETL.5540 | 40843568 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117078005 | Mar | T2 DI VOLTA-SOUTH 002/069 RPR STRW | 44309960 | VOLTA-SOUTH | 002/069 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871647 | 40.4198 | ETL.8300 | 40601122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117079525 | Feb | T2 DI COLGATE-PALERMO 11/217 REPL POLE | 31417717 | COLGATE-PALERMO | 011/217 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2016-04-11 | 2020-04-11 |  |  | 2021-02-10 | 2021-01-28 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.372696 | 39.3733 | ETL.6500 | 40873585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117079659 | Not Scheduled | T2 DI SPAULDING-SUMMIT 011/396 RPLC STRW | 31453471 | SPAULDING-SUMMIT | 011/396 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.448904 | 39.3176 | ETL.8060 | 40862168 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117079841 | Q2 | T2 DI COLGATE-PALERMO 22/442 RPR GYWW | 43728969 | COLGATE-PALERMO | 022/442 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-22 | 2020-04-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51824 | 39.458 | ETL.6500 | 43690666 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117081788 | Mar | T2 DI KONOCTI-MDLTWN 13/6 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 013/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2020-04-12 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.587482 | 38.7682 | ETL.6380 | 40810812 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117082467 | Mar | DI CLEAR LAKE-HOPLAND 001/009 RPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 001/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2021-05-31 | 2021-03-30 | 2021-04-02 | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.053571 | 38.9666 | ETL.6390 | 40875508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117086668 | Mar | T2 POE-RIO OSO 26/172 RPL INSS | 31434829 | POE-RIO OSO | 026/172 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-23 | 2020-04-23 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.518546 | 39.6154 | ETL.5540 | 40723994 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117086981 | Mar | T2 DI TABLE MTN-PLRMO 13/59 MRKS INST | 43760152 | TABLE MTN-PALERMO | 013/059 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-16 | 2020-04-16 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502682 | 39.4763 | ETL.5690 | 40865401 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117087209 | Mar | T2 DI KONOCTI-MIDDLETOWN 16/14 RPR INSW | 43761672 | KONOCTI-MIDDLETOWN | 016/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2021-05-31 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.573231 | 38.8085 | ETL.6380 | 40781665 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088303 | Mar | T2 DI VOLTA-SOUTH 001/033 RPR GYWW | 43827513 | VOLTA-SOUTH | 001/033 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-23 | 2020-04-23 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872792 | 40.4408 | ETL.8300 | 40875798 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088318 | Not Scheduled | T3 DI GRIZZLY TAP 001/008C RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.292472 | 39.8972 | ETL.2395 | 44550738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088319 | Not Scheduled | T3 DI GRIZZLY TAP 001/008R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.292472 | 39.8972 | ETL.2395 | 44550788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088590 | Not Scheduled | T3 DI GRIZZLY TAP 001/008L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.292472 | 39.8972 | ETL.2395 | 44550789 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088592 | Not Scheduled | T3 DI GRIZZLY TAP 001/007 REPR GYWW | 31475737 | TAP (CITY OF SANTA CLARA) | 001/007 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.292148 | 39.898 | ETL.2395 | 44550724 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088594 | Not Scheduled | T3 DI GRIZZLY TAP 001/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.292148 | 39.898 | ETL.2395 | 44550786 | Guy Stub-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088595 | Not Scheduled | T3 DI GRIZZLY TAP 001/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.292148 | 39.898 | ETL.2395 | 44550787 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088781 | Not Scheduled | T3 DI GRIZZLY TAP 001/011 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550727 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088784 | Not Scheduled | T3 DI GRIZZLY TAP 001/011 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550762 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117088785 | Not Scheduled | T3 DI GRIZZLY TAP 001/011 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550806 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117089684 | Not Scheduled | T3 DI GRIZZLY TAP 001/009 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117089685 | Not Scheduled | T3 DI GRIZZLY TAP 001/009 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550726 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117089686 | Not Scheduled | T3 DI GRIZZLY TAP 001/009 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550748 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117089916 | Not Scheduled | T3 DI GRIZZLY TAP 3/007 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321358 | 39.9031 | ETL.2395 | 44551437 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090100 | Not Scheduled | T3 DI GRIZZLY TAP 001/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550759 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090101 | Not Scheduled | T3 DI GRIZZLY TAP 001/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550776 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090103 | Not Scheduled | T3 DI GRIZZLY TAP 001/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550821 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090105 | Not Scheduled | T3 DI GRIZZLY TAP 001/006 RPR SPLW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550759 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090106 | Not Scheduled | T3 DI GRIZZLY TAP 001/005 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.289561 | 39.8998 | ETL.2395 | 44550757 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090108 | Not Scheduled | T3 DI GRIZZLY TAP 001/005 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.289561 | 39.8998 | ETL.2395 | 44550758 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117090320 | Not Scheduled | T3 DI GRIZZLY TAP 001/005 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.289561 | 39.8998 | ETL.2395 | 44550805 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117092105 | Not Scheduled | T2 DI JEFFERSON-STANFORD 0/11 RPR INSW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.276791 | 37.4619 | ETL.7220 | 40625778 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117092109 | Not Scheduled | T2NT DI VC-LKVLL #1 020/095 INS MRKS | 43740456 | VACA-LAKEVILLE #1 | 020/095 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.215082 | 38.2546 | ETL.5840 | 40762416 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117092713 | Not Scheduled | T2NT DI DRUM-SUMMIT#2 025/307 INS MRKW | 43889098 | DRUM-SUMMIT #2 | 025/307 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.36187 | 39.3099 | ETL.1450 | 40869623 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117093180 | Not Scheduled | T2NT DI DRUM SUMMIT#2 025/301L INS MRKS | 43888819 | DRUM-SUMMIT #2 | 025/301 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37153 | 39.3113 | ETL.1450 | 44553704 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117093189 | Not Scheduled | T2NT DI DRUM-SUMMIT#2 025/301R INS MRKS | 43888819 | DRUM-SUMMIT #2 | 025/301 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37153 | 39.3113 | ETL.1450 | 44553703 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117094215 | Not Scheduled | T2 DI VACA-LAKEVIL #1 021/098 INSTL MRKS | 43740456 | VACA-LAKEVILLE #1 | 021/098 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.228798 | 38.2523 | ETL.5840 | 40867192 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117094240 | Not Scheduled | T2 DI SPAULDING-SUMMIT 13/450 RPLC STRW | 31522645 | SPAULDING-SUMMIT | 013/450 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.414309 | 39.3282 | ETL.8060 | 40826204 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117095556 | Not Scheduled | T3 DI GRIZZLY TAP 001/014 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.299459 | 39.8956 | ETL.2395 | 44550827 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117095594 | Not Scheduled | T2 DI JEFFERSON-STANFORD 0/6 RPL STRW | 31434138 | JEFFERSON-STANFORD (NO FLY) | 000/006 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-17 | 2020-04-17 | 2020-08-26 | [6 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.279413 | 37.4604 | ETL.7220 | 40824854 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6 | EPNP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117096867 | Not Scheduled | T2 DI SPAULDING-SUMMIT 010/360 RPR GYWW | 43876247 | SPAULDING-SUMMIT | 010/360 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.466578 | 39.319 | ETL.8060 | 40650055 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117097094 | Feb | T2 EI BRENTWOOD-KELSO 007/037 RPL INSS | 31452001 | BRENTWOOD-KELSO | 007/037 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-26 | 2020-03-26 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.693537 | 37.8617 | ETL.4410 | 44815096 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117097231 | Not Scheduled | T2 PORT COSTA BRICK TAP 000/006B access |  | PORT COSTA BRICK TAP | 000/006B | CHS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2019-04-25 | 2021-04-25 | [7 empty] | TR2 | <90D | Central | Non-WSIP | [6 empty] | '-122.171306 | 38.0279 | ETL.6371 | 40742009 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117098808 | Not Scheduled | T2 DI DRUM-RIO OSO 020/161 REPAINT | 44304427 | DRUM-RIO OSO #1 | 020/161 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.093121 | 39.1071 | ETL.1420 | 40594933 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117099258 | Feb | T2 EI CHC-SL-SD #2 :21/110 RPR INSS | 43766021 | MOSS LANDING-SALINAS-SOLEDAD #2 | :021/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-01 | 2020-02-01 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-18 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.351488 | 36.5058 | ETL.2910 | 40624139 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 | 2019-07-15 | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117099911 | Q2 | T2 PARADISE-TABLE MTN 23/181 REPL ANCS | 31456796 | PARADISE-TABLE MTN | 023/181 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.626914 | 39.6982 | ETL.4316 | 40758646 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101218 | Not Scheduled | T2 DI JEFFERSON-STANFORD 0/9 GYWW RPR | 43877613 | JEFFERSON-STANFORD (NO FLY) | 000/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-17 | 2020-04-17 | 2020-08-26 | [6 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.277851 | 37.4615 | ETL.7220 | 40874138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101239 | Mar | T2 DI VOLTA-SOUTH 001/047 RPL STRW | 31470529 | VOLTA-SOUTH | 001/047 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-22 | 2020-04-22 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871742 | 40.432 | ETL.8300 | 40677148 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101306 | Not Scheduled | T2 EI BK CRK-RK CRK-CRT 00/04A RPNT STRT | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/004A | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-25 | 2024-04-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.351399 | 39.9066 | ETL.4430 | 40655542 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101423 | Not Scheduled | T3 EI GRIZZLY TAP 003/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321281 | 39.9023 | ETL.2395 | 44551400 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101428 | Not Scheduled | T3 EI GRIZZLY TAP 003/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321281 | 39.9023 | ETL.2395 | 44551467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101430 | Not Scheduled | T3 DI GRIZZLY TAP 001/015 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.300829 | 39.8957 | ETL.2395 | 44550812 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101431 | Not Scheduled | T3 DI GRIZZLY TAP 001/015 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.300829 | 39.8957 | ETL.2395 | 44550828 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101543 | Not Scheduled | T3 EI GRIZZLY TAP 003/008 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321709 | 39.9042 | ETL.2395 | 44551357 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101594 | Not Scheduled | T3 EI GRIZZLY TAP 003/008 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321709 | 39.9042 | ETL.2395 | 44551451 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117101782 | Not Scheduled | T2 EI SLT SPNGS-TIGER CREK 11/91 REPAINT | 43842278 | SALT SPRINGS-TIGER CREEK | 011/091 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-04-25 | 2021-04-25 | [7 empty] | TR2 | <90D | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-120.413491 | 38.4788 | ETL.3500 | 40579800 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117103496 | Not Scheduled | T3 EI GRIZZLY TAP 3/007 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-18 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.321358 | 39.9031 | ETL.2395 | 44551416 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117103719 | Mar | T3 DI FULTON-HOPLAND 26/03 RPL STRW | 31453752 | FULTON-HOPLAND | 026/003 | 70Y | E | 2020_(1a) PSPS |  | 2019-04-23 | 2019-10-23 | 2020-11-19 | 2020-11-20 | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.98844 | 38.8019 | ETL.6890 | 40664532 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-15 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-05-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117104788 | Q2 | T2 PARADISE-TABLE MTN 20/165 RPR GYWS | 43727174 | PARADISE-TABLE MTN | 020/165 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2020-04-26 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.577357 | 39.6897 | ETL.4316 | 44383208 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117104885 | Q2 | T2 PARADISE-TABLE MTN 20/164 RPR POLE | 43724325 | PARADISE-TABLE MTN | 020/164 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2020-04-26 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.575878 | 39.6894 | ETL.4316 | 40758508 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117105377 | Not Scheduled | T2 DI DRUM-SUMMIT #1 23/273 INSTL MRKW | 43910114 | DRUM-SUMMIT #1 | 023/273 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395358 | 39.311 | ETL.1440 | 44768882 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117105672 | Q2 | T2 EI PRDS-TBL MT 20/159C RPL POLE | 31453760 | PARADISE-TABLE MTN | 020/159 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2020-04-26 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561014 | 39.6874 | ETL.4316 | 44383201 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106280 | Not Scheduled | T3 DI GRIZZLY TAP 003/010R CMPLETED | 43760153 | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2019-10-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106281 | Not Scheduled | T3 DI GRIZZLY TAP 003/010C CMPLETED | 43760153 | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2019-10-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106282 | Not Scheduled | T3NT DI GRIZZLY TAP 003/010L INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-19 | 2023-04-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551372 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106284 | Not Scheduled | T3NT DI GRIZZLY TAP 003/010R INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-19 | 2023-04-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551469 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106285 | Not Scheduled | T3NT DI GRIZZLY TAP 003/010C INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-19 | 2023-04-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551470 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106330 | Mar | T2 DI VOLTA- SOUTH 001/042 RPR STRW | 43827513 | VOLTA-SOUTH | 001/042 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872548 | 40.4348 | ETL.8300 | 40877069 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106336 | Mar | T2 DI VOLTA-SOUTH 001/043 RPR INSW | 43827513 | VOLTA-SOUTH | 001/043 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872337 | 40.4341 | ETL.8300 | 40868019 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106348 | Q2 | T2 DI COLEMAN-CTTNWD 003/069 RPR STRW | 44309976 | COLEMAN-COTTONWOOD | 003/069 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-25 | 2020-04-25 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.185657 | 40.4169 | ETL.6430 | 40615792 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106497 | Not Scheduled | DI GRIZZLY TAP 000/001C RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44549998 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106512 | Mar | T2 DI VOLTA-SOUTH 002/051 RPR STRW | 44309960 | VOLTA-SOUTH | 002/051 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871603 | 40.4301 | ETL.8300 | 40650375 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106515 | Mar | T2 DI VOLTA-SOUTH 002/052 RPR SPLW | 44309960 | VOLTA-SOUTH | 002/052 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871613 | 40.4296 | ETL.8300 | 40752210 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117106539 | Not Scheduled | DI GRIZZLY TAP 000/001A RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44549954 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117107573 | Not Scheduled | DI JFFRSN-HLLSDLE #1 000/002B RPR GYWW | 43877610 | JEFFERSON-HILLSDALE JCT | 000/002B | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-25 | 2020-04-25 | 2020-07-13 | 2020-07-17 | [6 empty] | LATE | Central | WSIP | [6 empty] | '-122.286953 | 37.4587 | ETL.7190 | 40740530 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117107684 | Not Scheduled | T3 DI GRIZZLY TAP 000/001B RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44550027 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117107994 | Not Scheduled | T3 DI GRIZZLY TAP 3/13 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551402 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117108554 | Q2 | T2 DI COLEMAN-CTTWD 3/71 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/071 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-25 | 2020-04-25 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.18741 | 40.4172 | ETL.6430 | 40669940 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117108863 | Q2 | T2 PARADISE-TABLE MTN 14/118 RPL INSS | 31456702 | PARADISE-TABLE MTN | 014/118 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.506631 | 39.6548 | ETL.4316 | 41176898 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117109624 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/502 RPL STRW | 31453471 | SPAULDING-SUMMIT | 015/502 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379169 | 39.3222 | ETL.8060 | 40771531 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117110031 | Feb | T2 DI COLGATE-PALERMO 11/221 RPL STRW | 31517754 | COLGATE-PALERMO | 011/221 | 70Y | E | 2020_(1a) PSPS |  | 2019-04-22 | 2020-04-22 |  |  | 2021-02-10 | 2021-01-28 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.37601 | 39.3755 | ETL.6500 | 40664501 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117110034 | Feb | T2 DI COLGATE-PALERMO 11/222 RPL STRW | 31423185 | COLGATE-PALERMO | 011/222 | 70Y | E | 2020_(1a) PSPS |  | 2019-04-24 | 2020-04-24 |  |  | 2021-02-10 | 2021-01-28 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.376563 | 39.3761 | ETL.6500 | 40757197 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-06-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117110774 | Q2 | T2 EI PHILO JCT-ELK 07/003 RPR GYWW | 43762377 | PHILO JCT-ELK | 007/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-27 | 2021-05-31 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.251039 | 39.0476 | ETL.7780 | 40666580 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117111552 | Q2 | T2 DI KONOCTI-MIDDLETWN ;23/8 INST HRDW | 43761672 | KONOCTI-MIDDLETOWN | ;023/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-24 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610737 | 38.8993 | ETL.6380 | 40876736 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117112359 | Q2 | T2 DI BTTE VLLY-CRIBOU 007/054D RPR GYWW | 43930734 | BUTT VALLEY-CARIBOU | 007/054D | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-18 | 2020-04-18 |  |  | 2021-06-11 | 2021-06-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.147461 | 40.0865 | ETL.1180 | 44399900 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117113374 | Mar | T2 DI PARADISE-BUTTE 5/060 RPL INSS | 31454860 | PARADISE-BUTTE | 005/060 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2020-04-15 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.672185 | 39.7072 | ETL.4396 | 41127255 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117113825 | Mar | T2 DI VOLTA-SOUTH 002/049 RPR GYWW | 44309960 | VOLTA-SOUTH | 002/049 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-22 | 2020-04-22 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871633 | 40.4312 | ETL.8300 | 40592380 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117114514 | Not Scheduled | T3 DI GRIZZLY TAP 000/002 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-17 | 2019-10-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279382 | 39.8901 | ETL.2395 | 44403544 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117114581 | Not Scheduled | T2 DI STLS-MLS SS-MTCA 22/140 PAINT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 022/140 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-04-09 | 2022-04-09 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.695711 | 37.9474 | ETL.3830 | 40856463 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117114584 | Not Scheduled | T2 DI STLS-MLS SS-MTCA 22/139 PAINT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 022/139 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-04-09 | 2020-04-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.693845 | 37.9488 | ETL.3830 | 40865916 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117115077 | Q2 | DI HARTLEY-CLEARLAKE 027/003 REMV DEBRIS | 43760950 | HARTLEY-CLEARLAKE | 027/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-10 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.925384 | 39.0217 | ETL.7515 | 40667031 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117115191 | Not Scheduled | T2 EI PALERMO-COLGATE C004/020 RPR CONS | 43900094 | PALERMO-COLGATE | C004/020 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-28 | 2020-04-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.27042 | 39.3082 | ETL.5360 | 40582434 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117116835 | Not Scheduled | DI GRIZZLY TAP 000/005 A RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.278587 | 39.893 | ETL.2395 | 44549955 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117116836 | Not Scheduled | DI GRIZZLY TAP 000/005C RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.278587 | 39.893 | ETL.2395 | 44550028 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117116838 | Not Scheduled | DI GRIZZLY TAP 000/005B RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.278587 | 39.893 | ETL.2395 | 44549899 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117117756 | Not Scheduled | DI PALERMO-WYANDOTTE 001/012 REP GYWW | 43952543 | PALERMO-WYANDOTTE | 001/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-19 | 2020-04-19 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.540179 | 39.4673 | ETL.4315 | 41162776 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117117961 | Not Scheduled | T2 DI KILARC-DSCHTS 2/42 RMV VEG | 43930137 | KILARC-DESCHUTES | 002/042 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-04-24 | 2025-04-24 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.88718 | 40.6516 | ETL.7300 | 40600363 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117119180 | Q2 | PARADISE-TABLE MTN 022/173 RPR ANCS | 31456797 | PARADISE-TABLE MTN | 022/173 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 |  |  | 2021-04-30 | 2021-03-30 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.606588 | 39.6948 | ETL.4316 | 44712231 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117119189 | Q2 | PARADISE-TABLE MTN 22/171 INST DAMPS | 43875188 | PARADISE-TABLE MTN | 022/171 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-26 | 2020-04-26 |  |  | 2021-04-30 | 2021-03-30 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.597896 | 39.6933 | ETL.4316 | 44712215 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117119285 | Mar | T2 DI VOLTA-SOUTH 002/067 RPR SPLW | 44309960 | VOLTA-SOUTH | 002/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2020-04-26 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871649 | 40.4209 | ETL.8300 | 40868021 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117120652 | Not Scheduled | T2 DI PALERMO-OROVILLE 001/029 REP CRSW | 31474478 | PALERMO-OROVILLE #1 | 001/029 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-23 | 2020-07-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.538288 | 39.4599 | ETL.7730 | 40809918 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2019-07-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117121349 | Not Scheduled | T2 DI SPAULDING-SUMMIT 003/124 REPL POLE | 31453471 | SPAULDING-SUMMIT | 003/124 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.58876 | 39.3137 | ETL.8060 | 40771415 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117121362 | Mar | T2 DI VOLTA-SOUTH 001/032 RPR GYWW | 43827513 | VOLTA-SOUTH | 001/032 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-20 | 2021-05-31 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.872563 | 40.4414 | ETL.8300 | 40877110 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117121947 | Mar | T3 POE-RIO OSO 019/130 RPL INSS | 31434829 | POE-RIO OSO | 019/130 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-24 | 2019-10-24 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.481858 | 39.7147 | ETL.5540 | 40633646 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117122025 | Mar | T3 POE-RIO OSO 19/133 RPL INSS | 31434829 | POE-RIO OSO | 019/133 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-25 | 2019-10-25 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.483534 | 39.705 | ETL.5540 | 40684587 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117122665 | Not Scheduled | T2 DI SPAULDING-SUMMIT 004/150 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/150 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.576016 | 39.3072 | ETL.8060 | 40681444 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123534 | Not Scheduled | T2 DI SPAULDING-SUMMIT 004/142 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/142 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.579866 | 39.3083 | ETL.8060 | 40771499 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123537 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/495 RPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/495 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379842 | 39.3259 | ETL.8060 | 40826216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123777 | Mar | T2 DI VOLTA-SOUTH 003/089 RPR STRW | 44309963 | VOLTA-SOUTH | 003/089 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876855 | 40.4088 | ETL.8300 | 40826966 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123801 | Not Scheduled | T3NT DI DRUM-RIO OSO #2 001/018 REPAINT |  | DRUM-RIO OSO #2 | 001/018 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-29 | 2020-04-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.800608 | 39.2549 | ETL.1430 | 40858251 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-23 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123830 | Not Scheduled | T2 DI SPAULDING-SUMMIT 004/143 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/143 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.579404 | 39.3081 | ETL.8060 | 40751907 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123838 | Not Scheduled | T2 DI SPAULDING-SUMMIT 004/147 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/147 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-15 | 2020-04-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.577561 | 39.3075 | ETL.8060 | 40876679 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117123940 | Q2 | T2 DI BTTE VLLEY-CRBU 007/054D RPL ANCW | 31471617 | BUTT VALLEY-CARIBOU | 007/054D | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-27 | 2020-04-27 |  |  | 2021-06-11 | 2021-06-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.147461 | 40.0865 | ETL.1180 | 44399900 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117124612 | Mar | T2 DI VOLTA-SOUTH 003/076 RPR STRW | 44309963 | VOLTA-SOUTH | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87376 | 40.4169 | ETL.8300 | 40657235 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117124811 | Not Scheduled | T2 DI CHOWCHILLA-KERCKHF 1/008 RPR STRS | 43795033 | CHOWCHILLA-KERCKHOFF | 001/008 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.582894 | 37.0906 | ETL.1250 | 44191727 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117125357 | Not Scheduled | T3 DI GRIZZLY TAP 003/001 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2019-10-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.320267 | 39.8983 | ETL.2395 | 44551370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117125983 | Q2 | T2 DI COLEMAN-COTTONWOOD 03/72 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/072 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-25 | 2020-04-25 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.188207 | 40.4172 | ETL.6430 | 40667368 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117125984 | Q2 | T2 DI CLMN-CTTNWD 003/072 RPR SPLW | 44309976 | COLEMAN-COTTONWOOD | 003/072 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-25 | 2020-04-25 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.188207 | 40.4172 | ETL.6430 | 40667368 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117126534 | Mar | T2 DI TABLE MTN-PLRMO 7/32 INSTL MRKS | 43760152 | TABLE MTN-PALERMO | 007/032 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-16 | 2020-04-16 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.516766 | 39.5453 | ETL.5690 | 40670002 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117127050 | Not Scheduled | T2 DI SPAULDING-SMMT 4/156 RPL STRW | 31519330 | SPAULDING-SUMMIT | 004/156 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.573525 | 39.3067 | ETL.8060 | 40862154 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117128876 | Not Scheduled | DI SPAULDING-SUMMIT 008/268 INST MRKW | 43876243 | SPAULDING-SUMMIT | 008/268 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-30 | 2020-04-30 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.519991 | 39.3102 | ETL.8060 | 40590021 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117129203 | Not Scheduled | T2 DI SLT SPRNG-TGRCRK 006/052 RPR FOND | 43842265 | SALT SPRINGS-TIGER CREEK | 006/052 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-04-25 | 2024-04-25 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.320465 | 38.4774 | ETL.3500 | 40643393 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117129585 | Mar | T2 DI KESWICK-CASCADE 03/065 REMOVE STRW | 43859605 | KESWICK-CASCADE | 003/065 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.365805 | 40.6672 | ETL.7260 | 40577346 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117129689 | Feb | T3 DI KILARC-CDR CREEK 06/151 RPL STRW | 31452939 | KILARC-CEDAR CREEK | 006/151 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-27 | 2019-10-27 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.989997 | 40.7138 | ETL.7290 | 40657252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117129863 | Mar | T2 DI VOLTA-SOUTH 03/073 RPL CRSW | 31453744 | VOLTA-SOUTH | 003/073 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871663 | 40.4175 | ETL.8300 | 40600820 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-06-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117134374 | Not Scheduled | T2 FORT BRAGG-ELK 04/01 REP ACC ROAD | 43837882 | FORT BRAGG-ELK | 004/001 | CHS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-03 | 2021-05-01 |  |  |  | 2021-04-15 |  |  |  | TR2 |  | North Coast | Non-WSIP | [6 empty] | '-123.747387 | 39.1781 | ETL.2060 | 40584446 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117135999 | Mar | T2 DI VOLTA-SOUTH 003/080 RPR SPLW | 44309963 | VOLTA-SOUTH | 003/080 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876908 | 40.4165 | ETL.8300 | 40825105 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117136141 | Mar | T2 DI VOLTA-SOUTH 003/090 RPR STRW | 44309963 | VOLTA-SOUTH | 003/090 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876868 | 40.4076 | ETL.8300 | 40809981 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117136308 | Mar | T2 DI VOLTA-SOUTH 003/083 RPR SPLW | 44309963 | VOLTA-SOUTH | 003/083 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876902 | 40.414 | ETL.8300 | 40615850 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117136368 | Mar | T2 DI VOLTA-SOUTH 003/093 RPL INSW | 31483881 | VOLTA-SOUTH | 003/093 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2020-04-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876857 | 40.4043 | ETL.8300 | 40615853 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-06-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117136453 | Not Scheduled | EI DRUM-SUMMIT #2 16/189B INST MRKW | 43900106 | DRUM-SUMMIT #2 | 016/189B | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-30 | 2020-04-30 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.520693 | 39.3099 | ETL.1450 | 42572817 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117137049 | Not Scheduled | T3NT DI MORAGA-OAKLAND #3 00/06 PNT STRT | 43725286 | MORAGA-OAKLAND #3 | 000/006 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-05-01 | 2020-05-01 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.17228 | 37.8458 | ETL.2740 | 40804648 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117138079 | Feb | T2 DI SMARTVILLE-NICOLAS #2 0/6 RPR STRW | 43852590 | SMARTVILLE-NICOLAUS #2 | 000/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-01 | 2020-05-01 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.302217 | 39.2055 | ETL.8000 | 44177581 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117142697 | Not Scheduled | T3NT DI DRUM-RIO OSO #1 002/027 CANCEL | 44304427 | DRUM-RIO OSO #1 | 002/027 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-29 | 2020-04-29 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.811856 | 39.2479 | ETL.1420 | 40821341 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146256 | Not Scheduled | T3 DI GRIZZLY TAP 000/11R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279468 | 39.8976 | ETL.2395 | 44549929 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146382 | Not Scheduled | T3 EI GRIZZLY TAP 3/13L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-30 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551440 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146633 | Q4 | T3 EI KESWICK-TRINITY 004/066 RPR STRW | 43661466 | KESWICK-TRINITY | 004/066 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-26 | 2019-10-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.531553 | 40.6241 | ETL.7270 | 40701679 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146778 | Not Scheduled | T3 DI GRIZZLY TAP 3/13L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-30 | 2019-10-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551418 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146801 | Not Scheduled | T3 DI GRIZZLY TAP 000/003 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.284071 | 39.8978 | ETL.2395 | 44549884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146941 | Not Scheduled | T3 DI GRIZZLY TAP 3/13L RPR STRW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-30 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551418 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117146978 | Not Scheduled | T3 DI GRIZZLY TAP 001/001 REP GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.286359 | 39.8997 | ETL.2395 | 44549982 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117147211 | Not Scheduled | T3 DI GRIZZLY TAP 001/001 REP GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.286359 | 39.8997 | ETL.2395 | 44550004 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117147212 | Not Scheduled | T3 DI GRIZZLY TAP 001/001 REP GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.286359 | 39.8997 | ETL.2395 | 44550038 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117147414 | Not Scheduled | T3 DI GRIZZLY TAP 001/002R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.287584 | 39.8998 | ETL.2395 | 44549860 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117147419 | Not Scheduled | T3 DI GRIZZLY TAP 001/002L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-16 | 2019-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.287584 | 39.8998 | ETL.2395 | 44549933 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117147644 | Feb | T3 DI KILARC-CEDAR CRK 008/184 REPL STRW | 31452939 | KILARC-CEDAR CREEK | 008/184 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.990518 | 40.7291 | ETL.7290 | 40759577 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117148302 | Feb | T3 EI BRUNSWICK #1 000/003 RPL INSS | 31451763 | BRUNSWICK #1 TAP | 000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-19 | 2019-07-19 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008684 | 39.1445 | ETL.1422 | 40678231 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117148781 | Not Scheduled | T3 DI GRIZZLY TAP 000/012 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-29 | 2019-10-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.281573 | 39.8977 | ETL.2395 | 44550036 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117149046 | Mar | T2 DI VOLTA-SOUTH 004/097 REPAIR STRW | 44309963 | VOLTA-SOUTH | 004/097 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-01 | 2020-05-01 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.877577 | 40.4008 | ETL.8300 | 40615856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117149114 | Mar | T2 DI VOLTA-SOUTH 002/053 RPR STRW | 44309960 | VOLTA-SOUTH | 002/053 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-22 | 2020-04-22 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871648 | 40.429 | ETL.8300 | 40759365 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117149509 | Not Scheduled | T3 DI CRESTA-RIO OSO 13/111 INST HRDT | 43844884 | CRESTA-RIO OSO | 013/111 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-01 | 2019-11-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.45864 | 39.7688 | ETL.4590 | 40911293 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117151393 | Not Scheduled | T3NT DI EGL-RCK FTN-SVRD 001/008 REPAINT | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 001/008 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802834 | 38.8216 | ETL.4392 | 40871409 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-05-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117152650 | Not Scheduled | T2 DI VC-VCVLL-JMSN-N TWR 11/80 PNT STRS | 44305728 | VACA-VACAVILLE-JAMESON-NTH TWR | 011/080 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-29 | 2020-04-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.055628 | 38.3022 | ETL.4100 | 40589119 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117152862 | Feb | T3 DI DRUM-HIGGINS 011/108 RPL POLE | 31497888 | DRUM-HIGGINS | 011/108 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-25 | 2019-10-25 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.918022 | 39.1758 | ETL.4393 | 44172300 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117154831 | Q4 | T2 DI KESWICK-TRINITY 026/439 RPL INSW | 31471572 | KESWICK-TRINITY | 026/439 | 93I | E | Pre-2020_(2) High fire spread TD |  | 2019-04-30 | 2021-05-31 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - FSR 12/2020 | '-122.862768 | 40.6956 | ETL.7270 | 40915768 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q4 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117155368 | Feb | T2NT DI ORVL-THM-TB MT #1 2/10 INST MRKS | 43932170 | MTN #1(CDWR) | 002/010 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-19 | 2020-04-19 |  |  | 2021-02-20 | 2021-02-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519455 | 39.5466 | ETL.6621 | 42580633 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117155466 | Not Scheduled | T2 DI DELTA -MTN GATE 4/20 PNT STRT | 43866628 | DELTA-MOUNTAIN GATE JCT | 004/080 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-02 | 2024-05-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.374078 | 40.8902 | ETL.6750 | 40618038 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117156311 | Q4 | T3 DI KESWICK-TRINITY 005/072 RPR STRW | 43661466 | KESWICK-TRINITY | 005/072 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-27 | 2019-10-27 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117156660 | Not Scheduled | T2 DI BUCKS CRK-RCK-CRST :1/8 REPAINT | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :001/008 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-02 | 2023-05-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.359405 | 39.9025 | ETL.4430 | 40863666 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117156757 | Feb | T3 DI KILRC-CEDAR CREEK 013/282 RPL STRW | 31452939 | KILARC-CEDAR CREEK | 013/282 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939555 | 40.7901 | ETL.7290 | 40657260 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117156765 | Mar | T2 HUMBOLDT-TRINITY-115 kV 49/1 pol butt | 43729541 | HUMBOLDT-TRINITY | 049/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-03 | 2022-05-03 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1820 | 44324189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117156813 | Q2 | T2 DI TRINITY-MAPLE CRK 53/07 RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 053/007 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-30 | 2021-05-31 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.869921 | 40.7685 | ETL.8170 | 40808971 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-07-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117158236 | Q2 | T2 DI VLTA-DESCHUTES 14/309 RPL CRSW | 31440331 | VOLTA-DESCHUTES | 014/309 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-03 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.13041 | 40.5274 | ETL.8290 | 40656937 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117158237 | Q2 | T2 DI VLTA-DESCHUTES 14/309 RPR GYWW | 43939089 | VOLTA-DESCHUTES | 014/309 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-03 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.13041 | 40.5274 | ETL.8290 | 40656937 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117158594 | Mar | DI POE-RIO OSO 39/258 RPL INSS | 31454862 | POE-RIO OSO | 039/258 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-02 | 2020-05-02 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.517957 | 39.4273 | ETL.5540 | 40896918 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117158598 | Mar | T2 DI SBRTE-STDRD OIL SS #2 0/3 CANCEL | 31484431 | SOBRANTE-STANDARD OIL SW STA #1 | 000/003 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-03 | 2020-05-03 |  |  | 2021-03-29 | 2021-03-29 |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-122.209755 | 37.9086 | ETL.3790 | 40671682 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117158708 | Q2 | T2 DI CSCD-BNTN-DSCHTS 3/82 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | 003/082 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-01 | 2020-05-01 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.313488 | 40.6012 | ETL.6310 | 40759450 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117158751 | Feb | T2 DI PORT COSTA BRICK TAP 0/7 REPL STRW | 31438719 | PORT COSTA BRICK TAP | 000/007 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-05-03 | 2021-03-22 |  |  | 2021-02-19 | 2021-02-19 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.171622 | 38.0283 | ETL.6371 | 40857377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-05-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 117161245 | Not Scheduled | T3 DI DIABLO UNIT #1 005/003A INST HRDT | 43908768 | DIABLO UNIT #1 (NF) | 005/003A | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-02 | 2019-11-02 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Per DCPP Unit#1 Outage is October 2020 | '-120.847725 | 35.2145 | ETL.5940 | 40575759 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 543 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117161998 | Feb | T2 DI PLACER GOLD HIL #1 9/65 COTTER KEY |  | PLACER-GOLD HILL #1 | 009/065 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-02 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-19 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.148471 | 38.7611 | ETL.3340 | 40920924 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-06-12 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117162965 | Not Scheduled | T2 DI MDCNO-PHLO JCT-HPLD 07/01 RPR INSS | 43831064 | MENDOCINO #1 | 007/001 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-27 | 2020-04-27 | 2020-09-11 | 2020-09-12 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.161188 | 39.1678 | ETL.7530 | 41118206 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117164963 | Feb | T3 DI KILARC-CEDAR CREEK 7/170 STRW RPL | 31452939 | KILARC-CEDAR CREEK | 007/170 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-29 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.997387 | 40.7208 | ETL.7290 | 40592395 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-02-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117165040 | Feb | T3 DI KILARC-CEDAR CREEK 10/227 SPLW RPR | 43685209 | KILARC-CEDAR CREEK | 010/227 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2019-10-30 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.969525 | 40.7542 | ETL.7290 | 40766568 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117165043 | Mar | T2 DI KILARC-DESCHUTES 10/226 STRW RPR | 43826337 | KILARC-DESCHUTES | 010/226 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-27 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.017692 | 40.5758 | ETL.7300 | 40876516 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117165521 | Feb | T3 DI KILARC-CEDAR CREEK 11/252 RPR GYWW | 43685209 | KILARC-CEDAR CREEK | 011/252 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95676 | 40.7695 | ETL.7290 | 40592403 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117166491 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/137 INS MRKW | 43947948 | SPAULDING-SUMMIT | 003/137 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.582241 | 39.3091 | ETL.8060 | 40878092 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167297 | Q2 | T2 HILLSDLE JCT-HMB ?011/002 RPL INSS | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/002 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-14 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.419086 | 37.4772 | ETL.7060 | 40784163 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167434 | Q2 | T2 HILLSDLE JCT-HMB ?011/004 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/004 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-14 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.420323 | 37.4743 | ETL.7060 | 40838053 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167459 | Q2 | T2 HILLSDLE JCT-HMB ?011/005 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/005 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-14 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.420819 | 37.4734 | ETL.7060 | 40889141 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167527 | Not Scheduled | T2 DI JEFFERSON HILL 0/1 RPR GYWW | 43877610 | JEFFERSON-HILLSDALE JCT | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-25 | 2020-04-25 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.284343 | 37.4566 | ETL.7190 | 40588758 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 2 | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167745 | Q2 | T2 HILLSDLE JCT-HMB ?011/006 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/006 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-14 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.421867 | 37.4728 | ETL.7060 | 40639569 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167782 | Q2 | T2 HILLSDLE JCT-HMB ?011/007 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/007 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 |  |  | 2021-04-15 | 2021-04-14 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.42336 | 37.4721 | ETL.7060 | 40625862 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167997 | Not Scheduled | T2NT DI SMRTVLE-CMP FR WST 0/1 INS MRKW | 43852551 | SMARTVILLE-CAMP FAR WEST | 000/001 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-04 | 2020-05-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.303172 | 39.2088 | ETL.7970 | 42549744 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117167998 | Mar | T2 DI KILARC-DESCHUTES A023/494 RPR GYWW | 43682103 | KILARC-DESCHUTES | A023/494 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-29 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117169303 | Not Scheduled | T2 DI FITCH MTN#1 0/3 RPL STRW | 31492619 | FITCH MTN #1 TAP | 000/003 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-03 | 2020-05-03 | 2020-08-17 | 2020-08-23 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.844027 | 38.6064 | ETL.6891 | 40648712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117169515 | Not Scheduled | DI SBRNT-GZZLY-CLRMNT#1 002/026 PNT STRS | 44586187 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/026 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-05-03 | 2023-05-03 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.183441 | 37.876 | ETL.3740 | 40604230 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117170706 | Not Scheduled | T2 DI SISQUC-SNT YNZ SS 018/257 RPR GYWW | 43763696 | SISQUOC-SANTA YNEZ SW STA | 018/257 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-08 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.153972 | 34.6833 | ETL.3700 | 40751454 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-05-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117170818 | Not Scheduled | T2 DI STL-MNS SS-MTC #1 018/112 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 018/112 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-08 | 2020-04-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.638792 | 37.9897 | ETL.3830 | 40669923 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117171739 | Not Scheduled | T2 DI PITTSBURG-TESLA #1 20/091 RPL HRDT | 43753186 | PITTSBURG-TESLA #1 | 020/091 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-09 | 2020-04-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.674361 | 37.8381 | ETL.5510 | 40586628 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117173620 | Feb | T2 DI CLNGA #1-SAN MGUEL 30/00 RPR GYWS | 43763703 | COALINGA #1-SAN MIGUEL | 030/000 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-04 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-15 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.639635 | 35.8584 | ETL.8580 | 40594402 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-06-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117175032 | Q2 | T2 DI COLGATE-PALERMO 19/379 RPR STRW | 43728969 | COLGATE-PALERMO | 019/379 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2020-04-10 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.462708 | 39.4466 | ETL.6500 | 40672092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117175526 | Not Scheduled | T2 DI COTTONWOOD #1 005/037 RPR INSS | 44155926 | COTTONWOOD #1 | 005/037 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-05 | 2020-05-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267769 | 40.3198 | ETL.6620 | 40920723 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117176295 | Not Scheduled | T2 DI TESLA-SALADO-MNTCA 24/140 INS GMKW | 43841277 | TESLA-SALADO-MANTECA | 024/140 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-11 | 2020-04-11 | 2020-08-12 | 2020-08-13 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.210875 | 37.4821 | ETL.4000 | 40903941 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117176857 | Q2 | T2 DI STANLIUS-NEWARK 094/624 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 094/624 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-10 | 2020-04-10 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.896632 | 37.567 | ETL.3850 | 40772241 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117176902 | Q2 | T2 DI KONOCTI-MIDDLETOWN 27/000 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 027/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.666201 | 38.9055 | ETL.6380 | 40587058 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117178730 | Not Scheduled | T2 DI WST PNT-VLLY SPRNGS 5/64 REPR STRW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/064 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-04 | 2020-05-04 | [7 empty] | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8350 | 44405870 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117178736 | Not Scheduled | T2 DI WST PNT-VLLY SPRNGS 5/64 RPR STRW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/064 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-04 | 2020-05-04 | [7 empty] | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8350 | 44405869 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117179350 | Not Scheduled | T2 DI DRUM SUMMIT #2 27/330 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/330 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553539 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117179878 | Not Scheduled | T2 DI DRUM SUMMIT #2 27/328 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/328 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.331645 | 39.3131 | ETL.1450 | 44552402 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117179939 | Q2 | T2 DI HUMBOLDT-MPLE CRK 13/5L RPL STRW | 31485371 | HUMBOLDT-MAPLE CREEK | 013/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2020-04-30 |  |  | 2021-06-19 | 2021-06-14 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.885342 | 40.7679 | ETL.7130 | 44859704 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-02-24 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-02-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117180202 | Not Scheduled | T2 DI DRUM SUMMIT #2 27/328 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/328 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.331645 | 39.3131 | ETL.1450 | 44552449 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117180367 | Mar | T2 DI KILARC-DESCHUTES 10/228 RPR STRW | 43930440 | KILARC-DESCHUTES | 010/228 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-26 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.018676 | 40.5748 | ETL.7300 | 40602020 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117180381 | Not Scheduled | DI NEWARK-LIVCERMORE 014/087 PNT/CT STRS | 43752137 | NEWARK-LIVERMORE | 014/087 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-05-03 | 2020-05-03 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.792401 | 37.6251 | ETL.7660 | 40823795 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117180383 | Q2 | T2 DI VOLTA-DESCHUTES 014/314 REPL STRW | 31453473 | VOLTA-DESCHUTES | 014/314 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-03 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.134202 | 40.5288 | ETL.8290 | 40868541 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-05-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117180805 | Not Scheduled | T2 DI DRUM SUMMIT 27/328 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/328 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.331645 | 39.3131 | ETL.1450 | 44552309 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117181042 | Not Scheduled | T2 DI STANISLAUS-MNTECA#2 18/99 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 018/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-11 | 2020-04-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.639255 | 37.9892 | ETL.3820 | 40808614 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117181062 | Not Scheduled | T2 DI DRUM-SUMMIT #2 27/327R RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/327 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.331828 | 39.3128 | ETL.1450 | 44552406 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117181063 | Not Scheduled | T2 DI DRUM-SUMMIT #2 27/327 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/327 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.331828 | 39.3128 | ETL.1450 | 44552405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117181064 | Not Scheduled | T2 DI DRUM-SUMMIT #2 27/327 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/327 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-12 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.331828 | 39.3128 | ETL.1450 | 44552314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117181166 | Not Scheduled | DI COPPERMINE-TIVY VALLEY 22/9 RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2020-04-12 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307722 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117181167 | Not Scheduled | DI COPPERMINE-TIVY VALLEY 22/9 RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-12 | 2020-04-12 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117181570 | Not Scheduled | T2NT DI MLIN-RND MT #2 080/411 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 080/411 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2022-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.901398 | 40.993 | ETL.6020 | 40593552 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117182826 | Q2 | T2 DI LOWR LAKE-HOMESTAKE 0/1G RPLC STRW | 31460373 | LOWER LAKE-HOMESTAKE TAP | 000/001G | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-05-12 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.617429 | 38.9111 | ETL.1481 | 40743010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-02 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117184370 | Q3 | T2 DI WISHON-COPPERMINE 5/42 RPR FOND | 44571732 | WISHON-COPPERMINE | 005/042 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-06 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.534881 | 37.0701 | ETL.9330 | 40675160 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-08-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117184753 | Not Scheduled | T2 HILLSDALE JCT-HMB 005/052A road acces | 44305491 | HILLSDALE JCT-HALF MOON BAY | 005/052A | CHS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2019-05-08 | 2021-05-08 | [7 empty] | TR2 | <90D | Central | Non-WSIP | [6 empty] | '-122.414828 | 37.483 | ETL.7060 | 40695020 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117186236 | Q2 | T2NT DI MLIN-RND MTN #2 093/473 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 093/473 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2020-05-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.916797 | 40.8251 | ETL.6020 | 40663427 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117186539 | Q2 | T2 DI COLGATE-PALERMO 021/431 RPL STRW | 31423185 | COLGATE-PALERMO | 021/431 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-15 | 2020-04-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50906 | 39.4579 | ETL.6500 | 40757148 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117187575 | Not Scheduled | T2 DI DRUM-SUMMIT#2 27/326B RPR GYWW | 43876488 | DRUM-SUMMIT #2 | 027/326B | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-15 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332239 | 39.3121 | ETL.1450 | 42572856 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117187872 | Not Scheduled | GATES-PANOCHE #2_009/040 RPLC HRDS | 43863017 | GATES-PANOCHE #2 | 009/040 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.2040028 | 36.2405 | ETL.4730 | 44402089 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117187927 | Q2 | T2 DI MENDOCINO-WILLITS 12/1 RMV BUTT | 43877953 | MENDOCINO-WILLITS | 012/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-04-25 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.319308 | 39.3738 | ETL.7540 | 40584899 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-01 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117188094 | Not Scheduled | T2 DI CARBERRY SS-RND MTN 26/215 REPAINT | 43897848 | CARBERRY SW STA-ROUND MTN | 026/215 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-06 | 2020-05-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.927349 | 40.7948 | ETL.5410 | 40755336 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117188263 | Not Scheduled | T2 DI KONOCTI-MIDDLETOWN ;13/1A WASH INS | 43919388 | KONOCTI-MIDDLETOWN | ;013/001A | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-18 | 2020-04-18 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.593613 | 38.7647 | ETL.6380 | 41198418 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117188782 | Not Scheduled | T2 DI SPAULDING-SUMMIT 012/414 RPL POLE | 31495368 | SPAULDING-SUMMIT | 012/414 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.441125 | 39.3196 | ETL.8060 | 40810175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117189368 | Not Scheduled | T2 DI TRACY-LOS BAN 30/143 RPR GYWS | 43844596 | TRACY-LOS BANOS | 030/143 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-08 | 2020-05-08 | [6 empty] | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.218474 | 37.4895 | ETL.6130 | 40651827 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117190584 | Not Scheduled | DI KONOCTI-MIDDLETOWN 29/2 CANCEL | 43919877 | KONOCTI-MIDDLETOWN | 029/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-13 | 2020-04-13 | [6 empty] | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.626008 | 38.9122 | ETL.6380 | 40656001 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-05-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117191321 | Q2 | T2 DI FORT ROSS-GUALALA 058/02 RPL HRDD | 43920743 | GUALALA-MONTE RIO | 058/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-07 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.512932 | 38.7766 | ETL.6980 | 40656433 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117191538 | Not Scheduled | T2 DI TESLA-LOS BANOS#1 027/123 RPR GYWS | 43844592 | TESLA-LOS BANOS #1 | 027/123 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-08 | 2020-05-08 | [6 empty] | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.197147 | 37.4521 | ETL.6100 | 40658774 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117191685 | Not Scheduled | T2 DI TESLA-LOS BANOS#1 027/125 RPR GYWS | 43844592 | TESLA-LOS BANOS #1 | 027/125 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-08 | 2020-05-08 | [6 empty] | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.193908 | 37.446 | ETL.6100 | 40753727 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117191788 | Not Scheduled | DI FULTON-PUEBLO 040/207 RPR STRT | 43893848 | FULTON-PUEBLO | 040/207 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2020-05-06 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.714941 | 38.4968 | ETL.1600 | 40808458 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Lakeville |  |  | 2019-07-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117192261 | Feb | PITTS-COL STL 004/027 ajust SW 197 | 44609768 | PITTSBURG-COLUMBIA STEEL | 004/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-08 | 2020-05-08 |  |  | 2021-02-17 | 2021-02-17 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.876313 | 37.9869 | ETL.3300 | 40743393 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117192537 | Not Scheduled | T2 DI TESLA-METCALF 25/104 RPL INSS | 31460740 | TESLA-METCALF | 025/104 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-18 | 2020-04-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.680962 | 37.3587 | ETL.6110 | 40783376 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117192915 | Mar | T2 DI EAGLE ROCK-CORTINA :20/1 RPR HRDD | 43918877 | EAGLE ROCK-CORTINA | :020/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-18 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611978 | 39.0104 | ETL.1470 | 41176412 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117194464 | Not Scheduled | T2 DI TESLA-LOS BANOS 027/125 REMV NEST | 43844592 | TESLA-LOS BANOS #1 | 027/125 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-08 | 2020-05-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.193908 | 37.446 | ETL.6100 | 40753727 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117196522 | Mar | T2 HUMBOLDT-TRINITY 50/6 RMV DEBRIS | 43729541 | HUMBOLDT-TRINITY | 050/006 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-05-09 | 2025-05-09 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1820 | 44194944 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117197049 | Q2 | T3 DI YANKE (NORTH FRK) TAP 0/8 RPR GYWW | 44301879 | YANKE (NORTH FORK) TAP (IDLE) | 000/008 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-11 | 2019-10-11 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496938 | 37.2329 | ETL.9341 | 40872695 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117197185 | Q2 | T3 DI YANKE (NORTH FRK) TAP 0/9 RPR GYWW | 44301879 | YANKE (NORTH FORK) TAP (IDLE) | 000/009 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-11 | 2019-10-11 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.495373 | 37.2328 | ETL.9341 | 40871107 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Released |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117197297 | Not Scheduled | DI EVERGREEN ALMADEN 005/101 RPL INSW | 31440368 | EVERGREEN-ALMADEN | 005/101 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-24 | 2020-04-24 | [6 empty] | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-121.886589 | 37.2604 | ETL.6830 | 40633975 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117205244 | Mar | T2 HUMBOLDT-TRINITY 115kV 50/3L RMV DEBR | 43729541 | HUMBOLDT-TRINITY | 050/003 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-09 | 2024-05-09 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.024657 | 40.7294 | ETL.1820 | 44562267 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117205818 | Feb | T2NT DI BCK CRK-RK CRK-CRT 0/8 INST MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/008 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-09 | 2020-05-09 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.335965 | 39.9095 | ETL.4430 | 40862115 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117207174 | Q2 | T2 DI MALIN-RND MTN #2 92/471B INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/471B | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2020-05-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912495 | 40.8291 | ETL.6020 | 41162595 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117207177 | Q2 | T2 DI MALIN-RND MTN #2 92/471B INST MRKS | 43939115 | MALIN-ROUND MTN #2 | 092/471B | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2020-05-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912495 | 40.8291 | ETL.6020 | 41162595 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117208940 | Not Scheduled | T3 EI CARIBOU-PALERMO :31/250 RPR STRT | 44304491 | CARIBOU-PALERMO | :031/250 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-10 | 2019-11-10 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.458195 | 39.7687 | ETL.3190 | 40599297 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117208942 | Not Scheduled | T3 EI CARIBOU-PALERMO :31/250 RPR STUBS | 44304491 | CARIBOU-PALERMO | :031/250 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-10 | 2019-11-10 | [6 empty] | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.458195 | 39.7687 | ETL.3190 | 40599297 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117208980 | Not Scheduled | T2 DI FORT ROSS-GUALALA 55/001 RPR SPLW | 43920743 | GUALALA-MONTE RIO | 055/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-07 | 2020-05-07 | 2020-09-16 | 2020-09-19 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.491448 | 38.741 | ETL.6980 | 40584666 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-05-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117212890 | Q4 | T3 EI KESWICK-TRINITY 004/070C RPR CNDW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421136 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117212891 | Q4 | T3 EI KESWICK-TRINITY 004/070R RPR CNDW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2019-07-18 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421137 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117212986 | Not Scheduled | T3 EI GRIZZLY TAP 004/001R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117212987 | Not Scheduled | T3 EI GRIZZLY TAP 004/001C RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551385 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117212989 | Not Scheduled | T3 EI GRIZZLY TAP 003/017C RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551452 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117213080 | Not Scheduled | T3 EI GRIZZLY TAP 003/017R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-21 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551473 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117213249 | Mar | T2 EI HUMBOLDT-TRINITY 98/1R RPL STRW | 31474285 | HUMBOLDT-TRINITY | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.829449 | 40.7658 | ETL.1820 | 44562684 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-08-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117213280 | Mar | T2 EI HUMBOLDT-TRINITY 98/1C RPL STRW | 31474285 | HUMBOLDT-TRINITY | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-18 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.829449 | 40.7658 | ETL.1820 | 44562917 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-08-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117213281 | Q2 | T2 EI HMBLDT-BRDGVLL 109/005R RPL STRW | 31440336 | HUMBOLDT-BRIDGEVILLE | 109/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322614 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117213899 | Not Scheduled | T2 DI PINE GROVE TAP 2/50 GYWW RPR | 43843745 | PINE GROVE TAP | 002/050 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-10 | 2020-05-10 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.65385 | 38.4125 | ETL.8351 | 40690803 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117215066 | Before Feb | T2NT DI HALSEY-PLACER 1/33 INST MRKW | 43852441 | HALSEY-PLACER | 001/033 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-09 | 2020-05-09 |  |  | 2021-01-25 | 2021-01-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061588 | 38.9373 | ETL.6990 | 40598873 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117216142 | Not Scheduled | T2 DI HALSEY-PLACER 2/42 RPL POLE | 31517753 | HALSEY-PLACER | 002/042 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-10 | 2020-05-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.067105 | 38.9315 | ETL.6990 | 40873801 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117220542 | Q3 | T2 DI TESLA-NEWARK #2 020/133 RPR STRT |  | TESLA-NEWARK #2 | 020/133 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-17 | 2020-04-17 |  |  | 2021-07-17 | 2021-07-12 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.875917 | 37.5639 | ETL.5354 | 41152679 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | SFPUC | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117220686 | Q2 | T2 DI PALERMO-OROVLL #2 A006/76 RPL HRDD | 31475471 | PALERMO-OROVILLE #2 | A006/076 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-15 | 2020-04-15 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502701 | 39.5111 | ETL.7740 | 40824100 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC hold erdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117221236 | Not Scheduled | T3 DI DRM-GRSS VLY-WMR B017/388 RPL STRW | 31454605 | DRUM-GRASS VALLEY-WEIMAR | B017/388 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-10 | 2019-11-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.966014 | 39.134 | ETL.6760 | 40873749 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117221419 | Not Scheduled | T2 DI HELMS-GREGG #1 020/135 RMV NEST | 43825460 | HELMS-GREGG #1 | 020/135 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.287874 | 36.9624 | ETL.4870 | 40760551 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117221592 | Not Scheduled | T2 DI DRUM-SUMMIT#2 023/274L RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 023/274 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.393972 | 39.3291 | ETL.1450 | 44552576 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117221899 | Not Scheduled | T3NT DI EGLE RCK-REDBD :001/008 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :001/008 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-15 | 2021-04-15 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.788895 | 38.8368 | ETL.1480 | 40872960 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117222183 | Not Scheduled | T2 DI DRUM-SUMMIT#2 021/260C RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 021/260 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44559031 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117222189 | Q2 | T2 DI EAGLE ROCK-CRTN :013/011 RPR GYWW | 43918877 | EAGLE ROCK-CORTINA | :013/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-18 | 2021-05-31 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613404 | 38.9177 | ETL.1470 | 41176291 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117222419 | Not Scheduled | T2 DI DRUM-SUMMIT#2 21/260R RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 021/260 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44558990 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117222638 | Not Scheduled | T2 DI DRUM-RIO OSO #1 021/165 REPAINT | 44304427 | DRUM-RIO OSO #1 | 021/165 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-22 | 2024-04-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.104121 | 39.1027 | ETL.1420 | 40756217 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117225785 | Not Scheduled | DI HALSEY-PLACER 003/065 RPR STRS | 43852435 | HALSEY-PLACER | 003/065 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-10 | 2020-05-10 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.065467 | 38.9181 | ETL.6990 | 40602429 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226096 | Not Scheduled | T2 DI SPAULDING-SUMMIT 14/461 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/461 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.406206 | 39.3285 | ETL.8060 | 40770674 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226255 | Not Scheduled | OLIVE SW STA-SMYRNA 066/513 RMV NEST | 44301120 | OLIVE SW STA-SMYRNA | 066/513 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-09 | 2020-05-09 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-119.454797 | 35.7194 | ETL.1923 | 41127960 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226341 | Not Scheduled | T2 DI SPAULDING-SUMMIT 014/471 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/471 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.397813 | 39.3288 | ETL.8060 | 40770676 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226347 | Mar | T2 DI EAGLE ROCK-CORTINA :19/12 RPR GYWW | 43918877 | EAGLE ROCK-CORTINA | :019/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-18 | 2020-04-18 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611592 | 39.0076 | ETL.1470 | 41176410 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-17 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226385 | Not Scheduled | T2 DI HIGGINS-BELL 028/216 BNT MMBR |  | HIGGINS-BELL | 028/216 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-23 | 2020-04-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08292 | 39.033 | ETL.1412 | 40609049 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226748 | Mar | T2 DI HIGGINS-BELL 030/228 RPR SPLS | 43905781 | HIGGINS-BELL | 030/228 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-23 | 2020-04-23 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.066524 | 39.0077 | ETL.1412 | 40679272 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117226860 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/260L RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 021/260 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44558923 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117228819 | Not Scheduled | DI CPPERMINE-TVY VLLY 022/008R RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-22 | 2020-04-22 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307727 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117228943 | Not Scheduled | DI CPPERMINE-TVY VLLY 022/008L RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-22 | 2020-04-22 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117229337 | Mar | T2 DI KILARC-DESCHUTES A026/542 RPL STRW | 31440586 | KILARC-DESCHUTES | A026/542 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-24 | 2020-04-24 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.296332 | 40.5711 | ETL.7300 | 40702811 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117229687 | Mar | T2 DI KILARC-DESCHUTES A024/503 RPL STRW | 31478597 | KILARC-DESCHUTES | A024/503 | 70Y | E | 2020_(1a) PSPS |  | 2019-04-27 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.262771 | 40.566 | ETL.7300 | 40771353 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117230172 | Q2 | T2NT DI TESLA-METCALF 018/075 INST GMKS | 43877602 | TESLA-METCALF | 018/075 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-04-24 | 2020-04-24 |  |  | 2021-06-30 | 2021-06-28 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.640804 | 37.4503 | ETL.6110 | 40755175 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | 2019-06-04 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117230953 | Not Scheduled | T2 DI SPAULDING-SUMMIT 013/437 RPL STRW | 31453471 | SPAULDING-SUMMIT | 013/437 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.424355 | 39.3273 | ETL.8060 | 40828148 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117230958 | Not Scheduled | T2 DI SPAULDING-SUMMIT 014/465 RPL STRW |  | SPAULDING-SUMMIT | 014/465 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.40278 | 39.3286 | ETL.8060 | 40861952 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117231163 | Q2 | T2 DI COTTONWOD-RD BLFF 013/274 RPL HRDD | 43939201 | COTTONWOOD-RED BLUFF | 013/274 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-29 | 2020-04-29 |  |  | 2021-04-01 | 2020-09-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.259097 | 40.2279 | ETL.6660 | 40909610 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117231310 | Not Scheduled | T2 DI SPAULDING-SUMMIT 013/440 RPL STRW | 31453471 | SPAULDING-SUMMIT | 013/440 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.421713 | 39.3276 | ETL.8060 | 40876737 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117234284 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/494B RPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/494B | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380046 | 39.3274 | ETL.8060 | 42571859 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117234285 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/494A RPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/494A | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380083 | 39.3274 | ETL.8060 | 40810183 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117234286 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/494A CANCEL | 43876251 | SPAULDING-SUMMIT | 015/494A | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2020-04-29 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380083 | 39.3274 | ETL.8060 | 40810183 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117235232 | Mar | T2 DI EAGLE ROCK-CORTINA :17/13 RPR GYWW | 43918877 | EAGLE ROCK-CORTINA | :017/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-19 | 2021-05-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612304 | 38.977 | ETL.1470 | 44668641 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117237172 | Not Scheduled | T2 DI COTTLE-MELONES 043/253 RPLC SPLC | 43841261 | COTTLE-MELONES | 043/253 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537552 | 37.9444 | ETL.4530 | 40576190 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117237414 | Q3 | T2 DI MNTA VSTA LS GTOS 8/158 RMV VEGN |  | MONTA VISTA-LOS GATOS | 008/158 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2019-05-14 | 2020-05-14 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | LATE | Central | WSIP | [5 empty] | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-122.01346 | 37.2459 | ETL.7610 | 40767246 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117237736 | Q2 | T2 DI CASCAD-BTN-DSHTS A004/102 RPL INSW | 31475472 | CASCADE-BENTON-DESCHUTES | A004/102 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.303803 | 40.589 | ETL.6310 | 40789625 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117238398 | Not Scheduled | T2 DI DRUM-SUMMIT #2 020/243C RPL POLE | 31506920 | DRUM-SUMMIT #2 | 020/243C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.44124 | 39.3198 | ETL.1450 | 42572833 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117238470 | Not Scheduled | T2 DI SPAULDING-SUMMIT 013/436 RPL STRW | 31495368 | SPAULDING-SUMMIT | 013/436 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.425214 | 39.3271 | ETL.8060 | 40751929 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117238471 | Not Scheduled | T2 DI DRUM-SUMMIT #2 020/243B RPL POLE | 31506920 | DRUM-SUMMIT #2 | 020/243B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.441271 | 39.3198 | ETL.1450 | 42572832 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117238474 | Not Scheduled | T2 DI DRUM-SUMMIT #2 020/243A RPL POLE | 31506920 | DRUM-SUMMIT #2 | 020/243A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.441308 | 39.3199 | ETL.1450 | 40761259 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117238726 | Not Scheduled | T2 DI TESLA-METCALF 18/73 INS HRDS | 43888841 | TESLA-METCALF | 018/073 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-30 | 2024-04-30 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.63738 | 37.4571 | ETL.6110 | 40653183 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117239253 | Q2 | T2NT DI MALIN-RND MTN#2 87/444 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 087/444 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-04-30 | 2023-04-30 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.918917 | 40.8987 | ETL.6020 | 40753362 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117239384 | Q2 | T2 DI CASCD-BTN-DSHTS A008/172 RPR INSW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/172 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-04-26 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254291 | 40.5577 | ETL.6310 | 40842151 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117239465 | Q2 | T2 DI COTTONWOOD-RD BLFF 14/288 RPR STRW | 43939201 | COTTONWOOD-RED BLUFF | 014/288 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-29 | 2020-04-29 |  |  | 2021-04-01 | 2020-09-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254988 | 40.218 | ETL.6660 | 40909624 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117239869 | Mar | T2 DI KILARC-DESCHUTES 012/255 RPR STRW | 43930440 | KILARC-DESCHUTES | 012/255 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.037095 | 40.5673 | ETL.7300 | 40656984 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117240054 | Q2 | T2NT DI MALIN-RND MTN#2 87/444B INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 087/444B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-04-30 | 2023-04-30 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919367 | 40.8987 | ETL.6020 | 41162673 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117240149 | Q2 | T2 HAT CREEK #1-WESTWD 024/478 RPR ANCW | 44340173 | HAT CREEK #1-WESTWOOD | 024/478 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-02 | 2020-05-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.212768 | 40.688 | ETL.7030 | 40868478 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117242014 | Not Scheduled | T2 DI SPAULDING-SUMMIT 016/509 RPL SPLW | 43876251 | SPAULDING-SUMMIT | 016/509 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378637 | 39.3181 | ETL.8060 | 40770682 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117243251 | Feb | T2 DI TRINITY-MAPLE-CREEK 8/007 RPR SPLW | 43749708 | TRINITY-MAPLE CREEK | 008/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-14 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.065517 | 40.7569 | ETL.8170 | 40906368 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117245009 | Q2 | DI KNCTI-MDLTWN ;23/1 RPL BOND WIRE | 43919877 | KONOCTI-MIDDLETOWN | ;023/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-24 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.605848 | 38.8921 | ETL.6380 | 40586667 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117247795 | Not Scheduled | T2 DI CENTERVLLE-TBL MTN 4/67 RPR SPLICE | 43792089 | CENTERVILLE-TABLE MTN | 004/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-11 | 2020-05-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.702353 | 39.7386 | ETL.6320 | 40591722 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117247797 | Not Scheduled | T2 DI CENTERVLLE-TBL MTN 4/67 RPR STRW | 43792089 | CENTERVILLE-TABLE MTN | 004/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-11 | 2020-05-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.702353 | 39.7386 | ETL.6320 | 40591722 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117247986 | Q2 | T2 DI CASCADE-BENTN-DSCHTS 1/33 RPL POLE | 31427801 | CASCADE-BENTON-DESCHUTES | 001/033 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-01 | 2020-05-01 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.328975 | 40.6327 | ETL.6310 | 40759298 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117248045 | Mar | DI MTN QUARRIES TAP 0/13 RPL POLE | 31456752 | MTN QUARRIES TAP | 000/013 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-09 | 2020-05-09 |  |  | 2021-03-15 | 2021-03-15 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.056673 | 38.9158 | ETL.6991 | 40747065 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117248878 | Not Scheduled | DI DRUM-SUMMIT #1 023/278L RPL STRW | 31498145 | DRUM-SUMMIT #1 | 023/278 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-01 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.38842 | 39.3113 | ETL.1440 | 44767635 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117250216 | Feb | T3 DI KILARC-CEDAR CREEK 13/284 RPR GYWW | 43685209 | KILARC-CEDAR CREEK | 013/284 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-30 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.93861 | 40.791 | ETL.7290 | 40752222 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117250928 | Q3 | T2 EI MNTA VSTA-LOS GTS 9/171 RMV VEGN |  | MONTA VISTA-LOS GATOS | 009/171 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2019-04-29 | 2020-04-29 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | LATE | Central | WSIP | [5 empty] | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-122.00102 | 37.2416 | ETL.7610 | 40597932 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117251222 | Not Scheduled | T2 EI SPAULDING-SUMMIT 015/494C CANCEL | 31453471 | SPAULDING-SUMMIT | 015/494C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2020-04-29 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380026 | 39.3275 | ETL.8060 | 44204517 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117251385 | Q2 | T2 DI CTTNWD-PNRM 000/001 RPR GYWW | 43881008 | COTTONWOOD-PANORAMA | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-15 | 2020-05-15 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267408 | 40.4001 | ETL.1340 | 40591230 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117251419 | Q2 | T2 DI CTTNWD-PNRMA 000/001 RPR STRW | 43881008 | COTTONWOOD-PANORAMA | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-15 | 2020-05-15 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267408 | 40.4001 | ETL.1340 | 40591230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117252864 | Not Scheduled | T2NT DI DRUM-SMMT #2 018/217L INS MRKW | 43888819 | DRUM-SUMMIT #2 | 018/217 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.480702 | 39.3174 | ETL.1450 | 44552291 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117252894 | Feb | T2 DI PALERMO-COLGATE 17/81 INSTL MRKS | 43727762 | PALERMO-COLGATE | 017/081 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-17 | 2020-04-17 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502015 | 39.4113 | ETL.5360 | 40590994 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117253004 | Not Scheduled | T2 DI FORT BRAGG-ELK 012/008 RMV VEGN |  | FORT BRAGG-ELK | 012/008 | HNA | E | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-04-17 | 2020-04-17 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.789375 | 39.285 | ETL.2060 | 40876312 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117254556 | Q3 | T2 DI CRIBOU-PLUMAS JCT 015/007 RPL STRW | 31455444 | CARIBOU-PLUMAS JCT | 015/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-15 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.934872 | 39.9571 | ETL.6290 | 40824657 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117254850 | Not Scheduled | T2 DI SPALDING-SUMT 013/434 RPL STRW |  | SPAULDING-SUMMIT | 013/434 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.426888 | 39.3268 | ETL.8060 | 40650059 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255195 | Not Scheduled | T2NT DI MALIN-ROND MTN#2 55/275 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 055/275 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.607129 | 41.2644 | ETL.6020 | 40759602 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255225 | Not Scheduled | T2NT DI MALIN-ROND MTN#2 55/274 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 055/274 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.605329 | 41.2666 | ETL.6020 | 40761017 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255271 | Not Scheduled | T2NT DI MALIN-ROND MTN#2 55/276 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 055/276 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.609368 | 41.2616 | ETL.6020 | 40805303 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255386 | Q2 | T2NT DI MALIN-ROND MTN#2 57/282 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 057/282 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.620299 | 41.2482 | ETL.6020 | 40663432 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255494 | Not Scheduled | T2NT DI MALIN-ROND MTN#2 56/277 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 056/277 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.611518 | 41.259 | ETL.6020 | 40816575 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255616 | Not Scheduled | T2NT DI MALIN-ROND MTN#2 58/291 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 058/291 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.637086 | 41.2275 | ETL.6020 | 40595121 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255669 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 024/297R INS MRKW | 43888819 | DRUM-SUMMIT #2 | 024/297 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.376394 | 39.3146 | ETL.1450 | 44553508 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255680 | Q2 | T2NT DI MALIN-ROND MTN#2 58/286 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/286 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.628407 | 41.2382 | ETL.6020 | 40820537 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255684 | Q2 | T2NT DI MALIN-ROND MTN#2 57/283 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 057/283 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.62244 | 41.2455 | ETL.6020 | 40657481 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255767 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 65/329A CANCEL | 43939115 | MALIN-ROUND MTN #2 | 065/329 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2023-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7157 | 41.1425 | ETL.6020 | 41111817 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255802 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 024/297L INS MRKW | 43888819 | DRUM-SUMMIT #2 | 024/297 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.376394 | 39.3146 | ETL.1450 | 44553706 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255808 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 21/256R INST MRKW | 43888819 | DRUM-SUMMIT #2 | 021/256 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.422532 | 39.3277 | ETL.1450 | 44558951 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255821 | Q2 | T2NT DI MALIN-ROND MTN#2 60/300 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 060/300 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.654152 | 41.2065 | ETL.6020 | 40607839 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117255863 | Q2 | T2NT DI MALIN-ROND MTN#2 57/285 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 057/285 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.626242 | 41.2409 | ETL.6020 | 40764366 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117256015 | Q2 | T2NT DI MALIN-ROND MTN#2 58/288 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/288 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.631941 | 41.2338 | ETL.6020 | 40868961 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117256914 | Not Scheduled | T2 DI COTTONWOOD-DELVN#2 65/583 PNT STRS | 44305182 | COTTONWOOD-DELEVAN #2 | 065/583 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-07 | 2023-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.267916 | 40.3096 | ETL.4580 | 40657668 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117257188 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 025/299R INS MRKW | 43900106 | DRUM-SUMMIT #2 | 025/299 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-25 | 2020-04-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.373902 | 39.3129 | ETL.1450 | 44557612 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117257659 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 025/298 INST MRKW | 43900106 | DRUM-SUMMIT #2 | 025/298 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2020-04-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.375207 | 39.3138 | ETL.1450 | 44553540 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117257787 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 025/298 INST MRKW | 43888819 | DRUM-SUMMIT #2 | 025/298 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.375207 | 39.3138 | ETL.1450 | 44553674 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117258443 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 025/299L INS MRKW | 43888819 | DRUM-SUMMIT #2 | 025/299 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.373902 | 39.3129 | ETL.1450 | 44557724 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117259518 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 24/295L INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/295 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.377882 | 39.3165 | ETL.1450 | 44565822 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117259857 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 024/295 INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/295 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.377882 | 39.3165 | ETL.1450 | 44565768 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117259858 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 24/292R INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/292 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2025-04-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378222 | 39.3193 | ETL.1450 | 44558993 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117259906 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 92/470 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 092/470 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2020-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.910941 | 40.831 | ETL.6020 | 40868384 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117259971 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 24/292L INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/292 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378222 | 39.3193 | ETL.1450 | 44558932 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117260299 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 88/446 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 088/446 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2023-04-29 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.917832 | 40.8939 | ETL.6020 | 40819948 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117260484 | Not Scheduled | T2 DI DRUM-SUMMIT #2 023/281R RPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/281 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.383287 | 39.3281 | ETL.1450 | 44552351 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117260569 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 24/284R INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/284 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.381681 | 39.3251 | ETL.1450 | 44552282 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117260759 | Q2 | T2NT DI RND-MT-TBL-M #2 72/295 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 072/295 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-01 | 2020-05-01 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.767701 | 39.7785 | ETL.6070 | 40756156 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117261010 | Not Scheduled | T2 DI SPLDNG-SMMT 14/458 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/458 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.408805 | 39.3284 | ETL.8060 | 40702026 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117261019 | Not Scheduled | T2 DI SPLDNG-SMMT 14/468 REPL PL | 31453471 | SPAULDING-SUMMIT | 014/468 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-15 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.400114 | 39.3287 | ETL.8060 | 40660165 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117261974 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 24/284L INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/284 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-17 | 2020-04-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.381681 | 39.3251 | ETL.1450 | 44552590 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117262459 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/500 REPL POLE | 31453471 | SPAULDING-SUMMIT | 015/500 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-30 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37936 | 39.3236 | ETL.8060 | 40702061 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117262728 | Not Scheduled | T2 DI DRUM-SUMMIT #2 023/281L RPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/281 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-02 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.383287 | 39.3281 | ETL.1450 | 44552584 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117263419 | Not Scheduled | T2NT DI HIGGINS-BELL 031/237 PAINT STRS | 43905781 | HIGGINS-BELL | 031/237 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-04-23 | 2024-04-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.055396 | 38.9906 | ETL.1412 | 40593237 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117266723 | Not Scheduled | T2 DI PALERMO-COLGATE C005/021 INST MRKS | 43900094 | PALERMO-COLGATE | C005/021 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.274122 | 39.3081 | ETL.5360 | 40582214 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117266728 | Not Scheduled | T2 DI PALERMO-COLGATE C005/022 INST MRKS | 43900094 | PALERMO-COLGATE | C005/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.276801 | 39.308 | ETL.5360 | 40672939 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117266895 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 023/280 INST MRKS | 43900107 | DRUM-SUMMIT #2 | 023/280 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-02 | 2022-05-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.384786 | 39.3285 | ETL.1450 | 44553871 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117267072 | Mar | T2 DI TABLE MTN-PALERMO 13/60 INST MRKS | 43755803 | TABLE MTN-PALERMO | 013/060 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-16 | 2020-04-16 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502679 | 39.4739 | ETL.5690 | 40608778 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117268167 | Q2 | T2 DI HAT CRK #1 WSTWOOD 36/709 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 036/709 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-17 | 2020-05-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.062987 | 40.5571 | ETL.7030 | 40877501 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117268600 | Not Scheduled | T2 DI MALIN-RND MTN 84/429 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 084/429 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-03 | 2023-05-03 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.916103 | 40.9408 | ETL.6020 | 40870732 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117268925 | Not Scheduled | T2NT DI MALIN-RND MTN 83/424 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 083/424 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-03 | 2023-05-03 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915016 | 40.9553 | ETL.6020 | 40762175 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117268959 | Feb | T2 DI ROCK CRK-POE :06/49 RPR INSS | 43878132 | ROCK CREEK-POE | :006/049 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-17 | 2020-05-17 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.312566 | 39.9395 | ETL.5630 | 40867230 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117268985 | Not Scheduled | T2 DI MALIN-RND MTN 88/448 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 088/448 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-03 | 2023-05-03 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915843 | 40.8871 | ETL.6020 | 40871641 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117269071 | Q2 | T2 DI FORT ROSS-GUALALA 43/008 GYWW RPR | 43920743 | GUALALA-MONTE RIO | 043/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-03 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.316065 | 38.6937 | ETL.6980 | 40860962 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117269271 | Not Scheduled | T2 DI MALIN-RND MTN #2 085/432 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 085/432 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-01 | 2023-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.916716 | 40.9326 | ETL.6020 | 40690041 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117270049 | Not Scheduled | T2 DI PALERMO-COLGATE C004/018 INST MRKS | 43900094 | PALERMO-COLGATE | C004/018 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.262215 | 39.3086 | ETL.5360 | 40871485 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117270086 | Feb | T2 DI PALERMO-COLGATE 17/79 INST MRKS | 43727762 | PALERMO-COLGATE | 017/079 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-04-22 | 2020-04-22 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502078 | 39.4173 | ETL.5360 | 40866796 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117270226 | Not Scheduled | T2NT DI MALIN-RND MT #2 84/425 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 084/425 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-01 | 2023-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91521 | 40.9528 | ETL.6020 | 40759616 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117270790 | Q2 | T2 DI PIT #1-COTTONWOOD 24/195 REPL SPLS | 43879413 | PIT #1-COTTONWOOD | 024/195 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-05-03 | 2020-05-03 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 | '-121.879873 | 40.8072 | ETL.5390 | 40762590 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117271076 | Q3 | T2NT DI TESLA-METCALF 20/86 INST GMKS | 43888841 | TESLA-METCALF | 020/086 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-02 | 2020-05-02 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.654678 | 37.4218 | ETL.6110 | 40811955 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117272250 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 18/217R INST MRKW | 43888819 | DRUM-SUMMIT #2 | 018/217 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-16 | 2020-04-16 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.480702 | 39.3174 | ETL.1450 | 44552421 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117272254 | Not Scheduled | T2 DI PALERMO-COLGATE C003/013 INST MRKS | 43900094 | PALERMO-COLGATE | C003/013 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.244732 | 39.3093 | ETL.5360 | 40660219 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117272660 | Not Scheduled | T2 DI PALERMO-COLGATE C003/015 INST MRKS | 43900094 | PALERMO-COLGATE | C003/015 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.250569 | 39.3091 | ETL.5360 | 40757597 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117272664 | Not Scheduled | T2 DI PALERMO-COLGATE C003/014 INST MRKS | 43900094 | PALERMO-COLGATE | C003/014 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-01 | 2020-05-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.248188 | 39.3092 | ETL.5360 | 40757610 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117274983 | Not Scheduled | T2 DI DRUM-SUMMIT #2 019/225C RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/225C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-03 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.467422 | 39.3193 | ETL.1450 | 42572829 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117275037 | Not Scheduled | T2NT DI DRUM-SMMT #2 023/273R RPL POLE | 31527827 | DRUM-SUMMIT #2 | 023/273 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-06 | 2020-05-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395033 | 39.3291 | ETL.1450 | 44553711 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117275094 | Q2 | T2 DI VOLTA-DESCHUTES 015/319 RMV STUB | 43939089 | VOLTA-DESCHUTES | 015/319 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-03 | 2024-05-03 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.138413 | 40.5304 | ETL.8290 | 40700090 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117275482 | Q2 | T2NT DI RND MTN-TBLE MTN 67/279 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 067/279 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-06 | 2020-05-06 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.797139 | 39.8481 | ETL.6070 | 40867695 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117275626 | Not Scheduled | T2 DI DRUM-RIO OSO 25/189 PAINT STRS | 44304427 | DRUM-RIO OSO #1 | 025/189 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-02 | 2023-05-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.171175 | 39.0758 | ETL.1420 | 40870511 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117275798 | Q4 | T3 MAPLE CREEK-HPA 22/11 INS CRSBY CL | 43747047 | MAPLE CREEK-HOOPA | 022/011 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-01-10 | 2022-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.640275 | 40.986 | ETL.7490 | 44660734 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117276184 | Q2 | T3 EI DRUM-HIGGINS 2/29L RPL POLE | 31423101 | DRUM-HIGGINS | 002/029 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-14 | 2019-06-14 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.796776 | 39.2267 | ETL.4393 | 44172228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117276185 | Q2 | T3 EI DRUM-HIGGINS 3/36R RPL POLE | 31423101 | DRUM-HIGGINS | 003/036 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-15 | 2019-06-15 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.807961 | 39.2199 | ETL.4393 | 44172267 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117276326 | Q2 | T2 DI MALIN-RND MTN #2 65/329B RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 065/329B | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-02 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.716489 | 41.1419 | ETL.6020 | 41111818 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117276532 | Not Scheduled | T2NT DI MALIN-RD MTN #2 87/441 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 087/441 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-02 | 2023-05-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.918645 | 40.9068 | ETL.6020 | 40592584 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117277191 | Not Scheduled | T2 DI PIT #1-COTTONWOD 20/164 PAINT STRS | 44157589 | PIT #1-COTTONWOOD | 020/164 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-04 | 2023-05-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.810666 | 40.8239 | ETL.5390 | 40759727 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117277285 | Not Scheduled | T2 DI DRUM-RIO OSO #1 024/184 PAINT STRS | 44304427 | DRUM-RIO OSO #1 | 024/184 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-02 | 2022-05-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.159682 | 39.0805 | ETL.1420 | 40756314 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117277432 | Feb | T2 DI DRUM-RIO OSO #1 024/179 REPL INSS | 31431453 | DRUM-RIO OSO #1 | 024/179 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-20 | 2020-05-20 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.145678 | 39.0861 | ETL.1420 | 40865484 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117277716 | Q2 | T2 DI UKIAH-HPLND-CLVRDL 14/135 RPR STRW | 44306677 | UKIAH-HOPLAND-CLOVERDALE | 014/135 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2020-05-06 |  |  | 2021-04-16 | 2021-04-13 |  | TLN/TLQ error |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.096378 | 38.996 | ETL.4050 | 40772132 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117280454 | Q4 | T3 EI MIDDLE FORK-GOLD HILL 9/79R RPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 009/079 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-12-26 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.738363 | 38.9879 | ETL.5140 | 44553750 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2019-05-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117281300 | Not Scheduled | T2 DI MORAGA-LAKEWOOD 009/067 RPR FOND |  | MORAGA-LAKEWOOD | 009/067 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-03 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.113852 | 37.8762 | ETL.3741 | 40804925 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117281307 | Feb | DI RIO DELL JCT-BRDGVLLE 40/02 REPR GYWW | 43749703 | RIO DELL JCT-BRIDGEVILLE | 040/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-20 | 2020-05-20 |  |  | 2021-02-27 | 2021-02-15 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.789129 | 40.4762 | ETL.7850 | 40656598 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-01 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117283050 | Mar | T2 DI KILARC-DSCHTS 11/231 RPR GYWW | 43682103 | KILARC-DESCHUTES | 011/231 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.020167 | 40.5733 | ETL.7300 | 40676507 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117284759 | Not Scheduled | T2 EI ROLLINS TAP 0/11 INS ANCHOR EXT | 43790320 | ROLLINS TAP | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-02-25 | 2020-02-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.955117 | 39.1339 | ETL.6762 | 40751887 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117284811 | Not Scheduled | T2 DI DRUM-SUMMIT #2 19/225A RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/225A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-04 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.46742 | 39.3194 | ETL.1450 | 40586209 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117284873 | Q2 | T2 DI CLMN CTTNWOOD 000/001 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-14 | 2020-05-14 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.121614 | 40.4053 | ETL.6430 | 40598764 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117284905 | Not Scheduled | T2NT DI MLIN-RND MTN#2 87/444A CANCEL | 43939115 | MALIN-ROUND MTN #2 | 087/444A | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-06 | 2023-05-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919147 | 40.8987 | ETL.6020 | 41162672 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117284934 | Not Scheduled | DI DRUM-SUMMIT #2 19/227 INST MRKW | 43900109 | DRUM-SUMMIT #2 | 019/227 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-04 | 2020-05-04 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.465203 | 39.3193 | ETL.1450 | 44557576 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117285784 | Q4 | T3 DI DRUM-RIO OSO #2 9/91 HRDS RPL | 43852540 | DRUM-RIO OSO #2 | 009/091 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-06 | 2019-11-06 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1430 | 44304984 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-02-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117286602 | Not Scheduled | T2NT DI MRLN-RND MTN #2 84/428 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 084/428 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-04 | 2023-05-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91587 | 40.9439 | ETL.6020 | 40873267 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117287167 | Q2 | T2 DI MALIN-ROUND MTN#2 65/329 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 065/329A | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-04 | 2023-05-04 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.716422 | 41.1418 | ETL.6020 | 40868287 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117288238 | Feb | T2 BCKS CRK-RCK CRK-CRSTA 0/10 RPL DAMS | 43897311 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2020-05-11 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.341079 | 39.9091 | ETL.4430 | 40603364 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117288270 | Feb | T2 BUCKS CREEK-RCK CRK-CRST 0/9 REPL INS | 31462237 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/009 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2020-05-11 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.339367 | 39.9093 | ETL.4430 | 40892650 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-08-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117288370 | Q2 | T2 DI WST PNT-VLLY SPRGS 5/65A RPR GYWW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/065A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-07 | 2020-05-07 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.633935 | 38.3896 | ETL.8350 | 40824062 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog BLM |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117288404 | Not Scheduled | T2 DI PIT #1 CTTNWD 21/171 STRS PNT | 44157589 | PIT #1-COTTONWOOD | 021/171 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-06 | 2023-05-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.825979 | 40.8226 | ETL.5390 | 40592501 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117290764 | Q2 | T2 DI INDAN FLT-YOSEMITE 37/220 RPR FOND | 43938847 | ETL.1112.POLE.NWOD | 037/220 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-07 | 2020-05-07 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.808976 | 37.676 | ETL.1112 | 44420221 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  | NPS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117290810 | Not Scheduled | T2NT DI MALIN-RND MT #2 75/379 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 075/379 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-06 | 2022-05-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8494 | 41.0633 | ETL.6020 | 40868293 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117291136 | Q2 | T2NT DI MLN-RND MTN #2 090/458 INST GMKS | 43962821 | MALIN-ROUND MTN #2 | 090/458 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2023-05-08 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915505 | 40.861 | ETL.6020 | 40862531 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117291217 | Not Scheduled | T2NT DI MALIN-RND MTN 76/387 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 076/387 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-06 | 2022-05-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87322 | 41.0533 | ETL.6020 | 40816580 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117291311 | Q2 | T2NT DI MALIN-RND MTN#2 90/456 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 090/456 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2023-05-08 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.914806 | 40.8654 | ETL.6020 | 40818822 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117291486 | Not Scheduled | T2 DI DRUM-SUMMIT #2 019/225B RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/225B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-06 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.467419 | 39.3193 | ETL.1450 | 42572828 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117291591 | Not Scheduled | T2NT DI MALIN-RND MTN 81/412 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 081/412 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2022-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.902189 | 40.9915 | ETL.6020 | 40684098 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117291762 | Not Scheduled | T2 DI PLACER-GOLD HILL A004/037 RPL SPLW | 43910272 | PLACER-GOLD HILL #1 | A004/037 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-07 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.095847 | 38.8349 | ETL.3340 | 41123051 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292032 | Not Scheduled | T2NT DI MALN-RD MTN #2 091/463 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 091/463 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2020-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91528 | 40.8514 | ETL.6020 | 40657565 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292119 | Q2 | T2 DI FORT ROSS-GUALALA 57/9 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 057/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-07 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.516209 | 38.7716 | ETL.6980 | 40876082 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292226 | Not Scheduled | T2NT DI MALIN-RND MTN 90/461 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 090/461 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2023-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915988 | 40.855 | ETL.6020 | 40592655 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292326 | Q2 | T2NT DI MALIN-RND MTN 89/453A INSTL MRKS | 43939115 | MALIN-ROUND MTN #2 | 089/453A | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2022-05-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912926 | 40.8754 | ETL.6020 | 41111837 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292337 | Not Scheduled | T2 DI DRUM-SUMMIT #2 023/273L RPL POLE | 31497848 | DRUM-SUMMIT #2 | 023/273 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-06 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395033 | 39.3291 | ETL.1450 | 44553712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292366 | Not Scheduled | T2NT DI MLIN-RND MTN#2 77/391 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 077/391 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2022-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.882376 | 41.0436 | ETL.6020 | 40586430 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292427 | Not Scheduled | T2NT DI MALIN-RND MTN 89/451 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 089/451 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2023-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91347 | 40.879 | ETL.6020 | 40587307 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292474 | Not Scheduled | T2NT DI MALIN-RND MTN#2 85/434 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 085/434 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2023-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9172 | 40.9261 | ETL.6020 | 40752247 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292528 | Not Scheduled | T2NT DI MALIN-RND MTN#2 75/383 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 075/383 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2022-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.863086 | 41.0591 | ETL.6020 | 40663117 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292567 | Not Scheduled | T2NT DI MALIN-RND MTN#2 78/399 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 078/399 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2022-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890912 | 41.024 | ETL.6020 | 40868296 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292649 | Not Scheduled | T2NT DI MALIN-RND MTN#2 78/398A CANCEL | 43939115 | MALIN-ROUND MTN #2 | 078/398A | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-07 | 2022-05-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890795 | 41.0251 | ETL.6020 | 41162694 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117292768 | Not Scheduled | T2NT DI MALN-RND MTN #2 78/397 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 078/397 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2022-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890402 | 41.031 | ETL.6020 | 40816582 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293029 | Not Scheduled | T2NT DI MALN-RD MTN#2 092/471A CANCEL | 43939115 | MALIN-ROUND MTN #2 | 092/471A | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2020-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912347 | 40.8289 | ETL.6020 | 41162594 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293065 | Q2 | T2NT DI MALN-RD MTN#2 092/471A INST MRKS | 43939115 | MALIN-ROUND MTN #2 | 092/471A | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2020-05-08 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912347 | 40.8289 | ETL.6020 | 41162594 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293068 | Q2 | T2 EI BALCH-SANGER 000/001 RPL CONN | 43845830 | BALCH-SANGER | 000/001 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-21 | 2020-05-21 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.088691 | 36.9085 | ETL.1050 | 40583096 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293079 | Q4 | T3 DI KESWICK-TRINITY 4/70 RPR STRW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-08 | 2019-11-08 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293190 | Feb | T2 DI TRINITY MPL CRK 5/2 RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 005/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-08 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.0264 | 40.733 | ETL.8170 | 40906319 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293625 | Not Scheduled | T2 DI CTTNWD-DLVN 066/587 REPAINT | 44305182 | COTTONWOOD-DELEVAN #2 | 066/587 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-08 | 2020-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267909 | 40.3007 | ETL.4580 | 40819493 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293721 | Q2 | DI PALERMO-OROVILLE #2 A005/070 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A005/070 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-09 | 2020-05-09 |  |  | 2021-04-01 | 2021-03-29 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.504552 | 39.5078 | ETL.7740 | 40610831 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117293724 | Q2 | DI PALERMO-OROVILLE #2 A005/070 RPR STRW | 43724470 | PALERMO-OROVILLE #2 | A005/070 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-09 | 2020-05-09 |  |  | 2021-04-01 | 2021-03-29 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.504552 | 39.5078 | ETL.7740 | 40610831 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117294106 | Not Scheduled | T3 EI DIABLO UNIT #1 5/01 RPL HRDS | 43908329 | DIABLO UNIT #1 (NF) | 005/001 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-20 | 2019-11-20 | [7 empty] | TR3 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Per DCPP Unit#1 Outage is October 2020 | '-120.852759 | 35.2135 | ETL.5940 | 40593206 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117294232 | Q2 | T2 EI TESLA-METCALF 20/86 RPR GYWS | 43888756 | TESLA-METCALF | 020/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-20 | 2020-05-20 |  |  | 2021-06-30 | 2021-06-28 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.654678 | 37.4218 | ETL.6110 | 40811955 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117294236 | Q2 | T2NT EI TESLA-METCALF 20/86 INST MRKS | 43888756 | TESLA-METCALF | 020/086 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-20 | 2020-05-20 |  |  | 2021-06-30 | 2021-06-28 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.654678 | 37.4218 | ETL.6110 | 40811955 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117295256 | Feb | T2NT DI EL DRDO-MRI FLT #1 8/61 INS MRKS | 43869447 | ELDORADO-MISSOURI FLAT #1 | 008/061 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-09 | 2020-05-09 |  |  | 2021-02-21 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.76225 | 38.7561 | ETL.1530 | 40581059 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117295777 | Not Scheduled | T2 DI DRUM-HIGGINS 023/182 RPR STRS | 43852138 | DRUM-HIGGINS | 023/182 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.113179 | 39.0989 | ETL.4393 | 40913078 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117296421 | Not Scheduled | DI DRUM-SUMMIT #1 23/281R RPL POLE | 31498145 | DRUM-SUMMIT #1 | 023/281 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.382895 | 39.3113 | ETL.1440 | 44767638 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117296805 | Q2 | DI HAT CRK #1-WESTWOOD 48/930 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 048/930 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-05-21 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.019002 | 40.4004 | ETL.7030 | 40825618 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117296916 | Not Scheduled | T2NT DI MALIN-RND MTN 74/378 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 074/378 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-08 | 2022-05-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.847379 | 41.0644 | ETL.6020 | 40863447 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117297020 | Mar | DI HIGGINS-BELL 035/265 RPR SPLS | 43740275 | HIGGINS-BELL | 035/265 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-07 | 2020-05-07 |  |  | 2021-03-17 | 2021-03-14 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.059021 | 38.9369 | ETL.1412 | 40894680 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117297125 | Not Scheduled | T3NT DI CARIBOU-PALERMO :36/291 RMV VEGN |  | CARIBOU-PALERMO | :036/291 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-09 | 2021-05-09 | [7 empty] | TR3 | <90D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.48355 | 39.6997 | ETL.3190 | 40589241 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117297127 | Not Scheduled | T3 DI CARIBOU-PALRMO :36/291 BURIED MEMB | 44051418 | CARIBOU-PALERMO | :036/291 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2019-11-09 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.48355 | 39.6997 | ETL.3190 | 40589241 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117297348 | Not Scheduled | T2 DI WST PNT VLLY SPRGS 5/065B RPR GYWW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/065B | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-08 | 2020-05-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.633906 | 38.3896 | ETL.8350 | 42833790 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog BLM |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117297392 | Not Scheduled | T2 DI WST PNT VLLY SPRGS 5/065C RPR GYWW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/065C | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-08 | 2020-05-08 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.633879 | 38.3896 | ETL.8350 | 42833791 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog BLM |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117298533 | Not Scheduled | T2 DI DRUM-SUMMIT #2 21/251 INST MRKW | 43900106 | DRUM-SUMMIT #2 | 021/251 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-26 | 2020-04-26 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.430864 | 39.3256 | ETL.1450 | 44553709 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117298769 | Q2 | T2NT DI MLIN-RND MTN #2 92/470B INS MRKS | 43939115 | MALIN-ROUND MTN #2 | 092/470B | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-09 | 2020-05-09 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.911384 | 40.831 | ETL.6020 | 41162775 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117298941 | Not Scheduled | T2NT DI MLIN-RND MTN #2 92/470B CANCEL | 43939115 | MALIN-ROUND MTN #2 | 092/470B | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-09 | 2020-05-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.911384 | 40.831 | ETL.6020 | 41162775 | Guy Wire Mark /Indic-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117299069 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 81/414 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 081/414 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-09 | 2022-05-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.905929 | 40.9848 | ETL.6020 | 40753360 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117299285 | Not Scheduled | T2NT DI MLN-RND MTN#2 055/271 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 055/271 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-09 | 2020-05-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.59905 | 41.2743 | ETL.6020 | 40587310 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117299300 | Feb | T2NT DI BK CRK-RK CRK-CRT 06/53 INS MRKS | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/053 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-09 | 2020-05-09 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.416685 | 39.8427 | ETL.4430 | 40656154 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117299303 | Feb | T2 DI BCK CRK-RCK CRK-CRST 6/52 RPR STRT | 43897310 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/052 | ICQ | B | Pre-2020_(0) A and B Tags |  | 2019-05-09 | 2021-03-03 | 2021-02-24 | 2021-02-25 | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.415007 | 39.8445 | ETL.4430 | 40683792 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 117299434 | Mar | T2 HUMBOLDT-TRINITY 56/2 RMV DEBRIS | 44311174 | HUMBOLDT-TRINITY | 056/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-05-22 | 2024-05-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1820 | 44324186 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117299512 | Mar | T2 HUMBOLDT-TRINITY 056/003 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 056/003 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-22 | 2024-05-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.10637 | 40.7687 | ETL.1820 | 44562215 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117299925 | Not Scheduled | T2 EI EXCHEQUER-YOSMITE 15/49 PAINT STRS | 44585956 | EXCHEQUER-YOSEMITE | 015/049 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.117402 | 37.585 | ETL.8650 | 40859241 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117300353 | Feb | T2 DI TRINITY-MAPLE CREEK 20/5 REPL PL | 31456286 | TRINITY-MAPLE CREEK | 020/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2021-05-31 |  |  | 2021-02-20 | 2021-02-19 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.26918 | 40.7208 | ETL.8170 | 40765322 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117301321 | Not Scheduled | T2 DI COTTONWOOD-BENTON#1 1/25 RPL STRW | 31487865 | COTTONWOOD-BENTON #1 | 001/025 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-09 | 2020-05-09 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.283176 | 40.4053 | ETL.6640 | 40615969 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117302007 | Not Scheduled | T2 DI COTTONWOOD-BTN #1 1/26 RPL PL | 31487865 | COTTONWOOD-BENTON #1 | 001/026 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-10 | 2020-05-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.282328 | 40.4057 | ETL.6640 | 40586298 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117302323 | Q2 | T2 DI BALCH-SANGER 002/014 REPL DAMS | 43845834 | BALCH-SANGER | 002/014 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-21 | 2020-05-21 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.122037 | 36.8981 | ETL.1050 | 40748591 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117302331 | Q2 | T2 DI BALCH-SANGER 002/014 REPR STRT | 43845831 | BALCH-SANGER | 002/014 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-21 | 2020-05-21 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.122037 | 36.8981 | ETL.1050 | 40748591 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117302645 | Q3 | T2 DELTA MTN GATE JCT 012/164 RPL INSS | 31454737 | DELTA-MOUNTAIN GATE JCT | 012/164 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-22 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.314871 | 40.7808 | ETL.6750 | 42711806 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 93 | Q3 |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117303363 | Not Scheduled | T2 DI TESLA-SALADO #1 056/249 RPL INSS | 31462205 | TESLA-SALADO #1 | 056/249 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-10 | 2020-05-10 | 2020-08-14 | 2020-08-14 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.213969 | 37.4855 | ETL.3990 | 41137687 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 1 | 2020-01-08 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-01-08 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117303365 | Not Scheduled | T2 DI EL DORD-MO FLAT #1 10/93B RPR GYWW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 010/093B | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-10 | 2020-05-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.783738 | 38.7305 | ETL.1530 | 40740000 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117303368 | Feb | T3 DI ROUND MTN-CTNWD #3 28/228 RPL INSS | 31454792 | ROUND MTN-COTTONWOOD #3 | 028/228 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-10 | 2021-05-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.944952 | 40.7841 | ETL.5650 | 40889188 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117303494 | Not Scheduled | T2 DI VALLEY SPRINGS#1 12/232 RPR PL | 43836742 | VALLEY SPRINGS #1 | 012/232 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2020-05-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.914316 | 38.1082 | ETL.8210 | 40908316 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117303554 | Q2 | T2 DI LKEVILLE SNMA #1 002/028 WASH INSS | 43919384 | LAKEVILLE-SONOMA #2 | 002/028 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-09 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.537991 | 38.2683 | ETL.2070 | 42629068 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117303881 | Not Scheduled | T2 DI VALLEY SPRINGS#1 12/234 REPL PL | 31454707 | VALLEY SPRINGS #1 | 012/234 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2020-05-09 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.915693 | 38.1074 | ETL.8210 | 40906499 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117304734 | Feb | T2NT DI BKS CRK RK CK CRS 6/056 INS MRKS | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/056 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-11 | 2020-05-11 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421024 | 39.8365 | ETL.4430 | 40811850 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305112 | Feb | T2 DI RND MTN CTTNWD #3 52/469 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/469 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-11 | 2020-05-11 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.196048 | 40.4824 | ETL.5650 | 40868130 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305330 | Not Scheduled | T2NT DI MALIN-RND MT#2 52/257 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 052/257 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.571243 | 41.3085 | ETL.6020 | 40821634 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305417 | Not Scheduled | T2NT DI MLN-RND MTN#2 052/261 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 052/261 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.579031 | 41.2989 | ETL.6020 | 40595189 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305519 | Not Scheduled | T2 DI MALIN-RND MTN#2 54/268 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 054/268 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.593043 | 41.2817 | ETL.6020 | 40868959 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305753 | Not Scheduled | T2 DI MALIN-RND MTN#2 54/268 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 054/268 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.593043 | 41.2817 | ETL.6020 | 40868959 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305823 | Not Scheduled | T2 DI MALIN-RND MTN#2 53/265 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 053/265 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.586929 | 41.2892 | ETL.6020 | 40760689 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305902 | Not Scheduled | T2NT DI MALIN-RND MTN#2 54/267 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 054/267 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.591022 | 41.2842 | ETL.6020 | 40816573 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117305909 | Not Scheduled | T2 DI MALIN RND MTN #2 59/297 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 059/297 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-11 | 2020-05-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.64818 | 41.2138 | ETL.6020 | 40819378 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117306024 | Feb | T2 DI RND MTN CTTNWD #3 52/467 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/467 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-11 | 2020-05-11 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.194423 | 40.4844 | ETL.5650 | 40820617 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117306714 | Q3 | T2NT DI TESLA-METCALF 018/074 PR GYWS | 43888841 | TESLA-METCALF | 018/074 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-26 | 2020-04-26 |  |  | 2021-07-10 | 2021-07-05 |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.63959 | 37.4526 | ETL.6110 | 40761170 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117306766 | Not Scheduled | T2NT DI MALIN-RND MT#2 54/269 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 054/269 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.595077 | 41.2792 | ETL.6020 | 40868277 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117307083 | Mar | T2 HUMBOLDT-TRINITY 057/001L RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 057/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-22 | 2024-05-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.119308 | 40.7687 | ETL.1820 | 44562714 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117307588 | Not Scheduled | T2 DI PINE GROVE TAP 002/054 RPR GYWW | 43843745 | PINE GROVE TAP | 002/054 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-10 | 2020-05-10 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.655952 | 38.4132 | ETL.8351 | 40825780 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117307757 | Q2 | T2 DI CORDELIA #2 TAP 3/61B RPL STRW | 31454608 | CORDELIA #2 TAP | 003/061B | 70Y | E | 2020_(1a) PSPS |  | 2019-05-11 | 2020-05-11 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147892 | 38.2446 | ETL.8184 | 40740308 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117307905 | Q2 | T2 DI CORDELIA #2 TAP 3/61C RPL STRW | 31454608 | CORDELIA #2 TAP | 003/061C | 70Y | E | 2020_(1a) PSPS |  | 2019-05-11 | 2020-05-11 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147812 | 38.2446 | ETL.8184 | 40741886 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117308586 | Not Scheduled | T2NT DI MLN-RND MNTN #2 51/256 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 051/256 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.569179 | 41.311 | ETL.6020 | 40817697 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117308720 | Not Scheduled | T2NT DI MALIN-RND MTN#2 52/259 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 052/259 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-11 | 2020-05-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.57513 | 41.3037 | ETL.6020 | 40872626 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117308814 | Q2 | T2NT DI MLN-RND MNTN #2 58/287 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/287 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.62971 | 41.2366 | ETL.6020 | 40816577 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117308826 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 52/258 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 052/258 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-11 | 2020-05-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.573254 | 41.306 | ETL.6020 | 40868957 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117308939 | Q2 | T2NT DI CRBY SW ST-RD MN 16/130 INS MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 016/130 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-13 | 2020-05-13 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.753191 | 40.8567 | ETL.5410 | 40600949 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117309035 | Not Scheduled | DI VLY-SRPGS-MRTL#1 12/8 RPR STRW | 43844293 | VALLEY SPRINGS-MARTELL #1 | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.794106 | 38.3649 | ETL.8240 | 40864905 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117309564 | Not Scheduled | T2 DI MORAGA-OAKLAND #1 003/026 RPR FOND |  | MORAGA-OAKLAND #1 | 003/026 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-11 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.209839 | 37.8166 | ETL.2720 | 40804644 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-21 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117309739 | Not Scheduled | T2NT DI MALIN-RND MT#2 82/417 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 082/417 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-11 | 2022-05-11 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.910768 | 40.976 | ETL.6020 | 40816584 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117309977 | Q4 | T3 DI TRINITY-CTTONWD 20/149B RPR GYWW | 43861284 | TRINITY-COTTONWOOD | 020/149B | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2019-11-11 |  |  | 2021-11-22 | 2021-08-23 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.523343 | 40.6191 | ETL.4040 | 42622427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310112 | Not Scheduled | T2 DI MTN GTE JCT-CSCDE 6/78 RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 006/078 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-07 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.334135 | 40.6532 | ETL.7640 | 40876605 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310115 | Not Scheduled | T2 DI MTN GTE JCT-CSCDE 6/78 RPL STRW | 31498057 | MTN GATE JCT-CASCADE | 006/078 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-07 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.334135 | 40.6532 | ETL.7640 | 40876605 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310144 | Q4 | T3 DI TRINITY-CTTONWD 20/149C RPR GYWW | 43861284 | TRINITY-COTTONWOOD | 020/149C | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2019-11-11 |  |  | 2021-11-22 | 2021-08-23 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.523297 | 40.6191 | ETL.4040 | 42622428 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310301 | Not Scheduled | T2 DI COTTONWOOD-DLVN#2 64/574 PNT STRT | 44305182 | COTTONWOOD-DELEVAN #2 | 064/574 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-12 | 2022-05-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.268073 | 40.3285 | ETL.4580 | 40760052 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310380 | Q2 | T2 DI MALIN-ROND MT #2 78/395A INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/395A | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-11 | 2022-05-11 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890182 | 41.0353 | ETL.6020 | 41162685 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310488 | Q2 | T2 DI PIT #7 TAP 003/025 RPR GYWW | 43877044 | PIT #7 TAP | 003/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-11 | 2020-05-11 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939086 | 40.827 | ETL.5442 | 44553527 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117310540 | Q2 | T2 DI PIT #7 TAP 003/025 RPR GYWW | 43877044 | PIT #7 TAP | 003/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-11 | 2020-05-11 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939086 | 40.827 | ETL.5442 | 44553737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311044 | Mar | T2 DI HUMB TRIN 66/1C RPR SPLW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562793 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311046 | Mar | T2 DI HUMB TRIN 66/1R RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44563018 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311048 | Mar | T2 DI HUMB TRIN 66/1R RPR SPLW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44563018 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311120 | Mar | T2 DI HUMBOLDT-TRINITY 062/000R RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-12 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560520 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311123 | Mar | T2 DI HUMB TRIN 66/1L RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562899 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311128 | Mar | T2 DI HUMBOLDT-TRINITY 062/000C RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-12 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560577 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311129 | Mar | T2 DI HUMBOLDT-TRINITY 062/000L RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-12 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560488 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311210 | Mar | T2 DI HUMBOLDT TRINITY 062/000L RPR STRW | 44298744 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-12 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560488 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311214 | Not Scheduled | T2 DI MALIN RND MTN #2 59/295 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 059/295 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-12 | 2020-05-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.644795 | 41.218 | ETL.6020 | 40759604 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311217 | Not Scheduled | T2NT DI MAL RND MT#2 59/296 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 059/296 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-12 | 2020-05-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.646236 | 41.2162 | ETL.6020 | 40817701 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117311232 | Q2 | T2 DI BRDGVLLE-CTTNWD 042/339B REPL DAMS | 43862285 | BRIDGEVILLE-COTTONWOOD | 042/339B | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-05-22 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-123.064259 | 40.3909 | ETL.1110 | 42603424 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117311245 | Q2 | T2 DI FORT ROSS-GUALALA 048/007 RPL INSW | 31462492 | GUALALA-MONTE RIO | 048/007 | 93H | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2020-05-09 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.386039 | 38.7183 | ETL.6980 | 40808309 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  | 2019-07-11 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117313432 | Q2 | T2 DI FORT ROSS-GUALALA 054/005 RPR SPLW | 43920743 | GUALALA-MONTE RIO | 054/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-09 | 2021-05-31 | 2020-09-16 | 2020-09-19 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.481105 | 38.7362 | ETL.6980 | 40763641 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117313464 | Q2 | T2 DI PIT #7 TAP 003/026L RPL STRW | 31501365 | PIT #7 TAP | 003/026 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-11 | 2020-05-11 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117313466 | Q2 | T2 DI PIT #7 TAP 003/026C RPL STRW | 31501365 | PIT #7 TAP | 003/026 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-11 | 2020-05-11 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553558 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117313746 | Q2 | T2 DI LAYTONVILLE-WILLITS 12/3 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 012/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-23 | 2021-05-31 | 2021-05-26 | 2021-05-28 | 2021-05-26 | 2021-05-26 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.42253 | 39.5454 | ETL.8360 | 40666646 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117313868 | Q2 | IGNACIO-ALTO-SAUSLTO #1 13/94 RPLMB STRT | 44310662 | IGNACIO-ALTO-SAUSALITO #1 | 013/094 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-05-28 | 2021-05-24 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.526547 | 37.8773 | ETL.7160 | 40864752 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117314328 | Q2 | T2 DI CTTNWD BNTN #2 14/123 GYWW RPR | 43939217 | COTTONWOOD-BENTON #2 | 014/123 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-23 | 2020-05-23 |  |  | 2021-06-25 | 2021-06-24 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.397108 | 40.5581 | ETL.6650 | 44386695 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117314493 | Q2 | T2 DI CTTNWD BNTN #2 14/123 GYWW RPR | 43939217 | COTTONWOOD-BENTON #2 | 014/123 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-23 | 2020-05-23 |  |  | 2021-06-25 | 2021-06-24 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.397108 | 40.5581 | ETL.6650 | 44386696 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117314764 | Not Scheduled | T2NT DI PIT#3-PIT#1 3/30 INST MRKS | 43877631 | PIT #3-PIT #1 | 003/030 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-14 | 2020-05-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.554544 | 40.9589 | ETL.5400 | 40591617 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117314787 | Q2 | DI NEWARK-LIVERMORE 16/106 GYWW RPR | 43877617 | NEWARK-LIVERMORE | 016/106 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-23 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.78301 | 37.6422 | ETL.7660 | 40599748 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117314860 | Not Scheduled | T2 DI PTTSBRG-CLYTN #1 004/25B BNT MMBR | 44230505 | PITTSBURG-CLAYTON #1 | 004/025B | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-03-29 | 2020-03-29 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.907547 | 37.9829 | ETL.3280 | 40739984 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117314900 | Q2 | T2 DI HMBLDT-BRIDGEVILL 113/7R RPL STRW | 31471941 | HUMBOLDT-BRIDGEVILLE | 113/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-08 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322726 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117315075 | Not Scheduled | T2 DI DRUM-SUMMIT #1 019/222L RPL STRW | 31453474 | DRUM-SUMMIT #1 | 019/222 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.465171 | 39.3191 | ETL.1440 | 44764253 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117315989 | Not Scheduled | T2 DI CTRA CSTA-LS PSTS 11/74 RMV NEST | 43877325 | CONTRA COSTA-LAS POSITAS | 011/074 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-13 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.720782 | 37.8371 | ETL.4510 | 40659760 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | LVW | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117316169 | Not Scheduled | T2 DI CONTRA CST LSPOSTS 10/72 RMV STRS | 43841164 | CONTRA COSTA-LAS POSITAS | 010/072 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-13 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.727463 | 37.8418 | ETL.4510 | 40593917 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117316554 | Not Scheduled | T2NT DI MLIN-RND MTN #2 53/263 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 053/263 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-13 | 2024-05-13 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.582904 | 41.2942 | ETL.6020 | 40657477 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117316569 | Q2 | T2 DI HUMBOLDT-BRIDGEVILL 99/6R RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-08 | 2020-05-08 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322424 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-10 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117317137 | Not Scheduled | T2 DI HAAS-WOODCHUCK 000/015 RPR GYWW | 43825054 | HAAS-WOODCHUCK | 000/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2020-05-24 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.017879 | 36.9341 | ETL.8730 | 42717460 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117317443 | Feb | T2 DI PORT COSTA BRICK TAP 0/4B STRW RPR | 44621448 | PORT COSTA BRICK TAP | 000/004B | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-23 | 2020-05-23 |  |  | 2021-02-19 | 2021-02-19 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.16845 | 38.024 | ETL.6371 | 41101663 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117317678 | Q2 | T2 DI CBRY SW ST-RND MTN 25/206 INS MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 025/206 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-14 | 2020-05-14 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.907497 | 40.8001 | ETL.5410 | 40820237 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117318366 | Q2 | T2 DI TULE-SPRINGVILLE 18/012 GDWSH INSU | 43844570 | TULE-SPRINGVILLE | 018/012 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2020-05-24 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.826526 | 36.1185 | ETL.9040 | 40691214 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117318533 | Q2 | T2 DI TULE-SPRINGVILLE 21/014 RPR STRW | 43844575 | TULE-SPRINGVILLE | 021/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.786832 | 36.1344 | ETL.9040 | 40766145 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117318671 | Q2 | T2 DI TULE-SPRINGVILLE 22/018 RPL STRW | 31453078 | TULE-SPRINGVILLE | 022/018 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.769833 | 36.1396 | ETL.9040 | 40873924 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117319990 | Not Scheduled | T2 DI DRUM-SUMMIT #2 11/132L CANCEL | 43900300 | DRUM-SUMMIT #2 | 011/132 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-15 | 2020-05-15 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.59569 | 39.3304 | ETL.1450 | 44559003 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117321407 | Mar | T2 HUMBOLDT-TRINITY 057/003B RMV DEBRIS | 43729541 | HUMBOLDT-TRINITY | 057/003B | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-22 | 2024-05-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.124049 | 40.7716 | ETL.1820 | 40653711 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117322960 | Not Scheduled | T2NT DI PIT #3-PIT #1 8/71 ANTI CLB GRD | 43877628 | PIT #3-PIT #1 | 008/071 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-14 | 2020-05-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.633315 | 40.9191 | ETL.5400 | 40576227 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117323362 | Mar | T2 DI HUMBOLDT-TRINITY 63/3 RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-14 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117323364 | Mar | T2 DI HUMBOLDT-TRINITY 63/3 RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-14 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117323632 | Q2 | T2NT DI MALIN-RND MT#2 78/396 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/396 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2020-05-14 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890323 | 41.0336 | ETL.6020 | 40820539 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117323710 | Q2 | DI LAKEVILLE-IGNACIO #1 IG2/11 RMV NEST | 43919486 | LAKEVILLE-IGNACIO #1 | IG002/011 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-14 | 2023-05-14 |  |  | 2021-05-27 | 2021-05-26 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522675 | 38.1054 | ETL.4940 | 40593209 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117323713 | Feb | T2 DI RND MTN-CTTNWD #3 R1/16R RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/016 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-14 | 2020-05-14 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935935 | 40.7985 | ETL.5650 | 44765642 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117326078 | Q2 | DI CORDELIA #2 TAP 003/066 RPR GYWW | 43852763 | CORDELIA #2 TAP | 003/066 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-13 | 2020-05-13 |  |  | 2021-05-04 | 2021-04-26 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.152884 | 38.2504 | ETL.8184 | 40612471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117326087 | Q2 | T2 DI PIT #7 TAP 2/19 RPR GYWW | 43877044 | PIT #7 TAP | 002/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-13 | 2020-05-13 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9531 | 40.8316 | ETL.5442 | 44553526 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117327313 | Not Scheduled | EI VALLEY SPRINGS-MARTELL #12/8 RPR GYWW | 43853791 | VALLEY SPRINGS-MARTELL #1 | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.794106 | 38.3649 | ETL.8240 | 40864905 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117327674 | Q3 | T2 DI KRCKHF #1-KRCKHF #2 0/006 RPR FOND | 44571489 | KERCKHOFF #1-KERCKHOFF #2 | 000/006 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-14 | 2020-05-14 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.553113 | 37.084 | ETL.1880 | 40807000 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  | BLM | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-01-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117328150 | Not Scheduled | T2 DI PIT#5-RND MTN#2 008/083R CANCEL | 43877097 | PIT #5-ROUND MTN #2 | 008/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-15 | 2020-05-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929556 | 40.8715 | ETL.5430 | 44561331 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117329547 | Not Scheduled | T2 DI PIT#5-RND MTN#2 008/083R CANCEL | 43877097 | PIT #5-ROUND MTN #2 | 008/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-15 | 2020-05-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929556 | 40.8715 | ETL.5430 | 44561331 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117329674 | Q3 | T2 DI DELTA-MTN GATE JCT 01/29 RPR GYWW | 43866629 | DELTA-MOUNTAIN GATE JCT | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2020-05-28 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.402848 | 40.9194 | ETL.6750 | 40828038 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Q3 |  |  | 2019-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117329677 | Q3 | T2 DI DELTA-MTN GATE JCT 01/29 RPR STRW | 43866629 | DELTA-MOUNTAIN GATE JCT | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.402848 | 40.9194 | ETL.6750 | 40828038 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117329886 | Q4 | DI TRINITY-COTTONWOOD 11/87L RPL STRW | 31455647 | TRINITY-COTTONWOOD | 011/087 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-01-24 | 2020-01-24 |  |  | 2021-11-22 | 2021-08-23 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.420759 | 40.5099 | ETL.4040 | 44558367 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2019-07-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117329995 | Not Scheduled | STOCKTON ""A""-WEBER #2 A4/115 RPLC POLE | 31454638 | STOCKTON "A"-WEBER #2+ (NO FLY) | A004/115 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-28 | 2022-12-28 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.279372 | 37.9699 | ETL.8130 | 40754576 | Structure-Wood | Rotten | Replace | erdy ADER | ADER | With ADE for Review | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-12-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117330211 | Not Scheduled | LOCKEFORD #1 8/146 REPLACE POLE | 31454621 | LOCKEFORD #1 | 008/146 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-27 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.252301 | 38.0373 | ETL.9461 | 41185187 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117330213 | Not Scheduled | STOCKTON """"A""""-WEBER #3 1/31 RPLC POLE | 31455757 | STOCKTON "A"-WEBER #3+ (NO FLY) | 001/031 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-29 | 2020-12-29 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.27324 | 37.9473 | ETL.8140 | 40864347 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | None |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117330277 | Not Scheduled | T2 DI SALT SPRINGS-TGR CRK 6/55 CANCEL | 43842265 | SALT SPRINGS-TIGER CREEK | 006/055 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-15 | 2020-05-15 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.327523 | 38.4769 | ETL.3500 | 40745438 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117330278 | Not Scheduled | T2NT DI SALT SPGS-TGR CRK 6/55 INST MRKS | 43842276 | SALT SPRINGS-TIGER CREEK | 006/055 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-15 | 2020-05-15 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.327523 | 38.4769 | ETL.3500 | 40745438 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog USFS |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117330514 | Q2 | T2 DI TULE-SPRINGVILLE 23/14 INST MRKW | 43844569 | TULE-SPRINGVILLE | 023/014 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-24 | 2023-05-24 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.757135 | 36.1463 | ETL.9040 | 40766149 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117330601 | Mar | SALINAS-FIRESTONE #2 A2/99 RPLC POLE | 31455749 | SALINAS-FIRESTONE #2 (NO FLY) | A002/099 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-28 | 2020-12-28 |  |  | 2021-03-28 | 2021-03-26 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.625753 | 36.6548 | ETL.7910 | 40754306 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-06-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117330602 | Mar | SALINAS-FIRESTONE#2 A2/98 REPLACE POLE | 31455749 | SALINAS-FIRESTONE #2 (NO FLY) | A002/098 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-28 | 2020-12-28 | 2021-03-28 | 2021-03-28 | 2021-03-28 | 2021-03-26 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.625365 | 36.6552 | ETL.7910 | 40754358 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-06-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117330796 | Feb | T2 DI COLEMAN-SOUTH 8/166 RPR SPLW | 43939301 | COLEMAN-SOUTH | 008/166 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-14 | 2021-05-31 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.018229 | 40.4031 | ETL.6450 | 40634876 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-02-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117331605 | Not Scheduled | T2NT DI DRUM-SUMMIT#1 024/290A INST MRKW | 43910105 | DRUM-SUMMIT #1 | 024/290A | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2020-05-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.370402 | 39.3105 | ETL.1440 | 40814122 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117333720 | Q2 | T2 DI BALCH-SANGER 04/26 INST HRDS | 43845834 | BALCH-SANGER | 004/026 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-28 | 2020-05-28 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.142525 | 36.8801 | ETL.1050 | 40807127 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117335262 | Not Scheduled | T2NT DI MLN RND MTN #2 60/299 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 060/299 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2020-05-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.652215 | 41.2089 | ETL.6020 | 40870331 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117335349 | Not Scheduled | T2 DI DRUM-SUMMIT#1 25/299A RPL STRW | 31498145 | DRUM-SUMMIT #1 | 025/299A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355473 | 39.3094 | ETL.1440 | 40756925 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117335542 | Not Scheduled | T2 DI MALIN-ROUND MTN #2 54/270 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 054/270 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2020-05-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.59706 | 41.2768 | ETL.6020 | 40605717 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117335547 | Not Scheduled | T2 DI MALIN-ROUND MTN #2 59/293 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 059/293 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2020-05-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.640829 | 41.2229 | ETL.6020 | 40657482 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117335650 | Q4 | SALINAS-FIRESTONE #1 2/78 REPLACE POLE | 31454629 | SALINAS-FIRESTONE #1 (NO FLY) | 002/078 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-28 | 2021-05-31 | 2021-11-07 | 2021-11-07 | 2021-11-07 | 2021-11-05 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.630179 | 36.6547 | ETL.7900 | 40826029 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-08-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117335952 | Not Scheduled | LOCKEFORD-LODI #3 2/48 REPLACE POLE | 31454622 | LOCKEFORD-LODI #3 | 002/048 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-12-27 | 2022-12-27 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.201095 | 38.1015 | ETL.7450 | 40666094 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-09-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117336108 | Feb | T2 DI EL DRDO-MSSRI FLT#1 7/50 RPL SPLS | 43749467 | ELDORADO-MISSOURI FLAT #1 | 007/050 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-15 | 2020-05-15 |  |  | 2021-02-21 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.732031 | 38.7584 | ETL.1530 | 40581937 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117336234 | Not Scheduled | T2 DI WEIMAR-HALSEY 2/43 RPL STRW | 31498141 | WEIMAR-HALSEY | 002/043 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.998442 | 39.0072 | ETL.8340 | 40656021 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117336367 | Q2 | T2 DI TULE-SPRINGVILLE 22/12 RPL STRW | 31453078 | TULE-SPRINGVILLE | 022/012 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.773194 | 36.1357 | ETL.9040 | 40691226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117337090 | Q2 | T2 DI CTTNWD BNTN 06/65 RPR STRW | 43939217 | COTTONWOOD-BENTON #2 | 006/065 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-14 | 2020-05-14 |  |  | 2021-06-25 | 2021-06-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.356988 | 40.47 | ETL.6650 | 44561405 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117337909 | Q2 | GREEN VALLEY-LLAGAS :010/070 RPR STRT | 44571488 | GREEN VALLEY-LLAGAS | :010/070 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-17 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-03 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.651331 | 37.1038 | ETL.1720 | 40589047 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117338427 | Not Scheduled | T2 DI DRUM-SUMMIT#1 10/116 RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/116 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.615826 | 39.3218 | ETL.1440 | 44765214 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117338469 | Not Scheduled | T2 DI DRUM-SUMMIT#1 10/116 RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/116 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.615826 | 39.3218 | ETL.1440 | 44765215 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117338870 | Feb | T2 DI COLEMAN-SOUTH 10/221 RPR GYWW | 43939303 | COLEMAN-SOUTH | 010/221 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-05-16 | 2021-05-31 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.069819 | 40.4035 | ETL.6450 | 40759353 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-02-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117339944 | Q2 | T2 DI PIT#7 TAP 002/024 (R) RPL STRW | 31432828 | PIT #7 TAP | 002/024 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-14 | 2020-05-14 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.94041 | 40.8282 | ETL.5442 | 44553735 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340029 | Q2 | T2 DI COTTONWOOD-BENTN #2 6/058 RPR POLE | 43939217 | COTTONWOOD-BENTON #2 | 006/058 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-15 | 2020-05-15 |  |  | 2021-06-25 | 2021-06-24 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.346937 | 40.4627 | ETL.6650 | 44561230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340075 | Q2 | T2 DI HAT CRK#-WSTWD 035/673 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 035/673 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-17 | 2020-05-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.083455 | 40.5793 | ETL.7030 | 40676386 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340079 | Not Scheduled | T2NT DI MALIN-RND MT #2 50/252 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 050/252 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561061 | 41.321 | ETL.6020 | 40677650 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340377 | Not Scheduled | T2 DI PIT#1-COTTONWOOD 24/194 PNT STRS | 44157589 | PIT #1-COTTONWOOD | 024/194 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875518 | 40.8083 | ETL.5390 | 40759731 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340600 | Not Scheduled | T2 DI DRUM-SMMIT#1 022/264 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 022/264 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.410339 | 39.3111 | ETL.1440 | 44767646 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340618 | Q2 | T2 DI PIT #1-COTTONWOOD 9/76 RMV NEST | 43735854 | PIT #1-COTTONWOOD | 009/076 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-17 | 2020-05-17 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.642918 | 40.914 | ETL.5390 | 40817594 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117340705 | Q2 | T2 PARADISE-TABLE MTN 6/53 RPR CONS | 43727174 | PARADISE-TABLE MTN | 006/053 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-23 | 2020-05-23 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.539917 | 39.5412 | ETL.4316 | 40691000 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117341575 | Feb | T2 DI MTN GATE JCT-CASCADE 1/10 RMV IDLE | 31475739 | MTN GATE JCT-CASCADE | 001/010 | 93J | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2020-05-28 |  |  | 2021-02-20 | 2021-01-31 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566779 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Feb |  |  | 2020-02-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117341576 | Feb | T2 DI MTN GATE JCT-CASCADE 1/10 RMV IDLE | 31475739 | MTN GATE JCT-CASCADE | 001/010 | 93J | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2020-05-28 |  |  | 2021-02-20 | 2021-01-31 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566780 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Feb |  |  | 2020-02-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117341713 | Q2 | T2 EI BRDGEVLLE-COTTONWD 13/124R RPL PL | 31451465 | BRIDGEVILLE-COTTONWOOD | 013/124 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-28 | 2020-05-28 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.520412 | 40.3946 | ETL.1110 | 44424062 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117341936 | Feb | T2 DI TRINITY-MPE CRK 015/002R RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 015/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-16 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.177053 | 40.7465 | ETL.8170 | 44769593 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117341940 | Q2 | T2 DI PIT #7 TAP 001/012C RPR STRW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-18 | 2020-05-18 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117342185 | Not Scheduled | T2 EI HUMBOLDT-TRINITY 66/01 CANCEL |  | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-02-07 | 2020-02-07 | [6 empty] | CANCEL/CNCL |  | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562899 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-09 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117342340 | Mar | T2 EI HUMBOLDT-TRNTY 89/9L RMV POLE BUTT | 43729541 | HUMBOLDT-TRINITY | 089/009 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-28 | 2024-05-28 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.678463 | 40.7322 | ETL.1820 | 44562758 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117342342 | Mar | T2 EI HUMBOLDT-TRNTY 89/9R RMV POLE BUTT | 43729541 | HUMBOLDT-TRINITY | 089/009 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-28 | 2024-05-28 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.678463 | 40.7322 | ETL.1820 | 44562896 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117342394 | Q2 | T2 EI HUMBOLDT-BRIDGVLL 113/07L RPL STRW | 31471941 | HUMBOLDT-BRIDGEVILLE | 113/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-28 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117342959 | Q2 | T2 DI LAYTONVILLE-WILLITS 010/4 RPL STRW | 31469638 | LAYTONVILLE-WILLITS | 010/004 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-05-16 | 2022-05-16 | 2021-05-26 | 2021-05-28 | 2021-05-27 | 2021-05-27 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.401411 | 39.5293 | ETL.8360 | 40769335 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117343103 | Q2 | T2 DI TULE-SPRINGVILLE 013/006 RPR SPLW | 43844707 | TULE-SPRINGVILLE | 013/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-17 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.910839 | 36.1097 | ETL.9040 | 40808056 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117343428 | Q2 | T2 DI PARADISE-TBL MTN 24/182R RPL STRW | 31453760 | PARADISE-TABLE MTN | 024/182 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383236 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117343575 | Q2 | T2 DI PIT #5-ROUND MTN #2 2/26R RPL STRW | 31495386 | PIT #5-ROUND MTN #2 | 002/026 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-17 | 2020-05-17 |  |  | 2021-06-22 | 2021-06-21 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.951078 | 40.9569 | ETL.5430 | 44561410 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117343698 | Q2 | T2 DI PIT #5-ROUND MTN #2 2/26L RPL STRW | 31495386 | PIT #5-ROUND MTN #2 | 002/026 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-17 | 2020-05-17 |  |  | 2021-06-22 | 2021-06-21 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.951078 | 40.9569 | ETL.5430 | 44561296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117344386 | Q2 | T2NT DI CRBY SW S-RD MT 16/129 INST MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 016/129 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-17 | 2020-05-17 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.752192 | 40.858 | ETL.5410 | 40862817 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117344568 | Q2 | T2 DI TULE-SPRINGVILLE 17/14 RPR STRW | 43844627 | TULE-SPRINGVILLE | 017/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2020-05-25 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.836407 | 36.1122 | ETL.9040 | 40749733 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117344627 | Q2 | T2 DI TULE-SPRINGVILLE 21/12 RPR POLE | 43844625 | TULE-SPRINGVILLE | 021/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.787997 | 36.1354 | ETL.9040 | 40690993 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117344649 | Q2 | T2 DI TULE-SPRINGVILLE 21/12 RPR GYWW | 43844623 | TULE-SPRINGVILLE | 021/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.787997 | 36.1354 | ETL.9040 | 40690993 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117344994 | Q2 | T2 DI MALIN-RND MTN#2 048/238 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 048/238 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.533307 | 41.3551 | ETL.6020 | 40868953 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117345096 | Mar | T2 DI KONOCTI-MIDDLETOWN 016/013 RPR STR | 43919877 | KONOCTI-MIDDLETOWN | 016/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-03 | 2020-05-03 | 2021-03-01 | 2021-03-04 | 2021-03-03 | 2021-03-03 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573239 | 38.8077 | ETL.6380 | 40650686 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117345295 | Not Scheduled | T2 DI TESLA-LOS BANOS #1 26/120 RPR GYWS | 43844592 | TESLA-LOS BANOS #1 | 026/120 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-17 | 2020-05-17 | [6 empty] | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.203623 | 37.4642 | ETL.6100 | 40592674 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117345328 | Feb | T2 DI RND MTN-CTTNWD#3 47/408 RPL INSS | 31454792 | ROUND MTN-COTTONWOOD #3 | 047/408 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-17 | 2020-05-17 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.140197 | 40.5499 | ETL.5650 | 40886136 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117345333 | Q2 | EI IGNACIO-SBRNTE IG001/006 RPL DAMS | 43919486 | IGNACIO-SOBRANTE | IG001/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-30 | 2021-05-31 | 2020-08-07 | 2020-08-07 | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.5158216 | 38.1175 | ETL.4920 | 44652090 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117345656 | Not Scheduled | T2 CLAY-MARTEL - 60 kV_018/264 RPR INSL | 43846569 | CLAY-MARTEL | 018/264 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-30 | 2020-05-30 | [7 empty] | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.917603 | 38.341 | ETL.8250 | 40577086 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117346139 | Not Scheduled | T2 DI MALIN-RND MTN#2 048/241 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 048/241 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.539425 | 41.3476 | ETL.6020 | 40592574 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117346177 | Q2 | T2 DI MALIN-ROUND MTN#2 78/395 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/395 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2022-05-16 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890067 | 41.0353 | ETL.6020 | 40759612 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117346220 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 74/377 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 074/377 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2022-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.843971 | 41.0664 | ETL.6020 | 40819384 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117346574 | Not Scheduled | T2 DI DRUM SMMT#1 020/024A RPL STRW | 31453474 | DRUM-SUMMIT #1 | 020/243A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435004 | 39.3211 | ETL.1440 | 40595349 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117347192 | Not Scheduled | T2 DI MALIN-RND MTN#2 49/244 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 049/244 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.545267 | 41.3404 | ETL.6020 | 40759853 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117347194 | Q2 | T2 DI PIT#7 TAP 001/011 RPR INSW | 43877044 | PIT #7 TAP | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-18 | 2020-05-18 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.972763 | 40.8367 | ETL.5442 | 44553089 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117347644 | Q2 | T2 DI TUL SPVL 23/8 RPL STRW | 31453078 | TULE-SPRINGVILLE | 023/008 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-13 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.7633 | 36.1445 | ETL.9040 | 40873956 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117347854 | Not Scheduled | T2 DI MALIN-RND MTN #2 50/249 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 050/249 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.554875 | 41.3286 | ETL.6020 | 40868275 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117348005 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 20/237R INST MRKW | 43910108 | DRUM-SUMMIT #1 | 020/237 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-26 | 2020-04-26 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.443387 | 39.319 | ETL.1440 | 44762484 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117349323 | Not Scheduled | T2 DI MALIN-RND MTN #2 048/240 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 048/240 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537312 | 41.3501 | ETL.6020 | 40605573 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117349651 | Not Scheduled | T2 DI MALIN-RND MTN #2 50/250 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 050/250 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.557085 | 41.3259 | ETL.6020 | 40605576 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117362642 | Mar | T2 DI HUMBOLDT-TRINITY 57/7R RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-18 | 2020-05-18 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.135291 | 40.7676 | ETL.1820 | 44560508 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117362643 | Mar | T2 DI HUMBOLDT-TRINITY 57/7C RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-18 | 2020-05-18 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.135291 | 40.7676 | ETL.1820 | 44560630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117362644 | Mar | T2 DI HUMBOLDT-TRINITY 57/7L RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-18 | 2020-05-18 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.135291 | 40.7676 | ETL.1820 | 44560664 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117363311 | Not Scheduled | T3NT DI DRUM-HIGGINS 5/54 REPAINT | 43738143 | DRUM-HIGGINS | 005/054 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.838345 | 39.2112 | ETL.4393 | 40751895 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117363426 | Not Scheduled | T2 EI TGR CRK-VLLY SPRNGS 10/80 PNT STRS | 43844598 | TIGER CREEK-VALLEY SPRINGS | 010/080 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-05-30 | 2020-05-30 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.641077 | 38.372 | ETL.5790 | 40581561 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117363787 | Not Scheduled | T2 DI CRBRY SW ST-RD MT 24/194 PAIN STRS | 43897848 | CARBERRY SW STA-ROUND MTN | 024/194 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875352 | 40.8086 | ETL.5410 | 40765417 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117365081 | Not Scheduled | DI VALLEY SPRINGS #1 002/035 RPR STRW | 43844341 | VALLEY SPRINGS #1 | 002/035 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-14 | 2020-05-14 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.793474 | 38.2045 | ETL.8210 | 40904201 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117365914 | Not Scheduled | T2NT DI MLN-RND MTN #2 48/239 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 048/239 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535213 | 41.3527 | ETL.6020 | 40868273 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117366121 | Not Scheduled | T3NT DI DRUM-HIGGINS 005/056 REPAINT | 43738143 | DRUM-HIGGINS | 005/056 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839844 | 39.2087 | ETL.4393 | 40819914 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117366791 | Not Scheduled | T2 DI DRM SMMT #1 11/136C RPL POLE | 31521943 | DRUM-SUMMIT #1 | 011/136C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.587778 | 39.3332 | ETL.1440 | 42572738 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117366815 | Mar | T2 HUMBOLDT-TRINITY 053/004L RMV DEBRIS | 44298596 | HUMBOLDT-TRINITY | 053/004 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-20 | 2024-05-20 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.059793 | 40.7514 | ETL.1820 | 44260937 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117366864 | Mar | T2 HUMBOLDT-TRINITY 053/004L RPR GYWS | 43958295 | HUMBOLDT-TRINITY | 053/004 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-20 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.059793 | 40.7514 | ETL.1820 | 44260937 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117366990 | Not Scheduled | T2NT DI DRM SMMT #2 11/138 INST GMKW (R) | 43939697 | DRUM-SUMMIT #2 | 011/138 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565756 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367013 | Not Scheduled | T2NT DI DRM SMMT #2 11/138 INST GMKW (L) | 43939697 | DRUM-SUMMIT #2 | 011/138 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565766 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367020 | Q2 | T2NT DI MLN-RND MTN #2 75/380B INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/380B | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2022-05-20 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.852096 | 41.0619 | ETL.6020 | 41162688 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367045 | Not Scheduled | T2NT DI DRM SMMT #2 11/138 INST GMKW (C) | 43939697 | DRUM-SUMMIT #2 | 011/138 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565795 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367088 | Not Scheduled | T2NT DI MLN-RND MTN #2 75/380 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 075/380 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2022-05-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.851868 | 41.0616 | ETL.6020 | 40601184 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367101 | Mar | T2 HUMBOLDT-TRINITY 59/00L RMV BUTT | 44086433 | HUMBOLDT-TRINITY | 059/000 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-05-30 | 2020-05-30 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.150165 | 40.7618 | ETL.1820 | 44559974 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367317 | Not Scheduled | T2 DI DRM SMMT #1 11/136B REPL PL | 31521943 | DRUM-SUMMIT #1 | 011/136B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.587778 | 39.3332 | ETL.1440 | 42572737 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367435 | Not Scheduled | T2 DI DRM SMMT #1 11/137 RPL POLE (L) | 31453338 | DRUM-SUMMIT #1 | 011/137 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44162397 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367436 | Not Scheduled | T2 DI DRM SMMT #1 11/137 RPL POLE (C) | 31453338 | DRUM-SUMMIT #1 | 011/137 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44162398 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117367437 | Not Scheduled | T2 DI DRM SMMT #1 11/137 RPL POLE (R) | 31453338 | DRUM-SUMMIT #1 | 011/137 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585934 | 39.3332 | ETL.1440 | 44162399 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368022 | Not Scheduled | T2 DI RND MTN-CTTNWOOD#2 30/262 RPR STRT | 43876309 | ROUND MTN-COTTONWOOD #2 | 030/262 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-16 | 2020-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.118895 | 40.6019 | ETL.5640 | 40674359 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368271 | Not Scheduled | DI PIT#1-CTTNWD 50/446 RPR STRT |  | PIT #1-COTTONWOOD | 050/446 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-05-17 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 - Late due to project not having funding for 2020. | '-122.174879 | 40.5077 | ETL.5390 | 40817552 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117368300 | Not Scheduled | T2 DI DRM SMMT #1 11/136A RPL POLE | 31521943 | DRUM-SUMMIT #1 | 011/136A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.587773 | 39.3332 | ETL.1440 | 40870568 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368334 | Q2 | T2NT DI RND MT-TBL MT#2 65/273 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 065/273 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-20 | 2020-05-20 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.809947 | 39.8764 | ETL.6070 | 40654134 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368462 | Q2 | T2 DI CHWCLLA-KRCHF 0/7 RPR FOND | 43845838 | CHOWCHILLA-KERCKHOFF | 000/007 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-17 | 2021-05-31 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.569417 | 37.0911 | ETL.1250 | 40806771 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368483 | Not Scheduled | T2NT DI MALIN-RND MTN#2 51/254 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 051/254 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.565106 | 41.316 | ETL.6020 | 40759855 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368487 | Q2 | T2NT DI MALN-RND MTN #2 80/405B INS MRKS | 43939115 | MALIN-ROUND MTN #2 | 080/405B | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2022-05-20 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.89427 | 41.0064 | ETL.6020 | 41162609 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368542 | Q2 | DI COLEMAN-COTTONWOOD 0/10 RPR STRW | 44309976 | COLEMAN-COTTONWOOD | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-21 | 2020-05-21 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.128437 | 40.4063 | ETL.6430 | 40875720 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368582 | Not Scheduled | T2NT DI MALIN-RND MTN#2 52/260 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 052/260 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.577014 | 41.3014 | ETL.6020 | 40592107 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117368832 | Mar | T2 DI KILARC-DSCHTS A025/527 RPL STRW | 31478597 | KILARC-DESCHUTES | A025/527 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.282326 | 40.5712 | ETL.7300 | 40869368 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370212 | Not Scheduled | T2 DI CTTNWD-DLVN #2 71/619 REPAINT | 44305182 | COTTONWOOD-DELEVAN #2 | 071/619 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-20 | 2020-05-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267464 | 40.2265 | ETL.4580 | 40868467 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370586 | Not Scheduled | T2 DI DRUM-SUMMIT #1 19/222R RPL PL | 31453474 | DRUM-SUMMIT #1 | 019/222 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-31 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.465171 | 39.3191 | ETL.1440 | 44764252 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370673 | Not Scheduled | T2 DI DRUM-SUMMIT #1 20/243B RPL PL | 31453474 | DRUM-SUMMIT #1 | 020/243B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-31 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435024 | 39.3211 | ETL.1440 | 42572712 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370675 | Not Scheduled | T2 DI DRUM-SUMMIT #1 20/243C RPL PL | 31453474 | DRUM-SUMMIT #1 | 020/243C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-31 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435043 | 39.3211 | ETL.1440 | 42572714 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370763 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 22/262R INST MRKW | 43910105 | DRUM-SUMMIT #1 | 022/262 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-31 | 2020-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.413147 | 39.3118 | ETL.1440 | 44762491 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370921 | Q2 | T2 DI CLAY-MARTEL 033/505 RPR SPLS | 43853794 | CLAY-MARTEL | 033/505 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-16 | 2020-05-16 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845874 | 38.4703 | ETL.8250 | 40912846 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370950 | Feb | T2 EI RND MTN-COTTNWD #3 53/474 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 053/474 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-12 | 2020-05-12 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.200252 | 40.4774 | ETL.5650 | 40762834 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117370953 | Q2 | T2 DI RND MTN-TBL MTN #2 81/328 INS GMKS | 44156945 | ROUND MTN-TABLE MTN #2 | 081/328 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-20 | 2020-05-20 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701904 | 39.6591 | ETL.6070 | 40865961 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371163 | Feb | DI RIO DELL JCT-BRDGVLLE 39/4 RPR GYWW | 43749703 | RIO DELL JCT-BRIDGEVILLE | 039/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-20 | 2020-05-20 |  |  | 2021-02-27 | 2021-02-15 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.801747 | 40.4704 | ETL.7850 | 40750417 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-07-15 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-15 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371170 | Not Scheduled | T2 DI SPAULDING#3&#1 0/25 RPL STRW | 31445624 | SPAULDING #3-SPAULDING #1 | 000/025 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.635875 | 39.3373 | ETL.8050 | 44190838 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371301 | Not Scheduled | T3NT DI DRUM-HIGGINS 5/58 REPAINT | 43738143 | DRUM-HIGGINS | 005/058 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.841083 | 39.2067 | ETL.4393 | 40862205 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371708 | Feb | T2 DI PALERMO-COLGATE 016/078 INST MRKS | 43727762 | PALERMO-COLGATE | 016/078 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-16 | 2020-05-16 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50205 | 39.421 | ETL.5360 | 40867432 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371839 | Not Scheduled | T2 DI PIT #1-COTONWOD 021/174 REPAINT | 44157589 | PIT #1-COTTONWOOD | 021/174 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-16 | 2023-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.831553 | 40.8208 | ETL.5390 | 40762850 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371885 | Q2 | T2NT DI CBRY SW S-RD MT 24/193 INST MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 024/193 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-16 | 2020-05-16 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87365 | 40.809 | ETL.5410 | 40651116 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371922 | Not Scheduled | T2 DI PIT #1-COTONWOD 023/191 PAINT STRS | 44157589 | PIT #1-COTTONWOOD | 023/191 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-16 | 2024-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.86936 | 40.8099 | ETL.5390 | 40579857 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117371962 | Not Scheduled | T2 DI PIT #1-COTONWOD 022/185 PAINT STRS | 44157589 | PIT #1-COTTONWOOD | 022/185 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-16 | 2024-05-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.853583 | 40.8141 | ETL.5390 | 40760963 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117372116 | Feb | T2 DI KILARC-CDR CRK 6/148 STRW RPR | 43845231 | KILARC-CEDAR CREEK | 006/148 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-21 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.987757 | 40.7131 | ETL.7290 | 40600832 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374554 | Not Scheduled | T2NT DI MLN-RND MTN #2 075/381 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 075/381 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2022-05-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.856483 | 41.0607 | ETL.6020 | 40592581 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374578 | Not Scheduled | T2 DI DRUM-SUMMIT #1 024/292 RPL STRW | 31498145 | DRUM-SUMMIT #1 | 024/292 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.367486 | 39.3102 | ETL.1440 | 44762498 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374610 | Not Scheduled | T2 DI DRUM-SUMMIT #1 024/292 RPL STRW | 31498145 | DRUM-SUMMIT #1 | 024/292 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.367486 | 39.3102 | ETL.1440 | 44762499 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374740 | Not Scheduled | T3NT DI RND MTN-CTNWD #3 31/262 PNT TWR | 43755801 | ROUND MTN-COTTONWOOD #3 | 031/262 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-05-16 | 2022-05-16 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.979159 | 40.7432 | ETL.5650 | 40683282 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374743 | Not Scheduled | T2NT DI MLN-RND MTN #2 47/235 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 047/235 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.527493 | 41.3622 | ETL.6020 | 40762610 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374793 | Not Scheduled | T2NT DI LN-RND MTN #2 053/266 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 053/266 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2020-05-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.588992 | 41.2867 | ETL.6020 | 40817699 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374796 | Not Scheduled | DI DRUM-SUMMIT #2 21/250 RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/250 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.432381 | 39.3251 | ETL.1450 | 44558931 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117374798 | Not Scheduled | T2 DI DRUM-SUMMIT #2 21/250 RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/250 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.432381 | 39.3251 | ETL.1450 | 44559076 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374802 | Not Scheduled | T2NT DI MLN-ROND MTN #2 50/247 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 050/247 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.551137 | 41.3332 | ETL.6020 | 40819376 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374855 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/257L REPL PL | 31453742 | DRUM-SUMMIT #2 | 021/257 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42131 | 39.3278 | ETL.1450 | 44552535 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374857 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/257R REPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/257 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42131 | 39.3278 | ETL.1450 | 44552275 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374916 | Not Scheduled | T3 EI GRIZZLY TAP 3/1 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3202807 | 39.8983 | ETL.2395 | 44551462 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374928 | Not Scheduled | T3 EI GRIZZLY TAP 1/14 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.299472 | 39.8956 | ETL.2395 | 44550731 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374951 | Not Scheduled | T3 EI GRIZZLY TAP 000/012 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2019-12-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.281573 | 39.8977 | ETL.2395 | 44550003 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117374952 | Not Scheduled | T3 EI GRIZZLY TAP 0/13 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2019-12-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.2840844 | 39.8978 | ETL.2395 | 44549880 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375171 | Not Scheduled | T3 EI GRIZZLY TAP 0/2 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/002 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-02 | 2019-12-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.2793956 | 39.8901 | ETL.2395 | 44403545 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375226 | Not Scheduled | T3 EI GRIZZLY TAP 3/11 RPR SPLW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2019-12-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322234 | 39.9069 | ETL.2395 | 44551417 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375228 | Not Scheduled | T3 EI GRIZZLY TAP 3/13 RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3225367 | 39.9081 | ETL.2395 | 44551402 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375256 | Not Scheduled | T3 EI GRIZZLY TAP 4/1 RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551404 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375258 | Not Scheduled | T3 EI GRIZZLY TAP 003/014 RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3225909 | 39.9083 | ETL.2395 | 44551403 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375285 | Not Scheduled | T3 EI GRIZZLY TAP 003/017L RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-02 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551421 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375386 | Not Scheduled | T2 DI DRUM-SUMMT #1 8/93 RPR GYWW | 43910106 | DRUM-SUMMIT #1 | 008/093 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-20 | 2020-05-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.654494 | 39.3133 | ETL.1440 | 40603734 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375407 | Q2 | T2 DI BRDGVLLE-CTTNWD 001/019R RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 001/019 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.302767 | 40.3956 | ETL.1110 | 44424500 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375456 | Not Scheduled | T2 DI DRUM-SUMMIT 10/127 RPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/127 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-16 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.602768 | 39.3272 | ETL.1450 | 44212267 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375457 | Not Scheduled | T2 DI SPAUL SMM 16/506 RPL CRSW | 31454618 | SPAULDING-SUMMIT | 016/506 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2020-05-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378867 | 39.3194 | ETL.8060 | 44841031 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375458 | Not Scheduled | T2 DI SPAUL SMM 16/506R RPL CRSW | 31454618 | SPAULDING-SUMMIT | 016/506 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378867 | 39.3194 | ETL.8060 | 44841030 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375459 | Not Scheduled | T2 DI DRUM-SUMMIT #2 10/127 RPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/127 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44212220 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117375818 | Not Scheduled | T3 DI SLT SPRGS-TGR CRK 15/114 INST HRDS | 43842402 | SALT SPRINGS-TIGER CREEK | 015/114 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-21 | 2019-11-21 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.470277 | 38.4556 | ETL.3500 | 40745466 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117376077 | Not Scheduled | T2NT DI PIT#-COTTONWOOD 27/220 PNT STRS | 44157589 | PIT #1-COTTONWOOD | 027/220 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-17 | 2024-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.936099 | 40.7923 | ETL.5390 | 40601045 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117376230 | Not Scheduled | T3NT DI RND MTN-CTTNWD#3 33/278 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 033/278 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-17 | 2020-05-17 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.995076 | 40.7242 | ETL.5650 | 40868286 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117376367 | Not Scheduled | T2 DI DRUM-SUMMIT #1 021/255 RPL STRW | 31453474 | DRUM-SUMMIT #1 | 021/255 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.422919 | 39.3144 | ETL.1440 | 40821389 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117376401 | Not Scheduled | T2NT DI MALN-RND MTN #2 49/242 CANCEL | 44110674 | MALIN-ROUND MTN #2 | 049/242 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2024-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.541315 | 41.3452 | ETL.6020 | 40677646 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117376408 | Not Scheduled | T2 DI DRUM-SUMMIT #1 026/309 INST MRKS | 43910103 | DRUM-SUMMIT #1 | 026/309 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.338273 | 39.3103 | ETL.1440 | 40654788 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117376842 | Not Scheduled | T2 DI CRTNA-MNDCNO#1 058/284 INS HRDT | 44306522 | CORTINA-MENDOCINO #1 | 058/284 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-17 | 2020-05-17 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.147742 | 39.2368 | ETL.1330 | 40762067 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117377053 | Not Scheduled | T2 DI BRDGVLL-CTTNWOOD 056/414 INST HRDT | 43742048 | BRIDGEVILLE-COTTONWOOD | 056/414 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.296704 | 40.3877 | ETL.1110 | 40592236 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117377492 | Not Scheduled | T2NT DI MALIN-RND MTN#2 49/246 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 049/246 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-17 | 2020-05-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.549317 | 41.3354 | ETL.6020 | 40817695 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117377616 | Q2 | DI HAT CREEK #1 WESTWD 052/1012 REPL PL | 31456189 | HAT CREEK #1-WESTWOOD | 052/1012 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-05-20 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.008713 | 40.34 | ETL.7030 | 40877517 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117377735 | Not Scheduled | T2 DI BRDGVIL-CTTNWD 054/403 INST HRDT | 43742048 | BRIDGEVILLE-COTTONWOOD | 054/403 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.265348 | 40.3949 | ETL.1110 | 40676678 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117377941 | Not Scheduled | T2 DI DRUM-SUMMIT #2 21/254L RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/254 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553572 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117377942 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/254R RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/254 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553637 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378114 | Not Scheduled | T2NT DI MLN-RND MTN #2 51/253 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 051/253 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.563022 | 41.3186 | ETL.6020 | 40663111 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378308 | Q2 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-22 | 2020-05-22 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274855 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378322 | Q2 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-22 | 2020-05-22 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274853 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378323 | Q2 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-22 | 2020-05-22 |  |  | 2021-06-04 | 2021-05-25 |  |  |  |  | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274854 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378325 | Q2 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR STRW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-22 | 2020-05-22 |  |  | 2021-06-04 | 2021-05-25 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274855 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378417 | Not Scheduled | EI STANISLAUS-MANTECA #2 026/152 REPAINT |  | STANISLAUS-MANTECA #2 | 026/152 |  | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-03 | 2020-06-03 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.748745 | 37.9293 | ETL.3820 | 40642939 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378636 | Not Scheduled | EI STLS-MLN SW ST-MCA #1 025/161 REPAINT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 025/161 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-06-03 | 2020-06-03 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.751449 | 37.9286 | ETL.3830 | 40871567 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117378968 | Feb | T3 DI DRUM-HIGGINS 011/103L RPL STRW | 31504775 | DRUM-HIGGINS | 011/103 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2019-11-22 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.910423 | 39.1788 | ETL.4393 | 44172208 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117379370 | Feb | T3 DI DRUM-HIGGINS 011/103R RPL STRW | 31504775 | DRUM-HIGGINS | 011/103 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2019-11-22 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.910423 | 39.1788 | ETL.4393 | 44172209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117379373 | Before Feb | T2 DI RND MTN-TBLE MTN #2 56/241 REPAINT |  | ROUND MTN-TABLE MTN #2 | 056/241 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-05-18 | 2020-05-18 |  |  | 2020-12-30 | 2020-12-01 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.859275 | 39.9948 | ETL.6070 | 40592713 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2020-03-20 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117379586 | Not Scheduled | T2 DI DRUM SMMT#1 8/96 RPR GYWW | 43910107 | DRUM-SUMMIT #1 | 008/096 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.649594 | 39.3141 | ETL.1440 | 40654770 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117380422 | Not Scheduled | T2NT DI MALIN-RND MTN 2 49/245 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 049/245 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-18 | 2020-05-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.547007 | 41.3383 | ETL.6020 | 40753305 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117380460 | Q2 | T2 DI HAT CRK #1-WESTWD 36/700 RPR PL | 43939292 | HAT CREEK #1-WESTWOOD | 036/700 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-18 | 2020-05-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.068123 | 40.5627 | ETL.7030 | 40867621 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117380561 | Q2 | T2 DI CSCD BENT DECH 0/6 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | 000/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-23 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.338071 | 40.6519 | ETL.6310 | 40592314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383038 | Q2 | T2 PARADISE-TABLE MTN 19/158 RPR GYWS | 43727174 | PARADISE-TABLE MTN | 019/158 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-08 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.556682 | 39.6868 | ETL.4316 | 40828363 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383078 | Q2 | T2 DI CSCD BENT DESCH 2/58 REPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 002/058 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2020-05-24 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.321791 | 40.6194 | ETL.6310 | 41177773 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383092 | Q2 | T2 PARADISE-TBL MTN 019/158 RPR JUMS | 43727174 | PARADISE-TABLE MTN | 019/158 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-08 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.556747 | 39.6868 | ETL.4316 | 40856081 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383178 | Q2 | T2 DI BRDGVL-CTTNWD 39/312L RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 039/312 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-05-18 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. |  |  | ETL.1110 | 44424595 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117383283 | Q2 | T2 DI BRDGVL-CTTNWD 39/312R RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 039/312 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-05-18 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. |  |  | ETL.1110 | 44424597 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117383361 | Q2 | T2 DI BRDGVL-CTTNWD 39/312C RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 039/312 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-05-18 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. | '-121.628227 | 37.9501 | ETL.1110 | 44424596 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117383680 | Feb | T2NT DI BCKS CK-RK CK-CT :00/2 INST MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-20 | 2020-05-20 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.347817 | 39.9056 | ETL.4430 | 40673166 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383763 | Not Scheduled | T2 DI DRUM-SUMMIT #1 009/113R RPR GYWW | 43910109 | DRUM-SUMMIT #1 | 009/113 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.620904 | 39.3209 | ETL.1440 | 44765181 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383905 | Not Scheduled | T2 DI PALERMO-COLGATE C010/047 INST MRKS | 43900094 | PALERMO-COLGATE | C010/047 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-20 | 2020-05-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.379787 | 39.2999 | ETL.5360 | 40814787 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117383916 | Not Scheduled | STN-MLNS SW STA-MNTC #1 25/163 RPR STRT | 43852841 | STANISLAUS-MELONES SS-MANTECA #1+ | 025/163 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-06-04 | 2020-06-04 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.756719 | 37.927 | ETL.3830 | 40579579 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384009 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 021/256 INST MRKW | 43947609 | DRUM-SUMMIT #2 | 021/256 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-04-29 | 2020-04-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.422532 | 39.3277 | ETL.1450 | 44558952 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384248 | Not Scheduled | STNSS-MELNES SW-STA-MN#1 19/121 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 |  | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-06-04 | 2020-06-04 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-12-31 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384371 | Not Scheduled | T3NT DI RND MTN-CTTNWD#3 31/263 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 031/263 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-05-18 | 2020-05-18 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.979721 | 40.7425 | ETL.5650 | 40653348 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384397 | Not Scheduled | DI PIT #1-COTTONWOOD 013/111B PNT STRS | 43879413 | PIT #1-COTTONWOOD | 013/111B | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-04 | 2024-06-04 | [8 empty] | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.715711 | 40.8771 | ETL.5390 | 41162765 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384436 | Q2 | T2 DI TULE-SPRINGVILLE 015/003 RPL POLE | 31454783 | TULE-SPRINGVILLE | 015/003 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.878181 | 36.1088 | ETL.9040 | 40647888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384509 | Not Scheduled | T3NT DI PIT #1-COTTNWOOD 31/266 CANCEL | 43735854 | PIT #1-COTTONWOOD | 031/266 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-03 | 2020-06-03 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.982458 | 40.739 | ETL.5390 | 40803640 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384542 | Q2 | T2 DI NEWARK-LIVER 16/108 RPR GYWW | 43877617 | NEWARK-LIVERMORE | 016/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-23 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.782978 | 37.6451 | ETL.7660 | 40665818 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-05-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117384560 | Not Scheduled | T2 DI MNDCNO-WLLTS-FRT BRGG 5/4 RPL POLE | 31490868 | MENDOCINO-WILLITS-FORT BRAGG | 005/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-21 | 2020-05-21 | 2020-09-07 | 2020-09-10 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.275139 | 39.2926 | ETL.7550 | 40649095 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117385853 | Not Scheduled | T2 TESLA-SALADO-MANTECA -_026/159 HS | 43848440 | TESLA-SALADO-MANTECA | 026/159 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-04 | 2020-06-04 | 2020-08-12 | 2020-08-13 | [5 empty] | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-121.206644 | 37.4624 | ETL.4000 | 40912763 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117385925 | Not Scheduled | T2 DI SPAULDING-SUMMIT 016/504 RPR GYWW | 43923448 | SPAULDING-SUMMIT | 016/504 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379007 | 39.3208 | ETL.8060 | 40602277 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117385983 | Not Scheduled | T2 DI DRUM-SUMMIT #1 010/120C RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/120C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.611602 | 39.3236 | ETL.1440 | 42572657 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117386191 | Not Scheduled | T2 DI DRUM-SUMMIT #1 010/120A RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/120A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.611681 | 39.3237 | ETL.1440 | 40756804 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117386282 | Not Scheduled | T2 DI DRUM-SUMMIT #1 010/120B RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/120B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.611641 | 39.3237 | ETL.1440 | 42572656 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117386354 | Not Scheduled | T3 DI RD MT-TBL MT#2 020/103 CANCEL | 43790346 | ROUND MTN-TABLE MTN #2 | 020/103 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-22 | 2019-11-22 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.94473 | 40.5135 | ETL.6070 | 40657629 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117386526 | Not Scheduled | T2 DI DRUM-SUMMIT #2 023/272 RPL STRW | 31497848 | DRUM-SUMMIT #2 | 023/272 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.396444 | 39.329 | ETL.1450 | 44558953 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117386684 | Not Scheduled | T2 DI WEIMAR-HALSEY 005/138 REPL STRW | 31454601 | WEIMAR-HALSEY | 005/138 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-04 | 2020-06-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042332 | 38.9575 | ETL.8340 | 40822775 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117387387 | Q2 | DI HAT CRK#1-WESTWOOD 46/902 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 046/902 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-05-18 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022618 | 40.4214 | ETL.7030 | 40868252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117387961 | Q2 | T2 DI BRIDGEVILLE-CTNWD 17/154R RPL STRW | 31444708 | BRIDGEVILLE-COTTONWOOD | 017/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2019-12-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.583763 | 40.3819 | ETL.1110 | 44423380 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388013 | Q2 | T2NT DI MLIN-RND MTN #2 78/395B INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/395B | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-15 | 2022-05-15 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890339 | 41.0353 | ETL.6020 | 41162682 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388133 | Q2 | T2 DI TULE-SPRNGVIL 22/003 RPR STRW | 44323596 | TULE-SPRINGVILLE | 022/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.779342 | 36.1324 | ETL.9040 | 40663647 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388300 | Q2 | T2 DI TULE-SPRNGVIL 22/009 HOLD | 31453078 | TULE-SPRINGVILLE | 022/009 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.77482 | 36.1336 | ETL.9040 | 40872990 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388302 | Q2 | T2 DI TULE-SPRNGVIL 22/014 RPL POLE | 31453078 | TULE-SPRINGVILLE | 022/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.772154 | 36.1371 | ETL.9040 | 40766147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388426 | Not Scheduled | LOS BANOS-NIDWAY #2 102/425 RPLC INSL | 31455040 | LOS BANOS-MIDWAY #2 | 102/425 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-29 | 2020-05-29 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.8828858 | 35.9146 | ETL.6010 | 40782786 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117388428 | Q2 | LOS BANOS-MIDWAY #2 099/413 RPLC INSL | 31455040 | LOS BANOS-MIDWAY #2 | 099/413 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-29 | 2020-05-29 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.9145249 | 35.9491 | ETL.6010 | 40680859 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117388434 | Q2 | T2 DI TULE-SPRNGVILLE 020/006 RPR GYWW | 44323597 | TULE-SPRINGVILLE | 020/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.807757 | 36.1354 | ETL.9040 | 40808165 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388435 | Q2 | T2 DI TULE-SPRNGVILLE 020/006 RPR STRW | 44323598 | TULE-SPRINGVILLE | 020/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.807757 | 36.1354 | ETL.9040 | 40808165 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388438 | Q2 | T2 DI TULE-SPRNGVILLE 019/008 RPR STRW | 44323599 | TULE-SPRINGVILLE | 019/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.816131 | 36.1262 | ETL.9040 | 40860497 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388635 | Not Scheduled | T2 DI PALERMO-COLGATE C000/001 INST MRKS | 43900094 | PALERMO-COLGATE | C000/001 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.193041 | 39.331 | ETL.5360 | 40593157 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388644 | Before Feb | LOS BANOS-GATES #1 001/006 CANCEL | 31418847 | LOS BANOS-GATES #1 | 001/006 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-29 | 2020-05-29 | 2020-07-06 | 2020-08-19 | 2020-08-19 | 2020-07-06 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.011446 | 37.035 | ETL.6000 | 40843810 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy DCNL |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Before Feb |  |  | 2019-09-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117388717 | Q2 | T2 DI TULE-SPRNGVIL 21/018 RPR GYWW | 43844730 | TULE-SPRINGVILLE | 021/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.783408 | 36.1323 | ETL.9040 | 40859566 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388770 | Q2 | T2 DI TULE-SPRNGVIL 21/018 RPR POLE | 43844759 | TULE-SPRINGVILLE | 021/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.783408 | 36.1323 | ETL.9040 | 40859566 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388877 | Q2 | T2 DI BRDGEVLLE-CTTNWOOD 14/129R REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 014/129 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2020-05-24 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.531514 | 40.3943 | ETL.1110 | 44423276 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388901 | Q2 | T2 DI BRDGEVLLE-CTTNWOOD 14/129L REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 014/129 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2020-05-24 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.531514 | 40.3943 | ETL.1110 | 44423275 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388925 | Not Scheduled | T2 DI LAYTONVILLE-WILLITS 13/0A INS MRKW | 43877949 | LAYTONVILLE-WILLITS | 013/000A | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-24 | 2020-05-24 | 2020-10-14 | 2020-10-17 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.427093 | 39.5555 | ETL.8360 | 40905761 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388940 | Not Scheduled | T2 DI LAYTONVILLE-WILLITS 13/0A INS GMKW | 43877949 | LAYTONVILLE-WILLITS | 013/000A | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-24 | 2020-05-24 | 2020-10-14 | 2020-10-17 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.427093 | 39.5555 | ETL.8360 | 40905761 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117388946 | Q2 | T2 DI TULE-SPRNGVIL 16/002 RPR GYWW | 43844734 | TULE-SPRINGVILLE | 016/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.861836 | 36.1083 | ETL.9040 | 40691138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117389198 | Q2 | T2 DI TULE-SPRINGVILLE 22/4 RPL POLE | 31453078 | TULE-SPRINGVILLE | 022/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.778455 | 36.1325 | ETL.9040 | 40749787 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392042 | Q2 | T2 EI BRDGVLLE-COTTNWOOD 1/19L RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 001/019 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.302767 | 40.3956 | ETL.1110 | 44424499 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392043 | Not Scheduled | T3 EI GRIZZLY TAP 03/14 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-04 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.322578 | 39.9083 | ETL.2395 | 44551383 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392044 | Not Scheduled | T3 EI GRIZZLY TAP 03/14 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-04 | 2019-12-04 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.322578 | 39.9083 | ETL.2395 | 44551384 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392264 | Q2 | T2 DI TULE-SPRINGVILLE 022/002 RPR STRW | 44323681 | TULE-SPRINGVILLE | 022/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.780278 | 36.1323 | ETL.9040 | 40691222 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392304 | Q2 | T2 DI TULE-SPRINGVILLE 022/006 RPR STRW | 44323682 | TULE-SPRINGVILLE | 022/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.776665 | 36.1329 | ETL.9040 | 40808181 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392442 | Q2 | T2 DI BALCH-SANGER 000/002 RPL INSS | 31443424 | BALCH-SANGER | 000/002 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2020-05-24 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.090382 | 36.9083 | ETL.1050 | 40725024 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-06-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392559 | Q3 | T2 DI DLTA-MTN GATE JCT 002/065 RPL POLE | 31456311 | DELTA-MOUNTAIN GATE JCT | 002/065 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.386445 | 40.9022 | ETL.6750 | 40828048 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2019-10-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392620 | Not Scheduled | T2 DI DRUM-SUMMIT#1 26/306L RPL POLE | 31498145 | DRUM-SUMMIT #1 | 026/306 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.34313 | 39.3091 | ETL.1440 | 44768880 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392622 | Not Scheduled | T2 DI DRUM-SUMMIT#1 26/306R RPL POLE | 31498145 | DRUM-SUMMIT #1 | 026/306 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.34313 | 39.3091 | ETL.1440 | 44768881 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392645 | Q2 | T2 DI TULE-SPRINGVILLE 21/16 RPR STRW | 44323683 | TULE-SPRINGVILLE | 021/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.78525 | 36.1332 | ETL.9040 | 40823385 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392710 | Not Scheduled | T2 DI DRUM-SUMMIT#2 27/330 RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 027/330 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553673 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117392714 | Not Scheduled | T2 DI DRUM-SUMMIT#2 27/330 RPL STRW | 31497848 | DRUM-SUMMIT #2 | 027/330 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117393108 | Q2 | T2 DI TULE-SPRINGVILLE 23/4 RPR STRW | 44323685 | TULE-SPRINGVILLE | 023/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.76644 | 36.1424 | ETL.9040 | 40749793 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117393153 | Mar | T2 DI TULE-SPRINGVILLE 023/007 RPL STRW | 31455199 | TULE-SPRINGVILLE | 023/007 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-05-24 | 2021-03-24 |  |  | 2021-03-24 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.764266 | 36.144 | ETL.9040 | 40821819 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 117393446 | Not Scheduled | T2 DI DRUM-SUMMIT #1 023/273R INST MRKW | 43910107 | DRUM-SUMMIT #1 | 023/273 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395358 | 39.311 | ETL.1440 | 44768883 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117393705 | Q2 | T2 DI TULE-SPRINGVILLE 23/2 RPLC STRW | 31454783 | TULE-SPRINGVILLE | 023/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.767867 | 36.1414 | ETL.9040 | 40690997 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117394452 | Mar | T2 DI MNDN-WLT-FT BRG 041/001 RPL CRSW | 31456470 | MENDOCINO-WILLITS-FORT BRAGG | 041/001 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2020-05-24 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.775088 | 39.4291 | ETL.7550 | 40600287 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-10-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117394453 | Mar | T2 DI MNDN-WLT-FT BRG 041/001 RPR INSW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 041/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2020-05-24 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.775088 | 39.4291 | ETL.7550 | 40626981 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-10-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117394744 | Mar | T2 DI MNDCN-WLLTS-FRT BRGG 1/1 RPR GYWW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 001/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-05-28 | 2021-05-31 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.212959 | 39.2549 | ETL.7550 | 40585211 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117394752 | Q2 | T2 DI TULE-SPRINGVILE 026/003 RPR CNDW | 44323686 | TULE-SPRINGVILLE | 026/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.718374 | 36.1597 | ETL.9040 | 40663677 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117394874 | Feb | T3 DI KIL CED CRE 8/199 RPR GYWW | 43685209 | KILARC-CEDAR CREEK | 008/199 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-28 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983077 | 40.738 | ETL.7290 | 40868039 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117394913 | Q2 | T2 DI TULE-SPRINGVILLE 025/007 RPR STRW | 44323687 | TULE-SPRINGVILLE | 025/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-23 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.730133 | 36.1563 | ETL.9040 | 40807811 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395289 | Not Scheduled | T2 DI ROCK CREEK-POE 000/001 PAINT STRS | 43878132 | ROCK CREEK-POE | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-24 | 2024-05-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.34688 | 39.9058 | ETL.5630 | 40590786 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395303 | Not Scheduled | T2 DI COTTONWOOD #1 002/020 RMV NEST | 44155926 | COTTONWOOD #1 | 002/020 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-05-28 | 2020-05-28 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267978 | 40.3575 | ETL.6620 | 40910964 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395338 | Not Scheduled | T2 DI SPAULDING#3-SPAULDNG#1 0/1B RPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/001B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-29 | 2020-05-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644787 | 39.3248 | ETL.8050 | 42568604 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395467 | Mar | T2 DI MNDCN-WLLTS-FRT BRGG 39/2 WSH INSW | 43878161 | MENDOCINO-WILLITS-FORT BRAGG | 039/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2020-05-24 | 2020-09-07 | 2020-09-10 | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.746993 | 39.4136 | ETL.7550 | 40697974 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395515 | Q2 | T2NT DI MALIN-RND MTN#2 75/380A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/380A | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2022-05-21 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.851997 | 41.0618 | ETL.6020 | 41162689 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395670 | Q2 | T2 DI BALCH-SANGER 3/21 RPR CONS | 43845834 | BALCH-SANGER | 003/021 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2020-05-28 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.121034 | 36.8785 | ETL.1050 | 40583099 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395729 | Q2 | T2 DI TULE-SPRINGVILLE 25/12 RPR GYWW | 43844637 | TULE-SPRINGVILLE | 025/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.725504 | 36.1569 | ETL.9040 | 40691009 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395914 | Q2 | T2NT DI CARB SW-RND MTN R1/11 INST MRKS | 43897849 | CARBERRY SW STA-ROUND MTN | R001/011 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-21 | 2020-05-21 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938708 | 40.806 | ETL.5410 | 40586643 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117395977 | Not Scheduled | T2 DI SPULDNG#3-SPULDNG#1 0/1C RPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/001C | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-29 | 2020-05-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644736 | 39.3248 | ETL.8050 | 42568605 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117396085 | Q2 | T2 EI BRDGVILLE-CTTNWD 4/42L RPL STRW | 31455500 | BRIDGEVILLE-COTTONWOOD | 004/042 | 70Y | E | 2020_(1a) PSPS |  | 2019-05-22 | 2020-05-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.352025 | 40.3908 | ETL.1110 | 44424012 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117396086 | Q2 | T2 EI BRDGVILLE-CTTNWD 4/42R RPL STRW | 31455500 | BRIDGEVILLE-COTTONWOOD | 004/042 | 70Y | E | 2020_(1a) PSPS |  | 2019-05-22 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.352025 | 40.3908 | ETL.1110 | 44424013 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117396256 | Q2 | T2 DI TULE-SPRINGVILLE 25/10 RPR CNDW | 43844704 | TULE-SPRINGVILLE | 025/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.727579 | 36.1569 | ETL.9040 | 40609662 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117396773 | Mar | T3 DI POE-RIO OSO 020/136 REPL INSS | 31454862 | POE-RIO OSO | 020/136 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-05 | 2019-12-05 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.485151 | 39.695 | ETL.5540 | 40815306 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117396774 | Q2 | T2NT DI CRBRY SW S-RD-MT R1/12 INST MRKS | 43897849 | CARBERRY SW STA-ROUND MTN | R001/012 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-22 | 2020-05-22 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938402 | 40.8075 | ETL.5410 | 40661613 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117396914 | Q2 | T2 DI BRDGVLL-CTTNWOOD 024/210R REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 024/210 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-24 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.72074 | 40.3723 | ETL.1110 | 44423243 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117396999 | Not Scheduled | DI CARIBOU-PALERMO 4/39 REPR STRT | 44070463 | CARIBOU-PALERMO | 004/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2020-06-02 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117399033 | Not Scheduled | T2NT DI DRUM-SMMT#2 9/110L RPL POLE | 31527827 | DRUM-SUMMIT #2 | 009/110 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.624533 | 39.321 | ETL.1450 | 44553634 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117399290 | Not Scheduled | T2NT DI DRUM-SUMMIT#2 9/114R RPL POLE | 31498154 | DRUM-SUMMIT #2 | 009/114 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2020-05-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.620933 | 39.3211 | ETL.1450 | 44553635 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-06-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117399658 | Q2 | T2 DI BRDGEVLLE-CTTNWOOD 23/207R REPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 023/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2020-05-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.71398 | 40.3728 | ETL.1110 | 44424463 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117400350 | Mar | T3 DI VLTA-STH 0/5 RPR SPLW | 43827513 | VOLTA-SOUTH | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2019-11-28 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.865728 | 40.4574 | ETL.8300 | 40769405 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117400351 | Mar | T3 DI VLTA-STH 0/5 RPR GYWW | 43827513 | VOLTA-SOUTH | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2019-11-28 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.865728 | 40.4574 | ETL.8300 | 40769405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117400443 | Not Scheduled | T2 DI DRUM-SUMMIT #2 018/215R RPR STRW | 43939699 | DRUM-SUMMIT #2 | 018/215 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2020-05-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.482787 | 39.3172 | ETL.1450 | 44552502 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117400448 | Not Scheduled | T2 DI DRUM-SUMMIT #2 018/215R RPL POLE | 31527827 | DRUM-SUMMIT #2 | 018/215 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.482787 | 39.3172 | ETL.1450 | 44552502 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117401418 | Q2 | T2 DI TULE-SPRINGVILLE 26/5 RPL STRW | 31453078 | TULE-SPRINGVILLE | 026/005 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.71664 | 36.1602 | ETL.9040 | 40749766 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117401522 | Feb | T2 DI CSCDE-BNTN-DESCHTES 4/102 RPL STRW | 31431551 | CASCADE-BENTON-DESCHUTES | 004/102 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.311325 | 40.5898 | ETL.6310 | 40816304 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117401540 | Mar | T2 DI MNDO-WILTS-FRT BRAGG 40/9 RPL STRW | 31456136 | MENDOCINO-WILLITS-FORT BRAGG | 040/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-28 | 2020-05-28 | 2020-09-07 | 2020-09-10 | 2021-03-18 | 2021-03-18 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.769486 | 39.4277 | ETL.7550 | 40861258 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-08-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117401597 | Q2 | T2 DI PIT #7 TAP 0/4R RPL POLE | 31432828 | PIT #7 TAP | 000/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2020-05-30 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.985004 | 40.8433 | ETL.5442 | 44553523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117401670 | Q2 | T2 DI PIT #7 TAP 0/4L RPL POLE | 31432828 | PIT #7 TAP | 000/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2020-05-30 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.985004 | 40.8433 | ETL.5442 | 44553734 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117402299 | Not Scheduled | T2 DI PALERMO-COLGATE C011/51 INST MRKS | 43900094 | PALERMO-COLGATE | C011/051 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-21 | 2020-05-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.39715 | 39.2958 | ETL.5360 | 40593965 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117402464 | Not Scheduled | T2 DI MLN-RND MUNTAIN #2 47/233 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 047/233 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2020-05-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.524441 | 41.3659 | ETL.6020 | 40657475 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117402666 | Mar | T2 CLAY-MARTEL 23/326 REPL POLE | 31455189 | CLAY-MARTEL | 023/326 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-06 | 2020-06-06 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.836026 | 38.3525 | ETL.8250 | 40874170 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117402750 | Before Feb | T2NT DI PIT#1 CTTNWD 17/135 PNT TWR | 43879413 | PIT #1-COTTONWOOD | 017/135 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-05-23 | 2021-05-23 |  |  | 2020-12-30 | 2020-12-01 |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.760596 | 40.8466 | ETL.5390 | 40760961 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117402887 | Not Scheduled | T2 DI SOB-R #1 4/32 REPAINT | 43727737 | SOBRANTE-R #1 | 004/032 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-05-30 | 2021-05-30 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.289103 | 37.9187 | ETL.3770 | 40646648 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117403245 | Q2 | T2 DI TULE-SPRINGVILLE 21/17 RPR GYWW | 43844741 | TULE-SPRINGVILLE | 021/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.78438 | 36.1327 | ETL.9040 | 40807793 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117403248 | Q2 | T2 DI TULE-SPRINGVILLE 21/17 RPR STRW | 43844754 | TULE-SPRINGVILLE | 021/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.78438 | 36.1327 | ETL.9040 | 40807793 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117403599 | Q2 | T2 EI BRIDGVILL-COTTNWD 33/274 RPL STRW | 31444708 | BRIDGEVILLE-COTTONWOOD | 033/274 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2020-05-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.902454 | 40.3663 | ETL.1110 | 44424385 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117403742 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 020/240 INST MRKW | 43947609 | DRUM-SUMMIT #2 | 020/240 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2020-05-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.446359 | 39.3183 | ETL.1450 | 44559082 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117403749 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 020/240 INST MRKW | 43947609 | DRUM-SUMMIT #2 | 020/240 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2020-05-23 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.446359 | 39.3183 | ETL.1450 | 44559084 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117404160 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 020/238 INS MRKW | 43947609 | DRUM-SUMMIT #2 | 020/238 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2020-05-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.449412 | 39.3179 | ETL.1450 | 44559066 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117404412 | Feb | T2 DI ROCK CREEK-POE 006/045 INS MRKS | 43878133 | ROCK CREEK-POE | :006/045 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-22 | 2020-05-22 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.30877 | 39.9421 | ETL.5630 | 40758306 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117404670 | Q2 | T2 DI TULE-SPRINGVILLE 24/4 RPL STRW | 31454783 | TULE-SPRINGVILLE | 024/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-25 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.751137 | 36.1503 | ETL.9040 | 40749803 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117405390 | Q2 | T2NT DI MN-RND MTN #2 082/419A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 082/419A | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-11 | 2023-05-11 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913876 | 40.9704 | ETL.6020 | 41162607 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117407843 | Not Scheduled | T3 DI MORAGA-OAKLAND #1 000/004 RPR STRT | 44169721 | MORAGA-OAKLAND #1 | 000/004 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-06-03 | 2019-12-03 | [7 empty] | TR3 | LATE | Central | WSIP |  |  |  | REJECT: Crew reported work not needed. Engineer reviewed and disagreed. Please complete work required and resubmit. | Project | 2021- Late due to project not being funded for 2020 | '-122.170377 | 37.8467 | ETL.2720 | 40745865 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  | Reject | 2019-06-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117407845 | Not Scheduled | T2 DI PIT #3-PIT #1 000/005 RPR SPLS | 43877630 | PIT #3-PIT #1 | 000/005 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-01 | 2020-06-01 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.505227 | 40.9873 | ETL.5400 | 40762212 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408003 | Not Scheduled | T2 DI COT BEN #1 8/216 RPR GYWW | 43895726 | COTTONWOOD-BENTON #1 | 008/216 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2020-05-30 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.364132 | 40.4926 | ETL.6640 | 40616024 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408039 | Q2 | T2 DI CSCDE-BNTON-DSCHTS A8/167 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/167 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.258917 | 40.5586 | ETL.6310 | 40660592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408505 | Q2 | T3 DI PARADISE-TBL MTN 19/156L RPL POLE | 31453760 | PARADISE-TABLE MTN | 019/156 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-31 | 2019-11-30 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.553285 | 39.6864 | ETL.4316 | 44383197 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408507 | Q2 | T2 DI PARADISE-TBL MTN 6/55CC RPL STRW | 31453760 | PARADISE-TABLE MTN | 006/055CC | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-03 | 2020-06-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536794 | 39.5465 | ETL.4316 | 41184209 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408508 | Q2 | T3 DI PARADISE-TBL MTN 19/156R RPL STRW | 31453760 | PARADISE-TABLE MTN | 019/156 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-31 | 2019-11-30 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.553285 | 39.6864 | ETL.4316 | 44383198 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408587 | Q3 | T2 DI CARIBOU#2 16/11 INST HRDD | 43854201 | CARIBOU #2 | 016/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-01 | 2020-06-01 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.089685 | 40.0149 | ETL.6280 | 44217550 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408588 | Q2 | T2 DI HAT CRK #1 WES 18/351 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 018/351 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-05-30 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  | Email request sent to CIRT to DLFG. The down guys are attched by a 3rd party. Reference the placement of the down guys in the photos | CIRT can convert to LR if needed. | TR2 | LATE | North Valley | WSIP |  |  |  |  | CIRT | Tag to be DLFG. Non pge down guys. | '-121.297518 | 40.7605 | ETL.7030 | 40876270 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117408671 | Q2 | T2 DI PRDS-TBL MT 20/159L RPL POLE | 31453760 | PARADISE-TABLE MTN | 020/159 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-31 | 2020-05-31 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561043 | 39.6874 | ETL.4316 | 44383200 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408673 | Q2 | T2 DI PRDS-TBL MT 20/159R RPL POLE | 31453760 | PARADISE-TABLE MTN | 020/159 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-31 | 2020-05-31 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561043 | 39.6874 | ETL.4316 | 44383202 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408720 | Not Scheduled | T2 DI ROCK CREEK-POE 003/030 REPAINT | 43878133 | ROCK CREEK-POE | 003/030 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-24 | 2024-05-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.381175 | 39.8713 | ETL.5630 | 40608900 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408916 | Mar | T2 HUMBOLDT-TRINITY 059/002 RMV DEBRIS | 44311171 | HUMBOLDT-TRINITY | 059/002 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-30 | 2024-05-30 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.154046 | 40.7579 | ETL.1820 | 44560547 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408951 | Mar | T2 HUMBOLDT-TRINITY 060/001 RMV BUTTS | 43729542 | HUMBOLDT-TRINITY | 060/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-05-30 | 2024-05-30 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.167925 | 40.7509 | ETL.1820 | 44565330 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117408952 | Mar | T2 HUMBOLDT-TRINITY 52/04L RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 052/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-20 | 2024-05-20 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.054245 | 40.7433 | ETL.1820 | 44557451 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409006 | Q2 | T3 DI PARADISE-TBL MTN 22/172 RPL PL | 31453760 | PARADISE-TABLE MTN | 022/172 | 70Y | E | 2020_(1a) PSPS |  | 2019-06-03 | 2019-12-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383223 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117409007 | Q2 | T3 DI PARADISE-TBL MTN 22/172 RPL PL | 31453760 | PARADISE-TABLE MTN | 022/172 | 70Y | E | 2020_(1a) PSPS |  | 2019-06-03 | 2019-12-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383224 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117409031 | Feb | T2 BUCKS CRK-RCK CRK-CRSTA 6/52 RPL INSS | 31462237 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/052 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-28 | 2020-05-28 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.416699 | 39.8427 | ETL.4430 | 40726097 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Feb |  |  | 2019-08-29 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409052 | Not Scheduled | T2 DI WEIMAR-HALSEY 2/46 RPL STRW | 31454601 | WEIMAR-HALSEY | 002/046 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-04 | 2020-06-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.999683 | 39.0055 | ETL.8340 | 40824414 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409102 | Q2 | T3 DI PARADISE-TBL MTN 22/172 RPL PL | 31453760 | PARADISE-TABLE MTN | 022/172 | 70Y | E | 2020_(1a) PSPS |  | 2019-06-03 | 2019-12-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383225 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117409104 | Not Scheduled | T3 DI MIDDLE FORK#1 8/112 INS GYWW | 43852560 | MIDDLE FORK #1 | 008/112 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-03 | 2019-12-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.721797 | 39.0022 | ETL.8405 | 40611426 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409142 | Q2 | DI CSCDE-BNTN-DSCHUTS A009/188 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A009/188 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-29 | 2020-05-29 |  |  | 2021-04-30 | 2021-04-12 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.239968 | 40.5556 | ETL.6310 | 40868661 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409159 | Q2 | T2 DI TULE-SPRINGVILLE 017/010 RPR STRW | 44323688 | TULE-SPRINGVILLE | 017/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.838617 | 36.1104 | ETL.9040 | 40609770 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409294 | Mar | T2 DI TEJON-LEBEC 011/195 RPR GYWW | 43862364 | TEJON-LEBEC | 011/195 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-28 | 2021-05-31 |  |  | 2021-03-07 | 2021-03-06 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.889078 | 34.8712 | ETL.9250 | 40764570 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409596 | Q2 | T2 DI PARADISE-TBL MTN 25/192R RPL POLE | 31453760 | PARADISE-TABLE MTN | 025/192 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-07 | 2020-01-07 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.657896 | 39.7015 | ETL.4316 | 44383251 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409721 | Q2 | T2 DI PARADISE-TBL MT 006/055BB RPL POLE | 31453760 | PARADISE-TABLE MTN | 006/055BB | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-03 | 2020-06-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537116 | 39.5472 | ETL.4316 | 41184212 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117409914 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 020/238 INS MRKW | 43947609 | DRUM-SUMMIT #2 | 020/238 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-23 | 2020-05-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.449412 | 39.3179 | ETL.1450 | 44558961 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117413170 | Q2 | T2 DI PARADISE-TBL MT 006/055BC RPL POLE | 31453760 | PARADISE-TABLE MTN | 006/055BC | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-03 | 2020-06-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537064 | 39.5472 | ETL.4316 | 41184213 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416156 | Not Scheduled | T2 DI TESLA-METCALF 32/135 RPL INSS | 31460740 | TESLA-METCALF | 032/135 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-31 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.729081 | 37.2585 | ETL.6110 | 40782565 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416167 | Q2 | T2 DI PARADISE-TABLE MTN 6/55CA RPL STRW | 31453760 | PARADISE-TABLE MTN | 006/055CA | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-03 | 2020-06-03 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536926 | 39.5464 | ETL.4316 | 41184214 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416486 | Not Scheduled | T2 EI SLT SPRGS-TGR CRK 000/002 PNT STRS | 43852651 | SALT SPRINGS-TIGER CREEK | 000/002 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-06-05 | 2021-06-05 | [7 empty] | TR2 |  | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-120.220393 | 38.4965 | ETL.3500 | 40643380 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117416506 | Q2 | T2 DI MALIN-RND MTN#2 92/470A INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 092/470A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-31 | 2021-05-31 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.911181 | 40.831 | ETL.6020 | 41162774 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416607 | Not Scheduled | DI CARIBOU-PALERMO 1/12 BEMT MEMBER | 44069801 | CARIBOU-PALERMO | 001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-03 | 2020-06-03 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.541011 | 39.4665 | ETL.3190 | 40674849 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416620 | Not Scheduled | T2 DI DRUM-SMMT 8/101L RPL POLE | 31508705 | DRUM-SUMMIT #1 | 008/101 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-30 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.641466 | 39.3178 | ETL.1440 | 44768891 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416622 | Not Scheduled | 008/101 RIGHT SINGLE WOOD POLE | 31508705 | DRUM-SUMMIT #1 | 008/101 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-30 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.641466 | 39.3178 | ETL.1440 | 44768892 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117416687 | Q2 | EI HAT CRK #1-WESTWOOD 026/506 REPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 026/506 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-06 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.195935 | 40.672 | ETL.7030 | 40868480 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117417103 | Not Scheduled | T2NT DI PALERMO COLG C10/48 INST MRKS | 43900094 | PALERMO-COLGATE | C010/048 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-23 | 2020-05-23 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.38447 | 39.2988 | ETL.5360 | 40870439 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117417148 | Not Scheduled | T2NT DI POE-RIO OSO 024/162 PNT TWR | 43875008 | POE-RIO OSO | 024/162 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-28 | 2021-05-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.512229 | 39.6377 | ETL.5540 | 40673042 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117417247 | Not Scheduled | T2 DI PALERMO-COLGATE C10/46 INST MRKS | 43900094 | PALERMO-COLGATE | C010/046 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-05-24 | 2020-05-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.376645 | 39.3006 | ETL.5360 | 40815687 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117418273 | Not Scheduled | DI DRUM-SUMMIT #1 023/278R RPL PL | 31498145 | DRUM-SUMMIT #1 | 023/278 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-02 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.388359 | 39.3113 | ETL.1440 | 44767636 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117418464 | Not Scheduled | T2 EXCHEQUER-YOSEMITE 000/001A INST GMKS | 43863013 | EXCHEQUER-YOSEMITE | 000/001A | ICS | F | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2021-06-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-119.986024 | 37.5935 | ETL.8650 | 43250171 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 36 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117418499 | Not Scheduled | EI VALLEY SPRINGS #1 010/212 RPR STRW | 44290816 | VALLEY SPRINGS #1 | 010/212 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.8986 | 38.1147 | ETL.8210 | 40908297 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117418939 | Not Scheduled | T3 DI CARIBOU-PALERMO :031/251 HANGER | 44304491 | CARIBOU-PALERMO | :031/251 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-06 | 2019-12-06 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.460406 | 39.7663 | ETL.3190 | 40591572 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117418972 | Not Scheduled | T3 DI CARIBOU-PALERMO :031/251 REPR STRT | 44056495 | CARIBOU-PALERMO | :031/251 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-06 | 2019-12-06 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.460406 | 39.7663 | ETL.3190 | 40591572 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117419112 | Q2 | T2 DI BALCH-SANGER 006/036 RPR STRS | 43845834 | BALCH-SANGER | 006/036 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-06 | 2020-06-06 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.165481 | 36.8888 | ETL.1050 | 40807129 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427060 | Not Scheduled | DI CARIBOU-PALERMO 1/14 RPL HRDS | 44069801 | CARIBOU-PALERMO | 001/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2020-06-04 | [8 empty] | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.540504 | 39.4726 | ETL.3190 | 40793708 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427062 | Mar | DI PALERMO-OROVILLE #2 1/17 RPL INSS | 31486385 | PALERMO-OROVILLE #2 | 001/017 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-04 | 2020-06-04 |  |  | 2021-03-04 | 2021-03-04 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.539763 | 39.4683 | ETL.7740 | 42577600 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427063 | Not Scheduled | T2NT DI PARADISE-TBL MTN 12/107 PNT TWR | 43727174 | PARADISE-TABLE MTN | 012/107 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.511181 | 39.6384 | ETL.4316 | 40819272 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427064 | Not Scheduled | DI CARIBOU-PALERMO 1/14 RMV VEGN | 44070463 | CARIBOU-PALERMO | 001/014 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-04 | 2020-06-04 | [6 empty] | Likely veg |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427066 | Not Scheduled | DI CARIBOU-PALERMO 1/14 INS HRDS | 44070463 | CARIBOU-PALERMO | 001/014 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-04 | 2020-06-04 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427069 | Not Scheduled | DI CARIBOU-PALERMO 1/14 RPR STRT | 44069801 | CARIBOU-PALERMO | 001/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2020-06-04 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427071 | Not Scheduled | T2NT DI MLN-RND MTN #2 060/298 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 060/298 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-05-30 | 2021-05-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.650135 | 41.2114 | ETL.6020 | 40868963 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427085 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 010/127 RPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/127 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-05-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44212219 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-06-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427321 | Not Scheduled | T2 DI WEIMAR-HALSEY 005/118 RPL STRW | 31509756 | WEIMAR-HALSEY | 005/118 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-04 | 2020-06-04 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.032831 | 38.9675 | ETL.8340 | 40693594 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-10-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427435 | Q2 | DI CSCD-BNTN-DSCHTS A005/109 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/109 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2020-05-30 |  |  | 2021-04-30 | 2021-04-12 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.297935 | 40.5886 | ETL.6310 | 40759316 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427711 | Mar | DI CLEAR LAKE-HOPLAND 0/1 REPL PL | 31471834 | CLEAR LAKE-HOPLAND | 000/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-05 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.080952 | 38.973 | ETL.6390 | 40584484 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117427728 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/254C REPL POLE | 31453742 | DRUM-SUMMIT #2 | 021/254 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-07 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553513 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117428416 | Mar | T2NT DI TABLE MTN-PALERMO 9/44 INST HV | 44154424 | TABLE MTN-PALERMO | 009/044 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-04 | 2021-06-04 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.502375 | 39.5196 | ETL.5690 | 40753651 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117428419 | Feb | T3 DI KILARC-CEDAR CRK 7/163 RPL PL | 31496893 | KILARC-CEDAR CREEK | 007/163 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2019-12-04 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.000577 | 40.717 | ETL.7290 | 40759575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117428613 | Mar | T2 DI MNDCN-WLLTS-FRT BRGG 39/4 RPR INSW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 039/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-03 | 2020-06-03 | 2020-09-07 | 2020-09-10 | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.749607 | 39.4148 | ETL.7550 | 40750970 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117428619 | Mar | T2 DI MNDCN-WLLTS-FRT BRGG 39/4 RPR CRSW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 039/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-03 | 2020-06-03 | 2020-09-07 | 2020-09-10 | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.749607 | 39.4148 | ETL.7550 | 40750970 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117428878 | Not Scheduled | T2 DI APPLE HILL #2 TAP 000/016 RPL STRW | 31423866 | APPLE HILL #2 TAP | 000/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.682448 | 38.7491 | ETL.1541 | 40804792 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-03-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117429241 | Q2 | T2 DI SBRNT-GRZZL-CLRMNT#1 6/54 BENT MBR | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 006/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-05 | 2020-06-05 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.228018 | 37.8479 | ETL.3740 | 40580980 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117429345 | Not Scheduled | T3 DI DEER CREEK-DRUM 5/137 REM VEG |  | DEER CREEK-DRUM | 005/137 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-03 | 2019-12-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.776436 | 39.2601 | ETL.6690 | 40874914 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117429391 | Not Scheduled | T2 DI HAT CRK#1-PIT#1 6/82 RPR GYWW | 43685158 | HAT CREEK #1-PIT #1 | 006/082 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-05 | 2020-06-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.544773 | 40.9291 | ETL.7020 | 41149286 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117429411 | Not Scheduled | T3NT DI TGER CRK-VLLY SPRNGS 0/1 REPAINT | 43852921 | TIGER CREEK-VALLEY SPRINGS | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-30 | 2021-05-30 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.493507 | 38.4517 | ETL.5790 | 40596593 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117429470 | Q2 | T2NT DI MALIN-RND MTN #2 79/404 INS GMKW | 43621093 | MALIN-ROUND MTN #2 | 079/404 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-06 | 2021-06-06 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.893581 | 41.0085 | ETL.6020 | 40745485 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117429554 | Not Scheduled | T2NT DI MALIN-RND MTN #2 80/407 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 080/407 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-06 | 2022-06-06 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.896068 | 41.0026 | ETL.6020 | 40810966 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-28 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117430095 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/087 REPR INSS | 44304491 | CARIBOU-PALERMO | :011/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2019-12-07 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280057 | 39.9886 | ETL.3190 | 40910327 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117430536 | Not Scheduled | T2NT DI OLEUM-G #1 2/16 REPAINT | 44586166 | OLEUM-G #1 | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-05-30 | 2021-05-30 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.234101 | 38.0277 | ETL.3150 | 40804783 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117430539 | Mar | T3 DI DRUM-HIGGINS 009/093 REPR GYWW | 43852139 | DRUM-HIGGINS | 009/093 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2019-12-10 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8911 | 39.1763 | ETL.4393 | 44172115 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117430611 | Q2 | T2 EI CORDELIA #2 003/061A REPL STRW | 31454608 | CORDELIA #2 TAP | 003/061A | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2020-06-10 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147987 | 38.2445 | ETL.8184 | 40577175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117430834 | Mar | T2 DI MTN QUARRIES TAP 0/19 RPR GYWW | 43869988 | MTN QUARRIES TAP | 000/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-05 | 2020-06-05 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.049617 | 38.9145 | ETL.6991 | 40589600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117431594 | Q3 | T2 HMILTON BRNCH-CHSTER 0/014 RPL STRW | 31454645 | HAMILTON BRANCH-CHESTER | 000/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2020-06-04 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.083582 | 40.2744 | ETL.7000 | 40701185 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117431622 | Mar | T2 DI CLEAR LAKE-HOPLAND 1/4 RPL PL | 31501061 | CLEAR LAKE-HOPLAND | 001/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.058481 | 38.9685 | ETL.6390 | 40750154 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117431690 | Not Scheduled | T3NT DI MRGA-SN LNDRO #3 003/021 REPAINT | 43728142 | MORAGA-SAN LEANDRO #3 | 003/021 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) | 2019-05-31 | 2023-05-31 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.138206 | 37.8142 | ETL.2790 | 40580824 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117432050 | Feb | T2 DI COLEMAN-SOUTH 7/156 RPR JUMW | 43930460 | COLEMAN-SOUTH | 007/156 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2021-05-31 |  |  | 2021-02-12 | 2021-02-12 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.008965 | 40.4031 | ETL.6450 | 40721962 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-02-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117432432 | Not Scheduled | T3NT DI DESABLA-CENTERVILLE 0/0 PNT STRS | 43854279 | DESABLA-CENTERVILLE | 000/000 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-07 | 2022-06-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.631584 | 39.8689 | ETL.6720 | 44181036 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117432704 | Not Scheduled | DI SPAULDING-SUMMIT 8/269 INST MRKW | 43923448 | SPAULDING-SUMMIT | 008/269 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-05 | 2020-06-05 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.519483 | 39.3113 | ETL.8060 | 40586093 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117432757 | Not Scheduled | DI TRACY-LOS BANOS 008/043 RPL RPTS | 43851677 | TRACY-LOS BANOS | 008/043 | ICB | E | Pre-2020_(9a) Other ignition related |  | 2019-06-06 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.532636 | 37.6926 | ETL.6130 | 40651814 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Released |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117432773 | Mar | T2 DI KONOCTI-MIDDLETOWN 12/1A RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 012/001A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2020-06-07 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609195 | 38.7532 | ETL.6380 | 44371580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117432814 | Q2 | T2 DI LWR LK-HMSTK 13/13 BOND SPLIT BOLT | 43865623 | LOWER LAKE-HOMESTAKE TAP | 013/013 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-06 | 2021-05-31 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-05-12 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.411565 | 38.8623 | ETL.1481 | 40648971 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-02 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31