2021 Work Plan | 119315457 | Mar | T2 EI KILARC-DESCHUTES 10/222 RPR WPKR | 44406470 | KILARC-DESCHUTES | 010/222 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.01582 | 40.5777 | ETL.7300 | 40770437 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315619 | Q2 | T2 EI TRINITY-MAPLE CREEK 0/17 RPL INSW | 31512233 | TRINITY-MAPLE CREEK | 000/017 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.945835 | 40.7226 | ETL.8170 | 40906237 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315721 | Mar | T2 EI KILARC-DESCHUTES 9/195 RPR WDPKR | 44406470 | KILARC-DESCHUTES | 009/195 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.996602 | 40.5865 | ETL.7300 | 40617788 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315764 | Q3 | T2 DI CARIBOU-PLUMAS JCT 14/11 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 014/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.948979 | 39.9571 | ETL.6290 | 40585993 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315970 | Q3 | T2 DI CARIBOU-PLUMAS JCT 13/8 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 013/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.969171 | 39.9636 | ETL.6290 | 40862078 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316064 | Q2 | T2 EI WEIMAR #1 1/028 RPL PL | 31511049 | WEIMAR #1 | 001/028 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.968922 | 39.0294 | ETL.7560 | 40913136 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316085 | Mar | T2 EI EAGLE ROCK-CORTINA 15/002 RE-PLUMB | 44563312 | EAGLE ROCK-CORTINA | :015/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608593 | 38.9389 | ETL.1470 | 41176327 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316104 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 21/087 RPR GYWS |  | DIABLO-MIDWAY #3 | 021/087 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.486434 | 35.1655 | ETL.5980 | 40821269 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316106 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 82/419B RPR GYW |  | MALIN-ROUND MTN #2 | 082/419B |  | E | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.914197 | 40.9704 | ETL.6020 | 41162606 | Guy Pole-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316108 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 83/421 RPR GYWS |  | MALIN-ROUND MTN #2 | 083/421 |  | E | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.914326 | 40.9646 | ETL.6020 | 40595124 | Guy Pole-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316129 | Not Scheduled | T3 EI FULTON-HOPLAND 27/006 RPR POLE | 44579280 | FULTON-HOPLAND | 027/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-01-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.995965 | 38.8177 | ETL.6890 | 40817808 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316214 | Q3 | T2 DI CARIBOU-PLUMAS JCT 15/3 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 015/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.939714 | 39.9572 | ETL.6290 | 40649936 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316345 | Q4 | T2 EI KESWICK-TRINITY 21/315 RMV STEPS | 44406439 | KESWICK-TRINITY | 021/315 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.775255 | 40.7177 | ETL.7270 | 44649264 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316422 | Q3 | T2 BRIDGEVILLE-COTTONWD 73/529 INST DAMT | 44398374 | BRIDGEVILLE-COTTONWOOD | 073/529 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.561352 | 40.4781 | ETL.1110 | 40657077 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316613 | Not Scheduled | T2NT DI SPAULDING-SUMM 16/512 RMV PL BUT | 44402361 | SPAULDING-SUMMIT | 016/512 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378387 | 39.3163 | ETL.8060 | 40878079 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316619 | Q4 | T2 DI KESWICK-TRINITY 26/436 RMV BUTT | 43939188 | KESWICK-TRINITY | 026/436 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.860795 | 40.6953 | ETL.7270 | 40906096 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316861 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 17/541 INS MRKW | 44402132 | SPAULDING-SUMMIT | 017/541 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.36247 | 39.3097 | ETL.8060 | 44167349 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316893 | Q2 | T2 EI BRDGVLLE-CTTNWD 13/126L RPL STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 013/126 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5235134 | 40.3952 | ETL.1110 | 44424468 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316894 | Q2 | T2 EI BRDGVLLE-CTTNWD 13/126C RPL STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 013/126 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5235134 | 40.3952 | ETL.1110 | 44424469 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316895 | Q2 | T2 EI BRDGVLLE-CTTNWD 13/126R RPL STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 013/126 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5235134 | 40.3952 | ETL.1110 | 44424470 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316903 | Mar | T2 EI EAGLE ROCK-CORTINA :14/18 RPR POLE | 44563312 | EAGLE ROCK-CORTINA | :014/018 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.609317 | 38.936 | ETL.1470 | 41176321 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316925 | Q2 | T3 EI MRGN HLL JCT-GRN VLY NC 5/45 RPR S | 44438217 | GREEN VALLEY-LLAGAS | 005/045 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.7192661 | 37.0266 | ETL.1720 | 44513709 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119316932 | Q4 | T2 EI KESWICK-TRINITY 22/332 RMV PL BUT | 44406439 | KESWICK-TRINITY | 022/332 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.789966 | 40.7198 | ETL.7270 | 40909524 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317045 | Mar | T3 EI DRUM-GRASS VALY-WEIMAR 5/134 REPLU | 44379638 | DRUM-GRASS VALLEY-WEIMAR | 005/134 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.818654 | 39.2119 | ETL.6760 | 40693432 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317062 | Mar | T2 EI KILARC-DESCHUTES 11/239 RPR WDPKR | 44406470 | KILARC-DESCHUTES | 011/239 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.022578 | 40.5709 | ETL.7300 | 40617697 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317125 | Q2 | T2 EI TRINITY-MAPLE CREEK 34/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 034/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.52578 | 40.7103 | ETL.8170 | 40602155 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317128 | Q2 | T2 EI TRINITY-MAPLE CREEK 34/1 RMV PL BU | 44299848 | TRINITY-MAPLE CREEK | 034/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.52578 | 40.7103 | ETL.8170 | 40602155 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317137 | Q2 | T2NT EI MLN-RND MT #2 74/375B INST MRKS | 44305271 | MALIN-ROUND MTN #2 | 074/375B | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.838081 | 41.0698 | ETL.6020 | 41162683 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317139 | Q2 | T2NT EI MLN-RND MTN #2 74/375A INST MRKS | 44305271 | MALIN-ROUND MTN #2 | 074/375A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.837978 | 41.0697 | ETL.6020 | 41162687 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317152 | Q2 | EI TRINITY-MAPLE CREEK 31/0C RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 031/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.4699875 | 40.6908 | ETL.8170 | 44420660 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317154 | Q2 | EI TRINITY-MAPLE CREEK 31/0L RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 031/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.4699875 | 40.6908 | ETL.8170 | 44420659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317186 | Q2 | EI BRIDGEVIL COTONWOD 013/127 RMV PL BUT | 44404807 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424421 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317187 | Q2 | T2 EI BRIDGEVILLE-COTTNWD 13/127L RPR GY | 44404807 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424421 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317223 | Q2 | T2 EI TRINITY-MAPLE CREEK 30/4 RPR JUMPE | 44401954 | TRINITY-MAPLE CREEK | 030/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.466826 | 40.6917 | ETL.8170 | 40906462 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317227 | Q2 | T2 EI TRINITY-MAPLE CREEK 30/4 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 030/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.466826 | 40.6917 | ETL.8170 | 40906462 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317238 | Q2 | EI TRINITY-MAPLE CREEK 30/2 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 030/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.4615698 | 40.693 | ETL.8170 | 44567299 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317260 | Q2 | T2 EI TRINITY-MAPLE CREEK 30/3 RPL POLE | 31512223 | TRINITY-MAPLE CREEK | 030/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.463254 | 40.6926 | ETL.8170 | 40906460 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317263 | Q2 | EI T2NT TRINITY-MAPLE CREEK 30/004 RMV B | 44401994 | TRINITY-MAPLE CREEK | 030/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.466826 | 40.6917 | ETL.8170 | 40906462 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317279 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 13/127C RPR G | 44404807 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424422 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317344 | Q3 | T2NT DI CARIBOU-PLUMAS JCT 11/4 RMV BUTT | 44408852 | CARIBOU-PLUMAS JCT | 011/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.001994 | 39.9839 | ETL.6290 | 40758737 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317378 | Q2 | T2 EI HAT CRK #1-WESTWD 41/786 RPR ANCW | 44406426 | HAT CREEK #1-WESTWOOD | 041/786 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.028985 | 40.5051 | ETL.7030 | 40591882 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317383 | Q2 | T2 EI HAT CREEK #1-WESTWD 40/780 RPR INS | 44406426 | HAT CREEK #1-WESTWOOD | 040/780 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.030857 | 40.5095 | ETL.7030 | 40770769 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317386 | Q2 | T2 EI HAT CREEK #1-WSTWD 40/776 RPR STRW | 44406426 | HAT CREEK #1-WESTWOOD | 040/776 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.032147 | 40.5124 | ETL.7030 | 40616927 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317387 | Q2 | T2 EI HAT CREEK #1-WESTWD 40/770 RPR IN | 44406426 | HAT CREEK #1-WESTWOOD | 040/770 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.033997 | 40.5168 | ETL.7030 | 44311023 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317389 | Q2 | T2 EI HAT CREEK #1-WESTWD 40/779 INST HR | 44406426 | HAT CREEK #1-WESTWOOD | 040/779 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.031144 | 40.5102 | ETL.7030 | 44311024 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317391 | Q2 | EI T2NT HT CRK #1-WSTWD 40/776 RMV DEBRI | 44406426 | HAT CREEK #1-WESTWOOD | 040/776 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.032147 | 40.5124 | ETL.7030 | 40616927 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317394 | Not Scheduled | T3 EI FRNCH MDWS-MDDLE FRK 0/11 RPR GYWW | 44380540 | FRENCH MEADOWS-MIDDLE FORK | 000/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.414842 | 39.0766 | ETL.6870 | 40598777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317402 | Q2 | T2 EI HAT CRK #1-WESTWD 40/778 RPR STRW | 44406426 | HAT CREEK #1-WESTWOOD | 040/778 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.031487 | 40.511 | ETL.7030 | 40701319 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317412 | Q2 | T2 EI BRIDGEVLLE-COTTONWD 13/127R RPR GY | 44404807 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424423 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317426 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 13/127R RPR S | 44404807 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424423 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317500 | Q4 | T2 EI KESWICK-TRINITY 22/351 RMV PL BUTT | 44406439 | KESWICK-TRINITY | 022/351 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.803619 | 40.7156 | ETL.7270 | 40909534 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317502 | Q4 | T2NT DI KSWCK-TRNTY 22/335 RMV BUTT | 43939188 | KESWICK-TRINITY | 022/335 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.793548 | 40.7193 | ETL.7270 | 40906072 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317515 | Mar | T2 EI KILARC-DESCHUTES 15/330 RPR STRW | 44406470 | KILARC-DESCHUTES | 015/330 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.108495 | 40.5635 | ETL.7300 | 40877874 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317516 | Mar | T2 EI KILARC-DESCHUTES 15/321 RPL PL | 31509538 | KILARC-DESCHUTES | 015/321 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.100129 | 40.5637 | ETL.7300 | 40876510 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317519 | Mar | EI T2NT KILARC-DESCHUTES 15/321 RMV BUTT | 44406470 | KILARC-DESCHUTES | 015/321 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.100129 | 40.5637 | ETL.7300 | 40876510 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317599 | Q3 | T2 DI CARIBOU-PLUMAS JCT 8/000 RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | 008/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.051903 | 40.0083 | ETL.6290 | 40614982 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317620 | Q3 | T2 DI CARIBOU-PLUMAS JCT 13/1 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 013/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.976307 | 39.9676 | ETL.6290 | 40585991 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317622 | Q3 | T2 DI CRBU-PLUMAS JCT 13/000 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 013/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.977216 | 39.968 | ETL.6290 | 40614953 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317648 | Q2 | EI HAT CRK #1-WESTWD 49/961 RPL POLE | 31527025 | HAT CREEK #1-WESTWOOD | 049/961 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.015118 | 40.3777 | ETL.7030 | 40825622 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317663 | Q2 | EI HAT CREEK #1-WESTWOO 50/964 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 050/964 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.014732 | 40.3754 | ETL.7030 | 40591897 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317666 | Q2 | EI HAT CREEK #1-WESTWOOD 49/959 RPL CRSW | 31508175 | HAT CREEK #1-WESTWOOD | 049/959 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.015363 | 40.3792 | ETL.7030 | 40770056 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317749 | Q4 | T2NT DI KSWCK-TRNTY 19/283 RMV DEBRIS | 43939188 | KESWICK-TRINITY | 019/283 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.745358 | 40.7169 | ETL.7270 | 40827895 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317807 | Not Scheduled | DI TEMBLOR-SLO 27/163 RPL INSW | 31509625 | TEMBLOR-SAN LUIS OBISPO | 027/163 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 | [9 empty] | South | WSIP | [6 empty] | '-119.913044 | 35.3775 | ETL.3960 | 40678298 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317830 | Q2 | T2 DI TRNTY-MPLE CRK 40/0C RPL POL | 31509758 | TRINITY-MAPLE CREEK | 040/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.626398 | 40.72 | ETL.8170 | 44769586 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119317901 | Not Scheduled | T2 DI DRUM-SUMMIT #1 21/252 RMV PL BUTT | 44403319 | DRUM-SUMMIT #1 | 021/252 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.426416 | 39.3159 | ETL.1440 | 44338240 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119318136 | Q4 | T2 EI KESWICK-TRINITY 22/350 RPR POLE | 43939188 | KESWICK-TRINITY | 022/350 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.803438 | 40.7159 | ETL.7270 | 40906080 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119318193 | Q2 | T2 DI TRINTY-MAPLE CREEK 35/4L RPL STRW | 31509757 | TRINITY-MAPLE CREEK | 035/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.549178 | 40.7211 | ETL.8170 | 44565474 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119318194 | Q2 | T2 DI TRINTY-MAPLE CREEK 35/4C RPL STRW | 31509757 | TRINITY-MAPLE CREEK | 035/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.549178 | 40.7211 | ETL.8170 | 44565620 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119318196 | Q2 | T3 DI DRUM-HIGGINS 2/27R RPL STRW | 31423108 | DRUM-HIGGINS | 002/027 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.795057 | 39.2286 | ETL.4393 | 44172274 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119318231 | Q4 | T2 EI KESWICK-TRINITY 22/337 RMV PL BUTT | 44406439 | KESWICK-TRINITY | 022/337 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-07 | 2022-07-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.795265 | 40.7191 | ETL.7270 | 40906074 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323203 | Q4 | T2 DI KESWICK-TRINITY 28/486 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 028/486 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.897049 | 40.7092 | ETL.7270 | 44201732 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323344 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 21/88 RPL INSS | 31527002 | DIABLO-MIDWAY #2 | 021/088 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4811391 | 35.1639 | ETL.5970 | 40897218 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323606 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 14/129 RMV PL B | 44404807 | BRIDGEVILLE-COTTONWOOD | 014/129 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.531514 | 40.3943 | ETL.1110 | 44423275 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323737 | Mar | T2 EI KILARC-DESCHUTES 20/414 REFRAME | 31506150 | KILARC-DESCHUTES | 020/414 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.189564 | 40.5637 | ETL.7300 | 40771242 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323753 | Q2 | EI T2NT BRDGVLLE-CTTNWD 14/128 RMV PL BU | 44404807 | BRIDGEVILLE-COTTONWOOD | 014/128 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2022-07-07 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.529472 | 40.3948 | ETL.1110 | 44423306 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323829 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/25 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/025 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633724 | 39.3223 | ETL.8060 | 40751891 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119323835 | Not Scheduled | T3 EI BRUNSWICK #1 TAP 0/002 RPL HRDT | 44388503 | BRUNSWICK #1 TAP | 000/002 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-01-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.007122 | 39.1417 | ETL.1422 | 40660195 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324006 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/22 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/022 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.635795 | 39.3227 | ETL.8060 | 40702045 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324052 | Not Scheduled | EI T2NT MALIN-ROUND MTN #2 58/290 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 058/290 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.635598 | 41.2293 | ETL.6020 | 40592110 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324053 | Q2 | EI T2NT MLIN-RND MTN #2 58/289 INST GY M | 44408444 | MALIN-ROUND MTN #2 | 058/289 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.633626 | 41.2318 | ETL.6020 | 40868279 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324067 | Not Scheduled | T2 EI BLACK TAP 0/1 RPR GYWS | 44304022 | BLACK TAP | 000/001 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.974507 | 40.9911 | ETL.5431 | 40586415 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324074 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 22/090 RPLC INST | 31527002 | DIABLO-MIDWAY #2 | 022/090 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4720012 | 35.1622 | ETL.5970 | 40636714 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324080 | Not Scheduled | T2 EI BLACK TAP 000/001 RMV NEST | 44304022 | BLACK TAP | 000/001 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.974507 | 40.9911 | ETL.5431 | 40586415 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324122 | Q2 | T3 DI DRUM-SPAULDING 1/24 RPL INSW | 31508601 | DRUM-SPAULDING | 001/024 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.751796 | 39.2521 | ETL.6770 | 44874816 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324353 | Q3 | T2 EI CARIBOU-WESTWD 2/044 RPR GYWW |  | CARIBOU-WESTWOOD | 002/044 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.126605 | 40.1071 | ETL.6300 | 40751773 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324455 | Not Scheduled | T2 DI SPAULDING-SUMMIT 16/505 CANCEL | 44403403 | SPAULDING-SUMMIT | 016/505 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378971 | 39.3201 | ETL.8060 | 40660174 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324458 | Q4 | T2 DI KESWICK-TRINITY 21/323 RMV BUTT | 43939188 | KESWICK-TRINITY | 021/323 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.779905 | 40.7183 | ETL.7270 | 40909517 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324515 | Q2 | EI DRUM-HIGGINS 2/30 RPL POLE | 31509929 | DRUM-HIGGINS | 002/030 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-03 | 2021-03-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.7980123 | 39.2251 | ETL.4393 | 44172186 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324531 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/9 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/009 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.641098 | 39.3241 | ETL.8060 | 40861964 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324535 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/15 RMV PL BUTT | 44409175 | SPAULDING-SUMMIT | 000/015 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.639096 | 39.3233 | ETL.8060 | 40753993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324543 | Mar | T2 EI KILARC-DESCHUTES A23/485 RMV BUTT | 44406470 | KILARC-DESCHUTES | A023/485 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.247467 | 40.5638 | ETL.7300 | 40813410 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324545 | Mar | T2 EI KILARC-DESCHUTES A23/485 REFRAME | 44406470 | KILARC-DESCHUTES | A023/485 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.247467 | 40.5638 | ETL.7300 | 40813410 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324570 | Q4 | T2 DI KESWICK-TRINITY 21/323 RPLC INSW | 31508091 | KESWICK-TRINITY | 021/323 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.77977 | 40.7183 | ETL.7270 | 40919256 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324700 | Not Scheduled | T3 EI FULTON-HOPLAND :27/0 RPL POLE | 31508165 | FULTON-HOPLAND | :027/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-01-07 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.986797 | 38.798 | ETL.6890 | 40587798 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324771 | Q2 | T2 EI EAGLE ROCK-CORTINA 14/003 RPLC POL | 31509667 | EAGLE ROCK-CORTINA | :014/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.607763 | 38.9254 | ETL.1470 | 41176306 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324891 | Q2 | T2 EI FORT ROSS-GUALALA 048/014 RPL DAMP |  | GUALALA-MONTE RIO | 048/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.393307 | 38.719 | ETL.6980 | 40750356 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324896 | Q2 | T3 EI DRUM-HIGGINS 03/041L RPL POLE | 31509929 | DRUM-HIGGINS | 003/041 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-01-06 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8152821 | 39.2191 | ETL.4393 | 44172193 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324967 | Q4 | T2 DI KESWICK-TRINITY 16/214 RPR STRW | 43939188 | KESWICK-TRINITY | 016/214 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.69117 | 40.7204 | ETL.7270 | 40668383 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119324988 | Not Scheduled | T2 DI SPAULDING-SUMMIT 16/510 RPL STRW | 31508176 | SPAULDING-SUMMIT | 016/510 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378547 | 39.3174 | ETL.8060 | 40828154 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119325028 | Q3 | T2 EI CARIBOU-WESTWOOD 0/013A RPL STRW | 31508283 | CARIBOU-WESTWOOD | 000/013A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.145365 | 40.0913 | ETL.6300 | 40698983 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325029 | Q3 | T2 EI CARIBOU-WESTWOOD 0/013B RPL STRW | 31508283 | CARIBOU-WESTWOOD | 000/013 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.14533 | 40.0912 | ETL.6300 | 42624166 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325040 | Q3 | T2 EI CARIBOU-WESTWOOD 0/013C RPL STRW | 31508283 | CARIBOU-WESTWOOD | 000/013C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.145292 | 40.0912 | ETL.6300 | 42624167 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325046 | Q2 | T2 EI IGNACIO-BOLINAS #2 08/111 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 008/111 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.668783 | 38.1172 | ETL.7180 | 40585472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325121 | Mar | T3 EI DRUM-GRSS VLLY-WMAR 4/103 RPL STRW | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 004/103 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.802508 | 39.2187 | ETL.6760 | 40693327 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325285 | Q3 | BRDGVLLE-CTTNWD 75/537 RPL DAMPERS | 44404807 | BRIDGEVILLE-COTTONWOOD | 075/537 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.586364 | 40.4903 | ETL.1110 | 40634787 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325286 | Q3 | T2 EI DI BRDGVL-CTTNWD 74/536 RPL DAMPER | 43939216 | BRIDGEVILLE-COTTONWOOD | 074/536 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5846825 | 40.4895 | ETL.1110 | 44424365 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325295 | Q3 | T2 EI CARIBU-WSTWD 1/031A INST ARMOR ROD |  | CARIBOU-WESTWOOD | 001/031A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.128261 | 40.0979 | ETL.6300 | 40875472 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325304 | Q4 | T2 DI KESWICK-TRINITY 24/374 RPR INSW | 43939188 | KESWICK-TRINITY | 024/374 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.821089 | 40.7096 | ETL.7270 | 40919162 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325306 | Q2 | T2 DI IGNACIO-BOLINAS #2 13/160 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 013/160 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7180 | 44360911 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325308 | Q2 | T2 DI IGNACIO-BOLINAS #2 13/160 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 013/160 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7180 | 44360912 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325309 | Q2 | T2 DI IGNACIO-BOLINAS #2 13/160 BOND GUY | 44640732 | IGNACIO-BOLINAS #2 | 013/160 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7180 | 44360913 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325418 | Q2 | T2 EI EAGLE ROCK-CORTINA :14/001 RPR POL | 44563312 | EAGLE ROCK-CORTINA | :014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.607904 | 38.9246 | ETL.1470 | 41176304 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325422 | Q2 | T2 EI EAGLE ROCK-CORTINA :14/1 RPR GYWW | 44563312 | EAGLE ROCK-CORTINA | :014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.607904 | 38.9246 | ETL.1470 | 41176304 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325436 | Not Scheduled | T2 DI SAN LUIS OBISPO-CAY 8/64 RPR GYWW |  | SAN LUIS OBISPO-CAYUCOS | 008/064 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.692751 | 35.3196 | ETL.9090 | 40679125 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325439 | Feb | T3 DI DESABLA-CENTERVILL 1/21 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 001/021 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.630552 | 39.8523 | ETL.6720 | 44893476 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325462 | Mar | T3 DI DEER CREEK-DRUM 5/143 RPR SPLW | 44382781 | DEER CREEK-DRUM | 005/143 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.772054 | 39.2598 | ETL.6690 | 40757028 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325483 | Q3 | T2 EI CARIBOU #2 000/001 RPR GYWW |  | CARIBOU #2 | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.147408 | 40.0853 | ETL.6280 | 40585963 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325490 | Mar | GREEN VALLEY-LLAGAS-WD 6/49 RPLC INSW | 31509577 | GREEN VALLEY-LLAGAS | 006/049 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 | 2021-03-09 | 2021-03-11 | 2021-03-11 | 2021-03-09 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.714987 | 37.0323 | ETL.1720 | 40893776 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325547 | Q3 | EI BRIDGEVILE-COTONWD 072/523 RMV DEBRI | 44404807 | BRIDGEVILLE-COTTONWOOD | 072/523 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-07 | 2022-07-07 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5485234 | 40.4718 | ETL.1110 | 44424377 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325563 | Not Scheduled | T2 EI BRIDGEVILLE-COTTNWD 50/383 RMV VEG |  | BRIDGEVILLE-COTTONWOOD | 050/383 | HNA | E | 2020_(3) On high spread structure |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.207355 | 40.4166 | ETL.1110 | 40761532 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325631 | Feb | T3NT DI DESABLA-CENTERVIL 1/21 RMV BUTT |  | DESABLA-CENTERVILLE | 001/021 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.630552 | 39.8523 | ETL.6720 | 44893476 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325635 | Q4 | T2NT DI KESWICK-TRINITY 19/284 RMV BUTT | 43939188 | KESWICK-TRINITY | 019/284 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.746688 | 40.7167 | ETL.7270 | 40815299 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325730 | Q3 | T2 DI CARIBOU-PLUMAS JCT 11/3 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 011/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.002952 | 39.9844 | ETL.6290 | 40666908 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325733 | Q3 | T2 DI CARIBOU-PLUMAS JCT 13/4 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 013/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.973568 | 39.966 | ETL.6290 | 40769607 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325815 | Not Scheduled | EI T2NT BLACK TAP 0/2 RMV HRDT |  | BLACK TAP | 000/002 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.976527 | 40.9899 | ETL.5431 | 44188818 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325842 | Q2 | T2 EI IGNACIO-BOLINAS #2 9/114 RPL ANCHO | 31508167 | IGNACIO-BOLINAS #2 | 009/114 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.673265 | 38.1157 | ETL.7180 | 40751211 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325857 | Q2 | T2 EI EAGLE ROCK-CORTINA :13/21 RPR GYWW | 44563312 | EAGLE ROCK-CORTINA | :013/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.609054 | 38.9233 | ETL.1470 | 41176302 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325861 | Mar | T3 EI DRUM-RIO OSO #2 10/101 RMV STEP | 44388507 | DRUM-RIO OSO #2 | 010/101 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.92093 | 39.1749 | ETL.1430 | 40590518 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325901 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/8 RMV STUB | 44409514 | SPAULDING-SUMMIT | 000/008 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.641512 | 39.3243 | ETL.8060 | 40862199 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325902 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/4 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/004 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.643615 | 39.3247 | ETL.8060 | 40771546 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119325948 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/30 RMV PL BUTT | 44409175 | SPAULDING-SUMMIT | 000/030 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.630861 | 39.3218 | ETL.8060 | 40590059 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326061 | Q2 | EI HUMBOLDT-BRIDGEVILLE 91/4 RPR ADSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 091/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8370683 | 40.5485 | ETL.1810 | 44322303 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326091 | Q2 | T2 EI EAGLE ROCK-CORTINA :13/20 RPR GYWW | 44563312 | EAGLE ROCK-CORTINA | :013/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.609573 | 38.9228 | ETL.1470 | 41176300 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326180 | Not Scheduled | T2 DI SPAULDING-SUMMIT 000/030 RPL INSW | 31507463 | SPAULDING-SUMMIT | 000/030 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.630928 | 39.3218 | ETL.8060 | 40630493 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326464 | Q3 | T2 DI CARIBOU-WESTWOOD 8/156 RPR GYWW |  | CARIBOU-WESTWOOD | 008/156 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.079853 | 40.1791 | ETL.6300 | 40862085 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326466 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/26 RPL HRDW | 44409513 | SPAULDING-SUMMIT | 000/026 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633016 | 39.3222 | ETL.8060 | 40810198 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326486 | Q2 | DI HUMBOLDT-BRIDGEVILLE 91/3L RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 091/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322300 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326507 | Q2 | EI HAT CRK #1-WESTWD 48/933 REFRAM STRW | 31508175 | HAT CREEK #1-WESTWOOD | 048/933 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.018622 | 40.3981 | ETL.7030 | 40616947 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326518 | Q2 | EI HAT CREEK #1-WESTWOOD 49/950 RPR PL |  | HAT CREEK #1-WESTWOOD | 049/950 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.016447 | 40.3856 | ETL.7030 | 40816896 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326788 | Q4 | T2 DI KESWICK-TRINITY 023/367 RPR INSW | 43939188 | KESWICK-TRINITY | 023/367 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.81337 | 40.7114 | ETL.7270 | 40919283 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326872 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 45/354B RMV NES | 44143775 | BRIDGEVILLE-COTTONWOOD | 045/354 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.116361 | 40.3981 | ETL.1110 | 42603430 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326873 | Not Scheduled | EI T2NT BRIDGEVILLE-COTTONWOOD 47/3 RMV |  | BRIDGEVILLE-COTTONWOOD | 047/363 | HNA | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.146351 | 40.4076 | ETL.1110 | 40657057 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119326907 | Not Scheduled | T3 EI FRENCH MDWS-MIDDLE FORK 1/26 RPR R | 44388668 | FRENCH MEADOWS-MIDDLE FORK | 001/026 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.4222431 | 39.0672 | ETL.6870 | 40780081 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327157 | Q2 | T2 EI BRIDGEVLLE-CTTNWD 18/166 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 018/166 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.6076588 | 40.3802 | ETL.1110 | 44423852 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327158 | Q2 | EI BRIDGEVILLE-COTTONWOOD 18/165 REPL PL | 31508178 | BRIDGEVILLE-COTTONWOOD | 018/165 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.6057466 | 40.3804 | ETL.1110 | 44423919 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327163 | Q2 | EI BRIDGEVILLE-COTTONWOOD 18/165L REPL P | 31508178 | BRIDGEVILLE-COTTONWOOD | 018/165 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.6057466 | 40.3804 | ETL.1110 | 44423918 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327168 | Q2 | EI T2NT BRIDGEVILLE-COTTNWD 53/399 RPR F | 43706644 | BRIDGEVILLE-COTTONWOOD | 053/399 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-07 | 2022-07-07 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.2520693 | 40.3967 | ETL.1110 | 44424632 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327196 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/3 RPR CNDW | 44409513 | SPAULDING-SUMMIT | 000/003 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.643808 | 39.3247 | ETL.8060 | 40652035 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327251 | Mar | T2 EI KILARC-DESCHUTES 16/342 RPLC STRW | 31507647 | KILARC-DESCHUTES | 016/342 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120023 | 40.5635 | ETL.7300 | 40617715 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327283 | Mar | T2 EI KILARC-DESCHUTES 16/341 RPL PL | 31510880 | KILARC-DESCHUTES | 016/341 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.119056 | 40.5635 | ETL.7300 | 40876508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327290 | Mar | T2 EI KILARC-DESCHUTES 17/352 RPL PL | 31510880 | KILARC-DESCHUTES | 017/352 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.129414 | 40.5636 | ETL.7300 | 40590493 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327292 | Mar | T2 EI KILARC-DESCHUTES 16/348 RMV PL BUT | 44406470 | KILARC-DESCHUTES | 016/348 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.125916 | 40.5636 | ETL.7300 | 40817232 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327301 | Mar | T2 EI KILARC-DESCHUTES 16/351 RPR PL | 44406470 | KILARC-DESCHUTES | 016/351 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.128465 | 40.5636 | ETL.7300 | 44825403 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327306 | Mar | T2 EI KILARC-DESCHUTES 16/351 RPL HRDW | 44406470 | KILARC-DESCHUTES | 016/351 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.128465 | 40.5636 | ETL.7300 | 44825403 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327307 | Mar | T2 EI KILARC-DESCHUTES 16/348 RPL PL | 31510880 | KILARC-DESCHUTES | 016/348 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.125916 | 40.5636 | ETL.7300 | 40817232 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327590 | Q2 | HUMBOLDT-BRIDGEVILLE 90/2 RPR INSW | 44107184 | HUMBOLDT-BRIDGEVILLE | 086/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.788792 | 40.4869 | ETL.1810 | 40711015 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327599 | Not Scheduled | T2 ELK-GUALALA - 60 kV_064/003 | 31508609 | ELK-GUALALA | 064/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.540759 | 38.81 | ETL.8410 | 40667859 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327614 | Q2 | T3 EI IGNACIO-BOLINAS #2 022/252 WASH IN | 44640989 | IGNACIO-BOLINAS #2 | 022/252 | ICD | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7420631 | 37.9911 | ETL.7180 | 40833141 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327618 | Q3 | T2 EI CARIBOU-WESTWOOD 9/174 RPR STRW |  | CARIBOU-WESTWOOD | 009/174 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.073632 | 40.1913 | ETL.6300 | 40815700 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327667 | Mar | T2 EI KILARC-DESCHUTES A023/498 RPL PL | 31510880 | KILARC-DESCHUTES | A023/498 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.258904 | 40.5646 | ETL.7300 | 40864635 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327702 | Not Scheduled | T3 COLGATE-ALLEGHANY 8/228 REFRAME | 31508164 | COLGATE-ALLEGHANY | 008/228 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.050765 | 39.364 | ETL.6470 | 40822602 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327706 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 42/339A RPR FON | 43706644 | BRIDGEVILLE-COTTONWOOD | 042/339A | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.064268 | 40.3909 | ETL.1110 | 40817266 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327766 | Q3 | EI CARIBOU-PLUMAS JCT ;010/007 RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | ;010/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.915176 | 39.9348 | ETL.6290 | 40812743 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327829 | Q2 | T2 EI TRINITY-MAPLE CREEK_031/004 RPL SP | 44401954 | TRINITY-MAPLE CREEK | 031/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.484549 | 40.6899 | ETL.8170 | 40906467 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327947 | Q2 | EI T2NT TRINITY-MAPLE CREEK 19/1 RMV BUT | 44401994 | TRINITY-MAPLE CREEK | 019/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.248548 | 40.7346 | ETL.8170 | 40586385 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327964 | Q2 | T2 EI TRINITY-MAPLE CREEK 18/011 RPL POL | 31512224 | TRINITY-MAPLE CREEK | 018/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.238836 | 40.7374 | ETL.8170 | 40586383 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327968 | Q2 | EI TRINITY-MAPLE CREEK_018/015 RPL ANCHW | 31512224 | TRINITY-MAPLE CREEK | 018/015 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.2424411 | 40.7371 | ETL.8170 | 44771085 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327982 | Q2 | T2 EI TRINITY-MAPLE CREEK 19/1 RPL DMPRW | 44401954 | TRINITY-MAPLE CREEK | 019/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2485621 | 40.7346 | ETL.8170 | 40610945 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119327985 | Q2 | T3 EI IGNACIO-BOLINAS #2 20/237 REFRAME | 31508167 | IGNACIO-BOLINAS #2 | 020/237 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-01-07 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.756669 | 38.0106 | ETL.7180 | 40665557 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328010 | Q3 | T2NT DI CARIBOU-WESTWD 12/253 RMV BUTT |  | CARIBOU-WESTWOOD | 012/253 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.075439 | 40.2386 | ETL.6300 | 40867491 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328018 | Q2 | T2 EI HAT CRK #1-WSTWD 44/861 RPL PL | 31510437 | HAT CREEK #1-WESTWOOD | 044/861 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.022992 | 40.4519 | ETL.7030 | 40827509 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328049 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 1/53 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 001/053 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.623749 | 39.3171 | ETL.8060 | 44349482 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328070 | Q2 | T2 EI HAT CRK #1-WESTWD 41/793 REFRAM ST | 31508175 | HAT CREEK #1-WESTWOOD | 041/793 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.02677 | 40.5001 | ETL.7030 | 40877564 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328092 | Q3 | T2NT DI CARIBOU-WESTWD 11/220 RMV BUTT |  | CARIBOU-WESTWOOD | 011/220 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.071452 | 40.2189 | ETL.6300 | 40867485 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328093 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/33 RPR STRW | 44409513 | SPAULDING-SUMMIT | 000/033 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.629201 | 39.3215 | ETL.8060 | 40668714 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328116 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/37 RPR GYWW | 44409177 | SPAULDING-SUMMIT | 001/037 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.626915 | 39.321 | ETL.8060 | 44349478 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328117 | Q4 | T2 DI KESWICK TRINITY 28/488 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 028/488 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.898547 | 40.7095 | ETL.7270 | 40908544 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328209 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/21 RMV DEBRIS | 44409513 | SPAULDING-SUMMIT | 000/021 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.636413 | 39.3227 | ETL.8060 | 40610641 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328316 | Q2 | T2 EI FORT ROSS-GUALALA 33/004 RPR GYWW |  | GUALALA-MONTE RIO | 033/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.279337 | 38.5731 | ETL.6980 | 40750332 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328374 | Q3 | T2 DI CARIBOU-WESTWOOD 2/53 RPL HRDW |  | CARIBOU-WESTWOOD | 002/053 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.126141 | 40.1146 | ETL.6300 | 44189750 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328375 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/18 RMV BUTT | 44409175 | SPAULDING-SUMMIT | 000/018 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.637806 | 39.323 | ETL.8060 | 40864061 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328461 | Q4 | T2 DI KESWICK-TRINITY 22/332 RPR GYWW | 43939188 | KESWICK-TRINITY | 022/332 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.789966 | 40.7198 | ETL.7270 | 40909524 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328505 | Q2 | EI T2NT BRDGVLL-CTNWD 54/404 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 054/404 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-07 | 2022-07-07 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.266767 | 40.3947 | ETL.1110 | 40660355 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328555 | Q3 | T2 DI CARIBOU-WESTWOD 14/290 RMV BUTT |  | CARIBOU-WESTWOOD | 014/290 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08282 | 40.2617 | ETL.6300 | 40586006 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328572 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/34 RMV PL BUTT | 44409175 | SPAULDING-SUMMIT | 000/034 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.628689 | 39.3214 | ETL.8060 | 40751892 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328575 | Not Scheduled | T2 DI SPLDNG-SMMT 0/31 RMV PL BUTT | 44409175 | SPAULDING-SUMMIT | 000/031 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.630442 | 39.3217 | ETL.8060 | 40581014 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328673 | Q3 | T2 DI CARIBOU-WESTWD 9/168 RPR STRW |  | CARIBOU-WESTWOOD | 009/168 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.075308 | 40.1873 | ETL.6300 | 40591700 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328674 | Q3 | T2NT DI CARIBOU-WSTWD 9/168 RMV PL BUTT |  | CARIBOU-WESTWOOD | 009/168 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.075308 | 40.1873 | ETL.6300 | 40591700 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328705 | Not Scheduled | T2 EI BRDGVLLE-CTTNWD 46/357 RMV VEG |  | BRIDGEVILLE-COTTONWOOD | 046/357 | HNA | E | 2020_(3) On high spread structure |  | 2020-07-07 | 2021-07-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.125739 | 40.4001 | ETL.1110 | 40661025 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328882 | Q2 | T2 EI HAT CRK #1-WESTWD 44/862 RPL PL | 31510437 | HAT CREEK #1-WESTWOOD | 044/862 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023008 | 40.4512 | ETL.7030 | 40815888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328885 | Q2 | EI T2NT HAT CRK #1-WESTWD 44/850 RMV DEB | 44406426 | HAT CREEK #1-WESTWOOD | 044/850 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023095 | 40.46 | ETL.7030 | 40758811 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119328887 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 44/850 RPL P | 31508285 | HAT CREEK #1-WESTWOOD | 044/850 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023095 | 40.46 | ETL.7030 | 40758811 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329199 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/23 INST HV | 44388678 | SPAULDING-SUMMIT | 000/023 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.63482 | 39.3225 | ETL.8060 | 40644480 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329264 | Not Scheduled | T3NT DI DRUM-SUMMIT#2 4/48L RMV DEBRIS | 44388517 | DRUM-SUMMIT #2 | 004/048 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.711573 | 39.2859 | ETL.1450 | 44549946 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329267 | Not Scheduled | T3 DI DRUM-SUMMIT#2 4/48L RPR STRW | 44388516 | DRUM-SUMMIT #2 | 004/048 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711573 | 39.2859 | ETL.1450 | 44549946 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329280 | Mar | T2 EI KILARC-DESCHUTES 11/244 RPR INS HD | 44406470 | KILARC-DESCHUTES | 011/244 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.027281 | 40.5697 | ETL.7300 | 40770435 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329283 | Q2 | EI HAT CREEK #1-WESTWOOD 47/916 REFRAME | 31508175 | HAT CREEK #1-WESTWOOD | 047/916 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.020817 | 40.4109 | ETL.7030 | 40701260 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329294 | Not Scheduled | T2 KESWICK-TRINITY 23/355 RMV VEGN |  | KESWICK-TRINITY | 023/355 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.804982 | 40.7135 | ETL.7270 | 40909536 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329295 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 053/399 RPR FON | 43706644 | BRIDGEVILLE-COTTONWOOD | 053/399 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.2520693 | 40.3967 | ETL.1110 | 44424630 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329296 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 053/399 COTTER | 44143775 | BRIDGEVILLE-COTTONWOOD | 053/399 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.2520693 | 40.3967 | ETL.1110 | 44424630 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329320 | Q2 | EI HAT CREEK #1-WESTWOOD 47/920 REPL POL | 31522647 | HAT CREEK #1-WESTWOOD | 047/920 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.020337 | 40.408 | ETL.7030 | 40816894 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329321 | Q2 | EI HAT CREEK #1-WESTWOOD 47/909 RPL PL | 31510437 | HAT CREEK #1-WESTWOOD | 047/909 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.021708 | 40.4162 | ETL.7030 | 40770084 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329322 | Q2 | EI HAT CREEK #1-WESTWOOD 48/924 RPL PL | 31510437 | HAT CREEK #1-WESTWOOD | 048/924 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.019768 | 40.405 | ETL.7030 | 40591894 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329323 | Q2 | EI HAT CREEK #1-WESTWOOD 48/929 RPL PL | 31510437 | HAT CREEK #1-WESTWOOD | 048/929 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.019135 | 40.4012 | ETL.7030 | 40827569 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329390 | Not Scheduled | T3 DI DRUM-SUMMIT#2 4/48 RPL INSW | 44388516 | DRUM-SUMMIT #2 | 004/048 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711573 | 39.2859 | ETL.1450 | 40736299 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329458 | Q2 | T2 EI TRINITY-MAPLE CREEK 31/3L RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 031/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4810936 | 40.6893 | ETL.8170 | 44769573 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329462 | Q2 | EI T2NT TRINITY-MAPLE CREEK 31/3C RMV BU | 44401994 | TRINITY-MAPLE CREEK | 031/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4810936 | 40.6893 | ETL.8170 | 44769574 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329464 | Q2 | EI T2NT TRINITY-MAPLE CREEK 31/3R RMV BU | 44401994 | TRINITY-MAPLE CREEK | 031/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4810936 | 40.6893 | ETL.8170 | 44769575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329465 | Q2 | T2 EI TRINITY-MAPLE CREEK 31/003 RPR GYW | 44401954 | TRINITY-MAPLE CREEK | 031/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4810936 | 40.6893 | ETL.8170 | 44769575 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329466 | Q2 | T2 EI TRINITY-MAPLE CREEK 31/002 REPL PO | 31512224 | TRINITY-MAPLE CREEK | 031/002 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.478088 | 40.6898 | ETL.8170 | 40906465 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329512 | Q2 | T2 EI TRNTY-MPL CRK_031/001 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4747611 | 40.6902 | ETL.8170 | 44565314 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329743 | Mar | T3 EI MONTA VSTA-JFFRSN #1 14/58 RPL INS | 31513842 | MONTA VISTA-JEFFERSON #1 | 014/058 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2888168 | 37.3879 | ETL.5220 | 44377028 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329744 | Mar | T3 EI MONTA VSTA-JFFRSN #2 14/58 RPL INS | 31528464 | MONTA VISTA-JEFFERSON #2 | 014/058 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2888168 | 37.3879 | ETL.5230 | 44377029 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329805 | Q4 | T2NT DI KESWICK-TRINITY 23/366 RMV BUTT | 43939188 | KESWICK-TRINITY | 023/366 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.812757 | 40.7113 | ETL.7270 | 40906085 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329828 | Q3 | T2NT DI CARBU-WSTW 11/225 RMV BUTT |  | CARIBOU-WESTWOOD | 011/225 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.073913 | 40.2216 | ETL.6300 | 40769699 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119329837 | Q2 | T2 EI FORT ROSS-GUALALA 52/011 RPL PL | 31508619 | GUALALA-MONTE RIO | 052/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | 2021-06-07 | 2021-06-14 | 2021-06-09 | 2021-06-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.452003 | 38.7387 | ETL.6980 | 40596063 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330078 | Q3 | DI HAMLTN BRNCH-CHSTR 10/209 RMV PL BUTT | 43908598 | HAMILTON BRANCH-CHESTER | 010/209 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-31 | 2021-08-30 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.19563 | 40.3116 | ETL.7000 | 40601590 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330184 | Q3 | T3 EI CARIBOU #2 8/3 REFRAME CRSW | 31507658 | CARIBOU #2 | 008/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.220925 | 40.0131 | ETL.6280 | 40666805 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330251 | Not Scheduled | T2 EI DIABLO-GATES #1 59/240 RPR GYWT |  | DIABLO-GATES #1 | 059/240 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.29771 | 35.896 | ETL.5960 | 40605011 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330325 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/16 INS MRKW | 44409514 | SPAULDING-SUMMIT | 000/016 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6387 | 39.3232 | ETL.8060 | 40828167 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330326 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/16 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/016 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6387 | 39.3232 | ETL.8060 | 40828167 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330394 | Mar | T3 EI POTTER VALLEY-WILLITS 8/0 RPL POLE | 31507654 | POTTER VALLEY-WILLITS | 008/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.256933 | 39.3758 | ETL.7820 | 40614409 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330403 | Not Scheduled | T3 EI POTTER VALLEY-WILLITS 8/3 RPR GYWW | 44610689 | POTTER VALLEY-WILLITS | 008/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.262847 | 39.3731 | ETL.7820 | 40666634 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330404 | Mar | T3 EI POTTER VALLEY-WILLITS 8/1 RPL POLE | 31507654 | POTTER VALLEY-WILLITS | 008/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.259028 | 39.3749 | ETL.7820 | 40584802 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330446 | Q3 | T2 DI CARIBOU-WESTWOOD 6/122 RPR GYWW |  | CARIBOU-WESTWOOD | 006/122 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.102623 | 40.1637 | ETL.6300 | 40615003 | Ground Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330483 | Q2 | T2 EI FORT ROSS-GUALALA 52/6 RPL PL | 31508619 | GUALALA-MONTE RIO | 052/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | 2021-06-07 | 2021-06-14 | 2021-06-09 | 2021-06-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.446328 | 38.7369 | ETL.6980 | 40808669 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330504 | Q2 | T2 EI HAT CREEK #1-WESTWD 34/656 RPR STR |  | HAT CREEK #1-WESTWOOD | 034/656 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.093373 | 40.5899 | ETL.7030 | 40759230 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330507 | Not Scheduled | T2 EI BRIDGEVILLE-COTTONWOOD 55/411 MAST |  | BRIDGEVILLE-COTTONWOOD | 055/411 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.291301 | 40.3902 | ETL.1110 | 40756750 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330515 | Mar | EI T3NT DRUM-GRSS VLLY-WMR 8/207 RMV BUT | 44388665 | DRUM-GRASS VALLEY-WEIMAR | 008/207 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-08 | 2022-07-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.858097 | 39.1826 | ETL.6760 | 40756216 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330559 | Mar | T3 EI DRUM-GRASS VLLY-WMR 8/207 REPLUMB | 44388663 | DRUM-GRASS VALLEY-WEIMAR | 008/207 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8581106 | 39.1826 | ETL.6760 | 40786045 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330592 | Q4 | T2 EI SALINAS-LAURELES 9/206 RMV VEG |  | SALINAS-LAURELES | 009/206 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2021-07-08 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.71941 | 36.5805 | ETL.7930 | 40588377 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330621 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/20 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/020 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.636794 | 39.3228 | ETL.8060 | 40590001 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330624 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/14 INS GMKW | 44409514 | SPAULDING-SUMMIT | 000/014 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.639466 | 39.3233 | ETL.8060 | 40751889 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330625 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/14 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/014 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.639466 | 39.3233 | ETL.8060 | 40751889 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330749 | Q2 | T2 EI IGNACIO-BOLINAS #2 6/76 REFRAME | 31508167 | IGNACIO-BOLINAS #2 | 006/076 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.62999 | 38.1193 | ETL.7180 | 41124303 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330757 | Not Scheduled | T3 EI FULTON-HOPLAND 026/007 RPR GYWW | 44579280 | FULTON-HOPLAND | 026/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.98905 | 38.8046 | ETL.6890 | 40816675 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330781 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/35 RMV PL BUTT | 44409175 | SPAULDING-SUMMIT | 000/035 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.628119 | 39.3213 | ETL.8060 | 40746162 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330807 | Not Scheduled | T2 COALINGA #1-SAN MIGUEL 14/5 RPL INSS |  | COALINGA #1-SAN MIGUEL | 014/005 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.519286 | 36.0169 | ETL.8580 | 40796346 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330852 | Mar | EI T2NT KILARC-DESCHUTES 13/283 RMV DEBR | 44406470 | KILARC-DESCHUTES | 013/283 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2022-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.063947 | 40.5645 | ETL.7300 | 40617709 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330886 | Mar | T2 EI KILARC-DESCHUTES 13/282 RPL PL | 31510880 | KILARC-DESCHUTES | 013/282 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.062375 | 40.5644 | ETL.7300 | 40876526 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330900 | Q3 | T2NT DI CARIBOU-WESTWD 11/221 INS MRKW |  | CARIBOU-WESTWOOD | 011/221 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.071875 | 40.2195 | ETL.6300 | 40615009 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330943 | Feb | T2 RIO DELL JCT-BRDGVLL 31/7 RPL COND | 31510954 | RIO DELL JCT-BRIDGEVILLE | 031/007 | 93C | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.923642 | 40.4843 | ETL.7850 | 40824518 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-21 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119330998 | Mar | T3 EI DRUM-GRSS VLLY-WEIMAR 6/151 RPR SP | 44388663 | DRUM-GRASS VALLEY-WEIMAR | 006/151 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.830847 | 39.2073 | ETL.6760 | 40766654 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331074 | Q2 | T3 EI KONOCTI-EAGLE ROCK 2/4 GROUND WASH | 44610646 | KONOCTI-EAGLE ROCK | 002/004 | ICD | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7842457 | 38.8496 | ETL.6861 | 40779790 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331093 | Mar | T2 EI KILARC-DESCHUTES 13/284 RPLC STRW | 31507647 | KILARC-DESCHUTES | 013/284 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.064963 | 40.5645 | ETL.7300 | 40602027 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331096 | Mar | T2 EI KILARC-DESCHUTES 13/285 RPL PL | 31510880 | KILARC-DESCHUTES | 013/285 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.065518 | 40.5645 | ETL.7300 | 40701734 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331232 | Q2 | T2 EI TRINITY-MAPLE CREEK 1/9 REFRAME | 31510698 | TRINITY-MAPLE CREEK | 001/009 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.957384 | 40.7279 | ETL.8170 | 40906252 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331395 | Not Scheduled | T2 EI BRIDGEVILLE-COTTONWOOD 54/406 MAST |  | BRIDGEVILLE-COTTONWOOD | 054/406 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.276227 | 40.3935 | ETL.1110 | 40759201 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331494 | Q3 | T2 DI HMLTN BRNCH-CHSTR 11/244 RPR WPKR | 43908598 | HAMILTON BRANCH-CHESTER | 011/244 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.222597 | 40.3043 | ETL.7000 | 40810081 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331495 | Q3 | T2NT DI HMLTN BRCH-CHSTR 11/244 RMV BUTT | 43908598 | HAMILTON BRANCH-CHESTER | 011/244 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.222597 | 40.3043 | ETL.7000 | 40810081 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331497 | Q3 | T2 DI CARIBOU-PLUMAS JCT 13/12 RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | 013/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.966017 | 39.9619 | ETL.6290 | 40675224 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331517 | Mar | T3 MORAGA-SAN LEANDRO #1 7/5 RPR STRT |  | MORAGA-SAN LEANDRO #1 | 007/051 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113996 | 37.7534 | ETL.2770 | 40580813 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331548 | Q2 | T3 EI FULTON-CALISTOGA :5/6 RPR GYWW | 44597303 | FULTON-CALISTOGA | :005/006 | ICW | E | 2020_(1a) PSPS |  | 2020-07-08 | 2021-01-08 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588821 | 38.6653 | ETL.6880 | 40912463 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119331642 | Not Scheduled | T3 EI DIABLO-MIDWAY #2 10/041 RPL INSS | 31526475 | DIABLO-MIDWAY #2 | 010/041 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.6632687 | 35.1936 | ETL.5970 | 40612722 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331888 | Mar | T3 EI DRM-GRSS VALLY-WMR 8/204 REFRAME S | 31508223 | DRUM-GRASS VALLEY-WEIMAR | 008/204 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856741 | 39.1838 | ETL.6760 | 40598587 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119331904 | Q2 | EI HUMBOLDT-BRIDGEVILLE 90/3 RPR POLE | 44402106 | HUMBOLDT-BRIDGEVILLE | 090/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8325292 | 40.5294 | ETL.1810 | 44322280 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332143 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 10/039 RPL INSS | 31426864 | DIABLO-MIDWAY #3 | 010/039 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.6729984 | 35.1973 | ETL.5980 | 40886046 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332158 | Q2 | T2 EI BRIDGEVL-CTNWD 42/334 RPR GROUND W | 44404807 | BRIDGEVILLE-COTTONWOOD | 042/334 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.0490599 | 40.3894 | ETL.1110 | 44423195 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332412 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 52/391 RPR FOND | 44634179 | BRIDGEVILLE-COTTONWOOD | 052/391 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.229397 | 40.4115 | ETL.1110 | 40592235 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332496 | Q2 | DI HUMBOLDT-BRIDGEVILL 101/0 RPR STRW | 44402106 | HUMBOLDT-BRIDGEVILLE | 101/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322462 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332558 | Not Scheduled | EI LAKEVILLE-SONOMA #2 1/15 WASH INSU |  | LAKEVILLE-SONOMA #2 | 001/015 | ICI | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.5615925 | 38.2635 | ETL.2070 | 42629023 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332577 | Q3 | T2 EI CARIBOU-WESTWOOD 10/209 RPL POLE | 31511053 | CARIBOU-WESTWOOD | 010/209 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.066403 | 40.2125 | ETL.6300 | 44190976 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332657 | Mar | T2 EI KILARC-DESCHUTES 17/355 RMV PL BUT | 44406470 | KILARC-DESCHUTES | 017/355 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2022-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.13292 | 40.5636 | ETL.7300 | 40650332 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332661 | Mar | T2 EI KILARC-DESCHUTES 17/355 RPL PL | 31510880 | KILARC-DESCHUTES | 017/355 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.13292 | 40.5636 | ETL.7300 | 40650332 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332665 | Mar | T2 EI KILARC-DESCHUTES 17/358 RPL POLE | 31514615 | KILARC-DESCHUTES | 017/358 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.135519 | 40.5636 | ETL.7300 | 40817234 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332666 | Mar | T2 EI KILARC-DESCHUTES 17/364 REFRAME | 31506150 | KILARC-DESCHUTES | 017/364 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.141727 | 40.5636 | ETL.7300 | 40676543 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332667 | Mar | T2 EI KILARC-DESCHUTES 17/357 REFRAME | 31506150 | KILARC-DESCHUTES | 017/357 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.134464 | 40.5636 | ETL.7300 | 40759136 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332671 | Mar | T2 EI KILARC-DESCHUTES 17/366A RPR STRW | 44406470 | KILARC-DESCHUTES | 017/366A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.144097 | 40.5637 | ETL.7300 | 44416928 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332688 | Not Scheduled | T3 EI MRRO BY-SLR SW ST #1 8/35 RPL INSS | 31529344 | MORRO BAY-SOLAR SW STA #1 | 008/035 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7047386 | 35.3794 | ETL.5300 | 40782015 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332690 | Not Scheduled | T3 EI MRRO BY-SLR SW ST #2 8/35 RPL INSS | 31508487 | MORRO BAY-SOLAR SW STA #2 | 008/035 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7047386 | 35.3794 | ETL.5310 | 40782017 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332842 | Not Scheduled | T3 EI MRRO BY-SLR SW ST #2 8/34 RPL INSS | 31508487 | MORRO BAY-SOLAR SW STA #2 | 008/034 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7066738 | 35.3793 | ETL.5310 | 44660780 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332850 | Not Scheduled | EI CAYUCOS-CAMBRIA 10/064 RPR INSW |  | CAYUCOS-CAMBRIA | 010/064 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 | [9 empty] | South | WSIP | [6 empty] | '-120.9999805 | 35.5342 | ETL.8560 | 40794298 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332859 | Not Scheduled | T3 EI MRRO BY-SLR SW ST #1 8/34 RPL INSS | 31529344 | MORRO BAY-SOLAR SW STA #1 | 008/034 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7066738 | 35.3793 | ETL.5300 | 44660781 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332921 | Q2 | T3 DI SNTH LN-HLF MN BY ?10/6 RPR STRW | 44621667 | SNEATH LANE-HALF MOON BAY | ?010/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-01-07 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384407 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332923 | Q3 | T2NT DI CRBOU-WSTWD 18/368 RMV PL BUTT |  | CARIBOU-WESTWOOD | 018/368 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.047458 | 40.2922 | ETL.6300 | 40758766 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119332924 | Q3 | T2 DI CARIBOU-WESTWOOD 18/368 RPR INSW |  | CARIBOU-WESTWOOD | 018/368 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.047479 | 40.2922 | ETL.6300 | 40788853 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333167 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 12/048 RPL INSS | 31527002 | DIABLO-MIDWAY #2 | 012/048 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.634952 | 35.1782 | ETL.5970 | 40887895 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333440 | Q2 | T2 EI BRIDGEVILLE-COTTONWOOD 28/241 RPL | 31526498 | BRIDGEVILLE-COTTONWOOD | 028/241 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.8056632 | 40.3663 | ETL.1110 | 44561161 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333441 | Q2 | T2 EI BRIDGEVILLE-COTTONWOOD 28/241 RPL | 31526498 | BRIDGEVILLE-COTTONWOOD | 028/241 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.8056632 | 40.3663 | ETL.1110 | 44561160 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333564 | Q3 | T3 EI CARIBOU #2 8/002 REFRAME CRSW | 31507658 | CARIBOU #2 | 008/002 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.221982 | 40.0135 | ETL.6280 | 40675402 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333578 | Q2 | T2 EI KONOCTI-MIDDLETOWN 13/4 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 013/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.590443 | 38.7663 | ETL.6380 | 40769709 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333748 | Not Scheduled | EI LAKEVILLE-SONOMA #2 /14 WASH INSU |  | LAKEVILLE-SONOMA #2 | 001/014 | ICI | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.5645297 | 38.2632 | ETL.2070 | 42629021 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119333955 | Q2 | T2 EI KONOCTI-MIDDLETOWN 28/7 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 028/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.63534 | 38.9123 | ETL.6380 | 40808160 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334016 | Q3 | T2 DI CARIBOU-WESTWOOD 19/396 RPL STRW | 31508283 | CARIBOU-WESTWOOD | 019/396 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.02067 | 40.2989 | ETL.6300 | 40758770 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334163 | Q2 | T2 EI HAT CRK #1-WSTWD 39/751 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 039/751 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.040247 | 40.5311 | ETL.7030 | 40659938 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334164 | Q2 | T2 EI HAT CRK #1-WSTWD 38/742 RPR ANCHOR |  | HAT CREEK #1-WESTWOOD | 038/742 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.044123 | 40.5368 | ETL.7030 | 40667973 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334166 | Q2 | T2 EI HAT CREEK #1-WSTWD 38/739 RPL POLE | 31510437 | HAT CREEK #1-WESTWOOD | 038/739 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.045865 | 40.5387 | ETL.7030 | 40589868 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334170 | Q2 | T2 EI HAT CRK #1-WSTWD 39/751 RPR WP HOL |  | HAT CREEK #1-WESTWOOD | 039/751 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.040247 | 40.5311 | ETL.7030 | 40659938 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334282 | Not Scheduled | T3 EI FULTON-HOPLAND :026/006 RPR GYWW | 44579280 | FULTON-HOPLAND | :026/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.982207 | 38.7918 | ETL.6890 | 44878704 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334283 | Not Scheduled | T3 EI FULTON-HOPLAND :26/6 RPL DAMPERS | 44579280 | FULTON-HOPLAND | :026/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.982207 | 38.7918 | ETL.6890 | 44878704 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334301 | Q3 | T2 EI CARIBOU-WESTWOOD 0/1 RPR GYWW |  | CARIBOU-WESTWOOD | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.147269 | 40.0852 | ETL.6300 | 40913188 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334350 | Q2 | DI GATES-PANOCHE#1 14/70 RPR BENT STL | 44404664 | GATES-PANOCHE #1 | 014/070 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.265395 | 36.3184 | ETL.4720 | 40592390 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119334370 | Q2 | T2 EI HAT CREEK #1-WESTWD 33/635 RPR STR |  | HAT CREEK #1-WESTWOOD | 033/635 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.105467 | 40.603 | ETL.7030 | 40676378 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334374 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 33/638 RPR S |  | HAT CREEK #1-WESTWOOD | 033/638 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.10377 | 40.6011 | ETL.7030 | 40769974 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334375 | Q2 | T2 EI HAT CREEK #1-WESTWD 33/647 REFRAME | 31508135 | HAT CREEK #1-WESTWOOD | 033/647 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.098532 | 40.5955 | ETL.7030 | 40759228 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334376 | Q2 | T2 EI HAT CREEK #1-WESTWD 33/633 RPR STR |  | HAT CREEK #1-WESTWOOD | 033/633 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.106653 | 40.6042 | ETL.7030 | 40616919 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334382 | Q2 | T2 EI HAT CREEK #1-WESTWD 33/634 RPR STR |  | HAT CREEK #1-WESTWOOD | 033/634 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.106088 | 40.6036 | ETL.7030 | 40601699 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334383 | Q2 | T2 EI HAT CREEK #1-WESTWD 33/649 REFRAME | 31522648 | HAT CREEK #1-WESTWOOD | 033/649 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.09734 | 40.5943 | ETL.7030 | 40827600 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334384 | Q2 | T2 EI HAT CREEK #1-WESTWD 33/646 RPL STR | 31510437 | HAT CREEK #1-WESTWOOD | 033/646 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.099075 | 40.5961 | ETL.7030 | 40667963 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334444 | Q2 | EI HAT CRK #1-WSTWD 45/871 RPR WP HOLES |  | HAT CREEK #1-WESTWOOD | 045/871 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.022857 | 40.4446 | ETL.7030 | 40816890 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334451 | Q2 | T2 DI BRDGVILL-CTTNWOOD 32/263 RPR FOND | 44634168 | BRIDGEVILLE-COTTONWOOD | 032/263 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-08 | 2022-07-08 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.868995 | 40.3642 | ETL.1110 | 40605509 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334495 | Mar | T3 EI POTTER VALLEY-WILLITS 4/4 RPR POLE | 44610689 | POTTER VALLEY-WILLITS | 004/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.203952 | 39.3713 | ETL.7820 | 40769296 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334497 | Mar | T3 EI POTTER VALLEY-WLLTS 4/4 REFRAME CR | 31507791 | POTTER VALLEY-WILLITS | 004/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.203952 | 39.3713 | ETL.7820 | 40769296 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334498 | Mar | T3 EI POTTER VALLEY-WILLITS 5/5 RP STRW | 44610689 | POTTER VALLEY-WILLITS | 005/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.214617 | 39.3832 | ETL.7820 | 40750451 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334522 | Q2 | EI HAT CRK #1-WSTWD 46/901 RPR REFRAME | 31508135 | HAT CREEK #1-WESTWOOD | 046/901 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.022727 | 40.4221 | ETL.7030 | 40825614 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334525 | Q2 | EI HAT CRK #1-WSTWD 46/888 RPR WP HOLE |  | HAT CREEK #1-WESTWOOD | 046/888 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.02301 | 40.4317 | ETL.7030 | 40758927 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334530 | Q2 | EI HAT CRK #1-WSTWD 47/906 RPR REFRAME | 31508135 | HAT CREEK #1-WESTWOOD | 047/906 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.022087 | 40.4185 | ETL.7030 | 40675741 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334531 | Q2 | EI HAT CRK #1-WSTWD 46/900 RPR REFRAME | 31508135 | HAT CREEK #1-WESTWOOD | 046/900 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.022865 | 40.4228 | ETL.7030 | 40827513 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334533 | Q2 | EI HAT CRK #1-WSTWD 26/507 INST GYWW |  | HAT CREEK #1-WESTWOOD | 026/507 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.195363 | 40.6714 | ETL.7030 | 40867816 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334534 | Q2 | EI HAT CRK #1-WSTWD 47/906 RPR GRND WIRE |  | HAT CREEK #1-WESTWOOD | 047/906 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.022087 | 40.4185 | ETL.7030 | 40675741 | Ground Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334535 | Q2 | EI HAT CRK #1-WSTWD 46/892 RPR REFRAME | 31508135 | HAT CREEK #1-WESTWOOD | 046/892 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.023038 | 40.4285 | ETL.7030 | 40877511 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334582 | Mar | T2 EI KILARC-DESCHUTES A024/507 RPR PL | 44406470 | KILARC-DESCHUTES | A024/507 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.266003 | 40.5672 | ETL.7300 | 40877194 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334603 | Mar | T2 EI KILARC-DESCHUTES A024/511 RPR PL | 44406470 | KILARC-DESCHUTES | A024/511 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.26923 | 40.5684 | ETL.7300 | 40669390 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334660 | Mar | T2 EI KILARC-DESCHUTES 12/258 RPR PL | 44406470 | KILARC-DESCHUTES | 012/258 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.039372 | 40.5666 | ETL.7300 | 44825389 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334728 | Mar | T3 EI DRUM-GRASS VLLY-WMR 8/196 RPL STRW | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 008/196 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.853171 | 39.187 | ETL.6760 | 40664665 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119334755 | Q2 | T2 EI BRIDGEVILLE-COTTONWO 25/219 RPR WD | 44404807 | BRIDGEVILLE-COTTONWOOD | 025/219 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.7436497 | 40.3707 | ETL.1110 | 44515803 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334757 | Q2 | EI T2NT MALIN-RND MTN #2 71/360A INS MRK | 44408444 | MALIN-ROUND MTN #2 | 071/360A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.793149 | 41.0812 | ETL.6020 | 41191651 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334791 | Not Scheduled | T3 EI DRUM-RIO OSO #2 9/92 INST HDWT | 44388507 | DRUM-RIO OSO #2 | 009/092 | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.904248 | 39.1815 | ETL.1430 | 40672397 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334927 | Q3 | T2 EI CARIBOU-WESTWOOD 05/105A RPR GYWW |  | CARIBOU-WESTWOOD | 005/105A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.109663 | 40.1505 | ETL.6300 | 44191072 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334968 | Q2 | T2 EI TRINITY-MPL CRK 19/11 RMV PL BUTT | 44401994 | TRINITY-MAPLE CREEK | 019/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-08 | 2022-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.25859 | 40.7289 | ETL.8170 | 40586386 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334973 | Q2 | T2 EI TRINITY-MPL CRK 19/11 REPLACE POL | 31510697 | TRINITY-MAPLE CREEK | 019/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.25859 | 40.7289 | ETL.8170 | 40586386 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334975 | Q2 | T2 EI TRINITY-MAPLE CREEK 19/13 REFRAME | 31510697 | TRINITY-MAPLE CREEK | 019/013 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.260686 | 40.7273 | ETL.8170 | 40650357 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334991 | Q2 | T2 EI TRINITY-MPL CRK 19/11 INST DAMPER | 44401954 | TRINITY-MAPLE CREEK | 019/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2586036 | 40.7289 | ETL.8170 | 40610947 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119334996 | Q2 | T2 EI TRINITY-MAPLE CREEK 19/7 RPL POLE | 31510696 | TRINITY-MAPLE CREEK | 019/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.255007 | 40.7318 | ETL.8170 | 40821164 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335028 | Mar | T2 EI KILARC-DESCHUTES 19/407 RPR GYWW | 44406470 | KILARC-DESCHUTES | 019/407 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.182633 | 40.5638 | ETL.7300 | 44809982 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335029 | Mar | T2 EI KILARC-DESCHUTES 19/401 REFRAME | 31506150 | KILARC-DESCHUTES | 019/401 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.176237 | 40.5638 | ETL.7300 | 40602004 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335036 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 36/701 RPL S | 31510437 | HAT CREEK #1-WESTWOOD | 036/701 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.067513 | 40.5621 | ETL.7030 | 40617029 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335049 | Q2 | T2 EI TRINITY-MAPLE CREEK 31/6 RPR WP H | 44401994 | TRINITY-MAPLE CREEK | 031/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.486585 | 40.6908 | ETL.8170 | 44190923 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335050 | Q2 | T2 EI TRINITY-MAPLE CREEK 32/3 RPL POLE | 31510696 | TRINITY-MAPLE CREEK | 032/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.501 | 40.698 | ETL.8170 | 40906472 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335080 | Q2 | T2 EI HAT CREEK #1-WESTWD 36/699 RPR GYW |  | HAT CREEK #1-WESTWOOD | 036/699 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.068682 | 40.5633 | ETL.7030 | 40862091 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335100 | Q2 | T2 EI HT CRK #1-WSTWD 42/810 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 042/810 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.0234 | 40.4873 | ETL.7030 | 40769991 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335101 | Q2 | T2 EI HAT CRK #1-WSTWD 41/794 RPR HRD |  | HAT CREEK #1-WESTWOOD | 041/794 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.026413 | 40.4992 | ETL.7030 | 40876209 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335104 | Q2 | T2 EI HAT CRK #1-WSTWD 41/797 RPL INSUL | 31511086 | HAT CREEK #1-WESTWOOD | 041/797 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.025472 | 40.4971 | ETL.7030 | 40701248 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335105 | Q2 | T2 EI HAT CRK #1-WSTWD 42/807 RPL POLE | 31510437 | HAT CREEK #1-WESTWOOD | 042/807 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023465 | 40.4896 | ETL.7030 | 40675725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335106 | Q2 | T2 EI HAT CREEK #1-WESTWD 042/806 REPL P | 31508135 | HAT CREEK #1-WESTWOOD | 042/806 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023457 | 40.4904 | ETL.7030 | 40586014 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335111 | Q2 | T2 EI HAT CREEK #1-WSTWD 041/796 RPR GYW | 44406426 | HAT CREEK #1-WESTWOOD | 041/796 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.025733 | 40.4978 | ETL.7030 | 40591884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335112 | Q2 | T2 EI HAT CREEK #1-WESTWOD 41/796 RPR AN | 44406426 | HAT CREEK #1-WESTWOOD | 041/796 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.025733 | 40.4978 | ETL.7030 | 40591884 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335115 | Q2 | T2 EI HAT CRK #1-WSTWD 41/801 RPL POLE | 31510437 | HAT CREEK #1-WESTWOOD | 041/801 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.024002 | 40.4937 | ETL.7030 | 40827503 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335247 | Q2 | T3 EI DRUM-SPAULDING 4/097 RPL POLE | 31508495 | DRUM-SPAULDING | 004/097 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.713469 | 39.2848 | ETL.6770 | 40809634 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335264 | Q2 | T2 EI HAT CRK #1-WESTWD 32/617 RPR STRW |  | HAT CREEK #1-WESTWOOD | 032/617 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.116032 | 40.6144 | ETL.7030 | 40656905 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335266 | Q2 | T2 EI HAT CRK #1-WESTWD 32/624 RPR STRW |  | HAT CREEK #1-WESTWOOD | 032/624 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.111808 | 40.6099 | ETL.7030 | 40600250 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335270 | Q2 | T3 EI DRUM-SPAULDING 3/083 REPL SPLW | 44388666 | DRUM-SPAULDING | 003/083 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.723633 | 39.2812 | ETL.6770 | 40810145 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335277 | Q2 | T3 EI IGNACIO-BOLINAS #2 22/258 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 022/258 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.736301 | 37.9837 | ETL.7180 | 40585017 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335335 | Q2 | T2 EI HAT CRK #1-WESTWD 32/621 RPR STRW |  | HAT CREEK #1-WESTWOOD | 032/621 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.113685 | 40.6118 | ETL.7030 | 44653291 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335338 | Q2 | T2 EI HAT CREEK #1-WESTWOOD - 60 kV_031/ |  | HAT CREEK #1-WESTWOOD | 031/613 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.11826 | 40.6168 | ETL.7030 | 40877608 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335342 | Q2 | T2 EI HAT CRK #1-WESTWD 32/626 RPR STRW |  | HAT CREEK #1-WESTWOOD | 032/626 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.110643 | 40.6086 | ETL.7030 | 44653293 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335352 | Q2 | T2 EI HAT CRK #1-WESTWD 32/623 RPR STRW |  | HAT CREEK #1-WESTWOOD | 032/623 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.112398 | 40.6105 | ETL.7030 | 40876198 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335394 | Q3 | T2 EI CARIBOU-WESTWOOD 0/4 RPR IBWW |  | CARIBOU-WESTWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.14707 | 40.0859 | ETL.6300 | 40656481 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335426 | Q2 | T2 EI FORT ROSS-GULL 42/11 RPR GYWW | 44640986 | GUALALA-MONTE RIO | 042/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.312973 | 38.6802 | ETL.6980 | 40596054 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335501 | Q2 | T2 BRIDGEVILLE-COTTONWD 37/2 RMV PL BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/296 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2021-07-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.96706 | 40.3657 | ETL.1110 | 44515873 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335525 | Q2 | T2 EI FORT ROSS-GUALALA 33/011 REPL ANC | 31507794 | GUALALA-MONTE RIO | 033/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.28878 | 38.5748 | ETL.6980 | 40584646 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335780 | Q4 | DI MIDDLE FORK-GOLD HILL 9/81 RPR INSW |  | MIDDLE FORK-GOLD HILL | 009/081 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [8 empty] | ETL.5140 | 44141491 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335846 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 26/317L RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 026/317 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162123 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335847 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 23/280 INST MRKW | 44409006 | DRUM-SUMMIT #2 | 023/280 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.384786 | 39.3285 | ETL.1450 | 44553821 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335853 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/7 RMV PL BUTT | 44409175 | SPAULDING-SUMMIT | 000/007 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.64203 | 39.3247 | ETL.8060 | 40809700 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335854 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/7 RPR GYWW | 44409177 | SPAULDING-SUMMIT | 000/007 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.64203 | 39.3247 | ETL.8060 | 40809700 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335861 | Q2 | T2 EI TRINITY-MAPLE CREEK 32/2 RPL INSS | 31510665 | TRINITY-MAPLE CREEK | 032/002 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.499847 | 40.6974 | ETL.8170 | 44420779 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335892 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/132 BOND GUY | 44409003 | DRUM-SUMMIT #1 | 011/132 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.594343 | 39.3308 | ETL.1440 | 40756806 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119335894 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/132 RMV PL BUTT | 44409002 | DRUM-SUMMIT #1 | 011/132 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.594343 | 39.3308 | ETL.1440 | 40756806 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336040 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 17/544 RMV BUTT | 44409514 | SPAULDING-SUMMIT | 017/544 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.360928 | 39.3096 | ETL.8060 | 40878081 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336045 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 1/39 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 001/039 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.626439 | 39.3206 | ETL.8060 | 40701993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336059 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 14/386 RPR SPLW | 44388660 | COLGATE-ALLEGHANY | 014/386 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.997627 | 39.4366 | ETL.6470 | 40824266 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336125 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 14/386 RMV BUTT | 44388578 | COLGATE-ALLEGHANY | 014/386 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.997627 | 39.4366 | ETL.6470 | 40824266 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336150 | Q4 | DI MIDDLE FRK-GLD HILL 11/94C REPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 011/094 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP |  |  |  | REJECT: Crew was unable to complete work. Cotter key was replaced on LC# 119336273, Crew still needs to replace all Three Poles, LC#'s 119568183, 119568184 and 119336150 |  |  | '-120.773631 | 38.9722 | ETL.5140 | 44553715 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  | Reject |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336153 | Q2 | T2 DI IGNACIO-BOLINAS #1 6-63C RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 006/063C | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.631158 | 38.0254 | ETL.7140 | 41111826 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336154 | Q3 | T2 DI CARIBOU-WESTWOOD 18/365 RPLC STRW | 31508283 | CARIBOU-WESTWOOD | 018/365 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.05036 | 40.2915 | ETL.6300 | 40600738 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336303 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 13/350 RPR SPLW | 44388660 | COLGATE-ALLEGHANY | 013/350 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.009012 | 39.4206 | ETL.6470 | 40873678 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336349 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 0/13 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/013 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.639723 | 39.3233 | ETL.8060 | 40650034 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336371 | Not Scheduled | T3NT DI COLGATE-ALGHNY 13/350 RMV BUTT | 44388578 | COLGATE-ALLEGHANY | 013/350 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.009012 | 39.4206 | ETL.6470 | 40873678 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336384 | Not Scheduled | DI DRUM-SUMMIT #1 11/133 RMV DEBRIS | 44409002 | DRUM-SUMMIT #1 | 011/133 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.592582 | 39.3316 | ETL.1440 | 44338171 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119336385 | Mar | T3NT DI BRUNSWICK #1 005/042 RPR FOND | 44388504 | BRUNSWICK #1 TAP | 005/042 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-08 | 2022-07-08 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.035273 | 39.2139 | ETL.1422 | 40683049 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336388 | Not Scheduled | T2 DI BRDGEVLL-CTTONWD 32/264 RPR FOND |  | BRIDGEVILLE-COTTONWOOD | 032/264 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.875467 | 40.3646 | ETL.1110 | 40592215 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336463 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 12/338 REPL POLE | 31508409 | COLGATE-ALLEGHANY | 012/338 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.013388 | 39.4161 | ETL.6470 | 40818491 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119336475 | Q3 | T2 DI CARIBOU-WESTWOOD 3/74 RMV PL BUTT |  | CARIBOU-WESTWOOD | 003/074 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2022-07-08 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.125718 | 40.1305 | ETL.6300 | 44191075 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336476 | Q3 | T2 DI CARIBOU-WESTWOOD 3/74 RPR GYWW |  | CARIBOU-WESTWOOD | 003/074 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.125718 | 40.1305 | ETL.6300 | 44191075 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336519 | Q4 | T2 DI KESWICK-TRINITY 15/186 RPR WDPKR |  | KESWICK-TRINITY | 015/186 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.670049 | 40.7135 | ETL.7270 | 40876483 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336611 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 12/140 INS MRKW | 44409006 | DRUM-SUMMIT #2 | 012/140 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44150233 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336675 | Mar | T2 EI KILARC-DESCHUTES 14/292 RPL POLE | 31510880 | KILARC-DESCHUTES | 014/292 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.072216 | 40.5647 | ETL.7300 | 40600402 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119336884 | Q2 | T3 EI KONOCTI-EAGLE ROCK 1/7 RPR GYWW | 44565795 | KONOCTI-EAGLE ROCK | 001/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.785673 | 38.8381 | ETL.6861 | 40808788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337038 | Q2 | T2 EI FORT ROSS-GUALAL 51/005 RPR GYWW |  | GUALALA-MONTE RIO | 051/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | 2021-06-07 | 2021-06-14 | 2021-06-09 | 2021-06-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.430084 | 38.7316 | ETL.6980 | 40750317 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337136 | Q2 | T3 EI DRUM-SPAULDING 5/117 RPR GYWW | 44388666 | DRUM-SPAULDING | 005/117 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.704053 | 39.2934 | ETL.6770 | 40751876 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337174 | Q2 | T2 EI IGNACIO-BOLINS #2 6/80 INST FIBER | 44640732 | IGNACIO-BOLINAS #2 | 006/080 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.63217 | 38.121 | ETL.7180 | 40827654 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337192 | Q2 | DI IGNACIO-BOLINAS #1 6/63A RPLC HRDW | 44640733 | IGNACIO-BOLINAS #1 | 006/063A | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-05-03 | 2021-04-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.631133 | 38.0254 | ETL.7140 | 40770090 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337226 | Q2 | T2 EI FORT ROSS-GUALALA 51/3 BOND GUY |  | GUALALA-MONTE RIO | 051/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | 2021-06-07 | 2021-06-14 | 2021-06-09 | 2021-06-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.42658 | 38.7308 | ETL.6980 | 40661485 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337230 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 24/214 RPL PL | 31526498 | BRIDGEVILLE-COTTONWOOD | 024/214 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.729049 | 40.3717 | ETL.1110 | 44423973 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337231 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 24/214 RPL PL | 31526498 | BRIDGEVILLE-COTTONWOOD | 024/214 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.729049 | 40.3717 | ETL.1110 | 44423974 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337378 | Q3 | T2 CARIBOU #2 ;03/027 INST MRKW |  | CARIBOU #2 | ;003/027 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946307 | 39.9779 | ETL.6280 | 40824641 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337418 | Q2 | T3 EI KONOCTI-EAGLE ROCK 1/4 RPR ANCHOR | 44610613 | KONOCTI-EAGLE ROCK | 001/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.789028 | 38.8369 | ETL.6861 | 40769680 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337877 | Q3 | T2 EI CARIBOU-WESTWOOD 13/262 RPR ANCHOR |  | CARIBOU-WESTWOOD | 013/262 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.077412 | 40.2436 | ETL.6300 | 40758637 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119337912 | Q2 | T2 EI TRINITY-MAPLE CREEK 1/18 REPLACE P | 31510957 | TRINITY-MAPLE CREEK | 001/018 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.964397 | 40.7316 | ETL.8170 | 40906261 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338364 | Q2 | T2 EI TRINITY-MAPLE CREEK 10/6 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 010/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.097229 | 40.7669 | ETL.8170 | 40906400 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338444 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 51/388 RPR FO | 44634177 | BRIDGEVILLE-COTTONWOOD | 051/388 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.222763 | 40.4135 | ETL.1110 | 40759376 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338500 | Not Scheduled | T2 DI DRUM-SUMMIT #1 27/318A BOND GUY | 44409003 | DRUM-SUMMIT #1 | 027/318A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329101 | 39.3168 | ETL.1440 | 40597045 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338502 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 27/318A RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 027/318A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329101 | 39.3168 | ETL.1440 | 40597045 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338510 | Q3 | T2 DI CARIBOU #2 20/14 RPR INSW |  | CARIBOU #2 | 020/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.020951 | 40.0313 | ETL.6280 | 40788907 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338527 | Q2 | T2 EI HAT CREEK #1-WESTWOD 32/628 RPR WD | 31511044 | HAT CREEK #1-WESTWOOD | 032/628 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.109478 | 40.6074 | ETL.7030 | 40759224 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338535 | Q2 | T2 EI HAT CRK #1-WSTWD 26/504 RPL POLE | 31511044 | HAT CREEK #1-WESTWOOD | 026/504 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.197115 | 40.6733 | ETL.7030 | 40827487 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338539 | Q2 | T2 EI HAT CREEK #1-WSTWD 32/630 RPR WPKR |  | HAT CREEK #1-WESTWOOD | 032/630 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.108355 | 40.6061 | ETL.7030 | 40817145 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338554 | Q2 | T2 EI HAT CREEK #1-WESTWD 24/473 RPL STR | 31511044 | HAT CREEK #1-WESTWOOD | 024/473 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.21593 | 40.6909 | ETL.7030 | 40667946 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338610 | Not Scheduled | EI T3NT SAN RAMON-MORAGA 6/27 RPR ROAD |  | SAN RAMON-MORAGA | 006/027 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.018436 | 37.6879 | ETL.5660 | 40681921 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338766 | Q2 | T3 EI KONOCTI-EAGLE ROCK 1/0 RMV DEBRIS | 44610613 | KONOCTI-EAGLE ROCK | 001/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2021-01-09 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.795393 | 38.8358 | ETL.6861 | 44679459 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338823 | Q3 | T2 DI CARIBOU #2 ;004/3 RMV PL BUTTS |  | CARIBOU #2 | ;004/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946568 | 39.976 | ETL.6280 | 40651988 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338827 | Q3 | T2 DI CARIBOU #2 ;004/3 RPLC INSW | 31508413 | CARIBOU #2 | ;004/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.946568 | 39.976 | ETL.6280 | 40680882 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338962 | Not Scheduled | T2 DI DRUM-SUMMIT #1 27/318B BOND GUY | 44409003 | DRUM-SUMMIT #1 | 027/318 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329042 | 39.3168 | ETL.1440 | 42572739 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338968 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 27/318B RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 027/318 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329042 | 39.3168 | ETL.1440 | 42572739 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119338978 | Not Scheduled | T2 EI SPAULDING-SUMMIT 4/151 CANCEL | 44421022 | SPAULDING-SUMMIT | 004/151 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-09 | 2021-07-09 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.575442 | 39.3071 | ETL.8060 | 40668661 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339110 | Q3 | T2 DI CARIBOU #2 ;005/0 RMV PL BUTTS |  | CARIBOU #2 | ;005/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950517 | 39.9641 | ETL.6280 | 40614979 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339116 | Q3 | T2 DI CARIBOU #2 ;005/12 RPR POLE |  | CARIBOU #2 | ;005/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.952942 | 39.9578 | ETL.6280 | 40668318 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339171 | Q2 | T2 EI HAT CREEK #1-WESTD 24/470 RPR STRW |  | HAT CREEK #1-WESTWOOD | 024/470 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.217873 | 40.6927 | ETL.7030 | 40600229 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339204 | Not Scheduled | T2 EI SPAULDING-SUMMIT 4/153 RPR POLE | 44411158 | SPAULDING-SUMMIT | 004/153 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.574637 | 39.3069 | ETL.8060 | 40770653 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339288 | Mar | T2 EI KLRC-DSCHTS A023/494 RPR WP HOLES | 44406470 | KILARC-DESCHUTES | A023/494 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339289 | Mar | T2 EI KLRC-DSCHTS A023/492 RPR WP HOLES | 44406470 | KILARC-DESCHUTES | A023/492 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.25326 | 40.5639 | ETL.7300 | 40653264 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339297 | Mar | T2 EI KLRC-DSCHTS A023/490 RPL POLE | 31529821 | KILARC-DESCHUTES | A023/490 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.251558 | 40.5639 | ETL.7300 | 40588852 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339312 | Mar | T2 EI KILARC-DESCHUTES A023/491 RPL POL | 31510880 | KILARC-DESCHUTES | A023/491 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.252284 | 40.5639 | ETL.7300 | 40668064 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339342 | Not Scheduled | T2 DI DRUM-SUMMIT #1 22/264 RPR POLE | 44409003 | DRUM-SUMMIT #1 | 022/264 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.410339 | 39.3111 | ETL.1440 | 44767652 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339347 | Not Scheduled | T2 DI DRUM-SUMMIT #1 27/318C BOND GUY | 44409003 | DRUM-SUMMIT #1 | 027/318C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329001 | 39.3168 | ETL.1440 | 42572740 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339437 | Not Scheduled | COTTONWOOD #1 1/13 BENT STL |  | COTTONWOOD #1 | 001/013 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.268013 | 40.3703 | ETL.6620 | 40910955 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339474 | Not Scheduled | COTTONWOOD #1 1/14 BENT STL |  | COTTONWOOD #1 | 001/014 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.268012 | 40.3685 | ETL.6620 | 40910956 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339512 | Not Scheduled | COTTONWOOD #1 1/16 BENT STL |  | COTTONWOOD #1 | 001/016 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.268001 | 40.365 | ETL.6620 | 40910958 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339552 | Not Scheduled | T2 COTTONWOOD #1 2/17 BENT STL |  | COTTONWOOD #1 | 002/017 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267985 | 40.3632 | ETL.6620 | 40910961 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339562 | Not Scheduled | T2 DI DRUM-SUMMIT #2 24/288 RPL INSW | 31522060 | DRUM-SUMMIT #2 | 024/288 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.381621 | 39.3226 | ETL.1450 | 44552397 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339614 | Not Scheduled | T2 COTTONWOOD #1 2/19 BENT STL |  | COTTONWOOD #1 | 002/019 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.26796 | 40.3591 | ETL.6620 | 40910963 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339641 | Not Scheduled | DI DRUM-SUMMIT #2 11/135 RPL STRW | 31498154 | DRUM-SUMMIT #2 | 011/135 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.590784 | 39.3326 | ETL.1450 | 44561203 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119339652 | Not Scheduled | T2 COTTONWOOD #1 2/020 RPR FOUND |  | COTTONWOOD #1 | 002/020 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267978 | 40.3575 | ETL.6620 | 40910964 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339685 | Not Scheduled | T2 COTTONWOOD #1 03/028 RPR STRT |  | COTTONWOOD #1 | 003/028 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267857 | 40.3411 | ETL.6620 | 40910972 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339688 | Q2 | EI BRDGEVILE-COTNWD 19/175 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 019/175 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.6264916 | 40.3789 | ETL.1110 | 44423269 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339747 | Q3 | T2 DI CARIBOU #2 020/022 RMV PL BUTT |  | CARIBOU #2 | 020/022 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.015388 | 40.032 | ETL.6280 | 40675452 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339774 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 28/114 RPR GYWS |  | DIABLO-MIDWAY #2 | 028/114 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.366731 | 35.1656 | ETL.5970 | 40762410 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-23 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339795 | Q2 | T2 EI FORT ROSS-GUALAL 50/005 RPR GYWW |  | GUALALA-MONTE RIO | 050/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.414257 | 38.7262 | ETL.6980 | 40750315 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339804 | Q2 | T2 EI HAT CREEK #1-WSTWD 42/823 RPR WDPK | 44406426 | HAT CREEK #1-WESTWOOD | 042/823 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023307 | 40.4797 | ETL.7030 | 40868246 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339805 | Q2 | T2 EI HAT CREEK #1-WSTWD 42/823 REFRAME | 31508135 | HAT CREEK #1-WESTWOOD | 042/823 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023307 | 40.4797 | ETL.7030 | 40868246 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339858 | Q3 | T2 DI CARIBOU #2 020/020 RMV PL BUTT |  | CARIBOU #2 | 020/020 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.017555 | 40.032 | ETL.6280 | 40614863 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119339867 | Q2 | T2 EI HAT CRK #1-WESTWD 24/468 RPR STRW |  | HAT CREEK #1-WESTWOOD | 024/468 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.219153 | 40.6939 | ETL.7030 | 40868476 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340219 | Q3 | T2 EI CARIBOU-WESTWOOD 06/117 RPL PL | 31511053 | CARIBOU-WESTWOOD | 006/117 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.104725 | 40.1594 | ETL.6300 | 40768930 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340291 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 28/541 RPR P |  | HAT CREEK #1-WESTWOOD | 028/541 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.17434 | 40.6519 | ETL.7030 | 40656898 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340292 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 28/551 RERAM | 31508607 | HAT CREEK #1-WESTWOOD | 028/551 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.166768 | 40.6471 | ETL.7030 | 40656900 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340297 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 28/548 REFRA | 31508607 | HAT CREEK #1-WESTWOOD | 028/548 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.169115 | 40.6486 | ETL.7030 | 40617062 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340343 | Q2 | DI GATES-PANOCHE #1 15/74 RMV DEBRIS | 44404668 | GATES-PANOCHE #1 | 015/074 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.275872 | 36.3276 | ETL.4720 | 40753581 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119340362 | Q2 | T2 EI KONOCTI-MIDDLETWN 24/010 RPL PL | 31509670 | KONOCTI-MIDDLETOWN | 024/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.617406 | 38.9098 | ETL.6380 | 40615053 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340420 | Q2 | DI GATES-PANOCHE #1 15/74 RPR BENT STL | 44404664 | GATES-PANOCHE #1 | 015/074 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.275872 | 36.3276 | ETL.4720 | 40753581 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119340455 | Mar | EI KILARC-DESCHUTES 18/374 INST DAMPERS | 44406470 | KILARC-DESCHUTES | 018/374 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.151742 | 40.5637 | ETL.7300 | 44327689 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340456 | Mar | EI KILARC-DESCHUTES 18/375 RPR WP HOLE | 44406470 | KILARC-DESCHUTES | 018/375 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.152805 | 40.5637 | ETL.7300 | 40827908 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340472 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 28/113 RPL INSUL | 31527003 | DIABLO-MIDWAY #3 | 028/113 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.369773 | 35.1659 | ETL.5980 | 40651892 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340505 | Mar | EI KILARC-DESCHUTES 018/372 RPLC STRW | 31510880 | KILARC-DESCHUTES | 018/372 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.149921 | 40.5637 | ETL.7300 | 40668418 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340512 | Mar | T2 EI KILARC-DESCHUTES 17/367 RPR STRW | 44406470 | KILARC-DESCHUTES | 017/367 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.145169 | 40.5636 | ETL.7300 | 40827912 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340558 | Not Scheduled | T2NT DI DRM-SMMIT #2 28/333 RMV PL BUTT | 44409006 | DRUM-SUMMIT #2 | 028/333 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44420819 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340629 | Q2 | T3 DI PIT #1-COTTONWOOD 24/198 RPR STRT |  | PIT #1-COTTONWOOD | 024/198 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.887779 | 40.8051 | ETL.5390 | 40868865 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340793 | Not Scheduled | T2 DI DRUM-SUMMIT #2 012/143 RPL INSW |  | DRUM-SUMMIT #2 | 012/143 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.576588 | 39.3328 | ETL.1450 | 40792029 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340810 | Q2 | T3 DI PIT #1-COTTONWOOD 24/198 RPR FOND |  | PIT #1-COTTONWOOD | 024/198 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.887779 | 40.8051 | ETL.5390 | 40868865 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340836 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 31/598 RPL I | 31514229 | HAT CREEK #1-WESTWOOD | 031/598 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.129988 | 40.6242 | ETL.7030 | 40656903 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340837 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 31/605 RPR I |  | HAT CREEK #1-WESTWOOD | 031/605 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.124457 | 40.6207 | ETL.7030 | 40600247 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340838 | Q2 | T2 EI HAT CREEK #1-WETWD 21/417 RPR STR |  | HAT CREEK #1-WESTWOOD | 021/417 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.252508 | 40.7241 | ETL.7030 | 40759200 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340839 | Q2 | T2 EI HAT CREEK #1-WESTWD 31/598 RPR WDP | 31511044 | HAT CREEK #1-WESTWOOD | 031/598 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.129988 | 40.6242 | ETL.7030 | 40656903 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340861 | Q2 | T2 EI HAT CRK #1-WESTWD 21/413 RPR STRW |  | HAT CREEK #1-WESTWOOD | 021/413 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.255293 | 40.7263 | ETL.7030 | 40616901 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340906 | Q3 | T2 EI CARIBOU #2 2/19 RPR ANCS |  | CARIBOU #2 | 002/019 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.183217 | 40.0657 | ETL.6280 | 40867519 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340909 | Not Scheduled | T2 EI SPAULDING-SUMMIT 004/157 RPLC STRW | 31508780 | SPAULDING-SUMMIT | 004/157 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.573035 | 39.3066 | ETL.8060 | 40876682 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340939 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/101 RPR WPKR | 44410506 | SPAULDING-SUMMIT | 002/101 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.602143 | 39.3131 | ETL.8060 | 40650040 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119340995 | Feb | EI T3NT DESABLA-CENTERVILLE 1/23 RMV BUT |  | DESABLA-CENTERVILLE | 001/023 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.631388 | 39.8499 | ETL.6720 | 40649884 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341018 | Not Scheduled | T3 EI CARIBOU-PALERMO :31/253 RPL HRDT |  | CARIBOU-PALERMO | :031/253 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.463429 | 39.763 | ETL.3190 | 40668944 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341022 | Q2 | T2 EI TRINITY-MAPLE CREEK 033/000 RPLC S | 31510696 | TRINITY-MAPLE CREEK | 033/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.506317 | 40.7006 | ETL.8170 | 40906474 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341030 | Not Scheduled | T3 EI FULTON-HOPLAND 29/002 RPL POLE | 31508467 | FULTON-HOPLAND | 029/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.010828 | 38.8417 | ETL.6890 | 40677898 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341068 | Q2 | T2 EI HAT CREEK #1-WESTWD 30/583 RMV DEB | 44448898 | HAT CREEK #1-WESTWOOD | 030/583 | ICH | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.141767 | 40.6315 | ETL.7030 | 40825592 | Other | Other | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 625 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341081 | Q2 | DI GATES-PANOCHE #1 33/157 RMV HRDT | 44408184 | GATES-PANOCHE #1 | 033/157 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.474204 | 36.5274 | ETL.4720 | 40811179 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119341194 | Q2 | T2 EI TRINITY-MAPLE CREEK 21/008 RMV STE | 44364310 | TRINITY-MAPLE CREEK | 021/008 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.294937 | 40.709 | ETL.8170 | 44366791 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341196 | Q2 | T2 EI TRINITY-MAPLE CREEK 21/008 RPL DAM | 44364310 | TRINITY-MAPLE CREEK | 021/008 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2949508 | 40.709 | ETL.8170 | 44366801 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341197 | Q2 | EI TRINITY-MAPLE CREEK 21/1 RPL DAMPER | 44401954 | TRINITY-MAPLE CREEK | 021/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.2851526 | 40.7135 | ETL.8170 | 44420625 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341198 | Q2 | T2 EI TRINITY-MAPLE CREEK 21/7 RPL DAMPE | 44401954 | TRINITY-MAPLE CREEK | 021/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293377 | 40.7094 | ETL.8170 | 40803410 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341230 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/3 REFRAME | 31507980 | CARIBOU-PLUMAS JCT | ;009/003 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.934023 | 39.9394 | ETL.6290 | 40653377 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341232 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/3 RMV PL BUT | 44408852 | CARIBOU-PLUMAS JCT | ;009/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.934023 | 39.9394 | ETL.6290 | 40653377 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341234 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/0 RMV PL BUT | 44408852 | CARIBOU-PLUMAS JCT | ;009/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.93412 | 39.9405 | ETL.6290 | 40589791 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341235 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/0 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | ;009/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.93412 | 39.9405 | ETL.6290 | 40589791 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341257 | Not Scheduled | T3 EI FULTON-HOPLAND 28/012 RPL POLE | 31508467 | FULTON-HOPLAND | 028/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.004895 | 38.8348 | ETL.6890 | 40692989 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341365 | Q4 | T3 DRUM-RIO OSO #2 08/089 RPL INSW | 31521958 | DRUM-RIO OSO #2 | 008/089 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8904714 | 39.1869 | ETL.1430 | 44305011 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341376 | Q2 | T2 EI HAT CRK #1-WSTWD 19/377 RPL STRW | 31511044 | HAT CREEK #1-WESTWOOD | 019/377 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.279558 | 40.7459 | ETL.7030 | 40676307 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341377 | Q2 | T2 EI HAT CRK #1-WESTWD 19/369 REFRM STR | 31508607 | HAT CREEK #1-WESTWOOD | 019/369 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.285055 | 40.7504 | ETL.7030 | 40770735 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341378 | Q2 | T2 EI HT CRK #1-WSTWD 19/372 RPR STRW |  | HAT CREEK #1-WESTWOOD | 019/372 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.283085 | 40.7487 | ETL.7030 | 40816130 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341386 | Q2 | EI BRIDGEVILLE-COTTONWOOD 29/250 RPL POL | 31526498 | BRIDGEVILLE-COTTONWOOD | 029/250 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.8263454 | 40.3648 | ETL.1110 | 44561186 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341387 | Not Scheduled | T2 EI BRIDGEVILLE-COTNWD 30/255 RPR FOUN |  | BRIDGEVILLE-COTTONWOOD | 030/255 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.842474 | 40.3636 | ETL.1110 | 40760091 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341388 | Not Scheduled | T2 EI BRIDGEVILE-COTNWD 28/238 RPR FOUND |  | BRIDGEVILLE-COTTONWOOD | 028/238 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.797951 | 40.3668 | ETL.1110 | 40683960 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341390 | Not Scheduled | T2 DI CYCS-CMBRIA 15/107 GRNDWASH INSS |  | CAYUCOS-CAMBRIA | 015/107 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.071227 | 35.5803 | ETL.8560 | 40793377 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341393 | Not Scheduled | EI T3NT DRUM-RIO OSO #2 8/084 RMV VEG |  | DRUM-RIO OSO #2 | 008/084 | HNA | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.881811 | 39.1903 | ETL.1430 | 40761902 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341395 | Q3 | T3NT DRUM-RIO OSO #2 8/89 RPR ROAD | 44388506 | DRUM-RIO OSO #2 | 008/089 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-31 | 2021-07-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.890471 | 39.1869 | ETL.1430 | 44304979 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341396 | Q3 | EI T3NT DRUM-RIO OSO #2 7/79 RMV VEG | 43663366 | DRUM-RIO OSO #2 | 007/079 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-31 | 2021-07-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.876335 | 39.1933 | ETL.1430 | 40858065 | Road | Brush Fuel | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341403 | Mar | T3 EI DRUM-RIO OSO #2 7/79 RMV NEST | 44388509 | DRUM-RIO OSO #2 | 007/079 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2021-01-09 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876335 | 39.1933 | ETL.1430 | 40858065 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341416 | Mar | T3 DI MORAGA-CLAREMONT #2 2/19 RPLC INSS | 31530201 | MORAGA-CLAREMONT #2 | 002/019 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-03-23 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.197886 | 37.8607 | ETL.2710 | 40878712 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341427 | Q2 | T2 EI TRINITY-MAPLE CREEK 33/4 RPL ANCHO | 31510957 | TRINITY-MAPLE CREEK | 033/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5188866 | 40.7069 | ETL.8170 | 44771073 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341476 | Q3 | T2 EI CARIBOU #2 05/014 RPL PL | 31509660 | CARIBOU #2 | 005/014 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.218137 | 40.0416 | ETL.6280 | 42559992 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341479 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 38/734 RPR P |  | HAT CREEK #1-WESTWOOD | 038/734 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.048768 | 40.5418 | ETL.7030 | 40758799 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341482 | Q2 | T2 EI HAT CREEK #1-WESTWD 21/409 RPR GYW |  | HAT CREEK #1-WESTWOOD | 021/409 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.258083 | 40.7286 | ETL.7030 | 40817125 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341484 | Q2 | T2 EI HAT CRK #1-WESTWD 21/411 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 021/411 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.256705 | 40.7274 | ETL.7030 | 40877587 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341487 | Q2 | T2 EI HAT CRK #1-WESTWD 21/408 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 021/408 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.25876 | 40.7291 | ETL.7030 | 40769952 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341492 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 42/815 RPL P | 31511044 | HAT CREEK #1-WESTWOOD | 042/815 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023442 | 40.4846 | ETL.7030 | 40599854 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341498 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 42/817 RPR W |  | HAT CREEK #1-WESTWOOD | 042/817 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023397 | 40.4838 | ETL.7030 | 40675729 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341499 | Q2 | T2 EI HAT CREEK #1-WESTWD 42/818 RPR WDP |  | HAT CREEK #1-WESTWOOD | 042/818 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.02337 | 40.4834 | ETL.7030 | 40667981 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341518 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 38/735 RPR W |  | HAT CREEK #1-WESTWOOD | 038/735 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.0482 | 40.5412 | ETL.7030 | 40827619 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341519 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 37/727 REFRA | 31508607 | HAT CREEK #1-WESTWOOD | 037/727 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.052813 | 40.5462 | ETL.7030 | 40825604 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341530 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 38/732 RPR P |  | HAT CREEK #1-WESTWOOD | 038/732 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.049933 | 40.5431 | ETL.7030 | 40656665 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341531 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 38/733 RPR P |  | HAT CREEK #1-WESTWOOD | 038/733 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.049367 | 40.5424 | ETL.7030 | 40770761 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341532 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 38/729 RPR P |  | HAT CREEK #1-WESTWOOD | 038/729 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.051653 | 40.5449 | ETL.7030 | 40616924 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341533 | Q2 | T2 EI HAT CREEK #1-WESTWD 37/722 REPL PO | 31508607 | HAT CREEK #1-WESTWOOD | 037/722 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.05569 | 40.5493 | ETL.7030 | 40701317 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341534 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 37/728 RPR P |  | HAT CREEK #1-WESTWOOD | 037/728 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.052235 | 40.5456 | ETL.7030 | 40877569 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341539 | Not Scheduled | EI T3NT BRUNSWICK #1 TAP 2/19 INS ACG | 31508155 | BRUNSWICK #1 TAP | 002/019 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.034465 | 39.1705 | ETL.1422 | 40857283 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341541 | Not Scheduled | T2 EI HAT CREEK #1-WESTWOOD 37/722 RMV V |  | HAT CREEK #1-WESTWOOD | 037/722 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.05569 | 40.5493 | ETL.7030 | 40701317 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341543 | Q2 | T2 EI HAT CRK #1-WSTWD 38/736 RPR ANCHOR |  | HAT CREEK #1-WESTWOOD | 038/736 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.047627 | 40.5405 | ETL.7030 | 40815878 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341560 | Mar | T3 EI BRUNSWICK #2 TAP 2/18 RPL DAMPERS | 44388510 | BRUNSWICK #2 TAP | 002/018 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 |  |  | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.0344709 | 39.1686 | ETL.1431 | 40885585 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341564 | Q2 | EI _042/005 RPR GRND WASH | 44644114 | ELK-GUALALA | 042/005 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-20 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6812605 | 39.0569 | ETL.8410 | 44312669 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341622 | Q3 | T2 DI CARIBOU #2 ;3/27 RMV PL BUTT |  | CARIBOU #2 | ;003/027 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946307 | 39.9779 | ETL.6280 | 40824641 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341624 | Not Scheduled | DI GATES-PANOCHE #1 21/98 INST MRKW | 44408180 | GATES-PANOCHE #1 | 021/098 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.337014 | 36.3826 | ETL.4720 | 40863640 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119341627 | Q3 | T2 DI CARIBOU #2 ;3/20 RMV PL BUTT |  | CARIBOU #2 | ;003/020 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946183 | 39.9818 | ETL.6280 | 40614896 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341634 | Q3 | T2 DI CARIBOU #2 4/18 RMV BUTT |  | CARIBOU #2 | ;004/018 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.948745 | 39.9687 | ETL.6280 | 40865182 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341640 | Q4 | T3 DI MAPLE CREEK-HOOPA 10/10 RPL POLE | 31510885 | MAPLE CREEK-HOOPA | 010/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.771378 | 40.8912 | ETL.7490 | 44825368 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341725 | Q4 | T3 DI MDDL FRK-GLD HLL 7/64 RPR STRW | 44388577 | MIDDLE FORK-GOLD HILL | 007/064 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-07-08 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.717409 | 39.0037 | ETL.5140 | 44553638 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341812 | Not Scheduled | T2 DI CARIBOU-PALERMO :25/209 INS HRDT |  | CARIBOU-PALERMO | :025/209 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.420523 | 39.8364 | ETL.3190 | 40863363 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341813 | Not Scheduled | T2 DI CARIBOU-PLRMO :25/209 BURRIED STUB |  | CARIBOU-PALERMO | :025/209 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.420523 | 39.8364 | ETL.3190 | 40863363 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341815 | Feb | T3NT DI MORAGA-CLARMONT #1 2/17 RPR FOND | 44631266 | MORAGA-CLAREMONT #1 | 002/017 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-08 | 2022-07-08 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.193617 | 37.8618 | ETL.2700 | 44188777 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341816 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/11 RPR GYWW | 44410506 | SPAULDING-SUMMIT | 000/011 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.640462 | 39.3237 | ETL.8060 | 40586074 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341819 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 16/112 RPL STRW | 31510654 | CAYUCOS-CAMBRIA | 016/112 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.077407 | 35.5836 | ETL.8560 | 40606214 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-17 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341886 | Q3 | T2 DI CARIBOU-WESTWOOD 008/166 RPR CNDW |  | CARIBOU-WESTWOOD | 008/166 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.076402 | 40.1859 | ETL.6300 | 44191063 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341890 | Not Scheduled | DI GATES-PANOCHE #1 32/152 INST MRKS | 44408180 | GATES-PANOCHE #1 | 032/152 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [6 empty] | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.462384 | 36.5156 | ETL.4720 | 40663968 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119341892 | Not Scheduled | DI GATES-PANOCHE #1 20/96 INST MRKS | 44408180 | GATES-PANOCHE #1 | 020/096 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [6 empty] | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.332446 | 36.3776 | ETL.4720 | 40811794 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119341936 | Q2 | T2 DI IGNACIO-BOLINAS #1 6/63B RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 006/063 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.631148 | 38.0254 | ETL.7140 | 41111824 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341975 | Not Scheduled | T2NT DI SPAULDNG-SUMMIT 0/17 RMV PL BUTT | 44409514 | SPAULDING-SUMMIT | 000/017 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.638295 | 39.3231 | ETL.8060 | 40826222 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119341977 | Not Scheduled | T2NT DI SPAULDNG-SUMMIT 0/2 RMV DEBRIS | 44409514 | SPAULDING-SUMMIT | 000/002 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2022-07-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.644199 | 39.3246 | ETL.8060 | 40660099 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119348374 | Q2 | T2 TRINITY-MAPLE CREEK 39/5C RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 039/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-14 | 2021-06-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.618915 | 40.7192 | ETL.8170 | 44769577 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119348375 | Q2 | T2 TRINITY-MAPLE CREEK 39/5R RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 039/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-14 | 2021-06-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.618915 | 40.7192 | ETL.8170 | 44769578 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119348377 | Not Scheduled | T3NT DI FRNCH MDWS-MDL FRK 3/64 RMV BUTT | 44388669 | FRENCH MEADOWS-MIDDLE FORK | 003/064 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.449398 | 39.046 | ETL.6870 | 40766819 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119348378 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 3/64 RPLC ANCW | 44388668 | FRENCH MEADOWS-MIDDLE FORK | 003/064 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.449398 | 39.046 | ETL.6870 | 40766819 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350133 | Q3 | T2 EI CRIBOU-WSTWD 14/292 RPL ANCHOR | 31511088 | CARIBOU-WESTWOOD | 014/292 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.083862 | 40.2628 | ETL.6300 | 40656501 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350143 | Q2 | T2 EI HAT CRK #1-WSTWD 26/500 INST TIE W |  | HAT CREEK #1-WESTWOOD | 026/500 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.198738 | 40.6751 | ETL.7030 | 40676346 | Tie Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350145 | Q2 | T2 EI HAT CRK #1-WESTWD 26/498 RPR INSW |  | HAT CREEK #1-WESTWOOD | 026/498 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.199905 | 40.6762 | ETL.7030 | 40617059 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350147 | Q2 | T2 EI HAT CRK #1-WSTWD 26/499 RPR CRSW |  | HAT CREEK #1-WESTWOOD | 026/499 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19933 | 40.6756 | ETL.7030 | 40601621 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350164 | Not Scheduled | T3 EI DRUM-SPAULDING 004/106 RMV VEG |  | DRUM-SPAULDING | 004/106 | HNA | E | 2020_(3) On high spread structure |  | 2020-07-09 | 2021-01-09 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.707529 | 39.2879 | ETL.6770 | 40810147 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350165 | Not Scheduled | T3 EI DRUM-SPAULDING 004/104 RMV VEG |  | DRUM-SPAULDING | 004/104 | HNA | E | 2020_(3) On high spread structure |  | 2020-07-09 | 2021-01-09 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.708394 | 39.2868 | ETL.6770 | 40751833 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350193 | Q2 | EI BRIDGEVILLE-COTTONWOOD 27/235 RPR WPK | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/235 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7897022 | 40.3674 | ETL.1110 | 44561121 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350194 | Q2 | EI COTTONWOOD-HUMBOLDT_027/231 RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/231 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7781384 | 40.3682 | ETL.1110 | 44565796 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350196 | Q2 | T2 EI BRDGVLLE-CTTNWD 27/234B RPR INSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/234 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.787163 | 40.3676 | ETL.1110 | 42603532 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350197 | Q2 | T2 EI BRDGVLLE-CTTNWD 27/234C RPR INSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/234C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.787188 | 40.3676 | ETL.1110 | 42603533 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350211 | Q2 | T2 EI BRDGVLLE-CTTNWD 27/234A RMV DEBRIS | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/234A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.787173 | 40.3675 | ETL.1110 | 40762646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350213 | Q2 | EI BRIDGEVILLE-COTTONWOOD 28/237 RMV BUT | 44404807 | BRIDGEVILLE-COTTONWOOD | 028/237 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7945997 | 40.367 | ETL.1110 | 44561125 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350215 | Q2 | EI BRIDGEVILLE-COTTONWOOD 28/239L RMV BU | 44404807 | BRIDGEVILLE-COTTONWOOD | 028/239 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7987314 | 40.3668 | ETL.1110 | 44551292 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350216 | Q2 | EI BRIDGEVILLE-COTTONWOOD 27/235 RMV BUT | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/235 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7897022 | 40.3674 | ETL.1110 | 44561122 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350217 | Q2 | EI BRIDGEVILLE-COTTONWOOD 26/227 RPR GYW | 44404807 | BRIDGEVILLE-COTTONWOOD | 026/227 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7668032 | 40.369 | ETL.1110 | 44561148 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350218 | Q2 | EI BRIDGEVILLE-COTTONWOOD 27/229 RPR WPK | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/229 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7743949 | 40.3685 | ETL.1110 | 44561177 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350222 | Q2 | T2 EI BRDGVLLE-CTTNWD 27/234A RPR INSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 027/234A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.787173 | 40.3675 | ETL.1110 | 40762646 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350280 | Mar | T2 ATASCADERO-CAYUCOS 2/21 RPL POLE | 31508522 | ATASCADERO-CAYUCOS | 002/021 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-13 | 2021-06-13 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-122.566592 | 38.7929 | ETL.8480 | 44319816 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350281 | Mar | T2 ATASCADERO-CAYUCOS 2/21 RPL POLE | 31508522 | ATASCADERO-CAYUCOS | 002/021 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-13 | 2021-06-13 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-122.566592 | 38.7929 | ETL.8480 | 44319817 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350355 | Q3 | T2NT DI CRBOU-WESTWD 15/301 INS MRKW |  | CARIBOU-WESTWOOD | 015/301 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-07 | 2022-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08757 | 40.2678 | ETL.6300 | 40615018 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350448 | Not Scheduled | DI GATES-PANOCHE #2 23/106 RPL INST | 31514619 | GATES-PANOCHE #2 | 023/106 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.355033 | 36.4023 | ETL.4730 | 40839169 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119350643 | Q3 | DI CARIBOU-PLUMAS JCT ;10/2 INS MRKW | 44408852 | CARIBOU-PLUMAS JCT | ;010/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-08-20 | 2021-08-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.918952 | 39.9349 | ETL.6290 | 40657261 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350752 | Not Scheduled | EI SPAULDING-SUMMIT 4/162 RPR POLE | 44411158 | SPAULDING-SUMMIT | 004/162 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.570505 | 39.3061 | ETL.8060 | 40771552 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119350843 | Not Scheduled | EI T2NT SPAULDING-SUMMIT 19/615 INS MRKW | 44421024 | SPAULDING-SUMMIT | 019/615 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329391 | 39.3162 | ETL.8060 | 40828185 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119350911 | Q3 | T2NT DI CARIBOU #2 005/001 RMV STRW |  | CARIBOU #2 | ;005/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950792 | 39.9635 | ETL.6280 | 40600652 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119351052 | Not Scheduled | EI DIABLO-MIDWAY #3 45/186 RPL INSS | 31527003 | DIABLO-MIDWAY #3 | 045/186 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [9 empty] | South | WSIP | [6 empty] | '-120.072437 | 35.2277 | ETL.5980 | 40808234 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119351057 | Q2 | T2 EI IGNACIO-BOLINAS #2 7/087 REPULL GU | 44640735 | IGNACIO-BOLINAS #2 | 007/087 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.640659 | 38.1188 | ETL.7180 | 44660763 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119351132 | Not Scheduled | T3NT DI CLGT-ALLGHNY 12/339 RMV PL BUTT | 44388578 | COLGATE-ALLEGHANY | 012/339 | ICW | F | 2020_(1a) PSPS |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.013108 | 39.4163 | ETL.6470 | 40822620 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119351134 | Not Scheduled | T3 DI CLGT-ALLGHNY 12/339 RPR POLE | 44388660 | COLGATE-ALLEGHANY | 012/339 | ICW | E | 2020_(1a) PSPS |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.013108 | 39.4163 | ETL.6470 | 40822620 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119351192 | Q3 | EI T2NT CARIBOU-WESTWD 15/303 RMV PL BU | 31527022 | CARIBOU-WESTWOOD | 015/303 | 93J | F | 2020_(2) High fire spread TD |  | 2020-07-10 | 2022-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.087803 | 40.2684 | ETL.6300 | 40698926 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119351275 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 10/288 RPR POLE | 44388660 | COLGATE-ALLEGHANY | 010/288 | ICW | E | 2020_(1a) PSPS |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.03178 | 39.3907 | ETL.6470 | 40760713 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119351278 | Q3 | T2 DI CARIBOU #2 ;1/17 RMV BUTT |  | CARIBOU #2 | ;001/017 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962992 | 40.005 | ETL.6280 | 40809556 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119352316 | Q3 | T2 DI CRBU-WSTWD 6/129 RMV DEBRIS |  | CARIBOU-WESTWOOD | 006/129 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.098315 | 40.168 | ETL.6300 | 44191100 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353297 | Not Scheduled | T2 DI DRUM-SUMMIT #1 12/143C RPLC INSW | 31521959 | DRUM-SUMMIT #1 | 012/143C | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.574843 | 39.3329 | ETL.1440 | 42572964 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353310 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 35/143 RPR GYWT |  | DIABLO-MIDWAY #3 | 035/143 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.239066 | 35.1742 | ETL.5980 | 40651897 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353320 | Q3 | T2 DI CARIBOU-WESTWOOD 6/129 RPR GYWW |  | CARIBOU-WESTWOOD | 006/129 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.098315 | 40.168 | ETL.6300 | 44191100 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353361 | Q3 | T2 DI CARIBOU #2 ;003/25 RPR SPLW |  | CARIBOU #2 | ;003/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.946268 | 39.9791 | ETL.6280 | 44688366 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353365 | Q2 | T2 DI IGNACIO-BOLINAS #2 6/69 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 006/069 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7180 | 44360922 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353367 | Q2 | T2 DI IGNACIO-BOLINAS #2 6/69 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 006/069 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7180 | 44360923 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353369 | Q2 | T2 DI IGNACIO-BOLINAS #2 6/69 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 006/069 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7180 | 44360924 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353450 | Q3 | T2 DI CARIBOU #2 ;003/25 RMV POLE BUTT |  | CARIBOU #2 | ;003/025 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946268 | 39.9791 | ETL.6280 | 44688366 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353490 | Q2 | T2 EI FORT ROSS-GUALALA 49/10 REPLUMB PL |  | GUALALA-MONTE RIO | 049/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.403739 | 38.7228 | ETL.6980 | 40616622 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353503 | Not Scheduled | EI SPAULDING-SUMMIT 004/163 RMV VEG |  | SPAULDING-SUMMIT | 004/163 | HNA | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.570052 | 39.306 | ETL.8060 | 40751909 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119353563 | Q2 | T2 EI HAT CRK #1-WESTWD 27/523 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 027/523 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.1865 | 40.6617 | ETL.7030 | 44686475 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353566 | Q2 | T2 EI HAT CRK #1-WESTWD 26/510 RPL HRDD |  | HAT CREEK #1-WESTWOOD | 026/510 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.194047 | 40.6699 | ETL.7030 | 40676350 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353577 | Q2 | T2 EI HAT CREEK #1-WESTWD 27/521 RRP POL | 44406426 | HAT CREEK #1-WESTWOOD | 027/521 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.18763 | 40.6628 | ETL.7030 | 40701339 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353579 | Q2 | T2 EI HAT CREEK #1-WESTWD 27/520 RPL STR | 31511044 | HAT CREEK #1-WESTWOOD | 027/520 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.188205 | 40.6635 | ETL.7030 | 40601622 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353614 | Not Scheduled | EI SPAULDING-SUMMIT 004/164 INS MKRW | 44409514 | SPAULDING-SUMMIT | 004/164 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.569011 | 39.3057 | ETL.8060 | 40828165 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119353620 | Q4 | T3 DI MDDLE FRK-GLD HLL 9/83R RPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 009/083 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.744297 | 38.9859 | ETL.5140 | 44553515 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353648 | Q2 | T3 EI KONOCTI-EAGLE ROCK 0/10 RMV DEBRIS | 31508610 | KONOCTI-EAGLE ROCK | 000/010 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.80289 | 38.8333 | ETL.6861 | 40615030 | Anchor-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353663 | Q2 | EI T3NT KONOCTI-EAGLE ROCK 0/10 INS MRKW |  | KONOCTI-EAGLE ROCK | 000/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.80289 | 38.8333 | ETL.6861 | 40615030 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353788 | Q3 | T2 EI CARIBOU-WESTWOOD 15/304 RPR GYWW |  | CARIBOU-WESTWOOD | 015/304 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.08785 | 40.2687 | ETL.6300 | 40656504 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353789 | Q3 | T2 EI CARIBOU-WESTWOOD 15/304 RPR JUMPER |  | CARIBOU-WESTWOOD | 015/304 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.08785 | 40.2687 | ETL.6300 | 40656504 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353920 | Q3 | T2 EI CARIBOU-WESTWOOD A15/306 RPR GYWW |  | CARIBOU-WESTWOOD | A015/306 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.087574 | 40.2692 | ETL.6300 | 42624263 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119353997 | Not Scheduled | T2 DI CAYUCS-CAMBRIA 15/102 GRD WAS INSU |  | CAYUCOS-CAMBRIA | 015/102 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.063435 | 35.5755 | ETL.8560 | 40632358 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354045 | Q2 | T2 EI SALINAS-LAURELES A13/291 RPR GYWW | 44294541 | SALINAS-LAURELES | A013/291 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.790968 | 36.5698 | ETL.7930 | 40812153 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354053 | Not Scheduled | T2 EI TRINITY-MAPLE CREEK 12/0 RMV VEG |  | TRINITY-MAPLE CREEK | 012/000 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.1292786 | 40.77 | ETL.8170 | 44420604 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354063 | Q3 | T2 EI CARIBOU-WESTWOOD 13/271 RPR ANCHOR |  | CARIBOU-WESTWOOD | 013/271 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.077568 | 40.2492 | ETL.6300 | 40769658 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354067 | Not Scheduled | T2 EI SPAULDING-SUMMIT 19/606 RPR GYWW | 44421022 | SPAULDING-SUMMIT | 019/606 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.330831 | 39.313 | ETL.8060 | 40809681 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354090 | Q3 | T2 DI CARIBOU-WSTWD 19/384 RPL STRW | 31508283 | CARIBOU-WESTWOOD | 019/384 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.032705 | 40.297 | ETL.6300 | 40698938 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354097 | Q2 | T3 DI SNTH LN-HLF MN BY ?2/7 RPR STRW | 44621669 | SNEATH LANE-HALF MOON BAY | ?002/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-01-07 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384400 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354099 | Q2 | T3 DI SNTH LN-HLF MN BY ?2/7 RPR STRW | 44621669 | SNEATH LANE-HALF MOON BAY | ?002/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-07 | 2021-01-07 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384399 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354183 | Q3 | T2 EI CARIBOU-WESTWOOD 15/306C RPR BOND |  | CARIBOU-WESTWOOD | 015/306C | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.087662 | 40.2695 | ETL.6300 | 42624253 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354202 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 20/561 REPL BG | 44403306 | COLGATE-ALLEGHANY | 020/561 | ICM | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.894901 | 39.465 | ETL.6470 | 40593299 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354284 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 31/126 RPL INS | 31527002 | DIABLO-MIDWAY #2 | 031/126 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.315016 | 35.1695 | ETL.5970 | 40812078 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354344 | Q2 | T2 EI HAT CREEK #1-WESTWD 6/129 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 006/129 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.428848 | 40.896 | ETL.7030 | 40701203 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354362 | Q2 | T2 EI HAT CREEK #1-WSTWD 18/356 RPR WPKR |  | HAT CREEK #1-WESTWOOD | 018/356 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.294148 | 40.7577 | ETL.7030 | 40759192 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354363 | Q2 | T2 EI HAT CREEK #1-WSTWD 18/353 RPR WPKR |  | HAT CREEK #1-WESTWOOD | 018/353 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.296107 | 40.7593 | ETL.7030 | 40592091 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354366 | Q2 | T2 EI HAT CREEK #1-WSTWD 18/356 REFRAME | 31510955 | HAT CREEK #1-WESTWOOD | 018/356 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.294148 | 40.7577 | ETL.7030 | 40759192 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354423 | Feb | T2 EI TRINITY-MAPLE CREEK 2/014 RPL POLE | 31510696 | TRINITY-MAPLE CREEK | 002/014 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 | 2021-02-22 | 2021-02-27 | 2021-02-23 | 2021-02-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.979517 | 40.7343 | ETL.8170 | 40906276 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354541 | Mar | T3 EI ATASCADERO-CAYUCOS 004/037 RPR BND |  | ATASCADERO-CAYUCOS | 004/037 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.738716 | 35.4645 | ETL.8480 | 40597525 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354542 | Mar | T3 EI ATASCADERO-CAYUCOS 004/037 RPR GYW |  | ATASCADERO-CAYUCOS | 004/037 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.738716 | 35.4645 | ETL.8480 | 40597525 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354543 | Not Scheduled | T3 EI ATASCADERO-CAYUCOS 004/039 INST AM |  | ATASCADERO-CAYUCOS | 004/039 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.742773 | 35.4644 | ETL.8480 | 40663152 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354629 | Not Scheduled | T2 DI DRUM-SUMMIT#1 12/140 RMV PL BUTT | 44409001 | DRUM-SUMMIT #1 | 012/140 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.580091 | 39.3325 | ETL.1440 | 44338174 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354634 | Q3 | EI T2NT CARIBOU #2 16/015 RMV PL BUTT |  | CARIBOU #2 | 016/015 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08786 | 40.0157 | ETL.6280 | 40758689 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354644 | Q3 | T2 EI CARIBOU-WESTWOOD 15/307 RPR BOND |  | CARIBOU-WESTWOOD | 015/307 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.087248 | 40.2696 | ETL.6300 | 44191131 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354789 | Q2 | T3 EI KONOCTI-EAGLE ROCK 0/6 REPLUMB | 44610613 | KONOCTI-EAGLE ROCK | 000/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.807623 | 38.8319 | ETL.6861 | 40809243 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354819 | Not Scheduled | DI CARIBOU #2 ;007/016 RMV VEG |  | CARIBOU #2 | ;007/016 | HNA | F | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.958292 | 39.9393 | ETL.6280 | 40813511 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354838 | Not Scheduled | T2 DI DRUM-SUMMIT #2 12/139 RPLC INSW | 31522060 | DRUM-SUMMIT #2 | 012/139 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.583803 | 39.333 | ETL.1450 | 40636109 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354939 | Not Scheduled | T2 DI DRUM-SUMMIT #2 12/139L CANCEL | 44409005 | DRUM-SUMMIT #2 | 012/139 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.583803 | 39.333 | ETL.1450 | 44561220 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354947 | Q2 | T2 EI HAT CRK #1-WSTWD 17/328 RPR WDPKR |  | HAT CREEK #1-WESTWOOD | 017/328 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.313593 | 40.7735 | ETL.7030 | 40676295 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354976 | Q2 | T2 EI HAT CRK #1-WSTWD 17/333 INST IBWW |  | HAT CREEK #1-WESTWOOD | 017/333 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.310093 | 40.7706 | ETL.7030 | 40676299 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119354977 | Q2 | T2 EI HAT CREEK #1-WESTWD 16/324 RPR WDP |  | HAT CREEK #1-WESTWOOD | 016/324 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.316375 | 40.7757 | ETL.7030 | 40770732 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355023 | Not Scheduled | DI GATES-PANOCHE #1 22/102 INST MRKS | 44408180 | GATES-PANOCHE #1 | 022/102 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [6 empty] | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.346143 | 36.3926 | ETL.4720 | 40663951 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119355152 | Not Scheduled | T2 DI DRUM-SUMMIT #2 12/139L CANCEL | 44409005 | DRUM-SUMMIT #2 | 012/139 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.583803 | 39.333 | ETL.1450 | 44561220 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355161 | Not Scheduled | T2 DRUM-SUMMIT #1 23/271 INS DAMPER | 44420920 | DRUM-SUMMIT #1 | 023/271 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.398972 | 39.3105 | ETL.1440 | 40618823 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355174 | Q2 | EI T3NT MENDOCINO-WILLITS 9/4C RPL POLE | 31514050 | MENDOCINO-WILLITS | 009/004C | 70Y | F | 2020_(2) High fire spread TD |  | 2020-07-10 | 2022-07-10 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.303087 | 39.3367 | ETL.7540 | 40741994 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355178 | Q3 | T2 BRIDGEVILE-COTNWD 83/584 INST DMPR |  | BRIDGEVILLE-COTTONWOOD | 083/584 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7329545 | 40.4852 | ETL.1110 | 40919023 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355189 | Q4 | T3 DI MAPLE CREEK-HOOPA 17/6 RPR SPLW | 44178090 | MAPLE CREEK-HOOPA | 017/006 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.675507 | 40.9346 | ETL.7490 | 40827965 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355197 | Q3 | T2 EI CARIBOU #2 16/012 REFRAME | 31507658 | CARIBOU #2 | 016/012 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.089025 | 40.0148 | ETL.6280 | 40675435 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355265 | Before Feb | T3 GEYSERS #12-FULT 13/53 INST JUMP INSS | 31505663 | GEYSERS #12-FULTON | 013/053 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 | 2021-01-25 | 2021-01-28 | 2021-01-28 | 2021-01-25 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.765048 | 38.6739 | ETL.4750 | 44935322 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2021-01-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355310 | Q4 | T3 DI MAPLE CREEK-HOOPA 17/6 RPLC ANCW | 31508612 | MAPLE CREEK-HOOPA | 017/006 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.675507 | 40.9346 | ETL.7490 | 40827965 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355313 | Q3 | T2 DI CARIBOU-PLUMAS JCT 7/3 RPLC CRSW | 31511087 | CARIBOU-PLUMAS JCT | 007/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.063726 | 40.0147 | ETL.6290 | 40666899 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355318 | Not Scheduled | T2 DI DRUM-SUMMIT #2 23/283A RPR STRW | 44409005 | DRUM-SUMMIT #2 | 023/283A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.381174 | 39.3259 | ETL.1450 | 40650166 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355336 | Q2 | DI GATES-PANOCHE #1 23/110 MASTIC | 44408184 | GATES-PANOCHE #1 | 023/110 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-07-09 | 2022-07-09 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.364432 | 36.4128 | ETL.4720 | 40604960 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119355338 | Not Scheduled | DI GATES-PANOCHE #1 031/151 INS MRKS | 44408180 | GATES-PANOCHE #1 | 031/151 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [6 empty] | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.459972 | 36.5132 | ETL.4720 | 40587480 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119355453 | Q3 | T2 EI CARIBOU-WESTWOOD 18/378 RPR POLE |  | CARIBOU-WESTWOOD | 018/378 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.038968 | 40.2957 | ETL.6300 | 40769697 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355491 | Q3 | DI CARIBOU #2 ;5/19 RPR STRW |  | CARIBOU #2 | ;005/019 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.956092 | 39.9561 | ETL.6280 | 40864710 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355691 | Not Scheduled | T3NT DI CARBOU-TBL MTN 18/132 RMV DEBRIS |  | CARIBOU-TABLE MTN | 018/132 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.279929 | 39.983 | ETL.4440 | 40674583 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355720 | Q2 | T2 DI HAT CREEK #1-WSTWD 6/123 RPR SPLW | 44388736 | HAT CREEK #1-WESTWOOD | 006/123 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.431677 | 40.9001 | ETL.7030 | 40827458 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355821 | Q2 | T2 EI TRINITY-MAPLE CREEK 9/4 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 009/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.076825 | 40.7661 | ETL.8170 | 40906382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355852 | Not Scheduled | EI SPAULDING-SUMMIT 5/176 RPL POLE | 31508780 | SPAULDING-SUMMIT | 005/176 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.563141 | 39.306 | ETL.8060 | 40809655 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119355944 | Not Scheduled | T2 VALLEY SPRINGS-MARTELL #1 5/6 RPL PL | 31511433 | VALLEY SPRINGS-MARTELL #1 | 005/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.76161 | 38.2685 | ETL.8240 | 40813064 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119355970 | Q4 | DI MDDL FRK-GLD HLL 14/117L RPR POLE | 44396720 | MIDDLE FORK-GOLD HILL | 014/117 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-07-07 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.815866 | 38.9434 | ETL.5140 | 44553610 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356018 | Q3 | T2 EI CARIBOU #2 12/015 RPL STRW | 31508493 | CARIBOU #2 | 012/015 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.15152 | 40.0252 | ETL.6280 | 40758675 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356099 | Q3 | T2 EI CARIBOU #2 12/009 RPL STRW | 31508493 | CARIBOU #2 | 012/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.156512 | 40.0244 | ETL.6280 | 40875388 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356132 | Q3 | T2 EI CARIBOU #2 11/15 REFRAME | 31511090 | CARIBOU #2 | 011/015 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.167165 | 40.0217 | ETL.6280 | 40758671 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356146 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 44/182 RPL INST | 31527003 | DIABLO-MIDWAY #3 | 044/182 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.094312 | 35.2209 | ETL.5980 | 40655274 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356147 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 43/178 RPL INST | 31527003 | DIABLO-MIDWAY #3 | 043/178 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.106646 | 35.2163 | ETL.5980 | 40869950 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356148 | Not Scheduled | EI DIABLO-MIDWAY #3 45/185 RPL INST | 31527003 | DIABLO-MIDWAY #3 | 045/185 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [9 empty] | South | WSIP | [6 empty] | '-120.078622 | 35.2262 | ETL.5980 | 40749808 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356149 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 44/180 RPL INST | 31527003 | DIABLO-MIDWAY #3 | 044/180 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.097198 | 35.2198 | ETL.5980 | 40592861 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356151 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 43/178 RPL INSS | 31527002 | DIABLO-MIDWAY #2 | 043/178 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.1068 | 35.2156 | ETL.5970 | 40863913 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356153 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 43/177 RPL INSS | 31527002 | DIABLO-MIDWAY #2 | 043/177 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.109833 | 35.2145 | ETL.5970 | 40818971 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356170 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 45/184 RPL INS | 31527002 | DIABLO-MIDWAY #2 | 045/184 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.083115 | 35.2245 | ETL.5970 | 40749851 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356171 | Not Scheduled | EI DIABLO-MIDWAY #2 45/185 RPL INS | 31527002 | DIABLO-MIDWAY #2 | 045/185 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [9 empty] | South | WSIP | [6 empty] | '-120.078432 | 35.2257 | ETL.5970 | 40764249 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356172 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 44/182 RPL INS | 31527002 | DIABLO-MIDWAY #2 | 044/182 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.093805 | 35.2205 | ETL.5970 | 40655270 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356173 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 44/179 RPL INSS | 31527002 | DIABLO-MIDWAY #2 | 044/179 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.101095 | 35.2178 | ETL.5970 | 40863573 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356174 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 44/181 RPL INSS | 31527002 | DIABLO-MIDWAY #2 | 044/181 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.095939 | 35.2197 | ETL.5970 | 40584206 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356228 | Q4 | T3 DI MIDDLE FORK-GOLD HL 7/62 RPR STRW | 44388577 | MIDDLE FORK-GOLD HILL | 007/062 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-07 | 2021-01-07 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.714408 | 39.0032 | ETL.5140 | 44565821 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356231 | Q2 | T2 EI KONOCTI-MIDDLETOWN 23/9 REPUL GYWW | 44610651 | KONOCTI-MIDDLETOWN | 023/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.611176 | 38.8997 | ETL.6380 | 44667815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356240 | Not Scheduled | T2 EI KONOCTI-MIDDLETOWN ;023/008 RPR ST | 44610651 | KONOCTI-MIDDLETOWN | ;023/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.610737 | 38.8993 | ETL.6380 | 40876736 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356251 | Q2 | T2 EI FORT ROSS-GUALALA 50/0 BOND GUY |  | GUALALA-MONTE RIO | 050/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.408029 | 38.7256 | ETL.6980 | 40587392 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356322 | Q2 | EI HUMBOLDT-BRIDGEVILLE 95/3 RPR GYWW | 44107184 | HUMBOLDT-BRIDGEVILLE | 095/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8543052 | 40.6006 | ETL.1810 | 44322356 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356329 | Q2 | EI HUMBOLDT-BRIDGEVILLE 95/2 RPR WP HOLE | 44402106 | HUMBOLDT-BRIDGEVILLE | 095/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8543264 | 40.5989 | ETL.1810 | 44322352 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356362 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 30/120 RPL INS |  | DIABLO-MIDWAY #3 | 030/120 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.340106 | 35.1682 | ETL.5980 | 40605000 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356366 | Q3 | T2 EI CARIBOU #2 16/9 REFRAME | 31508650 | CARIBOU #2 | 016/009 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.090562 | 40.0152 | ETL.6280 | 40867537 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356417 | Not Scheduled | T2 DI DRUM-SUMMIT #1 1/121 INST MRKW | 44409002 | DRUM-SUMMIT #1 | 010/121 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44149434 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356543 | Not Scheduled | DI DRUM-SUMMIT #2 027/331 RPR STRW | 44409005 | DRUM-SUMMIT #2 | 027/331 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.329839 | 39.3159 | ETL.1450 | 44553636 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119356571 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/10 RPR SPLIC | 44408852 | CARIBOU-PLUMAS JCT | ;009/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.931315 | 39.9371 | ETL.6290 | 44168162 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356579 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/11 RPR COND | 44408852 | CARIBOU-PLUMAS JCT | ;009/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.930668 | 39.9369 | ETL.6290 | 44168163 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356594 | Q3 | T2 EI CARIBOU-WESTWOOD 17/360 RPL POLE | 31511053 | CARIBOU-WESTWOOD | 017/360 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.055087 | 40.29 | ETL.6300 | 40758643 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356629 | Mar | T2 EI KONOCTI-MIDDLETOWN 14/3 BOND GYWW | 44610651 | KONOCTI-MIDDLETOWN | 014/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.582463 | 38.7758 | ETL.6380 | 40650680 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356635 | Q3 | T2NT DI CARIBOU #2 ;2/23 RMV BUTT |  | CARIBOU #2 | ;002/023 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.947645 | 39.9936 | ETL.6280 | 40649923 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356657 | Not Scheduled | EI T2NT KONOCTI-MIDDLETOWN 13/9 INST MRK |  | KONOCTI-MIDDLETOWN | 013/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.585788 | 38.772 | ETL.6380 | 40862459 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356659 | Mar | EI T2NT KONOCTI-MIDDLETOWN 15/8 INST MRK |  | KONOCTI-MIDDLETOWN | 015/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.566537 | 38.7943 | ETL.6380 | 44141955 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356674 | Not Scheduled | DI GATES-PANOCHE #1 21/97 RPR SHLS | 44407459 | GATES-PANOCHE #1 | 021/097 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2021-07-08 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.334731 | 36.3801 | ETL.4720 | 44402055 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119356710 | Mar | EI T2NT KONOCTI-MIDDLETWN 013/7 INST MR |  | KONOCTI-MIDDLETOWN | 013/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.586643 | 38.77 | ETL.6380 | 40810249 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356715 | Q2 | HUMBOLDT-BRIDGEVILLE 93/5 RPL INSW | 31506838 | HUMBOLDT-BRIDGEVILLE | 093/005 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.854545 | 40.577 | ETL.1810 | 40778875 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356740 | Q2 | EI HUMBOLDT-BRIDGEVILLE 95/0 RPR COND | 44107184 | HUMBOLDT-BRIDGEVILLE | 095/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8543679 | 40.5948 | ETL.1810 | 44322346 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356773 | Mar | T2 COTTONWD-HMBLDT_57/7 INST SPLC | 44299237 | HUMBOLDT-TRINITY | 057/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.1352914 | 40.7676 | ETL.1820 | 44560630 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356774 | Q2 | EI TRINITY-MAPLE CREEK_012/003C RPL POLE | 31510696 | TRINITY-MAPLE CREEK | 012/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.1351781 | 40.7675 | ETL.8170 | 44769654 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356776 | Not Scheduled | T2 FULTON-HOPLAND 32/1 RPR ANCW | 44579280 | FULTON-HOPLAND | 032/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.0413 | 38.8724 | ETL.6890 | 40770432 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356796 | Not Scheduled | T2NT DI DRM-SUMMIT #1 21/246 CANCEL | 44409002 | DRUM-SUMMIT #1 | 021/246 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-09 | 2022-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.431896 | 39.3192 | ETL.1440 | 40590119 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356876 | Q2 | T2 HAT CREEK #1-WESTWOOD 26/513 REPL SPL | 44406426 | HAT CREEK #1-WESTWOOD | 026/513 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19227 | 40.6679 | ETL.7030 | 40769958 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356895 | Not Scheduled | T3 FULTON-LAKVLLE 30/130 INST JUMP INSS | 31506378 | FULTON-LAKEVILLE | 030/130 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5940427 | 38.4281 | ETL.4950 | 41130051 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356903 | Q2 | T2 HAT CREEK #1-WESTWOOD 26/515 RPR SPLW | 44406426 | HAT CREEK #1-WESTWOOD | 026/515 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.191028 | 40.6667 | ETL.7030 | 40825588 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119356955 | Feb | T3 COLGATE-GRASS VALLEY 6/160 REFRAME | 31508498 | COLGATE-GRASS VALLEY | 006/160 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-01-10 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.095503 | 39.283 | ETL.6490 | 40665603 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357052 | Q2 | T2 EI HAT CRK #1-WSTWD 22/426 RPR WDPKR |  | HAT CREEK #1-WESTWOOD | 022/426 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.246468 | 40.7189 | ETL.7030 | 40770739 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357073 | Q2 | T2 EI HAT CREEK #V1-WSTWD 3/064 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 003/064 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.484512 | 40.9189 | ETL.7030 | 40701309 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357080 | Q2 | EI T2NT HAT CREEK #1-WESTWD 2/60 RMV BUT | 44406426 | HAT CREEK #1-WESTWOOD | 002/060 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.488467 | 40.9195 | ETL.7030 | 40866448 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357091 | Q2 | T2 EI HAT CREEK #1-WESTWD 29/571 RMV PL |  | HAT CREEK #1-WESTWOOD | 029/571 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.15127 | 40.6374 | ETL.7030 | 40759214 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357093 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 2/60 RPR GYW |  | HAT CREEK #1-WESTWOOD | 002/060 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.488467 | 40.9195 | ETL.7030 | 40866448 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357100 | Q2 | T2 EI HAT CRK #1-WESTWD 2/059 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 002/059 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.489493 | 40.9197 | ETL.7030 | 40825654 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357101 | Q2 | T2 EI HAT CREEK #1-WESTWD 3/63 RPR GYWW | 44406426 | HAT CREEK #1-WESTWOOD | 003/063 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.485583 | 40.9191 | ETL.7030 | 40601689 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357110 | Q2 | EI T2NT HAT CREEK #1-WESTWD 2/59 RMV BUT | 44406426 | HAT CREEK #1-WESTWOOD | 002/059 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.489493 | 40.9197 | ETL.7030 | 40825654 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357165 | Mar | T3 EI DRUM-RIO OSO #2 6/070 RMV DEBRIS | 44388509 | DRUM-RIO OSO #2 | 006/070 | ICS | E | 2020_(3) On high spread structure |  | 2020-07-10 | 2021-01-10 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.864171 | 39.2045 | ETL.1430 | 40597636 | Conductor-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357195 | Q3 | T2 EI CARIBOU #2 6/6 RPR GYWW |  | CARIBOU #2 | 006/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.219702 | 40.034 | ETL.6280 | 40816772 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357217 | Q4 | T2 DI KESWICK-TRINITY 23/371 RPR STRW |  | KESWICK-TRINITY | 023/371 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [8 empty] | ETL.7270 | 44421167 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357218 | Q4 | T2 DI KESWICK-TRINITY 23/371 RPL HRDD |  | KESWICK-TRINITY | 023/371 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [8 empty] | ETL.7270 | 44421168 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357219 | Q3 | T2NT DI CARIBOU #2 ;001/018 RMV DEBRIS |  | CARIBOU #2 | ;001/018 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962523 | 40.0046 | ETL.6280 | 40862065 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357234 | Not Scheduled | T2 DI DRUM-SUMMIT #2 21/259 INST MRKW | 44403340 | DRUM-SUMMIT #2 | 021/259 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.417381 | 39.3283 | ETL.1450 | 44552536 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357249 | Q2 | T2 EI HAT CRK #1-WESTWD 25/487 RPR HRDW |  | HAT CREEK #1-WESTWOOD | 025/487 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.206953 | 40.6827 | ETL.7030 | 40877589 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357270 | Q2 | T2 EI HT CRK #1-WSTWD 25/491 RPL POLE | 31511044 | HAT CREEK #1-WESTWOOD | 025/491 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.204437 | 40.6803 | ETL.7030 | 40676342 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357297 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 25/490 REFRA | 31510955 | HAT CREEK #1-WESTWOOD | 025/490 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.20497 | 40.6809 | ETL.7030 | 40601619 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357359 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 11/217 REFRA | 31508607 | HAT CREEK #1-WESTWOOD | 011/217 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.387557 | 40.837 | ETL.7030 | 40617056 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357382 | Q2 | T2 EI HAT CREEK #1-WSTWD 11/223 RPL POLE | 31510952 | HAT CREEK #1-WESTWOOD | 011/223 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.3848 | 40.8329 | ETL.7030 | 40676199 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357384 | Q2 | T2 EI HAT CREEK #1-WESTWD 11/215 RPL STR | 31508285 | HAT CREEK #1-WESTWOOD | 011/215 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.388545 | 40.8383 | ETL.7030 | 40827607 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357385 | Q2 | T2 EI HAT CRK #1-WSTWD 11/220 RPR POLE |  | HAT CREEK #1-WESTWOOD | 011/220 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.386108 | 40.8349 | ETL.7030 | 40827577 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357441 | Q4 | T3NT DI KESWICK-TRINITY 3/57 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 003/057 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.520258 | 40.6163 | ETL.7270 | 40770362 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357442 | Not Scheduled | T2NT DI DRUM-SUMMT #2 20/239C INST MRKW | 44409006 | DRUM-SUMMIT #2 | 020/239C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.448041 | 39.3178 | ETL.1450 | 44150221 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357444 | Q3 | T2 DI CARIBOU #2 ;5/2 RMV POLE BUTT |  | CARIBOU #2 | ;005/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950977 | 39.9629 | ETL.6280 | 40668314 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357447 | Not Scheduled | DI GATES-PANOCHE #1 16/78 RPR ADSS | 44404668 | GATES-PANOCHE #1 | 016/078 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.28697 | 36.3352 | ETL.4720 | 40871179 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119357448 | Q3 | T2 DI CARIBOU-WESTWOOD 14/285 RPR GYWW |  | CARIBOU-WESTWOOD | 014/285 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-07-09 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.080148 | 40.2586 | ETL.6300 | 40810073 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357529 | Q3 | T2 DI CARIBOU #2 ;003/021 RMV PL BUTT |  | CARIBOU #2 | ;003/021 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946252 | 39.9813 | ETL.6280 | 40600685 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357547 | Not Scheduled | T2 EI SPAULDING-SUMMIT 10/343 RPR WPKR | 44421022 | SPAULDING-SUMMIT | 010/343 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.477166 | 39.3175 | ETL.8060 | 44145233 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357586 | Q3 | T2 DI CARIBOU #2 ;004/017 RMV PL BUTT |  | CARIBOU #2 | ;004/017 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.9484 | 39.9693 | ETL.6280 | 40812755 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357588 | Q3 | T2 DI CARIBOU #2 ;005/005 RMV PL BUTT |  | CARIBOU #2 | ;005/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.951672 | 39.9614 | ETL.6280 | 40768854 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357593 | Q3 | T2 DI CARIBOU #2 13/11 RMV PL BUTT |  | CARIBOU #2 | 013/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.135252 | 40.0293 | ETL.6280 | 40585970 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357594 | Q3 | T2 DI CARIBOU #2 13/11 RPR GYWW |  | CARIBOU #2 | 013/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.135252 | 40.0293 | ETL.6280 | 40585970 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357596 | Mar | T3 DI GRN VLY LLGAS 5/37R RPL INSW | 31508437 | GREEN VALLEY-LLAGAS | 005/037 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 | 2021-03-09 | 2021-03-11 | 2021-03-11 | 2021-03-09 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.723804 | 37.0152 | ETL.1720 | 40630825 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357597 | Mar | T3 DI GRN VLY LLGAS 5/37L RPR STRW | 44610147 | GREEN VALLEY-LLAGAS | 005/037 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-01-09 | 2021-03-09 | 2021-03-11 | 2021-03-11 | 2021-03-09 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.723804 | 37.0152 | ETL.1720 | 44400964 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357598 | Mar | T3NT DI GRN VLY LLGAS 5/37L RMV PL BUTT | 44610147 | GREEN VALLEY-LLAGAS | 005/037 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-03-11 | 2021-03-09 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.723804 | 37.0152 | ETL.1720 | 44400964 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357599 | Q4 | T3 DI MIDDLE FRK-GLD HLL 9/82R RPR STRW | 44388577 | MIDDLE FORK-GOLD HILL | 009/082 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.743045 | 38.9864 | ETL.5140 | 44553544 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357646 | Not Scheduled | T3 DIABLO-GATES #1 0/2C RPL INSS | 31526446 | DIABLO-GATES #1 | 000/002C | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-01-08 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.8457787 | 35.2207 | ETL.5960 | 44374365 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357667 | Not Scheduled | DI GATES PANOCHE #1 22/101 INST MRKS | 44408180 | GATES-PANOCHE #1 | 022/101 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-08 | 2022-07-08 | [6 empty] | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.343856 | 36.3901 | ETL.4720 | 40587476 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119357677 | Q3 | T2NT DI CARIBOU #2 ;002/015 INST MRKW |  | CARIBOU #2 | ;002/015 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.952032 | 39.9969 | ETL.6280 | 40768850 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357760 | Q4 | T2 DI MAPLE CREEK-HOOPA 7/1 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 007/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.816323 | 40.8508 | ETL.7490 | 44735724 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357787 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 22/265 INST MRKW | 44409006 | DRUM-SUMMIT #2 | 022/265 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44155609 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357825 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 19/224 INST MRKW | 44409002 | DRUM-SUMMIT #1 | 019/224 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162111 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357830 | Q4 | T2 DI KESWICK-TRINITY 7/92 RPR STRW |  | KESWICK-TRINITY | 007/092 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.576451 | 40.6446 | ETL.7270 | 44649313 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357867 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 16/317 REFRA | 31510955 | HAT CREEK #1-WESTWOOD | 016/317 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.32119 | 40.7796 | ETL.7030 | 40616880 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357876 | Not Scheduled | T2 DI DRUM-SUMMIT #1 19/225 RPR STRW | 44409003 | DRUM-SUMMIT #1 | 019/225 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.460476 | 39.3191 | ETL.1440 | 40813766 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357877 | Not Scheduled | T2 DI DRUM-SUMMIT #1 10/118A RPL PL | 44645317 | DRUM-SUMMIT #1 | 010/118A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.612922 | 39.3224 | ETL.1440 | 40642865 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357885 | Q2 | T2 DI BRGVL-CTWD 16/50 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 016/150 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44424110 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119357900 | Q4 | T2 DI KESWICK-TRINITY 10/128 RPR WPKR |  | KESWICK-TRINITY | 010/128 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.633423 | 40.6672 | ETL.7270 | 40576555 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358038 | Q4 | T3NT DI MAPLE CRK-HOOPA 19/6 INST MRKW | 44394730 | MAPLE CREEK-HOOPA | 019/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.649295 | 40.9494 | ETL.7490 | 44145869 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358083 | Q4 | T2 DI KESWICK-TRINITY 23/357B RPR WPKR |  | KESWICK-TRINITY | 023/357B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.805664 | 40.7124 | ETL.7270 | 42621521 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358086 | Q4 | T3NT DI KESWICK-TRINITY 4/66 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 004/066 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.531553 | 40.6241 | ETL.7270 | 40701679 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358108 | Q2 | EI T2NT TRINITY-MAPLE CRK 20/3 RMV PL BU | 44401994 | TRINITY-MAPLE CREEK | 020/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2649765 | 40.724 | ETL.8170 | 44565419 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358115 | Not Scheduled | T3 EI FRENCH MDWS-MDDLE FRK 11/208 REFRA | 31508611 | FRENCH MEADOWS-MIDDLE FORK | 011/208 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.586257 | 39.0111 | ETL.6870 | 40761242 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358140 | Not Scheduled | T2 EI TRINITY-MAPLE CREEK 22/003 RMV VE |  | TRINITY-MAPLE CREEK | 022/003 | HNA | F | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.303195 | 40.707 | ETL.8170 | 40650361 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358141 | Q2 | T2 EI TRINITY-MAPLE CREEK 22/5 REPL POLE | 31510957 | TRINITY-MAPLE CREEK | 022/005 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.308297 | 40.7057 | ETL.8170 | 40752264 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358143 | Q2 | EI T2NT TRINITY-MAPLE CREEK 22/5 RMV BUT | 44401994 | TRINITY-MAPLE CREEK | 022/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.308297 | 40.7057 | ETL.8170 | 40752264 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358145 | Q2 | EI T2NT TRINITY-MAPLE CREEK 22/8 RMV BUT | 44401994 | TRINITY-MAPLE CREEK | 022/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.314576 | 40.7047 | ETL.8170 | 40862474 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358146 | Q2 | T2 EI TRINITY-MAPLE CREEK 22/8 RPL DAMPE | 44401954 | TRINITY-MAPLE CREEK | 022/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.314576 | 40.7047 | ETL.8170 | 40862474 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358208 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 9/104C RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 009/104C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2022-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633799 | 39.3173 | ETL.1440 | 42572650 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358281 | Q4 | T3 DI MAPLE CREEK-HOOPA 16/000 RPR GYWW | 44178090 | MAPLE CREEK-HOOPA | 016/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.69957 | 40.9194 | ETL.7490 | 44735739 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358292 | Not Scheduled | T2 DI DRUM-SUMMIT #2 20/239B RPR STRW | 44420922 | DRUM-SUMMIT #2 | 020/239B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.44805 | 39.3178 | ETL.1450 | 44150220 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358390 | Q3 | T2 DI CARIBOU-WESTWOOD 12/54 RPR GYWW |  | CARIBOU-WESTWOOD | 012/254 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.075458 | 40.2393 | ETL.6300 | 40589850 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358401 | Q3 | T2 DI CARIBOU #2 20/17 RPR GYWW |  | CARIBOU #2 | 020/017 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.020452 | 40.031 | ETL.6280 | 40824619 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358403 | Q3 | T2 DI CARIBOU #2 20/17 RMV PL BUTT |  | CARIBOU #2 | 020/017 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-09 | 2022-07-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.020452 | 40.031 | ETL.6280 | 40824619 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358800 | Not Scheduled | T3 GEYSERS #12-FULTON 1/6 RMV IDLE CND | 44396147 | GEYSERS #12-FULTON | 001/006 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-11 | 2021-01-11 | [5 empty] | TLN/TLQ - should be TLN |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.767206 | 38.7958 | ETL.4750 | 41129171 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119358821 | Q2 | T3 GEYSERS #12-FULTON 1/7 RMV IDLE CND | 44396147 | GEYSERS #12-FULTON | 001/007 | ICQ | E | 2020_(1a) PSPS |  | 2020-07-11 | 2021-01-11 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76768 | 38.7909 | ETL.4750 | 41129172 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119358825 | Not Scheduled | T3 GEYSERS #12-FULTON 1/8 RMV IDLE CND | 44396147 | GEYSERS #12-FULTON | 001/008 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-11 | 2021-01-11 | [5 empty] | TLN/TLQ - should be TLN |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76751 | 38.7883 | ETL.4750 | 41129175 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359029 | Not Scheduled | T2 DI DRUM-SUMMIT #1 18/208 INST NUT | 44391347 | DRUM-SUMMIT #1 | 018/208 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44180231 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359419 | Q2 | T2 EI HAT CRK #1-WESTWD 9/186 REFRAME | 31508607 | HAT CREEK #1-WESTWOOD | 009/186 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.4018 | 40.8574 | ETL.7030 | 40770835 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359420 | Q2 | T2 EI HAT CREEK #1-WESTWD 6/117 RPL STRW | 31508607 | HAT CREEK #1-WESTWOOD | 006/117 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.43617 | 40.9027 | ETL.7030 | 40600132 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359485 | Q2 | EI COTTONWD-HUMBOLDT 20/185 RPL ANCHW |  | BRIDGEVILLE-COTTONWOOD | 020/185 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.6574011 | 40.3768 | ETL.1110 | 44515775 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359491 | Q2 | T2 EI HAT CRK #1-WESTWD 10/191 REFRAME | 31508607 | HAT CREEK #1-WESTWOOD | 010/191 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.399712 | 40.8543 | ETL.7030 | 40600143 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359493 | Q2 | T2 EI HAT CRK #1-WESTWD 9/187 REFRAME | 31508607 | HAT CREEK #1-WESTWOOD | 009/187 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.401325 | 40.8567 | ETL.7030 | 40770068 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359498 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/388 RPR G |  | HAT CREEK #1-WESTWOOD | 020/388 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.27267 | 40.7402 | ETL.7030 | 40759196 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359510 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 21/407 RPR G |  | HAT CREEK #1-WESTWOOD | 021/407 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.259393 | 40.7296 | ETL.7030 | 40759198 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359512 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/397 RPR G |  | HAT CREEK #1-WESTWOOD | 020/397 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.266348 | 40.7353 | ETL.7030 | 44686396 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359516 | Q2 | T2 EI HAT CREEK #1-WESTWD 20/390 RPR GYW |  | HAT CREEK #1-WESTWOOD | 020/390 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.271192 | 40.7392 | ETL.7030 | 40827583 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359519 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/388 RPR W |  | HAT CREEK #1-WESTWOOD | 020/388 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.27267 | 40.7402 | ETL.7030 | 40759196 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359520 | Q2 | T2 EI HAT CRK #1-WSTWD 20/389 RPR WDPKR |  | HAT CREEK #1-WESTWOOD | 020/389 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.271912 | 40.7397 | ETL.7030 | 40769950 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359521 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/392 RPR G |  | HAT CREEK #1-WESTWOOD | 020/392 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.26988 | 40.7381 | ETL.7030 | 40868468 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359523 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 21/406 RPR G |  | HAT CREEK #1-WESTWOOD | 021/406 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.260183 | 40.7302 | ETL.7030 | 40667944 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359525 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/392 RPR W |  | HAT CREEK #1-WESTWOOD | 020/392 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.26988 | 40.7381 | ETL.7030 | 40868468 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359526 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/387 RPR P | 44406426 | HAT CREEK #1-WESTWOOD | 020/387 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.273263 | 40.7409 | ETL.7030 | 40667942 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359528 | Q2 | T2 EI HAT CREEK #1-WSTWD 20/386 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 020/386 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.274027 | 40.7415 | ETL.7030 | 44686395 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359538 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/401 RPR G |  | HAT CREEK #1-WESTWOOD | 020/401 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.263613 | 40.733 | ETL.7030 | 40816134 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359540 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/400 REPUL | 44406426 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359544 | Q2 | T2 EI HAT CREEK #1-WSTWD 20/389 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 020/389 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.271912 | 40.7397 | ETL.7030 | 40769950 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359545 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/391 RPR G |  | HAT CREEK #1-WESTWOOD | 020/391 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.270547 | 40.7386 | ETL.7030 | 44686474 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359549 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/394 RPR W |  | HAT CREEK #1-WESTWOOD | 020/394 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.268358 | 40.7369 | ETL.7030 | 40617095 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359551 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/387 REPUL | 44406426 | HAT CREEK #1-WESTWOOD | 020/387 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.273263 | 40.7409 | ETL.7030 | 40667942 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359553 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/399 RPL P | 31510952 | HAT CREEK #1-WESTWOOD | 020/399 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.264958 | 40.7341 | ETL.7030 | 40759025 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359554 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 20/398 RPR G |  | HAT CREEK #1-WESTWOOD | 020/398 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.265607 | 40.7347 | ETL.7030 | 40770737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359565 | Q2 | T2 EI HAT CRK #1-WSTWD 23/454 RPL PL | 31510952 | HAT CREEK #1-WESTWOOD | 023/454 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.22812 | 40.7021 | ETL.7030 | 40656892 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359567 | Q2 | EI BRIDGEVILLE-CTTNW 23/204 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 023/204 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7066242 | 40.3733 | ETL.1110 | 44423439 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359569 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 23/456 RPR W |  | HAT CREEK #1-WESTWOOD | 023/456 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.226893 | 40.7009 | ETL.7030 | 40759029 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359570 | Q2 | EI T2NT HAT CREEK #1-WSTWD 23/456 RMV BU |  | HAT CREEK #1-WESTWOOD | 023/456 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.226893 | 40.7009 | ETL.7030 | 40759029 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359576 | Q2 | EI T2NT HAT CRK #1-WESTWD 24/460 RMV PL |  | HAT CREEK #1-WESTWOOD | 024/460 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-10 | 2022-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.224298 | 40.6986 | ETL.7030 | 40600226 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359644 | Q2 | T2 EI HAT CRK #1-WESTWD 7/145 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 007/145 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.42121 | 40.8851 | ETL.7030 | 40868426 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359647 | Q2 | T2 EI HAT CREEK #1-WESTWD 7/137 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 007/137 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.425068 | 40.8906 | ETL.7030 | 40600135 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359649 | Q2 | T2 EI HAT CRK #1-WESTWD 7/138 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 007/138 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.424552 | 40.8899 | ETL.7030 | 40601604 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359652 | Q2 | T2 EI HAT CRK #1-WESTWD 7/144 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 007/144 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.421668 | 40.8858 | ETL.7030 | 40825569 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359664 | Q4 | T2 DI KESWICK-TRINITY 10/135 RPR CRSW | 43939188 | KESWICK-TRINITY | 010/135 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.634479 | 40.6728 | ETL.7270 | 40862145 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359668 | Q4 | T2 DI KESWICK-TRINITY 11/141 RPR POLE | 43939188 | KESWICK-TRINITY | 011/141 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.636418 | 40.6807 | ETL.7270 | 40752199 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359675 | Q2 | T2 EI HAT CRK#1-WESTWD 15/292 RPR BOND | 44406426 | HAT CREEK #1-WESTWOOD | 015/292 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.338462 | 40.7935 | ETL.7030 | 40827469 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359680 | Q4 | T2 DI MAPLE CREEK-HOOP 8/2 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 008/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.804388 | 40.862 | ETL.7490 | 44735730 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359685 | Q4 | T3 DI MAPLE CREEK-HOOP 13/10 RPL INSW | 31508655 | MAPLE CREEK-HOOPA | 013/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.728742 | 40.9053 | ETL.7490 | 44885541 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359686 | Q4 | T2 DI MAPLE CREEK-HOOPA 8/6 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 008/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.79892 | 40.8658 | ETL.7490 | 40811047 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359687 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 7/86 RPL INSW | 31510655 | DIVIDE-CABRILLO #2 | 007/086 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436272 | 34.7235 | ETL.1370 | 40788151 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359688 | Q4 | T2 DI MAPLE CREEK-HOOP 5/10 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 005/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.82227 | 40.8332 | ETL.7490 | 44837759 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359704 | Q2 | T2 EI HAT CREEK #1-WESTWD 015/289 RPLC S | 31511044 | HAT CREEK #1-WESTWOOD | 015/289 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.34057 | 40.7952 | ETL.7030 | 40616865 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359715 | Q2 | T2 EI HAT CRK #1-WSTWD 15/297 REFRAME | 31510955 | HAT CREEK #1-WESTWOOD | 015/297 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.334983 | 40.7907 | ETL.7030 | 40827471 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359750 | Q2 | DI GATES-PANOCHE #2 016/077 RPR STRT | 44404664 | GATES-PANOCHE #1 | 016/077 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-07 | 2021-07-07 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.284031 | 36.3334 | ETL.4720 | 40811172 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119359751 | Q4 | T3 DI MAPLE CREEK-HOOPA 12/9 INS PLUMB | 44178090 | MAPLE CREEK-HOOPA | 012/009 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.74925 | 40.9063 | ETL.7490 | 40884631 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359752 | Q4 | T2 DI MAPLE CREEK-HOOPA 2/2 RPL STRW | 31510885 | MAPLE CREEK-HOOPA | 002/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.84281 | 40.7851 | ETL.7490 | 44969788 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359756 | Q4 | T3 DI MAPLE CREEK-HOOPA 12/11 RPR INSW | 44178090 | MAPLE CREEK-HOOPA | 012/011 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.746799 | 40.9054 | ETL.7490 | 40628772 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359770 | Q4 | T2 DI KESWICK-TRINITY 10/125 RPR GYWW |  | KESWICK-TRINITY | 010/125 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.631073 | 40.6657 | ETL.7270 | 40650309 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119359771 | Q4 | T2 DI KESWICK-TRINITY 11/144 RPR GYWW |  | KESWICK-TRINITY | 011/144 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.639354 | 40.6836 | ETL.7270 | 44649360 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360007 | Q3 | T2NT EI CARIBOU #2 014/022 INST MRKW |  | CARIBOU #2 | 014/022 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-10 | 2022-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.115278 | 40.0255 | ETL.6280 | 40675427 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360015 | Q3 | T2 EI CARIBOU #2 14/18 REFRAME | 31529094 | CARIBOU #2 | 014/018 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.117633 | 40.026 | ETL.6280 | 40876625 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360020 | Q3 | T2 EI CARIBOU #2 14/14 RPL POLE | 31509660 | CARIBOU #2 | 014/014 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.119535 | 40.0263 | ETL.6280 | 40769533 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360022 | Q3 | T2 EI CARIBOU #2 14/21 RPR GYWW |  | CARIBOU #2 | 014/021 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.11579 | 40.0257 | ETL.6280 | 40600616 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360085 | Q4 | T3 DI MDDLE FRK-GLD HLL 9/83L RPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 009/083 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-09 | 2021-01-09 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.744297 | 38.9859 | ETL.5140 | 44553641 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360113 | Not Scheduled | T2 DI DRUM-SUMMIT #1 17/207 RPLC STRW | 31521943 | DRUM-SUMMIT #1 | 017/207 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.487738 | 39.3162 | ETL.1440 | 40590113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360114 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 17/207 RMV DEBRIS | 44409002 | DRUM-SUMMIT #1 | 017/207 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2022-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.487738 | 39.3162 | ETL.1440 | 40590113 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360115 | Not Scheduled | T3NT DI ATASCADERO-CAYUCOS 5/43 RMV BUTT |  | ATASCADERO-CAYUCOS | 005/043 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-13 | 2022-07-13 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.755688 | 35.4631 | ETL.8480 | 40606006 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-27 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360348 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 43/176 RPL INST | 31527005 | DIABLO-MIDWAY #2 | 043/176 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.112678 | 35.2134 | ETL.5970 | 40812085 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360780 | Not Scheduled | EI SPAULDING-SUMMIT 005/172 INS MKRW | 44411160 | SPAULDING-SUMMIT | 005/172 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2022-07-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.56505 | 39.3059 | ETL.8060 | 40668662 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119360871 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 1/25 RPR XAR |  | HAT CREEK #1-WESTWOOD | 001/025 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.522715 | 40.9248 | ETL.7030 | 40770817 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119360896 | Q2 | T3 WISHON-SAN JOAQUIN #3 007/003 RPL PL | 31508943 | WISHON-SAN JOAQUIN #3 | 007/003 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-13 | 2021-01-13 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-19 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.506676 | 37.1566 | ETL.9340 | 44655747 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy ADER | ADER | With ADE for Review | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119361055 | Q3 | T2 EI CARIBOU #2 14/13 INST MRKW |  | CARIBOU #2 | 014/013 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-13 | 2022-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.120733 | 40.0264 | ETL.6280 | 40656551 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361145 | Mar | HUMBOLDT-TRINITY # 1 58/0 RPL STRW | 31511241 | HUMBOLDT-TRINITY | 058/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.1390699 | 40.7658 | ETL.1820 | 44194949 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361257 | Mar | T3 EI BRUNSWICK #2 TAP 005/034 RPL INSUL | 31506897 | BRUNSWICK #2 TAP | 005/034 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 |  |  | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.0363616 | 39.2021 | ETL.1431 | 40780894 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361265 | Q2 | T2 EI PHILO JCT-ELK 14/006 RPR GYWW | 44610684 | PHILO JCT-ELK | 014/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.372948 | 39.0308 | ETL.7780 | 40826124 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361341 | Not Scheduled | T2 EI SPAULDING-SUMMIT 2/104 RPR WPKR | 44435091 | SPAULDING-SUMMIT | 002/104 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.600559 | 39.3134 | ETL.8060 | 40828179 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361342 | Not Scheduled | T2 EI SPAULDING-SUMMIT 2/106 REFRAME | 31511249 | SPAULDING-SUMMIT | 002/106 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.599555 | 39.3136 | ETL.8060 | 42571847 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361343 | Not Scheduled | T2 EI SPAULDING-SUMMIT 2/105 REFRAME | 31511249 | SPAULDING-SUMMIT | 002/105 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.600064 | 39.3135 | ETL.8060 | 42571846 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361377 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 22/196L RPL PL | 31526498 | BRIDGEVILLE-COTTONWOOD | 022/196 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.6874107 | 40.3746 | ETL.1110 | 44424091 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361378 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 22/198 RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 022/198 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.6915227 | 40.3744 | ETL.1110 | 44424382 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361402 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 17/128 GRWSH INSU |  | CAYUCOS-CAMBRIA | 017/128 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.103341 | 35.5959 | ETL.8560 | 40840490 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361498 | Q2 | T2 EI PHILO JCT-ELK 17/005 WASH INSW | 44610686 | PHILO JCT-ELK | 017/005 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4198405 | 39.0554 | ETL.7780 | 40793153 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361520 | Not Scheduled | T2 DI CAYUCS-CAMBRA 17/127 RPL INSW | 31508885 | CAYUCOS-CAMBRIA | 017/127 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.101971 | 35.5953 | ETL.8560 | 40794813 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361537 | Q2 | T2 EI PHILO JCT-ELK 17/006 RPR FOUND |  | PHILO JCT-ELK | 017/006 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4208 | 39.0564 | ETL.7780 | 40820707 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361726 | Q4 | T3 DI MAPLE CREEK-HOOPA 10/13 RPL ANCW | 31508654 | MAPLE CREEK-HOOPA | 010/013 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.770896 | 40.895 | ETL.7490 | 44769635 | Anchor-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361763 | Q2 | T2 EI PHILO JCT-ELK 17/007 RPL PL | 31511245 | PHILO JCT-ELK | 017/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.422665 | 39.0583 | ETL.7780 | 40819515 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361790 | Not Scheduled | T3 EI MONTE RIO-FULTON 14/007 RPL INSW | 31508608 | MONTE RIO-FULTON | 014/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.0093109 | 38.4779 | ETL.7630 | 40852752 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119361838 | Q3 | EI T2NT CARIBOU #2 14/011 RMV DEBRIS |  | CARIBOU #2 | 014/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-13 | 2022-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.122393 | 40.0266 | ETL.6280 | 40600614 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362225 | Q2 | T2 EI HAT CRK #1-WSTWD 9/184 RPR CROSSAR |  | HAT CREEK #1-WESTWOOD | 009/184 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.40275 | 40.8587 | ETL.7030 | 40676183 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362491 | Q4 | T2 DI KESWICK-TRINITY 15/190 RMV PL BUTT |  | KESWICK-TRINITY | 015/190 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-13 | 2021-07-13 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.672176 | 40.7145 | ETL.7270 | 40668396 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362631 | Not Scheduled | EI SPAULDING-SUMMIT 5/181 RPL POLE | 31508780 | SPAULDING-SUMMIT | 005/181 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.560773 | 39.3061 | ETL.8060 | 40702037 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119362632 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 4/39 GRWSH INSU |  | ATASCADERO-CAYUCOS | 004/039 | ICD | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.742767 | 35.4644 | ETL.8480 | 40694318 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362677 | Q2 | T2 EI MI-WUK-CURTIS 25/1 (R) RPL STRW | 31508526 | ETL.1073.POLE.WDPS | 025/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-06-17 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294459 | 37.9858 | ETL.1073 | 44774790 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362699 | Q2 | EI TRINITY-MAPLE CREEK 10/017 RMV BUTT | 44401994 | TRINITY-MAPLE CREEK | 010/017 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.108163 | 40.7689 | ETL.8170 | 44420596 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362703 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;009/020 REFRAM | 31511248 | CARIBOU-PLUMAS JCT | ;009/020 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.924595 | 39.9352 | ETL.6290 | 40595031 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362827 | Q2 | T2 EI BRDGVL-CTTNWD 39/317 RPR ARMR ROD | 44404807 | BRIDGEVILLE-COTTONWOOD | 039/317 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.0122121 | 40.3804 | ETL.1110 | 44425579 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362867 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 018/133 RPL INSW | 31511422 | CAYUCOS-CAMBRIA | 018/133 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.111191 | 35.5993 | ETL.8560 | 44652092 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362869 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 018/133 RMV DEBRIS |  | CAYUCOS-CAMBRIA | 018/133 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 | [7 empty] | TR2 |  | South | WSIP | [8 empty] | ETL.8560 | 44171821 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119362951 | Not Scheduled | EI SPAULDING-SUMMIT 005/185 RPLC STRW | 31508780 | SPAULDING-SUMMIT | 005/185 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55909 | 39.3061 | ETL.8060 | 40828177 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119363032 | Q4 | T3 DI MAPLE CREEK-HOOPA 13/4 REFAME | 31508612 | MAPLE CREEK-HOOPA | 013/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.739705 | 40.9053 | ETL.7490 | 40752761 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363036 | Q4 | T3 DI MAPLE CREEK-HOOPA 014/001 RPR STRW | 44192340 | MAPLE CREEK-HOOPA | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-01-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.727342 | 40.9049 | ETL.7490 | 40586851 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363063 | Mar | HUMBOLDT-TRINITY 58/2A RPL POLE | 31511241 | HUMBOLDT-TRINITY | 058/002A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.1434714 | 40.7648 | ETL.1820 | 44562666 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363081 | Q4 | T2 DI MAPLE CREEK-HOOPA 7/0 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 007/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.817702 | 40.8495 | ETL.7490 | 44735723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363145 | Not Scheduled | T2 DI DIVIDE-CABRILLO#2 10/131 RPR PL |  | DIVIDE-CABRILLO #2 | 010/131 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436504 | 34.6784 | ETL.1370 | 40876937 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363181 | Q2 | T2NT DI BRDGVL-CTTNWD 15/140 RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 015/140 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.556997 | 40.3878 | ETL.1110 | 44424098 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363183 | Q2 | T2 DI BRDGVL-CTTNWD 15/140 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 015/140 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.556997 | 40.3878 | ETL.1110 | 44424098 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363185 | Q2 | T2NT DI BRDGVL-CTTNWD 15/141 RMV DEBRIS | 44404807 | BRIDGEVILLE-COTTONWOOD | 015/141 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.558525 | 40.3874 | ETL.1110 | 44424112 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363249 | Not Scheduled | T2 DI DRUM-SUMMIT #2 10/119B RPL POLE |  | DRUM-SUMMIT #2 | 010/119B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613 | 39.3225 | ETL.1450 | 42572782 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363269 | Not Scheduled | T2 DI DRUM-SUMMIT #2 10/119A RPL POLE |  | DRUM-SUMMIT #2 | 010/119A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613035 | 39.3226 | ETL.1450 | 40650155 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363317 | Q3 | T2 EI CARIBOU #2 ;03/021 RPR STRW |  | CARIBOU #2 | ;003/021 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946252 | 39.9813 | ETL.6280 | 40600685 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363380 | Q3 | T2 EI CARIBOU-PLUMAS JCT ;9/25 RPR HDWW | 44408852 | CARIBOU-PLUMAS JCT | ;009/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.921457 | 39.935 | ETL.6290 | 40769034 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363381 | Q3 | EI T2NT CARIBOU-PLUMAS JCT 14/11 RMV DEB | 44408852 | CARIBOU-PLUMAS JCT | 014/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-13 | 2022-07-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.948979 | 39.9571 | ETL.6290 | 40585993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363389 | Q2 | EI ELK-GUALALA 44/006 RPL HRDD | 44610591 | ELK-GUALALA | 044/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.684686 | 39.0283 | ETL.8410 | 40820736 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363551 | Q3 | T2 DI CARIBOU-WESTWOOD 13/264 RPR GYWW |  | CARIBOU-WESTWOOD | 013/264 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.077827 | 40.2446 | ETL.6300 | 40824693 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363558 | Q3 | T2 DI CRIBU-WSTWD 13/264 RPR PL |  | CARIBOU-WESTWOOD | 013/264 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.077827 | 40.2446 | ETL.6300 | 40824693 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363581 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 43/174 RPL INST | 31527005 | DIABLO-MIDWAY #2 | 043/174 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.117426 | 35.2116 | ETL.5970 | 40753891 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363710 | Q3 | T3 DI DONNELLS-MI-WUK 9/5R RPR GYWW | 44623516 | DONNELLS-CURTIS | 009/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.112507 | 38.1447 | ETL.1400 | 44774096 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363717 | Q3 | T2 EI CARIBOU-PLUMAS JCT 14/15 RPR WPKR | 44408852 | CARIBOU-PLUMAS JCT | 014/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.9445 | 39.9571 | ETL.6290 | 40768906 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363784 | Not Scheduled | T2 EI FULTON-CALISTOGA :0/002 RPR CONW | 44597303 | FULTON-CALISTOGA | :000/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.578174 | 38.5928 | ETL.6880 | 40912408 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119363991 | Q3 | T2 EI CARIBOU-PLUMAS JCT 12/4 RPL POLE | 31511242 | CARIBOU-PLUMAS JCT | 012/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.98833 | 39.9757 | ETL.6290 | 40769605 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364040 | Q4 | T2 DI KESWICK-TRINITY 14/180 RPR GYWW |  | KESWICK-TRINITY | 014/180 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.669336 | 40.7065 | ETL.7270 | 40590466 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364070 | Q4 | T2 DI KESWICK-TRINITY 13/164 RPR GYWW |  | KESWICK-TRINITY | 013/164 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.644004 | 40.6928 | ETL.7270 | 44649285 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364122 | Q2 | T2 EI FORT ROSS-GUALALA 41/2 RPR GYWW |  | GUALALA-MONTE RIO | 041/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.309859 | 38.6582 | ETL.6980 | 40656379 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364163 | Not Scheduled | T2 EI SPAULDING-SUMMIT 2/118 INST HRDD | 44391371 | SPAULDING-SUMMIT | 002/118 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.593698 | 39.3126 | ETL.8060 | 40590007 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364191 | Not Scheduled | T3 COLGATE-ALLEGHANY 20/561 RPL STRW | 31508702 | COLGATE-ALLEGHANY | 020/561 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.894901 | 39.465 | ETL.6470 | 40593299 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364276 | Mar | T2 EI KILARC-DESCHUTES 18/387 RPL PL | 31511244 | KILARC-DESCHUTES | 018/387 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.163639 | 40.5638 | ETL.7300 | 40868583 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364278 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 21/421 RPR W |  | HAT CREEK #1-WESTWOOD | 021/421 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.249798 | 40.7218 | ETL.7030 | 40868470 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364305 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 21/419 RPR G |  | HAT CREEK #1-WESTWOOD | 021/419 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.251233 | 40.723 | ETL.7030 | 40817127 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364306 | Q2 | T2 EI HAT CRK #1-WSTWD 21/420 REFRAME C | 31508607 | HAT CREEK #1-WESTWOOD | 021/420 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.25036 | 40.7224 | ETL.7030 | 40825581 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364309 | Q2 | T2 EI HAT CRK #1-WSTWD 21/420 RPR GYWW | 44406426 | HAT CREEK #1-WESTWOOD | 021/420 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.25036 | 40.7224 | ETL.7030 | 40825581 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364313 | Q3 | T2 EI CARIBOU-PLUMAS JCT 14/13 RPR WPKR | 44408852 | CARIBOU-PLUMAS JCT | 014/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.946742 | 39.9571 | ETL.6290 | 40649935 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364319 | Mar | T3 EI DRUM-RIO OSO #2 6/065 RPL ANCHOR | 31509484 | DRUM-RIO OSO #2 | 006/065 | 93Z | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.858508 | 39.2109 | ETL.1430 | 40757182 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364332 | Mar | T3 EI DRUM-RIO OSO #2 6/65 RPR GYWW | 44391342 | DRUM-RIO OSO #2 | 006/065 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.858508 | 39.2109 | ETL.1430 | 40757182 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364334 | Mar | T3 EI DRUM-RIO OSO #2 5/063 RPR GYWW | 44391342 | DRUM-RIO OSO #2 | 005/063 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-01-13 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.855862 | 39.213 | ETL.1430 | 40655122 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364340 | Mar | EI T3NT DRUM-RIO OSO #2 5/059 RMV DEBRIS | 44391343 | DRUM-RIO OSO #2 | 005/059 | ICS | F | 2020_(1a) PSPS |  | 2020-07-13 | 2022-07-13 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.849947 | 39.2164 | ETL.1430 | 40870587 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119364348 | Q2 | T2 EI TRINITY-MAPLE CREEK 18/2 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 018/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.228198 | 40.7374 | ETL.8170 | 40689254 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364352 | Q2 | T2 EI TRINITY-MAPLE CREEK 18/8 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 018/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.234357 | 40.7369 | ETL.8170 | 40862469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364428 | Q2 | EI HUMBOLDT-BRIDGEVILLE 93/003 RPR WDPKR | 44402106 | HUMBOLDT-BRIDGEVILLE | 093/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8545724 | 40.5745 | ETL.1810 | 44322330 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364430 | Q2 | EI HUMBOLDT-BRIDGEVILLE 93/3 RPR WDPKR | 44402106 | HUMBOLDT-BRIDGEVILLE | 093/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8545724 | 40.5745 | ETL.1810 | 44322328 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364431 | Q2 | EI HUMBOLDT-BRIDGEVILLE 93/003 RPR WDPKR | 44402106 | HUMBOLDT-BRIDGEVILLE | 093/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8545724 | 40.5745 | ETL.1810 | 44322329 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364517 | Q3 | T2 EI CARIBOU #2 ;4/024 RPL CRSW | 31507658 | CARIBOU #2 | ;004/024 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.949835 | 39.9659 | ETL.6280 | 40769621 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364586 | Q3 | T2 EI CARIBOU #2 14/04 GRND WASH INSW |  | CARIBOU #2 | 014/004 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127515 | 40.0285 | ETL.6280 | 40769557 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364599 | Q3 | T2 EI CARIBOU #2 ;01/004 RPL PL | 31509660 | CARIBOU #2 | ;001/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.966912 | 40.0105 | ETL.6280 | 40769642 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364631 | Q3 | T2 EI CARIBOU #2 014/5 RPR ANCW |  | CARIBOU #2 | 014/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.126589 | 40.0284 | ETL.6280 | 40768815 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364733 | Q2 | EI T2NT HAT CREEK #1-WESTWOOD 4/96 RMV B |  | HAT CREEK #1-WESTWOOD | 004/096 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.453323 | 40.9126 | ETL.7030 | 40815933 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364825 | Mar | EI T2NT KNCTI-MIDDLETWN 016/014 INST MA |  | KONOCTI-MIDDLETOWN | 016/014 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.573231 | 38.8085 | ETL.6380 | 40752528 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364826 | Q2 | T2 EI KONOCTI-MIDDLETOWN 16/15 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 016/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.573191 | 38.8094 | ETL.6380 | 40768972 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364861 | Q4 | T2 DI KESWICK-TRINITY 010/126 RPR GYWW |  | KESWICK-TRINITY | 010/126 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.631297 | 40.6659 | ETL.7270 | 40752144 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364885 | Mar | T2 HUMBOLDT-TRINITY 93/3C RPR STRW | 44299237 | HUMBOLDT-TRINITY | 093/003C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.739633 | 40.7485 | ETL.1820 | 44926550 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119364887 | Mar | T2 HUMBOLDT-TRINITY 93/3B RPR STRW | 44299237 | HUMBOLDT-TRINITY | 093/003B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.739634 | 40.7484 | ETL.1820 | 44926596 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365234 | Not Scheduled | T2 EI BRIDGEVILLE-CTTNWD 39/3 RPL BNT MM |  | BRIDGEVILLE-COTTONWOOD | 039/316 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.010925 | 40.3803 | ETL.1110 | 40821498 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365235 | Q2 | EI COTTONWOOD-HUMBOLDT_039/311 RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 039/311 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.9997677 | 40.3743 | ETL.1110 | 44550747 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365447 | Q2 | T2 EI HT CRK #1-WSTWD 23/444 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/444 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.234585 | 40.708 | ETL.7030 | 40656890 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365450 | Q2 | EI T2NT HT CRK #1-WSTWD 23/451 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/451 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.230127 | 40.7039 | ETL.7030 | 40616904 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365453 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 23/453 RPL P | 31510952 | HAT CREEK #1-WESTWOOD | 023/453 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.228792 | 40.7027 | ETL.7030 | 40701228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365454 | Q2 | EI T2NT HAT CRK #1-WSTWD 23/447 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/447 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.232648 | 40.7062 | ETL.7030 | 40827485 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365455 | Q2 | EI T2NT HT CRK #1-WSTWD 23/448 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/448 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.232052 | 40.7056 | ETL.7030 | 40816136 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365521 | Mar | T2 WV HUMBOLDT-TRINITY 93/3A COATING | 44356920 | HUMBOLDT-TRINITY | 093/003A | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.739634 | 40.7484 | ETL.1820 | 44926549 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365522 | Q4 | T3 DI MDDL FRK-GLD HLL 29/220 RPL ANCHW | 31509420 | MIDDLE FORK-GOLD HILL | 029/220 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-01-13 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9727 | 38.78 | ETL.5140 | 44141874 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365541 | Q2 | T2 EI HAT CREEK #1-WESTWD 2/54 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 002/054 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.494633 | 40.9205 | ETL.7030 | 40671157 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365542 | Q2 | EI T2NT HAT CREEK #1-WESTWD 2/52 RMV DEB |  | HAT CREEK #1-WESTWOOD | 002/052 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.496568 | 40.9208 | ETL.7030 | 40616832 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365543 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 2/52 RPR GYW |  | HAT CREEK #1-WESTWOOD | 002/052 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.496568 | 40.9208 | ETL.7030 | 40616832 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365546 | Q2 | T2 EI HAT CRK #1-WESTWD 2/056 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 002/056 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.492542 | 40.9202 | ETL.7030 | 40756786 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365564 | Q2 | T2 EI HAT CREEK #1-WESTWD 2/056 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 002/056 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.492542 | 40.9202 | ETL.7030 | 40756786 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365565 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 2/54 RPR GYW |  | HAT CREEK #1-WESTWOOD | 002/054 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.494633 | 40.9205 | ETL.7030 | 40671157 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365573 | Q2 | EI T2NT HAT CREEK #1-WSTWD 2/51 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 002/051 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.49739 | 40.9209 | ETL.7030 | 40865910 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365575 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 2/51 RPR GYW |  | HAT CREEK #1-WESTWOOD | 002/051 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.49739 | 40.9209 | ETL.7030 | 40865910 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365613 | Not Scheduled | T2 COTTONWOOD #1 7/051 RPR INSS | 44406039 | COTTONWOOD #1 | 007/051 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.2675784 | 40.2896 | ETL.6620 | 40920735 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365657 | Not Scheduled | T2 DI DRUM-SUMMIT #1 10/125R RPL POLE | 31508705 | DRUM-SUMMIT #1 | 010/125 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.603704 | 39.3266 | ETL.1440 | 44768911 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365660 | Not Scheduled | T2 COTTONWOOD #1 7/049 RPR STRT |  | COTTONWOOD #1 | 007/049 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267611 | 40.2948 | ETL.6620 | 40910990 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-25 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119365924 | Not Scheduled | EI SPAULDING-SUMMIT 6/211 RPL POLE | 31508780 | SPAULDING-SUMMIT | 006/211 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.548077 | 39.3062 | ETL.8060 | 40660130 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119366456 | Not Scheduled | T2 DI DRUM-SUMMIT #2 23/274R RPL POLE | 31497848 | DRUM-SUMMIT #2 | 023/274 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.393972 | 39.3291 | ETL.1450 | 44552299 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119366458 | Not Scheduled | T2 DI DRUM-SUMMIT #2 23/274L RPL POLE | 31497848 | DRUM-SUMMIT #2 | 023/274 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.393972 | 39.3291 | ETL.1450 | 44552576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119366467 | Q2 | EI T2NT BRDGVLL-CTTNWD 39/3 | 44634170 | BRIDGEVILLE-COTTONWOOD | 039/315 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-13 | 2022-07-13 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.010022 | 40.3798 | ETL.1110 | 40820499 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119366566 | Q4 | T2 EI MAPLE CREEK-HOOPA 27/008 RPR JUMPE | 44394730 | MAPLE CREEK-HOOPA | 027/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.670948 | 41.0407 | ETL.7490 | 40877972 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119366704 | Q4 | T2 EI KESWICK-TRINITY 22/335 RPR GYWW |  | KESWICK-TRINITY | 022/335 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.793548 | 40.7193 | ETL.7270 | 40906072 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119366847 | Not Scheduled | T3 EI FULTON-CALISTOGA :006/007 RPL ANCH | 31507893 | FULTON-CALISTOGA | :006/007 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.589498 | 38.6794 | ETL.6880 | 40912477 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367199 | Not Scheduled | EI SPAULDING-SUMMIT 006/218 RPLC STRW | 31509215 | SPAULDING-SUMMIT | 006/218 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545193 | 39.307 | ETL.8060 | 40876685 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119367253 | Q4 | T3 EI MAPLE CREEK-HOOPA 27/006 INST JMPR | 44394730 | MAPLE CREEK-HOOPA | 027/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-01-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.671397 | 41.0387 | ETL.7490 | 44645848 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367310 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 12/138 INST MRKW | 44409002 | DRUM-SUMMIT #1 | 012/138 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2022-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162401 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367340 | Not Scheduled | EI SPAULDING-SUMMIT 6/217 RPL POLE | 31509215 | SPAULDING-SUMMIT | 006/217 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545602 | 39.3069 | ETL.8060 | 40878058 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119367363 | Not Scheduled | T2 EI SPAULDING-SUMMIT 3/123 RPL POLE |  | SPAULDING-SUMMIT | 003/123 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.589626 | 39.3135 | ETL.8060 | 40771495 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367364 | Not Scheduled | T2 EI SPAULDING-SUMMIT 3/123 REFRAME | 31510883 | SPAULDING-SUMMIT | 003/123 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.589626 | 39.3135 | ETL.8060 | 40771495 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367393 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/128 RPR STRW |  | DRUM-SUMMIT #1 | 011/128 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.599784 | 39.3284 | ETL.1440 | 44837632 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367396 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/128 RPR STRW |  | DRUM-SUMMIT #1 | 011/128 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.599784 | 39.3284 | ETL.1440 | 44837687 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367504 | Not Scheduled | EI SPAULDING-SUMMIT 006/216 RPLC STRW | 31509215 | SPAULDING-SUMMIT | 006/216 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.546197 | 39.3067 | ETL.8060 | 40826227 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119367516 | Q2 | T2 DI BRDGVL-CTTNWD 16/147 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 016/147 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44423954 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367657 | Not Scheduled | T2 DI DRUM-SUMMIT #1 19/231 CANCEL |  | DRUM-SUMMIT #1 | 019/231 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.453455 | 39.3181 | ETL.1440 | 40671393 | Structure-Wood | Rotten | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367679 | Q2 | EI T2NT HAT CRK #1-WESTWD 1/42 INST GMRK | 44406426 | HAT CREEK #1-WESTWOOD | 001/042 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.506407 | 40.9223 | ETL.7030 | 40667923 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367690 | Mar | T2 EI KONOCTI-MIDDLETOWN ;22/8 RPL POLE | 31509670 | KONOCTI-MIDDLETOWN | ;022/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-03-01 | 2021-03-04 | 2021-03-03 | 2021-03-03 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.603626 | 38.886 | ETL.6380 | 40876724 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367717 | Not Scheduled | EI SPAULDING-SUMMIT 6/214 RPL POLE | 31508780 | SPAULDING-SUMMIT | 006/214 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.546829 | 39.3066 | ETL.8060 | 40770659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119367722 | Q2 | T2 EI HAT CRK #1-WESTWD 1/42 RPR GYWW | 44406426 | HAT CREEK #1-WESTWOOD | 001/042 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.506407 | 40.9223 | ETL.7030 | 40667923 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367724 | Q2 | EI T2NT HAT CREEK #1-WESTWD 1/42 RMV DEB | 44406426 | HAT CREEK #1-WESTWOOD | 001/042 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.506407 | 40.9223 | ETL.7030 | 40667923 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367893 | Q3 | EI T2NT CARIBOU #2 ;5/7 RMV DEBRIS |  | CARIBOU #2 | ;005/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-14 | 2022-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.952058 | 39.9603 | ETL.6280 | 40824643 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367896 | Q3 | EI T2NT CARIBOU #2 ;005/002 INST MRKW |  | CARIBOU #2 | ;005/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-14 | 2022-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950977 | 39.9629 | ETL.6280 | 40668314 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367903 | Q3 | T2 EI CARIBOU #2 ;5/001 REFRAME | 31508650 | CARIBOU #2 | ;005/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950792 | 39.9635 | ETL.6280 | 40600652 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367906 | Q3 | T2 EI CARIBOU #2 5/4 RPL HDWW |  | CARIBOU #2 | ;005/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.951342 | 39.9618 | ETL.6280 | 40755461 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367911 | Q3 | EI T2NT CARIBOU #2 ;5/7 REGRADE |  | CARIBOU #2 | ;005/007 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-14 | 2022-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.952058 | 39.9603 | ETL.6280 | 40824643 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367913 | Q3 | T2 EI CARIBOU #2 5/005 RPL HDWW |  | CARIBOU #2 | ;005/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.951672 | 39.9614 | ETL.6280 | 40768854 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367914 | Q3 | T2 EI CARIBOU #2 ;5/000 REFRAME | 31508650 | CARIBOU #2 | ;005/000 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950517 | 39.9641 | ETL.6280 | 40614979 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367915 | Q3 | EI T2NT CARIBOU #2 5/4 RMV BUTT |  | CARIBOU #2 | ;005/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-14 | 2022-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.951342 | 39.9618 | ETL.6280 | 40755461 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367961 | Q2 | T2 DI BRDGVL-CTTNWD 15/143L RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/143 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44232660 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367963 | Q2 | T2 DI BRDGVL-CTTNWD 15/143L RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/143 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44232660 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367965 | Q2 | T2 DI BRDGVL-CTTNWD 15/143 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/143 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44232661 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119367968 | Q2 | T2 DI BRDGVL-CTTNWD 15/143 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/143 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44232662 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368003 | Not Scheduled | EI SPAULDING-SUMMIT 006/212 RMV BUTT | 44410505 | SPAULDING-SUMMIT | 006/212 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2022-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.547634 | 39.3064 | ETL.8060 | 40659223 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119368084 | Q2 | T2 EI HAT CRK #1-WSTWD 12/234 REPL POLE | 31508607 | HAT CREEK #1-WESTWOOD | 012/234 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.378662 | 40.826 | ETL.7030 | 40827579 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368085 | Q2 | T2 EI HAT CREEK #1-WESTWD 11/226 RPL STR | 31508285 | HAT CREEK #1-WESTWOOD | 011/226 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.38335 | 40.8309 | ETL.7030 | 40877466 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368086 | Q2 | T2 EI HAT CREEK #1-WESTWD 12/238 REPL PO | 31508607 | HAT CREEK #1-WESTWOOD | 012/238 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.375913 | 40.8237 | ETL.7030 | 40770845 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368089 | Q2 | T2 EI HAT CREEK #1-WESTWD 12/237 REPL PO | 31508607 | HAT CREEK #1-WESTWOOD | 012/237 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.376592 | 40.8243 | ETL.7030 | 40701213 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368090 | Q2 | T2 EI HAT CRK #1-WESTWD 11/229 REFRAME | 31508607 | HAT CREEK #1-WESTWOOD | 011/229 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.381875 | 40.8288 | ETL.7030 | 40759149 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368091 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 11/227 RERAM | 31508607 | HAT CREEK #1-WESTWOOD | 011/227 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.382863 | 40.8302 | ETL.7030 | 40600152 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368172 | Not Scheduled | T2 DI DRUM-SUMMIT #1 10/125L RPL POLE | 31508705 | DRUM-SUMMIT #1 | 010/125 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.603704 | 39.3266 | ETL.1440 | 44768909 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368173 | Not Scheduled | T2 DI DRUM-SUMMIT #1 10/125C REPL POLE | 31508705 | DRUM-SUMMIT #1 | 010/125 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.603704 | 39.3266 | ETL.1440 | 44768910 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368283 | Q4 | T3 DI MAPLE CREEK-HOOPA 10/0 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 010/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-01-13 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324523 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368285 | Feb | T2 DI MNT VST-JEFFRSN #1 3/14 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 003/014 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2022-07-13 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.122918 | 37.3304 | ETL.5220 | 40753082 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368303 | Mar | T2 EI KILARC-DESCHUTES 15/316 RPL PL | 31511244 | KILARC-DESCHUTES | 015/316 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.094572 | 40.5639 | ETL.7300 | 40759311 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368310 | Q2 | EI HUMBOLDT #1 10/10 RPR POLE | 44394725 | HUMBOLDT #1 | 010/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-04-17 | 2021-04-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-124.060813 | 40.8993 | ETL.7113 | 40588565 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368383 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 39/157 RPL INSS | 31527003 | DIABLO-MIDWAY #3 | 039/157 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.1791273 | 35.1874 | ETL.5980 | 40836742 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368615 | Not Scheduled | T2 DI DRUM-SUMMIT #2 27/329 RPL INSW | 31522060 | DRUM-SUMMIT #2 | 027/329 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.331222 | 39.3138 | ETL.1450 | 40889544 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368691 | Not Scheduled | T3 EI FULTON-CALISTOGA :006/011 RPL ANCH | 31507893 | FULTON-CALISTOGA | :006/011 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.592248 | 38.6835 | ETL.6880 | 40912481 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368757 | Not Scheduled | T2 DI DRUM-SUMMIT #2 19/232 RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/232 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.457942 | 39.319 | ETL.1450 | 44558958 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368759 | Not Scheduled | T2 DI DRUM-SUMMIT #1 9/105 CANCEL | 44434591 | DRUM-SUMMIT #1 | 009/105 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.632847 | 39.3176 | ETL.1440 | 44837642 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368777 | Q2 | EI T2NT BRIDGEVILLE-CTTNWD 39/309 MASTIC | 44634169 | BRIDGEVILLE-COTTONWOOD | 039/309 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-14 | 2022-07-14 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.99608 | 40.3723 | ETL.1110 | 40604118 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368854 | Q2 | T2 DI ELK-GUALALA 37/6 RPR GYWW | 44610591 | ELK-GUALALA | 037/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.711012 | 39.1257 | ETL.8410 | 44810763 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368866 | Q3 | T2 EI CARIBOU #2 :000/017 REFRM STRW | 31508650 | CARIBOU #2 | :000/017 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.063331 | 40.0129 | ETL.6280 | 40824677 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368875 | Not Scheduled | EI SPAULDING-SUMMIT 06/213 RPLC STRW | 31508780 | SPAULDING-SUMMIT | 006/213 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.547298 | 39.3065 | ETL.8060 | 40771503 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119368925 | Not Scheduled | T2 DI CARIBOU-PALERMO :22/182 RMV DEBRIS |  | CARIBOU-PALERMO | :022/182 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-14 | 2022-07-14 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37803 | 39.8724 | ETL.3190 | 40738807 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119368928 | Q3 | T2 DI BRDGVLL-CTTNWD 84/592L INST SPT BT | 44404493 | BRIDGEVILLE-COTTONWOOD | 084/592 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.753812 | 40.4863 | ETL.1110 | 44424578 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369017 | Not Scheduled | T2 DI DRUM-SUMMIT #1 7/84 RPL INSW | 31521959 | DRUM-SUMMIT #1 | 007/084 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.666826 | 39.3083 | ETL.1440 | 40725965 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369019 | Not Scheduled | T2 DI DRUM-SUMMIT #2 18/215L RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/215 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.482787 | 39.3172 | ETL.1450 | 44552420 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369100 | Q4 | T3NT DI MAPLE CREEK-HOOPA 12/6C RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 012/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.757625 | 40.9071 | ETL.7490 | 44743797 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369104 | Q4 | T3NT DI MAPLE CREEK-HOOPA 12/6R RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 012/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2022-07-13 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.757625 | 40.9071 | ETL.7490 | 44743798 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369185 | Not Scheduled | T2 DI DRUM-SUMMIT #2 011/136 CANCEL | 31511240 | DRUM-SUMMIT #2 | 011/136 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.589739 | 39.3329 | ETL.1450 | 44559160 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369298 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 19/220 RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 019/220 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2022-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.467611 | 39.3191 | ETL.1440 | 44768920 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369301 | Q2 | T3 EI FULTON-CALISTOGA -017/7 RPL STRW | 31508652 | FULTON-CALISTOGA | '-017/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.478422 | 38.4732 | ETL.6880 | 40808995 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369383 | Q2 | T2 EI KONOCTI-MIDDLETOWN 17/005 RPR STR | 44610651 | KONOCTI-MIDDLETOWN | 017/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.575277 | 38.818 | ETL.6380 | 40752566 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369424 | Q2 | DI SN LS OBSP-SNT MRI 22/103 RPLC HANGER | 44401937 | SAN LUIS OBISPO-SANTA MARIA | 022/103 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 |  |  | 2021-04-15 | 2021-04-01 | [5 empty] | South | WSIP | [6 empty] | '-120.44473 | 35.0026 | ETL.3540 | 40677651 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369595 | Mar | DIABLO-MIDWAY #2 49/201 RPL INSS | 31522252 | DIABLO-MIDWAY #2 | 049/201 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-03-11 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-120.004051 | 35.2438 | ETL.5970 | 40608466 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369617 | Not Scheduled | EI T2NT SPAULDING-SUMMIT 3/131 RMV PL B | 44410505 | SPAULDING-SUMMIT | 003/131 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2022-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.585129 | 39.3101 | ETL.8060 | 40701999 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369678 | Mar | T2 EI DIABLO-MIDWAY #2 38/156 RPL INST | 31527005 | DIABLO-MIDWAY #2 | 038/156 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-03-08 | 2021-03-10 | 2021-03-10 | 2021-03-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.183232 | 35.1851 | ETL.5970 | 40812079 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369679 | Mar | T2 EI DIABLO-MIDWAY #2 39/158 RPL INST | 31527005 | DIABLO-MIDWAY #2 | 039/158 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-03-08 | 2021-03-10 | 2021-03-10 | 2021-03-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.175335 | 35.1886 | ETL.5970 | 40871219 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369690 | Mar | T2 EI DIABLO-MIDWAY #2 38/155 RPL INST | 31527005 | DIABLO-MIDWAY #2 | 038/155 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-03-08 | 2021-03-10 | 2021-03-10 | 2021-03-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.185375 | 35.1842 | ETL.5970 | 40753825 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369691 | Mar | T2 EI DIABLO-MIDWAY #2 39/160 RPL INSS | 31527005 | DIABLO-MIDWAY #2 | 039/160 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-03-08 | 2021-03-10 | 2021-03-10 | 2021-03-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.1667328 | 35.1926 | ETL.5970 | 40631764 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369982 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 13/358 RPR SPLW | 44394870 | COLGATE-ALLEGHANY | 013/358 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.006548 | 39.4245 | ETL.6470 | 40817342 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119369988 | Q3 | T2 DI BRDGVL-CTTNWD 74/536 RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 074/536 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.1110 | 44424364 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370263 | Q3 | T2 DI BRDGVILL-CTTNWD 82/579 RPR SPLW | 44477511 | BRIDGEVILLE-COTTONWOOD | 082/579 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.718048 | 40.4809 | ETL.1110 | 44423963 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370288 | Mar | T2 EI KONOCTI-MIDDLETOWN 19/8 RPL POLE | 31509670 | KONOCTI-MIDDLETOWN | 019/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-03-03 | 2021-03-03 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.583894 | 38.8482 | ETL.6380 | 40876728 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370331 | Q2 | T2 EI TRINITY-MAPLE CRK 14/001 REPL POLE | 31510957 | TRINITY-MAPLE CREEK | 014/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.15943 | 40.7544 | ETL.8170 | 40594599 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370452 | Q3 | T2 DI CARIBOU #2 7/0 RPR GYWW |  | CARIBOU #2 | 007/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.21723 | 40.0225 | ETL.6280 | 40614769 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370492 | Q2 | T2 LAURELES-OTTER 3/001 RPL PL | 31511702 | LAURELES-OTTER | 003/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71788 | 36.4449 | ETL.7380 | 40585835 | Structure-Wood | No Good/Out of Stdrd | Replace | APPR | APPR | Awaiting Supervisor Approval | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370560 | Not Scheduled | T2 DI DRUM-SUMMIT#2 22/268 CANCEL |  | DRUM-SUMMIT #2 | 022/268 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.402081 | 39.3288 | ETL.1450 | 44558464 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370567 | Not Scheduled | T2 DI DRUM-SUMMIT#2 22/267 CANCEL | 31511240 | DRUM-SUMMIT #2 | 022/267 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.404137 | 39.3288 | ETL.1450 | 44557725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370637 | Q2 | EI HUMBOLDT-BRIDGEVILLE 106/5 RPL DAMPE | 44356653 | HUMBOLDT-BRIDGEVILLE | 106/005 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.9570958 | 40.7361 | ETL.1810 | 40787094 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370706 | Q3 | T2 DI BRIDGVL-CTTNWD 78/558 RPLC HRDW | 44431445 | BRIDGEVILLE-COTTONWOOD | 078/558 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.647621 | 40.4809 | ETL.1110 | 44512076 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370715 | Q2 | T2 EI FORT ROSS-GUALALA 44/002 RPL POLE | 31508619 | GUALALA-MONTE RIO | 044/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.319864 | 38.6958 | ETL.6980 | 40686500 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370719 | Q2 | T2 EI FORT ROSS-GUALALA 44/001 RPL POLE | 31508619 | GUALALA-MONTE RIO | 044/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.318856 | 38.6954 | ETL.6980 | 40601525 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370744 | Q2 | T2 EI ELK-GUALALA 47/9 RPR GYWW | 44610591 | ELK-GUALALA | 047/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.679365 | 38.9859 | ETL.8410 | 40870898 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370777 | Not Scheduled | EI SPAULDING-SUMMIT 006/209 RMV BUTT | 44411160 | SPAULDING-SUMMIT | 006/209 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2022-07-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.548877 | 39.3059 | ETL.8060 | 40590015 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119370846 | Not Scheduled | T2 EI SPAULDING-SUMMIT 004/140 RPL POLE | 31508780 | SPAULDING-SUMMIT | 004/140 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.580788 | 39.3086 | ETL.8060 | 40660117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370863 | Q2 | T2 EI FORT ROSS-GUALAL 39/11 RPR GYWW |  | GUALALA-MONTE RIO | 039/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.315093 | 38.6381 | ETL.6980 | 40596048 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119370869 | Not Scheduled | T3 COLGATE-ALLEGHANY 8/226 REFRAME | 31504764 | COLGATE-ALLEGHANY | 008/226 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.051637 | 39.3634 | ETL.6470 | 40760425 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371044 | Q3 | T2 EI CARIBOU-PLUMAS JCT 11/004 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 011/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.001994 | 39.9839 | ETL.6290 | 40758737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371046 | Q3 | T2 EI CARIBOU-PLUMAS JCT 11/000 RPR ANCH | 44408852 | CARIBOU-PLUMAS JCT | 011/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.005893 | 39.9857 | ETL.6290 | 40599532 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371050 | Q3 | T2 EI CARIBOU-PLUMAS JCT 11/000 REFRAME | 31511248 | CARIBOU-PLUMAS JCT | 011/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.005893 | 39.9857 | ETL.6290 | 40599532 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371227 | Q3 | T2 EI CARIBOU-PLUMAS JCT 15/2 RMV DEBRI | 44408852 | CARIBOU-PLUMAS JCT | 015/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.94062 | 39.9571 | ETL.6290 | 40698825 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371331 | Q3 | T2 EI CARIBOU-PLUMAS JCT 15/4 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 015/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.937997 | 39.9572 | ETL.6290 | 40769613 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371332 | Q3 | T2 EI CARIBOU-PLUMAS JCT 14/16 RPR WPKR | 44408852 | CARIBOU-PLUMAS JCT | 014/016 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.94371 | 39.9571 | ETL.6290 | 40810060 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371333 | Q3 | T2 EI CARIBOU-PLUMAS JCT 15/2 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 015/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.94062 | 39.9571 | ETL.6290 | 40698825 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371352 | Mar | T2 MNDCN-WLLTS-FRT BRGG 21/8 RPR JUMPER | 44644642 | MENDOCINO-WILLITS-FORT BRAGG | 021/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-03-18 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.477588 | 39.3841 | ETL.7550 | 40876365 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371510 | Q3 | EI T2NT CARIBOU #2 16/001 RMV BUTT |  | CARIBOU #2 | 016/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-14 | 2022-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.095375 | 40.0176 | ETL.6280 | 44217548 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371538 | Not Scheduled | EI T2NT HAT CRK #1-WESTWOOD 2/46 CANCEL | 44406426 | HAT CREEK #1-WESTWOOD | 002/046 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 | [6 empty] | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-121.50241 | 40.9217 | ETL.7030 | 40671153 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371548 | Q2 | EI T2NT HAT CRK #1-WESTWD 2/44 RMV BUTT | 44406426 | HAT CREEK #1-WESTWOOD | 002/044 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.50444 | 40.922 | ETL.7030 | 40596892 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371552 | Q2 | T2 EI HAT CREEK #1-WESTWD 2/46 RPL STRW | 31508285 | HAT CREEK #1-WESTWOOD | 002/046 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.50241 | 40.9217 | ETL.7030 | 40671153 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371587 | Q2 | T2 EI TRINITY-MAPLE CREEK 26/6 RPL DAMPE | 44401954 | TRINITY-MAPLE CREEK | 026/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.390041 | 40.7056 | ETL.8170 | 40906426 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371603 | Q2 | T2 EI TRINITY-MAPLE CREEK 26/0 RPR JUMPE | 44401954 | TRINITY-MAPLE CREEK | 026/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.37653 | 40.7042 | ETL.8170 | 40906423 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371606 | Q2 | EI T2NT TRINITY-MPL CRK 25/2A RMV BUTT | 44575117 | TRINITY-MAPLE CREEK | 025/002A | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2022-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.363722 | 40.7039 | ETL.8170 | 40906420 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371607 | Q2 | T2 EI TRINITY-MAPLE CRK 25/1 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 025/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.3578174 | 40.7042 | ETL.8170 | 44420632 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371608 | Q2 | EI T2NT TRINITY-MAPLE CREEK 25/4 RMV BUT | 44401994 | TRINITY-MAPLE CREEK | 025/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.369916 | 40.7035 | ETL.8170 | 40903783 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371610 | Q2 | T2 EI TRINITY-MAPLE CRK 25/1 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 025/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.3578174 | 40.7042 | ETL.8170 | 44420633 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371613 | Q2 | T2 EI TRINITY-MAPLE CRK 25/1 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 025/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.3578174 | 40.7042 | ETL.8170 | 44420631 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371617 | Not Scheduled | T2 EI SPAULDING-SUMMIT 11/373 RPL STRW |  | SPAULDING-SUMMIT | 011/373 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.459738 | 39.3189 | ETL.8060 | 40770664 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371662 | Q2 | T2 DI BRDGVLLE-CTTONWD 17/158 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 017/158 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.592078 | 40.3813 | ETL.1110 | 44424089 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371663 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 020/233 CANCEL | 44409002 | DRUM-SUMMIT #1 | 020/233 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2022-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.449439 | 39.3178 | ETL.1440 | 44837667 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371667 | Not Scheduled | T2 DI DRUM-SUMMIT #2 010/116 CANCEL |  | DRUM-SUMMIT #2 | 010/116 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.617113 | 39.3217 | ETL.1450 | 44553127 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371673 | Q3 | T2 EI CARIBOU #2 ;00/016 REFRAME | 31508650 | CARIBOU #2 | ;000/016 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962593 | 40.021 | ETL.6280 | 40826432 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371785 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 38/156 RPL INSS | 31527003 | DIABLO-MIDWAY #3 | 038/156 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.1837094 | 35.1855 | ETL.5980 | 40839519 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371786 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 40/162 RPL INSS | 31527006 | DIABLO-MIDWAY #3 | 040/162 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.162839 | 35.1948 | ETL.5980 | 40724334 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371787 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 40/162A RPL INSS | 31527006 | DIABLO-MIDWAY #3 | 040/162A | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.1581152 | 35.1967 | ETL.5980 | 40578774 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371788 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 38/154 RPL INSS | 31527003 | DIABLO-MIDWAY #3 | 038/154 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.187911 | 35.1839 | ETL.5980 | 40791396 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371789 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 40/161 RPL INSS | 31527006 | DIABLO-MIDWAY #3 | 040/161 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.1656154 | 35.1937 | ETL.5980 | 40619377 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371790 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 39/160 RPL INSS | 31527003 | DIABLO-MIDWAY #3 | 039/160 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.1675065 | 35.1929 | ETL.5980 | 40631766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371791 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 41/165 RPL INST | 31527006 | DIABLO-MIDWAY #3 | 041/165 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.147445 | 35.2008 | ETL.5980 | 40753831 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371803 | Q3 | T2 DI BRDGVILL-CTTNWD 84/589L RPR GYWW | 44431445 | BRIDGEVILLE-COTTONWOOD | 084/589 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.747395 | 40.4867 | ETL.1110 | 44424612 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119371857 | Not Scheduled | T2 DI DRUM-SUMMIT #2 12/146 CANCEL | 31522060 | DRUM-SUMMIT #2 | 012/146 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.572744 | 39.3316 | ETL.1450 | 42573142 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119372709 | Not Scheduled | T3 EI FRENCH MDWS-MDDLE FRK 9/171 RPR GY | 44394874 | FRENCH MEADOWS-MIDDLE FORK | 009/171 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.55055 | 39.0173 | ETL.6870 | 40768420 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119372730 | Not Scheduled | T3 EI FRH MEADOWS-MID FORK 11/219 REFRAM | 31509218 | FRENCH MEADOWS-MIDDLE FORK | 011/219 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.598058 | 39.0095 | ETL.6870 | 40824477 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119372731 | Not Scheduled | T3 EI FRH MEADOWS-MID FORK 11/218 REFRAM | 31509218 | FRENCH MEADOWS-MIDDLE FORK | 011/218 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.596669 | 39.0097 | ETL.6870 | 40766792 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119372803 | Q2 | EI GATES-PANOCHE #1 0/1 BENT STEEL | 44490730 | GATES-PANOCHE #1 | 000/001 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.125045 | 36.142 | ETL.4720 | 40587467 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119372914 | Not Scheduled | T2 DI DRUM-SUMMIT #2 7/81B RPL STRW |  | DRUM-SUMMIT #2 | 007/081B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.668185 | 39.3078 | ETL.1450 | 44150204 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119373213 | Not Scheduled | EI SPAULDING-SUMMIT 5/196 INST MRKW | 44421024 | SPAULDING-SUMMIT | 005/196 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.554214 | 39.305 | ETL.8060 | 40809657 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119373469 | Not Scheduled | EI FULTON-CALISTOGA :001/000 RPR ANCW | 31509848 | FULTON-CALISTOGA | :001/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.5820816 | 38.6102 | ETL.6880 | 44286449 | Anchor-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119373507 | Q3 | T2NT DI CARIBOU #2 ;4/24 RMV PL BUTT |  | CARIBOU #2 | ;004/024 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-14 | 2022-07-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.949835 | 39.9659 | ETL.6280 | 40769621 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119373749 | Not Scheduled | EI T3NT POE-RIO OSO 19/131 RPR FOND |  | POE-RIO OSO | 019/131 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2022-07-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.482265 | 39.7127 | ETL.5540 | 40590426 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374044 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/127 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 011/127 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.600692 | 39.328 | ETL.1440 | 44837678 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374048 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/127 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 011/127 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.600692 | 39.328 | ETL.1440 | 44837666 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374129 | Q3 | T2 EI CARIBOU #2 6/4 REFRAME | 31508650 | CARIBOU #2 | :006/004 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.978305 | 39.9685 | ETL.6280 | 40751769 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374136 | Q3 | T2 EI BRIDGEVILLE-GARBERVLE 14/0A RPL A | 31508615 | BRIDGEVILLE-GARBERVILLE | 014/000A | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.733887 | 40.3165 | ETL.6220 | 44404635 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374154 | Q2 | EI KONOCTI-EAGLE ROCK 009/006 RPR GYWW | 44610613 | KONOCTI-EAGLE ROCK | 009/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-05-07 | 2021-05-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.741828 | 38.9289 | ETL.6861 | 40809254 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374216 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 14/383 RMV PL BUTT | 44394869 | COLGATE-ALLEGHANY | 014/383 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-14 | 2022-07-14 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.998751 | 39.4355 | ETL.6470 | 40664624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374218 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 14/383 RPR INSW | 44394868 | COLGATE-ALLEGHANY | 014/383 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.998751 | 39.4355 | ETL.6470 | 44843342 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374237 | Not Scheduled | T2 DI DRUM-SUMMIT #1 18/217 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 018/217 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.472918 | 39.3181 | ETL.1440 | 44149465 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374275 | Q3 | T2 EI CARIBOU #2 3/3 RPL POLE | 31509660 | CARIBOU #2 | ;003/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.945828 | 39.9903 | ETL.6280 | 40666874 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374346 | Q3 | T2 EI CARIBOU #2 3/4 RPL POLE | 31509660 | CARIBOU #2 | ;003/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.945865 | 39.99 | ETL.6280 | 40754019 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374380 | Q2 | T2NT DI HT CRK #1-WSTW 24/477 RMV DEBRIS |  | HAT CREEK #1-WESTWOOD | 024/477 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.213393 | 40.6886 | ETL.7030 | 40825584 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374491 | Not Scheduled | EI SPAULDING-SUMMIT 005/193 RMV BUTT | 44411160 | SPAULDING-SUMMIT | 005/193 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.555461 | 39.3053 | ETL.8060 | 40751849 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374537 | Q3 | T2 EI BRIDGEVILLE-GARBERVLE 14/04 RPL AN | 31508615 | BRIDGEVILLE-GARBERVILLE | 014/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.736301 | 40.3126 | ETL.6220 | 40769385 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374594 | Not Scheduled | EI SPAULDING-SUMMIT 005/195 INST MRKW | 44411160 | SPAULDING-SUMMIT | 005/195 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.554655 | 39.3051 | ETL.8060 | 40810159 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374655 | Not Scheduled | EI SPAULDING-SUMMIT 5/205 INST MRKW | 44421024 | SPAULDING-SUMMIT | 005/205 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55056 | 39.3053 | ETL.8060 | 40810161 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374712 | Not Scheduled | EI SPAULDING-SUMMIT 5/199 RPR GYWW | 44411158 | SPAULDING-SUMMIT | 005/199 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55259 | 39.3048 | ETL.8060 | 40590012 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374713 | Not Scheduled | EI SPAULDING-SUMMIT 5/199 RMV PL BUTT | 44411160 | SPAULDING-SUMMIT | 005/199 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55259 | 39.3048 | ETL.8060 | 40590012 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374885 | Not Scheduled | EI SPAULDING-SUMMIT 5/203 RPL POLE | 31508780 | SPAULDING-SUMMIT | 005/203 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.551146 | 39.3051 | ETL.8060 | 40751851 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374914 | Not Scheduled | T2 DI DRUM-SUMMIT #1 009/113 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 009/113 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.620904 | 39.3209 | ETL.1440 | 40876967 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374952 | Not Scheduled | EI SPAULDING-SUMMIT 5/204 RMV PL BUTT | 44421023 | SPAULDING-SUMMIT | 005/204 | ICH | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.550679 | 39.3052 | ETL.8060 | 40770657 | Other | Other | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 625 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374991 | Not Scheduled | EI SPAULDING-SUMMIT 005/206 RMV BUTT | 44411160 | SPAULDING-SUMMIT | 005/206 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.550272 | 39.3054 | ETL.8060 | 40826189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119374993 | Q3 | T2 EI CARIBOU #2 ;003/000 RPL STRW | 31509660 | CARIBOU #2 | ;003/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946463 | 39.9919 | ETL.6280 | 40614893 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119374999 | Not Scheduled | EI T3NT POE-RIO OSO 19/133 RPR FOND |  | POE-RIO OSO | 019/133 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2022-07-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.483519 | 39.705 | ETL.5540 | 40655113 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375005 | Not Scheduled | T2 EI CARIBOU-PALERMO 12/110 RPR FOND |  | CARIBOU-PALERMO | 012/110 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375361 | Q2 | T2 DI HAT CRK #1-WSTWD 26/502 REFRAME | 31511712 | HAT CREEK #1-WESTWOOD | 026/502 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.197975 | 40.6742 | ETL.7030 | 40770749 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375367 | Q2 | T2NT DI HT CRK #1-WSTWD 26/502 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 026/502 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.197975 | 40.6742 | ETL.7030 | 40770749 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375419 | Q2 | T2NT DI HAT CRK #1-WSTWD 32/628 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 032/628 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.109478 | 40.6074 | ETL.7030 | 40759224 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375422 | Q3 | T2 EI BRIDGEVILLE-GARBRVLLE 13/11 RPLC S | 31511711 | BRIDGEVILLE-GARBERVILLE | 013/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.731089 | 40.3194 | ETL.6220 | 40586733 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375532 | Not Scheduled | EI T3NT POE-RIO OSO 19/134 RPR FOND |  | POE-RIO OSO | 019/134 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2022-07-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.484173 | 39.701 | ETL.5540 | 40757242 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375558 | Mar | T3 EI MORAGA-SAN LEANDRO #1 0/3 RMV HRDT | 44303861 | MORAGA-SAN LEANDRO #1 | 000/003 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-01-15 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.163595 | 37.8423 | ETL.2770 | 40644205 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375752 | Not Scheduled | EI SPAULDING-SUMMIT 06/225 RPR GYWW | 44449606 | SPAULDING-SUMMIT | 006/225 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.540096 | 39.3083 | ETL.8060 | 40586089 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119375765 | Q2 | T2 DI HAT CRK #1-WSTWD 38/745 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 038/745 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.042408 | 40.5349 | ETL.7030 | 40827571 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119375842 | Not Scheduled | EI SPAULDING-SUMMIT 06/226 RPL PL | 31527024 | SPAULDING-SUMMIT | 006/226 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.53934 | 39.3086 | ETL.8060 | 44167330 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119375864 | Not Scheduled | DI DRUM-SUMMIT #2 8/97L RMV DEBRIS | 44409006 | DRUM-SUMMIT #2 | 008/097 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2022-07-14 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44150212 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119375876 | Q2 | T2 DI HAT CREEK #1-WESTW 37/713 RMV DEBR |  | HAT CREEK #1-WESTWOOD | 037/713 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.060945 | 40.5549 | ETL.7030 | 40667971 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376007 | Q2 | EI SALINAS-LAURELES A016/346 RPR GYWW | 44391519 | SALINAS-LAURELES | A016/346 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | [5 empty] | South | WSIP | [6 empty] | '-121.831935 | 36.5817 | ETL.7930 | 40600117 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376199 | Not Scheduled | EI T2NT MALIN-RND MT #2 68/344A CANCEL | 44408444 | MALIN-ROUND MTN #2 | 068/344A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.751783 | 41.114 | ETL.6020 | 40576653 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376369 | Q3 | DI BRIDGEVILLE-GRBRVL 15/0 RMV PL BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 015/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.735914 | 40.3048 | ETL.6220 | 40591090 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376410 | Q3 | DI BRIDGEVILLE-GRBRVL 15/0 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 015/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.735914 | 40.3048 | ETL.6220 | 40591090 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376474 | Q2 | T2 DI HT CRK #1-WSTWD 26/514 RMV PL BUTT | 44388736 | HAT CREEK #1-WESTWOOD | 026/514 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.191597 | 40.6673 | ETL.7030 | 40817133 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376560 | Not Scheduled | T2 DI DRUM-SUMMIT #1 8/96 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 008/096 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.649594 | 39.3141 | ETL.1440 | 44837655 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376729 | Not Scheduled | T2 DI DRUM-SUMMIT #1 8/96 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 008/096 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.649594 | 39.3141 | ETL.1440 | 44837644 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376763 | Not Scheduled | T2 DI DRUM-SUMMIT #1 8/96C RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 008/096 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.649594 | 39.3141 | ETL.1440 | 44837694 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376778 | Q2 | T2 DI HAT CREEK #1-WSTWD 21/419 RPR STRW |  | HAT CREEK #1-WESTWOOD | 021/419 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.251233 | 40.723 | ETL.7030 | 40817127 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376804 | Mar | EI SALINAS-LAURELES A16/341 RPR ANCHOR | 44625135 | SALINAS-LAURELES | A016/341 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-03-04 | 2021-03-04 | [5 empty] | South | WSIP | [6 empty] | '-121.828512 | 36.581 | ETL.7930 | 40812841 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376853 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 13/6 INST | 44300097 | BRIDGEVILLE-GARBERVILLE | 013/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.726103 | 40.3215 | ETL.6220 | 40810925 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119376866 | Mar | EI T3NT MORAGA-SAN LEANDRO #1 1/10 RPR F | 44303861 | MORAGA-SAN LEANDRO #1 | 001/010 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-15 | 2022-07-15 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.157119 | 37.8303 | ETL.2770 | 40581569 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377194 | Not Scheduled | EI T3NT MORAGA-SAN LEANDRO #1 1/11 PAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 001/011 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-15 | 2022-07-15 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.155406 | 37.8289 | ETL.2770 | 40594276 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377198 | Q2 | T2 EI KONOCTI-MIDDLETOWN 18/007 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 018/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.581242 | 38.8363 | ETL.6380 | 40824705 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377230 | Q2 | T2 EI KONOCTI-MIDDLETOWN 18/003 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 018/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.579322 | 38.8304 | ETL.6380 | 44667802 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377236 | Not Scheduled | T3 EI MONTE RIO-FULTON 8/001 RPL POLE | 31509533 | MONTE RIO-FULTON | 008/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-01-15 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.90421 | 38.4902 | ETL.7630 | 40584630 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377269 | Q2 | EI GATES-PANOCHE #1 1/8 BENT STEEL | 44490730 | GATES-PANOCHE #1 | 001/008 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.137272 | 36.1579 | ETL.4720 | 40863626 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119377301 | Q2 | T2 EI KONOCTI-MIDDLETOWN 18/002 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 018/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.578492 | 38.828 | ETL.6380 | 40661647 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377342 | Not Scheduled | EI SPAULDING-SUMMIT 6/230 RPL POLE | 31509215 | SPAULDING-SUMMIT | 006/230 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.537378 | 39.3085 | ETL.8060 | 40828132 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119377385 | Q2 | T2NT DI HT CRK #1-WESTWD 27/532 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 027/532 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.181282 | 40.6562 | ETL.7030 | 40656896 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377489 | Not Scheduled | EI SPAULDING-SUMMIT 06/231 RPL STRW | 31509215 | SPAULDING-SUMMIT | 006/231 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.536893 | 39.3083 | ETL.8060 | 40818274 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119377579 | Not Scheduled | EI SPAULDING-SUMMIT 6/232 RPL POLE | 31509215 | SPAULDING-SUMMIT | 006/232 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.536426 | 39.3081 | ETL.8060 | 40878060 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119377595 | Q2 | T2NT DI HAT CRK #1-WSTWD 23/454 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/454 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.22812 | 40.7021 | ETL.7030 | 40656892 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377643 | Not Scheduled | T2 DI DRUM-SUMMIT #1 11/134 RPR GYWW | 44434591 | DRUM-SUMMIT #1 | 011/134 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.590688 | 39.3324 | ETL.1440 | 44768916 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377649 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 11/134R RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 011/134 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2022-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.590688 | 39.3324 | ETL.1440 | 44768916 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377688 | Not Scheduled | EI SPAULDING-SUMMIT 6/233 RPL POLE | 31509215 | SPAULDING-SUMMIT | 006/233 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535956 | 39.308 | ETL.8060 | 40869725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119377708 | Not Scheduled | T2 EI SPAULDING-SUMMIT 4/146 RMV VEG |  | SPAULDING-SUMMIT | 004/146 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.577999 | 39.3076 | ETL.8060 | 40878088 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377814 | Not Scheduled | T2 COTTONWOOD #1 009/063 RPR STRT |  | COTTONWOOD #1 | 009/063 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267394 | 40.2572 | ETL.6620 | 40905999 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377875 | Not Scheduled | T2 COTTONWOOD #1 009/063 RPR INSS |  | COTTONWOOD #1 | 009/063 | ICH | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.2674075 | 40.2572 | ETL.6620 | 40915668 | Other | Other | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 625 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377881 | Not Scheduled | T2 COTTONWOOD #1 10/067 RPR STRT |  | COTTONWOOD #1 | 010/067 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267342 | 40.2488 | ETL.6620 | 40906003 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-25 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377924 | Not Scheduled | T2 COTTONWOOD #1 009/062 RPR STRT |  | COTTONWOOD #1 | 009/062 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267421 | 40.2617 | ETL.6620 | 40905998 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-25 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377957 | Not Scheduled | T2 COTTONWOOD #1 10/065 RPR STRT |  | COTTONWOOD #1 | 010/065 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267374 | 40.253 | ETL.6620 | 40906001 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119377984 | Mar | EI T3NT DRUM-RIO OSO #2 4/47 RPR FOND | 44394762 | DRUM-RIO OSO #2 | 004/047 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-15 | 2022-07-15 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.833207 | 39.2279 | ETL.1430 | 40805175 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378091 | Q2 | EI T2NT HT CRK #1-WSTWD 12/249 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 012/249 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.368238 | 40.8175 | ETL.7030 | 40817101 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378093 | Not Scheduled | T2 EI SPAULDING-SUMMIT 11/381 RMV DEBRIS | 44449037 | SPAULDING-SUMMIT | 011/381 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2022-07-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.456226 | 39.3183 | ETL.8060 | 44349554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378123 | Not Scheduled | T2 EI SPAULDING-SUMMIT 11/378 RPL POLE |  | SPAULDING-SUMMIT | 011/378 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.45746 | 39.3186 | ETL.8060 | 40603899 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378132 | Feb | T3 DRUM-RIO OSO #1 1/017 RPR INSULATOR | 44394479 | DRUM-RIO OSO #1 | 001/017 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-01-15 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.7988352 | 39.2562 | ETL.1420 | 40836520 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378134 | Q3 | T2 EI CARIBOU-PLUMAS JCT 13/001 RPR PL | 44408852 | CARIBOU-PLUMAS JCT | 013/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.976307 | 39.9676 | ETL.6290 | 40585991 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378153 | Q3 | T2 EI CARIBOU-PLUMAS JCT 13/5 RPR COND | 44408852 | CARIBOU-PLUMAS JCT | 013/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.972203 | 39.9653 | ETL.6290 | 40751789 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378154 | Q3 | T2 EI CARIBOU-PLUMAS JCT 013/006 RPR GYW | 44408852 | CARIBOU-PLUMAS JCT | 013/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.971142 | 39.9647 | ETL.6290 | 40826460 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378158 | Q3 | EI T2NT CARIBOU-PLUMAS JCT 13/4 RMV DEBR | 44408852 | CARIBOU-PLUMAS JCT | 013/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-15 | 2022-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.973568 | 39.966 | ETL.6290 | 40769607 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378198 | Not Scheduled | EI SPAULDING-SUMMIT 6/236 RPL POLE | 31509215 | SPAULDING-SUMMIT | 006/236 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-15 | 2021-07-15 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.534399 | 39.3078 | ETL.8060 | 40702002 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119378261 | Q2 | T3 EI FULTON-CALISTOGA -018/005 RPL STR | 31509532 | FULTON-CALISTOGA | '-018/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-01-15 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.480612 | 38.4853 | ETL.6880 | 40751140 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378309 | Not Scheduled | T2NT DI BRDGVLL-CTTNWD 81/570 RPR FOND | 44623123 | BRIDGEVILLE-COTTONWOOD | 081/570 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-14 | 2022-07-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.693467 | 40.475 | ETL.1110 | 40580987 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378313 | Q2 | EI T2NT HAT CRK #1-WESTWD 01/040 RMV DEB |  | HAT CREEK #1-WESTWOOD | 001/040 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.50837 | 40.9226 | ETL.7030 | 40590008 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378322 | Q2 | EI T2NT HAT CRK #1-WESTWD 1/035 RMV PL |  | HAT CREEK #1-WESTWOOD | 001/035 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.513273 | 40.9234 | ETL.7030 | 40757927 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378448 | Q3 | T2 EI CARIBOU-PLUMAS JCT 9/001 RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | 009/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.034862 | 40.0014 | ETL.6290 | 40591663 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378462 | Q3 | T2 EI CARIBOU-PLUMAS JCT 007/007 REFRAME | 31511248 | CARIBOU-PLUMAS JCT | 007/007 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.062997 | 40.0123 | ETL.6290 | 40824651 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378492 | Q3 | T2 EI CARIBOU-PLUMAS 009/012 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 009/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.024505 | 39.9985 | ETL.6290 | 40698801 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378800 | Q2 | EI T2NT TRINITY-MAPL CRK 27/004 RMV BUTT | 44401994 | TRINITY-MAPLE CREEK | 027/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.401999 | 40.7021 | ETL.8170 | 40906431 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378801 | Q2 | T2 EI TRINITY-MAPLE CRK 27/4 RPL DAMPER | 44401954 | TRINITY-MAPLE CREEK | 027/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4020129 | 40.7021 | ETL.8170 | 40916100 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378808 | Q2 | T2 EI TRINITY-MAPLE CREEK 28/0 RPR GYWW | 44364310 | TRINITY-MAPLE CREEK | 028/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.413178 | 40.7002 | ETL.8170 | 44846600 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119378968 | Q3 | DI BRDGVL-GRBRVL 15/3 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 015/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.735558 | 40.3019 | ETL.6220 | 40666736 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379065 | Q2 | T2 EI TRINITY-MAPLE CREEK 13/09 RPR COND | 44273074 | TRINITY-MAPLE CREEK | 013/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.156801 | 40.7565 | ETL.8170 | 40893773 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379066 | Q2 | T2 EI TRINITY-MAPLE CREEK 13/7 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 013/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.153101 | 40.7592 | ETL.8170 | 44846603 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379067 | Q2 | EI TRINITY-MAPLE CREEK 13/8 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 013/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.1542482 | 40.7582 | ETL.8170 | 44311003 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379093 | Not Scheduled | T2NT DI DRM-SUMMIT #1 21/248 RMV PL BUTT | 44409002 | DRUM-SUMMIT #1 | 021/248 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-13 | 2022-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.429569 | 39.3178 | ETL.1440 | 44740277 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379151 | Not Scheduled | T3 EI MIDDLE FORK #1 1/25 RPR WP HOLE | 44394961 | MIDDLE FORK #1 | 001/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-01-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.603801 | 39.0054 | ETL.8405 | 40809620 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379152 | Not Scheduled | EI T3NT MIDDLE FORK #1 1/20 CANCEL | 44394962 | MIDDLE FORK #1 | 001/020 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-15 | 2022-07-15 | [6 empty] | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-120.600654 | 39.0086 | ETL.8405 | 40660027 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379165 | Not Scheduled | T3 EI MIDDLE FORK #1 1/26 RPR WP HOLE | 44394961 | MIDDLE FORK #1 | 001/026 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-01-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.604437 | 39.0048 | ETL.8405 | 40874885 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379284 | Q2 | T2NT DI HAT CRK #1-WSTWD 23/442 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/442 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.236194 | 40.7095 | ETL.7030 | 40592097 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379289 | Not Scheduled | EI LOS BANOS-GATES #1 078/329 RPLC INSS | 31515416 | LOS BANOS-GATES #1 | 078/329 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.1511655 | 36.1728 | ETL.6000 | 40889748 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119379489 | Before Feb | DI BRDGVL-GRBRVL 34/6 INST DAMW | 44300097 | BRIDGEVILLE-GARBERVILLE | 034/007 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 |  |  | 2021-01-24 | 2021-01-17 | [5 empty] | North Coast | WSIP |  |  |  | REJECT: As notes from CIRT term in SAP and per dwg 022487, span with splice shall install damper on both sides of the span. Need to install damper on the back span of pole 34/7 as well. The additional photos are still only showing dampers on 34/6. (WV team: plea |  |  | '-123.767556 | 40.1127 | ETL.6220 | 40851726 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Before Feb | Found in 2020 | Not FSR Upgrade | IC | Before Feb |  | Reject | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379523 | Q2 | T2NT DI HT CRK#1-WSTWD 26/510 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 026/510 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.194047 | 40.6699 | ETL.7030 | 40676350 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379589 | Q2 | EI GATES-PANOCHE #1 002/010 RPR STRT | 44490730 | GATES-PANOCHE #1 | 002/010 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.141669 | 36.1631 | ETL.4720 | 40592378 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119379656 | Q3 | DI BRIDGEVL-GRBRVL 14/12 RMV BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 014/012 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.736491 | 40.3058 | ETL.6220 | 40698372 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379659 | Q3 | DI BRIDGEVL-GRBRVL 14/12 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 014/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.736491 | 40.3058 | ETL.6220 | 40698372 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379715 | Q2 | T2 EI LAKEVILLE #2 A8/147 RPR GYWW |  | LAKEVILLE #2 | A008/147 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.575048 | 38.164 | ETL.7340 | 40811636 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379767 | Not Scheduled | T3 EI FRNCH MDWS-MID FRK 8/165 RPR WP HO | 44394874 | FRENCH MEADOWS-MIDDLE FORK | 008/165 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-01-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.545182 | 39.0201 | ETL.6870 | 40809611 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379841 | Q3 | DI BRDGVL-GRBRVL 23/3 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 023/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.73684 | 40.2125 | ETL.6220 | 40650773 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379868 | Q2 | T2 EI LAKEVILLE #2 A7/146 RPR GYWW |  | LAKEVILLE #2 | A007/146 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.575443 | 38.1642 | ETL.7340 | 40617288 | Ground Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119379887 | Q3 | DI BRIDGEVILLE-GRBERVLLE 19/00 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 019/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.767842 | 40.2606 | ETL.6220 | 40591106 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380002 | Mar | EI T3NT CORTINA-MENDOCINO #1 19/92 RPR F | 44238817 | CORTINA-MENDOCINO #1 | 019/092 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-16 | 2022-07-16 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.5486 | 39.0036 | ETL.1330 | 40657044 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380122 | Q2 | T3 EI MORAGA-SAN LEANDRO #1 2/14 RPL INS |  | MORAGA-SAN LEANDRO #1 | 002/014 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-01-16 |  |  | 2021-05-25 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1494272 | 37.8242 | ETL.2770 | 40774028 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-02-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380174 | Q2 | T2 DI HAT CREEK #1-WESTW 29/571 REFRAME | 31511712 | HAT CREEK #1-WESTWOOD | 029/571 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.15127 | 40.6374 | ETL.7030 | 40759214 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380226 | Q2 | T2 DI HAT CRK #1-WSTWD 39/765 RPL STRW | 31511043 | HAT CREEK #1-WESTWOOD | 039/765 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.035768 | 40.5207 | ETL.7030 | 40827558 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380438 | Not Scheduled | EI GATES-PANOCHE #1 02/012 RMV DEBRIS | 44507423 | GATES-PANOCHE #1 | 002/012 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2022-07-16 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.146013 | 36.1682 | ETL.4720 | 40663918 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119380468 | Q3 | T2 EI BRIDGEVILLE-GARBERVILL 12/15 INS J | 44300097 | BRIDGEVILLE-GARBERVILLE | 012/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.722548 | 40.3305 | ETL.6220 | 40752663 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380469 | Q3 | T2 EI BRIDGEVILLE-GRBRVLL 12/15 RMV PL B | 44572647 | BRIDGEVILLE-GARBERVILLE | 012/015 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-16 | 2022-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.722548 | 40.3305 | ETL.6220 | 40752663 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380572 | Q2 | T2 DI HAT CRK #1-WSTWD 34/655 RMV DEBRIS |  | HAT CREEK #1-WESTWOOD | 034/655 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.093897 | 40.5905 | ETL.7030 | 40667965 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380579 | Q2 | T2 DI HT CRK #1-WSTWD 25/486 RMV PL BUTT | 44388736 | HAT CREEK #1-WESTWOOD | 025/486 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.207628 | 40.6832 | ETL.7030 | 40825586 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380600 | Q2 | T2 DI HAT CRK #1-WESTW 38/733 RMV DEBRIS |  | HAT CREEK #1-WESTWOOD | 038/733 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.049367 | 40.5424 | ETL.7030 | 40770761 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380859 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 13/4 INS J | 44300097 | BRIDGEVILLE-GARBERVILLE | 013/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.723552 | 40.3243 | ETL.6220 | 40752618 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380860 | Q3 | T2 EI BRIDGEVILLE-GRBRVLL 13/4 RMV PL BU | 44572647 | BRIDGEVILLE-GARBERVILLE | 013/004 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-16 | 2022-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.723552 | 40.3243 | ETL.6220 | 40752618 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119380862 | Q3 | T2 EI BRIDGEVILLE-GARBERVILL 13/4 RPR S | 44300097 | BRIDGEVILLE-GARBERVILLE | 013/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.723552 | 40.3243 | ETL.6220 | 40752618 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381057 | Q3 | T2 EI BRIDGVLE-GRBRVLE 13/2 INST JMP INS | 31509854 | BRIDGEVILLE-GARBERVILLE | 013/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.721844 | 40.3262 | ETL.6220 | 40698387 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381069 | Q3 | EI T2NT BRIDGVLE-GRBRVLE 13/2 INST ANMW | 44300097 | BRIDGEVILLE-GARBERVILLE | 013/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-16 | 2022-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.721844 | 40.3262 | ETL.6220 | 40698387 | Animal Guard-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381204 | Q3 | T2 EI CARIBOU-PLUMAS JCT 8/6 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 008/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.048235 | 40.0053 | ETL.6290 | 40816720 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381207 | Q3 | T2 EI CARIBOU-PLUMAS JCT 8/6 RPR HRDW | 44408852 | CARIBOU-PLUMAS JCT | 008/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.048235 | 40.0053 | ETL.6290 | 40816720 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381355 | Q2 | T2 DI HAT CRK #1-WSTWD 41/785 RPR SPLW | 44388736 | HAT CREEK #1-WESTWOOD | 041/785 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.02935 | 40.5059 | ETL.7030 | 40616930 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381453 | Feb | DI LAYTONVILLE-COVELO 12/11 RPL STRW | 31509539 | LAYTONVILLE-COVELO | 012/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.271055 | 39.7537 | ETL.7390 | 40600459 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381497 | Q2 | T3 EGL RCK-FLTN-SLVRD 5/25 INST JMP INSS | 31508696 | EAGLE ROCK-FULTON-SILVERADO | 005/025 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-01-16 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7968525 | 38.7723 | ETL.4392 | 40791333 | Insulator-Steel | No Good/Out of Stdrd | Replace | POST | POST | POST Estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381787 | Q3 | T2 EI BRIDGEVILLE-GARBRVILL 12/13 RPLC S | 31511711 | BRIDGEVILLE-GARBERVILLE | 012/013 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.723295 | 40.3321 | ETL.6220 | 40666701 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381847 | Not Scheduled | T3 EAGLE RCK-FLTN-SLVRDO :3/12 INS JMPRS |  | EAGLE ROCK-FULTON-SILVERADO | :003/012 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-01-16 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.762949 | 38.6953 | ETL.4392 | 41129315 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381864 | Q2 | T2 EI PHILO JCT-ELK 015/001 RPR GYWW | 44610684 | PHILO JCT-ELK | 015/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.38057 | 39.0355 | ETL.7780 | 44784137 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381947 | Q3 | T2 EI BRIDGEVILLE-GARBERVILL 12/12 INS J | 44300097 | BRIDGEVILLE-GARBERVILLE | 012/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.723737 | 40.333 | ETL.6220 | 40661851 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381958 | Q3 | DI BRDGVL-GRBRVL 23/6 RMV BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 023/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-08-28 | 2021-08-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.732927 | 40.2115 | ETL.6220 | 40826263 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381960 | Q3 | EI T2NT BRIDGEVILLE-GRBRVILL 12/12 INS A | 44300097 | BRIDGEVILLE-GARBERVILLE | 012/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-16 | 2022-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.723737 | 40.333 | ETL.6220 | 40661851 | Animal Guard-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119381965 | Q3 | T2 EI BRIDGEVILLE-GARBERVLL 12/12 RPR GY | 44300097 | BRIDGEVILLE-GARBERVILLE | 012/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.723737 | 40.333 | ETL.6220 | 40661851 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119382132 | Q3 | DI BRDGVL-GRBRVL 23/6 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 023/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.732927 | 40.2115 | ETL.6220 | 40826263 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119382142 | Q3 | T2 EI BRDVLE-GRBRVLE 12/11 RPL POLE | 31511711 | BRIDGEVILLE-GARBERVILLE | 012/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.723904 | 40.334 | ETL.6220 | 40586732 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119382263 | Not Scheduled | EI SPAULDING-SUMMIT 6/238 RPL POLE | 31516090 | SPAULDING-SUMMIT | 006/238 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.533313 | 39.3076 | ETL.8060 | 40771505 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119382274 | Not Scheduled | EI SPAULDING-SUMMIT 6/239 RMV PL BUTT | 44421024 | SPAULDING-SUMMIT | 006/239 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2022-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.532763 | 39.3075 | ETL.8060 | 40751915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119382309 | Q3 | DI BRDGVL-GRBRVL 23/1 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 023/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.739166 | 40.2127 | ETL.6220 | 40600486 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119382368 | Q2 | T2 EI LAKEVILLE #2 A5/108 RPR GYWW |  | LAKEVILLE #2 | A005/108 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.600807 | 38.1898 | ETL.7340 | 43219788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119382459 | Q3 | DI BRDGVL-GRBRVL 23/5 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 023/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.734448 | 40.2119 | ETL.6220 | 40752670 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119385916 | Q2 | T3 EI MORAGA-SAN LEANDRO #2 3/24 RPR INS | 44621676 | MORAGA-SAN LEANDRO #2 | 003/024 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-01-16 |  |  | 2021-05-27 | 2021-05-26 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1349905 | 37.8089 | ETL.2780 | 40792385 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119393221 | Q2 | T2 DI HAT CRK #1-WSTWD 35/690 RPR STRW |  | HAT CREEK #1-WESTWOOD | 035/690 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.073997 | 40.569 | ETL.7030 | 40867619 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119400653 | Not Scheduled | T3 EI MIDDLE FORK #1 2/42 RPR STRW | 44394961 | MIDDLE FORK #1 | 002/042 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-01-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.62304 | 39.0014 | ETL.8405 | 40810137 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119420930 | Q2 | EI ELK-GUALALA 049/003 RPL DAMW | 44610591 | ELK-GUALALA | 049/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.680151 | 38.9657 | ETL.8410 | 40667866 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119449083 | Not Scheduled | T2 EI CARIBOU-PALERMO 27/221 INST HRDT |  | CARIBOU-PALERMO | :027/221 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119458281 | Q3 | T2 DI CARIBOU-PLUMAS JCT 1/13 RPL INSW | 31511091 | CARIBOU-PLUMAS JCT | 001/013 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.119074 | 40.0721 | ETL.6290 | 40686100 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119458333 | Not Scheduled | T2 COTTONWOOD #1 :11/74 RPR BENT STL |  | COTTONWOOD #1 | 011/074 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267221 | 40.2309 | ETL.6620 | 40906010 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119460630 | Not Scheduled | EI SPAULDING-SUMMIT 7/252 RMV PL BUTT | 44421024 | SPAULDING-SUMMIT | 007/252 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2022-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525392 | 39.3067 | ETL.8060 | 44349511 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119461361 | Not Scheduled | EI STANISLAUS-NEWARK #1 95/626 RPR JUMS | 44621440 | STANISLAUS-NEWARK #1 (12KV) | 095/626 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 | [9 empty] | Central | WSIP | [6 empty] | '-121.90368 | 37.5623 | ETL.3850 | 40828821 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461362 | Q2 | EI STANISLAUS-NEWARK #1 93/618 BENT MEMB |  | STANISLAUS-NEWARK #1 (12KV) | 093/618 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.883363 | 37.5741 | ETL.3850 | 40878651 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461363 | Not Scheduled | EI STANISLAUS-NEWARK #1 093/619 INS RPTS |  | STANISLAUS-NEWARK #1 (12KV) | 093/619 | 93R | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2021-07-16 | [9 empty] | Central | WSIP | [6 empty] | '-121.88565 | 37.5729 | ETL.3850 | 40877299 | Raptor Guard-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 530 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461489 | Not Scheduled | EI LOS BANOS-MIDWAY #2 008/039 RPLC INSS | 31527042 | LOS BANOS-MIDWAY #2 | 008/039 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.9410407 | 36.942 | ETL.6010 | 40894135 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 30 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119461496 | Q2 | T2NT DI HT CRK #1-WESTW 23/445 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 023/445 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.233885 | 40.7074 | ETL.7030 | 40770862 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461498 | Feb | DI LAYTONVILLE-COVELO 13/11 RPL STRW | 31509539 | LAYTONVILLE-COVELO | 013/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.263023 | 39.7632 | ETL.7390 | 40584788 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461517 | Feb | T2 DRM-RIO OSO #1 30/222 INST JMPR INSUL | 44448949 | DRUM-RIO OSO #1 | 030/222 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.255502 | 39.0415 | ETL.1420 | 40647520 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461561 | Q3 | T2 EI CARIBOU-PLUMAS JCT 13/013 RPL PL | 31511242 | CARIBOU-PLUMAS JCT | 013/013 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.965032 | 39.9613 | ETL.6290 | 40666925 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461562 | Q3 | T2 EI CARIBOU-PLUMAS JCT 14/0 RPR HRDRW | 44408852 | CARIBOU-PLUMAS JCT | 014/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.960995 | 39.9599 | ETL.6290 | 40614956 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461631 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 43/842 RPR S |  | HAT CREEK #1-WESTWOOD | 043/842 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023158 | 40.4659 | ETL.7030 | 40770867 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461633 | Q2 | T2 EI HAT CREEK #1-WSTWD 43/838 RPR WDPK | 44406426 | HAT CREEK #1-WESTWOOD | 043/838 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023195 | 40.4689 | ETL.7030 | 40589874 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461643 | Q2 | EI T2NT HAT CREK #1-WSTWD 43/838 RMV DEB | 44406426 | HAT CREEK #1-WESTWOOD | 043/838 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-16 | 2022-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023195 | 40.4689 | ETL.7030 | 40589874 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461721 | Q2 | T2NT DI HT CRK #1-WSTWD 22/436 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 022/436 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.239995 | 40.713 | ETL.7030 | 40770741 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461733 | Q2 | EI T2NT HAT CRK #1-WSTWD 13/252 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 013/252 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.366153 | 40.8159 | ETL.7030 | 40770721 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461735 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 13/254 REFRA | 31510955 | HAT CREEK #1-WESTWOOD | 013/254 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.364833 | 40.8147 | ETL.7030 | 40877470 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461747 | Not Scheduled | EI SPAULDING-SUMMIT 7/253 INST MRKW | 44421024 | SPAULDING-SUMMIT | 007/253 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2022-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525025 | 39.3067 | ETL.8060 | 44349512 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119461780 | Q2 | T2 EI TRINITY-MAPLE CREEK 15/005 RPR GYW | 44401954 | TRINITY-MAPLE CREEK | 015/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.183181 | 40.7437 | ETL.8170 | 40752256 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461990 | Q2 | T2NT DI HAT CRK#1-WSTWD 27/529 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 027/529 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.18311 | 40.6579 | ETL.7030 | 40600238 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119461994 | Q2 | T2NT DI HAT CRK#1-WSTWD 27/535 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 027/535 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.17898 | 40.6548 | ETL.7030 | 40827594 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462145 | Q2 | T2 EI TRINITY-MAPLE CREEK 021/000 RPL IN | 31511867 | TRINITY-MAPLE CREEK | 021/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2790257 | 40.7159 | ETL.8170 | 44771075 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462167 | Q2 | EI T2NT TRINITY-MAPLE CRK 21/000 RMV DEB | 44401994 | TRINITY-MAPLE CREEK | 021/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2790257 | 40.7159 | ETL.8170 | 44771077 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462195 | Q2 | T2 DI HAT CREEK #1-WESTW 43/838 RPR GYWW | 44388736 | HAT CREEK #1-WESTWOOD | 043/838 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023195 | 40.4689 | ETL.7030 | 40589874 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462210 | Mar | T2 EI KONOCTI-MIDDLETOWN 20/8 REPL POLE | 31509670 | KONOCTI-MIDDLETOWN | 020/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-03-03 | 2021-03-03 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.594168 | 38.8639 | ETL.6380 | 44262517 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462211 | Q2 | T2 EI KONOCTI-MIDDLETOWN 19/010 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 019/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.585146 | 38.8502 | ETL.6380 | 40615068 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462213 | Not Scheduled | T2 EI SPAULDING-SUMMIT 11/395 INST MRKW | 44449037 | SPAULDING-SUMMIT | 011/395 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2022-07-16 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.449411 | 39.3176 | ETL.8060 | 44156125 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462215 | Q3 | T2 EI CARIBOU-PLUMAS JCT 6/015 RPL HRDW | 44408852 | CARIBOU-PLUMAS JCT | 006/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.062372 | 40.0193 | ETL.6290 | 40758608 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119462216 | Not Scheduled | T2 EI CARIBOU-PLUMAS JCT 6/009 RPR FOUND |  | CARIBOU-PLUMAS JCT | 006/009 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.063375 | 40.0223 | ETL.6290 | 40875441 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464055 | Q2 | EI T2NT HAT CRK #1-WSTWD 13/251 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 013/251 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.366893 | 40.8165 | ETL.7030 | 40701217 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464079 | Q3 | T2 DI CARIBOU-PLUMAS JCT 2/11 RPLC INSW | 31511091 | CARIBOU-PLUMAS JCT | 002/011 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.111311 | 40.0616 | ETL.6290 | 40627352 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464141 | Feb | DI LYTNVL-COVELO 7/9 INST GMKW |  | LAYTONVILLE-COVELO | 007/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.346587 | 39.7144 | ETL.7390 | 40875254 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464142 | Feb | DI LYTNVL-COVELO 7/9 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 007/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-14 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.346587 | 39.7144 | ETL.7390 | 40875254 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464144 | Feb | DI LYTNVL-COVELO 7/9 RPLC INSW | 31510994 | LAYTONVILLE-COVELO | 007/009 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-14 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.347158 | 39.714 | ETL.7390 | 40899700 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-26 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464145 | Feb | DI LYTNVL-COVELO 7/9 INST HV |  | LAYTONVILLE-COVELO | 007/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.346587 | 39.7144 | ETL.7390 | 40875254 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464146 | Q2 | DI HAT CRK #1-WSTWD 52/1011 RPLC INSW | 31509689 | HAT CREEK #1-WESTWOOD | 052/1011 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.008786 | 40.3408 | ETL.7030 | 40841665 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464352 | Q2 | T2NT DI HT CRK #1-WSTWD 31/598 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 031/598 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.129988 | 40.6242 | ETL.7030 | 40656903 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464354 | Q3 | T2 DI CARIBOU-PLMS JCT 3/1 RPR SPLW | 44408852 | CARIBOU-PLUMAS JCT | 003/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.106531 | 40.058 | ETL.6290 | 40585982 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464359 | Q2 | T2 DI HAT CRK #1-WSTWD 39/755 RPR STRW |  | HAT CREEK #1-WESTWOOD | 039/755 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.038998 | 40.5282 | ETL.7030 | 40827501 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119464384 | Q3 | DI BRIDGEVILLE-GARBERVILLE 15/4 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 015/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.735612 | 40.3011 | ETL.6220 | 40752620 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119465001 | Q2 | T2 DI HAT CRK 1-WSTWD 31/613 RMV PL BUTT |  | HAT CREEK #1-WESTWOOD | 031/613 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.11826 | 40.6168 | ETL.7030 | 40877608 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119465004 | Q2 | T2NT DI HT CRK #1-WSTD 34/665 RMV DEBRIS |  | HAT CREEK #1-WESTWOOD | 034/665 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.088112 | 40.5843 | ETL.7030 | 40667967 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466398 | Q2 | T2 DI HAT CREEK #1-WESTW 43/832 RPL INSW | 31511086 | HAT CREEK #1-WESTWOOD | 043/832 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.02329 | 40.4735 | ETL.7030 | 44860093 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466610 | Q2 | T2 DI HAT CREEK #1-WESTW 38/741 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 038/741 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.044953 | 40.5375 | ETL.7030 | 40675712 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466730 | Q2 | T2 DI HAT CRK #1-WSTWD 32/624 INST IBWW |  | HAT CREEK #1-WESTWOOD | 032/624 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.111808 | 40.6099 | ETL.7030 | 40600250 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466737 | Q2 | T2NT DI HT CRK #1-WSTWD 33/643 RMV BUTT | 44388736 | HAT CREEK #1-WESTWOOD | 033/643 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.100832 | 40.598 | ETL.7030 | 40600253 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466747 | Q2 | T2 EI WEIMAR #1 000/001 RPR GYWW | 44449611 | WEIMAR #1 | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.987841 | 39.0358 | ETL.7560 | 44263355 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466778 | Not Scheduled | T3 EI FLTN-CALISTOGA -10/1 RMV CLIMB STE |  | FULTON-CALISTOGA | 010/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-01-17 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.570464 | 38.5946 | ETL.6880 | 44740428 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466792 | Feb | DI LAYTONVILLE-COVELO 7/8 INST GMRKW |  | LAYTONVILLE-COVELO | 007/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.347337 | 39.7136 | ETL.7390 | 40876447 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466794 | Feb | DI LAYTONVILLE-COVELO 7/8 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 007/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.347337 | 39.7136 | ETL.7390 | 40876447 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466795 | Feb | DI LAYTONVILLE-COVELO 7/8 RPR STRW | 44610673 | LAYTONVILLE-COVELO | 007/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.347337 | 39.7136 | ETL.7390 | 40876447 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466799 | Q2 | T2 DI HAT CREEK #1-WESTW 41/798 RPR SPLW |  | HAT CREEK #1-WESTWOOD | 041/798 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.025177 | 40.4964 | ETL.7030 | 40656672 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466860 | Feb | DI LAYTONVILLE-COVELO 8/6 RPR STRW | 44610673 | LAYTONVILLE-COVELO | 008/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.337499 | 39.7218 | ETL.7390 | 40808779 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466865 | Not Scheduled | T3 EI MIDDLE FRK #1 3/50 RPR WP HOLE | 44396748 | MIDDLE FORK #1 | 003/050 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-17 | 2021-01-17 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.63422 | 38.9977 | ETL.8405 | 40677918 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119466882 | Feb | DI LAYTONVILLE-COVELO 8/6 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 008/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.337499 | 39.7218 | ETL.7390 | 40808779 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467005 | Q2 | T2NT DI HAT CRK #1-WSTWD 28/541 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 028/541 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.17434 | 40.6519 | ETL.7030 | 40656898 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467007 | Q2 | T2NT DI HAT CRK #1-WSTWD 26/518 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 026/518 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.189327 | 40.6647 | ETL.7030 | 40600235 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467009 | Q2 | T2 DI HAT CRK #1-WSTWD 35/674 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 035/674 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.082882 | 40.5787 | ETL.7030 | 40667969 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467014 | Feb | DI LAYTONVILLE-COVELO 13/10 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 013/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.263081 | 39.7625 | ETL.7390 | 40614489 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467066 | Feb | DI LAYTONVILLE-COVELO 13/10 RPR STRW | 44610673 | LAYTONVILLE-COVELO | 013/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.263081 | 39.7625 | ETL.7390 | 40614489 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467153 | Q2 | T2 EI PHILO JCT-ELK 014/000 RPR GYWW | 44610684 | PHILO JCT-ELK | 014/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.365437 | 39.0248 | ETL.7780 | 44784134 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467163 | Not Scheduled | T2 VALLY SPRGS-MARTELL #1 8/15 RPLC STRW | 31508941 | VALLEY SPRINGS-MARTELL #1 | 008/015 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.769666 | 38.3152 | ETL.8240 | 40753640 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467406 | Not Scheduled | T2 EI SPAULDING-SUMMIT 18/588 RPL POLE | 31510882 | SPAULDING-SUMMIT | 018/588 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-17 | 2021-07-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.340105 | 39.3097 | ETL.8060 | 40577368 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467460 | Not Scheduled | FULTON-PUEBLO :6/12 RPL STRW | 31511864 | FULTON-PUEBLO | :006/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.365707 | 38.4608 | ETL.1600 | 40657781 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467552 | Q2 | T2 DI HT CRK #1 WSTWD 43/842 RPR HRDD |  | HAT CREEK #1-WESTWOOD | 043/842 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023158 | 40.4659 | ETL.7030 | 40770867 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467594 | Q2 | T2 DI HT CRK #1 WSTWD 43/842 TIE WIRE |  | HAT CREEK #1-WESTWOOD | 043/842 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023158 | 40.4659 | ETL.7030 | 40802444 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467617 | Q2 | EI STANISLAUS-NEWARK #1 93/617 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 093/617 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.881005 | 37.5754 | ETL.3850 | 40826971 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467663 | Not Scheduled | T2 EI SPAULDING-SUMMIT 018/586 RPR STRW | 44449606 | SPAULDING-SUMMIT | 018/586 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-17 | 2021-07-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.340594 | 39.3096 | ETL.8060 | 40577367 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467664 | Q3 | T2 DI CARIBOU-PLUMAS JCT 6/2 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 006/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.066628 | 40.0285 | ETL.6290 | 40698792 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467677 | Q3 | T2 DI CARIBOU-PLUMAS JCT 3/13 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 003/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.095261 | 40.0509 | ETL.6290 | 40666895 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467862 | Q2 | EI T2NT LAURELES-OTTER 2/11 RMV BUTT | 44587870 | LAURELES-OTTER | 002/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-17 | 2022-07-17 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71587 | 36.4514 | ETL.7380 | 40591168 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467865 | Q2 | EI T2NT LAURELES-OTTER 002/013 RMV BUTT | 44587870 | LAURELES-OTTER | 002/013 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-17 | 2022-07-17 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.715985 | 36.4499 | ETL.7380 | 40666351 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119467897 | Not Scheduled | EI SPAULDING-SUMMIT 007/258 RPR STRW | 31509215 | SPAULDING-SUMMIT | 007/258 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523467 | 39.3073 | ETL.8060 | 40828136 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119467916 | Not Scheduled | EI SPAULDING-SUMMIT 007/260 RPLC STRW | 31510882 | SPAULDING-SUMMIT | 007/260 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.522823 | 39.3078 | ETL.8060 | 40878062 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119467958 | Q3 | T2 EI CARIBOU-PLUMAS JCT 6/4 RPR JUMPER | 44408852 | CARIBOU-PLUMAS JCT | 006/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.066182 | 40.0272 | ETL.6290 | 40769600 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468020 | Not Scheduled | EI SPAULDING-SUMMIT 7/262 INST MRKW | 44421024 | SPAULDING-SUMMIT | 007/262 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2022-07-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.522013 | 39.3084 | ETL.8060 | 44349513 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119468022 | Not Scheduled | T2 EI SPAULDING-SUMMIT 18/584 RPR STRW | 44449606 | SPAULDING-SUMMIT | 018/584 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-17 | 2021-07-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.341282 | 39.3094 | ETL.8060 | 40586102 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468260 | Not Scheduled | T3 EI FULTON-CALISTOGA 0/003 RPL STRW | 31509532 | FULTON-CALISTOGA | 000/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-01-17 |  |  |  | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.441283 | 38.5094 | ETL.6880 | 40667686 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468374 | Q2 | T2 DI HT CRK #1 WSTWD 54/1063 RPLC STRW | 31511043 | HAT CREEK #1-WESTWOOD | 054/1063 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.000487 | 40.3074 | ETL.7030 | 42625079 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468399 | Q3 | EI STANISLAUS-NEWARK #1 92/611 RMV VEG |  | STANISLAUS-NEWARK #1 (12KV) | 092/611 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-17 | 2021-07-17 |  |  | 2021-08-15 | 2021-08-01 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-121.872223 | 37.5855 | ETL.3850 | 40602897 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468463 | Q2 | T2 DI HTCRK#1 WSTWD 31/601 RMV PL BUTT |  | HAT CREEK #1-WESTWOOD | 031/601 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127653 | 40.6227 | ETL.7030 | 40827493 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468521 | Mar | EI T3NT MRG-SAN LNDR #1 5/39 RPR MASTIC |  | MORAGA-SAN LEANDRO #1 | 005/039 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2022-07-17 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.125017 | 37.7796 | ETL.2770 | 41147698 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468561 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 7/91 RPR STRT |  | DIVIDE-CABRILLO #2 | 007/091 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436286 | 34.7172 | ETL.1370 | 40866910 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468563 | Q2 | DI HAT CREEK #1-WESTW 51/984 REPL POLE | 31511043 | HAT CREEK #1-WESTWOOD | 051/984 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.012178 | 40.3604 | ETL.7030 | 40599866 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468565 | Q3 | T2 DI CARIBOU-PLUMAS JCT 2/5 RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | 002/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.115522 | 40.066 | ETL.6290 | 40751782 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468569 | Q3 | T2 DI CARIBOU-PLUMAS JCT 4/0 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.093367 | 40.0497 | ETL.6290 | 40589802 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119468860 | Q2 | T2NT DI HAT CRK#1-WSTWD 41/792 RMV PL BT |  | HAT CREEK #1-WESTWOOD | 041/792 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.026985 | 40.5007 | ETL.7030 | 40809585 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469007 | Q2 | T2 DI HAT CRK#1-WSTWD 53/1038 REFRAME | 31511712 | HAT CREEK #1-WESTWOOD | 053/1038 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.001793 | 40.3208 | ETL.7030 | 40751794 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469015 | Q2 | EI GATES-PANOCHE #1 6/032 RPR STRT | 44490730 | GATES-PANOCHE #1 | 006/032 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-17 | 2021-07-17 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.18769 | 36.2195 | ETL.4720 | 40663926 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119469044 | Not Scheduled | T3 EI FULTON-CALISTOGA 0/009 INST HRDD |  | FULTON-CALISTOGA | 000/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-01-17 |  |  |  | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.445538 | 38.5144 | ETL.6880 | 40861400 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469061 | Mar | T2 ELK-GUALALA 51/9 RPL GUY POLE | 31509676 | ELK-GUALALA | 051/009 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 |  |  | 2021-03-29 | 2021-03-29 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.674672 | 38.929 | ETL.8410 | 44946529 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469063 | Q2 | T2 EI ELK-GUALALA 51/001 RPL ANCHOR | 31521863 | ELK-GUALALA | 051/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.676653 | 38.9396 | ETL.8410 | 40595309 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469227 | Not Scheduled | T2NT DI UKH-HPLN-CLVR 10/92 CANCEL | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 010/092 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2022-07-16 | [6 empty] | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-123.125452 | 39.0458 | ETL.4050 | 40755571 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469241 | Q2 | T2 DI HT CRK #1 WSTWD 53/1033 REFRAME | 31511712 | HAT CREEK #1-WESTWOOD | 053/1033 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.003238 | 40.3246 | ETL.7030 | 40867635 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469256 | Feb | DI LYTNVLLE-CVLO 13/3 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.267813 | 39.7564 | ETL.7390 | 40666670 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469337 | Q2 | T2NT DI HT CRK #1-WSTWD 26/509 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 026/509 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.194428 | 40.6704 | ETL.7030 | 40601697 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469353 | Feb | DI LYTNVLLE-CVLO 8/5 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 008/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.338228 | 39.7213 | ETL.7390 | 40768645 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469398 | Not Scheduled | T3 EI MNT RIO-FRT ROSS 21/4 RPR WP HOLE |  | ETL.6979.POLE.WOOD | 021/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-17 | 2021-01-17 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.120014 | 38.477 | ETL.6979 | 40770583 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469402 | Feb | NT DI LYTNVLLE-CVLO 8/5 INST GMKW |  | LAYTONVILLE-COVELO | 008/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.338228 | 39.7213 | ETL.7390 | 40768645 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469443 | Q3 | T2 DI CARIBOU-PLUMAS JCT 4/2 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.09144 | 40.0486 | ETL.6290 | 40675189 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469446 | Feb | DI LAYTONVILLE-COVELO 13/5 RPL POLE | 31509539 | LAYTONVILLE-COVELO | 013/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-24 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.266387 | 39.7578 | ETL.7390 | 40768647 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469448 | Feb | DI LAYTONVILLE-COVELO 8/4 RPL STRW | 31527835 | LAYTONVILLE-COVELO | 008/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.339466 | 39.7204 | ETL.7390 | 40750456 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-26 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469453 | Not Scheduled | EI T3NT CASTRO VALLEY-NEWARK 5/29 RMV VE |  | CASTRO VALLEY-NEWARK | 005/029 | CHS | F | 2020_(3) On high spread structure |  | 2020-07-17 | 2022-07-17 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.001242 | 37.6485 | ETL.4450 | 40587524 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469478 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 4/64 RPL INSUL | 31515253 | DIVIDE-CABRILLO #2 | 004/064 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.437459 | 34.7605 | ETL.1370 | 40641777 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469496 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 4/64 RPL STRW | 31511648 | DIVIDE-CABRILLO #2 | 004/064 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.43746 | 34.7605 | ETL.1370 | 40618683 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469582 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 8/95 RPR STRW |  | DIVIDE-CABRILLO #2 | 008/095 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436277 | 34.7132 | ETL.1370 | 40598169 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469621 | Not Scheduled | EI SPAULDING-SUMMIT 06/223 INST GMKW | 44449037 | SPAULDING-SUMMIT | 006/223 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-17 | 2022-07-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.542759 | 39.3076 | ETL.8060 | 40751853 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119469622 | Not Scheduled | EI SPAULDING-SUMMIT 6/223 INST MRKW | 44449037 | SPAULDING-SUMMIT | 006/223 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-17 | 2022-07-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.542759 | 39.3076 | ETL.8060 | 40751853 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119469726 | Q3 | T2 EI CARIBOU-PLUMAS JCT 5/4 RPR WDPKR | 44408852 | CARIBOU-PLUMAS JCT | 005/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-17 | 2021-07-17 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.073704 | 40.0382 | ETL.6290 | 40769627 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469727 | Q3 | T2 EI CARIBOU-PLUMAS JCT 5/7 REFRAME | 31511690 | CARIBOU-PLUMAS JCT | 005/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-17 | 2021-07-17 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.070667 | 40.0365 | ETL.6290 | 40824673 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469799 | Feb | DI LAYTONVILLE-COVELO 2/3 RPLC POLE | 31509539 | LAYTONVILLE-COVELO | 002/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.43768 | 39.6947 | ETL.7390 | 40648606 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469815 | Q2 | T2 DI HAT CRK#1-WSTWD 33/648 RPR WPKR |  | HAT CREEK #1-WESTWOOD | 033/648 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.09794 | 40.5949 | ETL.7030 | 40769976 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469922 | Q3 | T2 DI CARB-WESTWOOD 1/24 RMV IDLE HRDW |  | CARIBOU-WESTWOOD | 001/024 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.136437 | 40.0953 | ETL.6300 | 40675249 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469935 | Q2 | DI HAT CRK #1-WSTWD 49/951 RPR STRW |  | HAT CREEK #1-WESTWOOD | 049/951 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.01634 | 40.3847 | ETL.7030 | 40825620 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469939 | Q2 | T2 DI HAT CRK #1-WSTWD 27/527 RPLC STRW | 31511043 | HAT CREEK #1-WESTWOOD | 027/527 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.184198 | 40.6591 | ETL.7030 | 40877489 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119469975 | Q2 | T2 EI HAT CREEK #1-WESTWD 43/836 RPL ANC | 31511712 | HAT CREEK #1-WESTWOOD | 043/836 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-17 | 2021-07-17 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.023208 | 40.4704 | ETL.7030 | 44859226 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119470081 | Q2 | T2NT DI HTCRK#1 WSD 26/500 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 026/500 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-15 | 2022-07-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.198738 | 40.6751 | ETL.7030 | 40676346 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119470121 | Not Scheduled | T2 EI CARIBOU-PALERMO :13/108 RPR CNDS |  | CARIBOU-PALERMO | :013/108 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40858895 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119470132 | Q4 | EI MAPLE CREEK-HOOPA 027/012 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 027/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-17 | 2021-07-17 |  |  | 2021-10-02 | 2021-07-26 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.672565 | 41.0445 | ETL.7490 | 40701856 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119470148 | Q2 | DI HAT CRK #1-WSTWD 52/1014 RPR SPLW | 44388736 | HAT CREEK #1-WESTWOOD | 052/1014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-14 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.008407 | 40.3385 | ETL.7030 | 40589883 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119470202 | Q3 | T2 DI CAR PLU JCT 3/8 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 003/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.100035 | 40.0536 | ETL.6290 | 40868071 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119470217 | Q3 | T2 DI CARIBOU-PLUMAS JCT 4/13 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.07861 | 40.0411 | ETL.6290 | 40656457 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471070 | Q2 | T2 DI HATCREEK #1-WESTW 53/1039 REPL POL | 31511712 | HAT CREEK #1-WESTWOOD | 053/1039 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.001493 | 40.32 | ETL.7030 | 40770001 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471076 | Q3 | T2 DI CARIBOU-PLUMA JCT 5/8 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 005/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.06995 | 40.036 | ETL.6290 | 40876656 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471218 | Q3 | T2 DI CARIBOU-PLMS JCT 3/14 RPLC HRDW | 44408852 | CARIBOU-PLUMAS JCT | 003/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.093992 | 40.0502 | ETL.6290 | 40751761 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471389 | Q3 | T2 EI BRIDGEVILLE-GARBERVLLE 11/14 RPR S | 44299806 | BRIDGEVILLE-GARBERVILLE | 011/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.721642 | 40.3432 | ETL.6220 | 40769364 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471416 | Q3 | T2 EI BRIDGEVILLE-GRBRVILE 12/0 RMV PL B | 44299809 | BRIDGEVILLE-GARBERVILLE | 012/000 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.72205 | 40.3427 | ETL.6220 | 40591078 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471439 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 12/4 REFRA | 31511889 | BRIDGEVILLE-GARBERVILLE | 012/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.724238 | 40.34 | ETL.6220 | 40769362 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471468 | Q3 | T2 EI BRIDGEVILLE-GARBERVILE 12/6 RPL IN | 31509854 | BRIDGEVILLE-GARBERVILLE | 012/006 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.7245699 | 40.3386 | ETL.6220 | 40854992 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471498 | Q3 | T2 EI BRIDGEVILLE-GARBERVLLE 11/10 REGRA | 44453320 | BRIDGEVILLE-GARBERVILLE | 011/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.718999 | 40.3464 | ETL.6220 | 44414891 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471514 | Q3 | T2 EI BRIDGEVILLE-GARBERVLLE 11/11 RPR J | 44300097 | BRIDGEVILLE-GARBERVILLE | 011/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.719705 | 40.3455 | ETL.6220 | 40600498 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119471563 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 1/4 RPR GY | 44300097 | BRIDGEVILLE-GARBERVILLE | 001/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-18 | 2021-07-18 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.801607 | 40.4692 | ETL.6220 | 44799538 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119472647 | Q2 | DI TRINITY-MAPLE CREEK 000/002 RPR INSW | 44401954 | TRINITY-MAPLE CREEK | 000/002 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8170 | 40915890 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119472976 | Q3 | DI BRIDGEVILLE-GRBRVL 15/1 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 015/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.735407 | 40.3039 | ETL.6220 | 40586738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473255 | Not Scheduled | T2 DI CARIBOU-PALERMO :008/068 RPR CONS |  | CARIBOU-PALERMO | :008/068 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.247789 | 40.0076 | ETL.3190 | 40910310 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473268 | Not Scheduled | T2 DI DRUM-SUMMIT #2 10/122A RPR STRW | 44449514 | DRUM-SUMMIT #2 | 010/122A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.60952 | 39.3247 | ETL.1450 | 40810272 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473295 | Q2 | DI HAT CRK #1-WESTWD 26/505 RMV PL BUT |  | HAT CREEK #1-WESTWOOD | 026/505 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.196537 | 40.6726 | ETL.7030 | 40816141 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473554 | Not Scheduled | T2 DI DRUM-SUMMIT #2 9/110R RPL POLE | 31498154 | DRUM-SUMMIT #2 | 009/110 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624533 | 39.321 | ETL.1450 | 44553511 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473582 | Not Scheduled | EI T3NT MORAGA-SAN LEANDRO #1 6/44 PAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 006/044 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-20 | 2022-07-20 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.117688 | 37.7663 | ETL.2770 | 40745881 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473691 | Not Scheduled | T2 DI DRUM-SUMMIT #2 9/111 RPR STRW | 44449514 | DRUM-SUMMIT #2 | 009/111 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44212071 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473694 | Not Scheduled | T2 DI DRUM-SUMMIT #2 10/122B RPR STRW | 44449514 | DRUM-SUMMIT #2 | 010/122B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.609499 | 39.3247 | ETL.1450 | 42572871 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473855 | Mar | EI T3NT MORAGA-SAN LEANDRO #1 6/44 RPR F |  | MORAGA-SAN LEANDRO #1 | 006/046 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2022-07-20 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.116036 | 37.7634 | ETL.2770 | 40822219 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473857 | Not Scheduled | T3 EI FULTON-CALISTOGA ;7/4 RPR HRDWS |  | FULTON-CALISTOGA | ;007/004 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  |  | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.612938 | 38.4971 | ETL.6880 | 40760762 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119473897 | Not Scheduled | T2 DI CARIBOU-PALERMO :0/8 RMV STEP |  | CARIBOU-PALERMO | :000/008 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2022-07-20 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119474006 | Q2 | EI GATES-PANOCHE #1 6/033 RPR BENT STL | 44490730 | GATES-PANOCHE #1 | 006/033 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.189738 | 36.2221 | ETL.4720 | 40651597 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119474206 | Not Scheduled | T2 DRUM-SUMMIT #2 10/125L REPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/125 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.605855 | 39.3261 | ETL.1450 | 44766899 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119474336 | Mar | EI T3NT MORAGA-SAN LEANDRO #1 6/48 RPR F |  | MORAGA-SAN LEANDRO #1 | 006/048 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2022-07-20 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.113983 | 37.7596 | ETL.2770 | 40861175 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119474496 | Q2 | EI GATES-PANOCHE #1 08/039 RPR STRT | 44490730 | GATES-PANOCHE #1 | 008/039 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.201933 | 36.2378 | ETL.4720 | 40863286 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119474783 | Not Scheduled | T3 EI MIDDLE FORK #1 3/49 REGRADE | 44396748 | MIDDLE FORK #1 | 003/049 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.633097 | 38.9982 | ETL.8405 | 44809328 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119474804 | Q2 | T3 EI MORAGA-SAN LEANDRO #1 7/51 REPLUMB | 44621675 | MORAGA-SAN LEANDRO #1 | 007/051 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-01-20 |  |  | 2021-05-25 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.114009 | 37.7534 | ETL.2770 | 40604499 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119474820 | Not Scheduled | T2 DRUM-SUMMIT #2 10/125R REPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/125 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-16 | 2021-07-16 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.605855 | 39.3261 | ETL.1450 | 44766900 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119475061 | Q3 | T2 DI CARIBOU #2 20/519 RPl SPLW |  | CARIBOU #2 | 020/519 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.026142 | 40.0256 | ETL.6280 | 44259799 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119475209 | Q3 | T2 DI BRIDGEVL-CTTNWD 79/562A RPR SHLS | 44398374 | BRIDGEVILLE-COTTONWOOD | 079/562A | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.658851 | 40.4779 | ETL.1110 | 40676751 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119475257 | Not Scheduled | T3 EI FULTON-CALISTOGA 1/0 RPL STRW | 31509532 | FULTON-CALISTOGA | 001/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-01-20 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.451017 | 38.5175 | ETL.6880 | 40588899 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119475277 | Q2 | DI GATES-PANOCHE #1 024/114 RPR FOND | 44571495 | GATES-PANOCHE #1 | 024/114 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.373667 | 36.4229 | ETL.4720 | 40762377 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119475742 | Q2 | EI GATES-PANOCHE #1 34/162 RPR STRT | 44490730 | GATES-PANOCHE #1 | 034/162 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.486328 | 36.5395 | ETL.4720 | 40663972 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119475812 | Q2 | T2 DI BRDGEVLLE-CTTNWD 42/333 RPL INSS | 31512268 | BRIDGEVILLE-COTTONWOOD | 042/333 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.046557 | 40.3891 | ETL.1110 | 40636286 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119475927 | Not Scheduled | T3 EI MIDDLE FORK #1 4/068 REFRAME | 31509675 | MIDDLE FORK #1 | 004/068 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.655896 | 38.9988 | ETL.8405 | 40822821 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476380 | Q3 | T2 DI CARIBOU #2 019/498 RPR SPLW |  | CARIBOU #2 | 019/498 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.034385 | 40.0179 | ETL.6280 | 44259018 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476403 | Q2 | DI HAT CREEK #1-WESTWOOD 46/885 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 046/885 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.023015 | 40.4331 | ETL.7030 | 40591891 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476423 | Not Scheduled | T3 EI MDDL FRK #1 4/072 RPR WP HOLES | 44396748 | MIDDLE FORK #1 | 004/072 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.659845 | 38.9994 | ETL.8405 | 40598771 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476480 | Mar | T3 EI DRUM-GRASS VALLEY-WMR 6/165 RPL PO | 31508223 | DRUM-GRASS VALLEY-WEIMAR | 006/165 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-21 | 2021-03-15 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.838304 | 39.2003 | ETL.6760 | 40865387 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476536 | Not Scheduled | T2 EI FULTON-CALISTOGA 0/005 REPL POLE | 31510985 | FULTON-CALISTOGA | 000/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  |  | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.440079 | 38.5109 | ETL.6880 | 40751148 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476548 | Q2 | T2 DI BRIDGEVL-CTTNWD 41/330 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 041/330 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.043598 | 40.3871 | ETL.1110 | 44862901 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476588 | Q2 | T2 EI BRIDGVLE-CTNWD 58/426 RPR JUMPR | 44398374 | BRIDGEVILLE-COTTONWOOD | 058/426 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.338827 | 40.3783 | ETL.1110 | 40657063 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476591 | Mar | EI COALINGA #1-SAN MIGUEL 007/000 INS GM | 44507639 | COALINGA #1-SAN MIGUEL | 007/000 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-20 | 2022-07-20 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.45593 | 36.0959 | ETL.8580 | 40609728 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476723 | Not Scheduled | T2 EI ELK-GUALALA 053/002 RPR COND | 44610591 | ELK-GUALALA | 053/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.679627 | 38.912 | ETL.8410 | 44190781 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476804 | Q3 | DI BRIDGEVILLE-GARBERVILLE 22/9 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 022/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402629 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476805 | Q3 | DI BRIDGEVILLE-GARBERVILLE 22/9 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 022/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476807 | Q3 | DI BRIDGEVILLE-GARBERVILLE 22/9 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 022/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-15 | 2021-07-15 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402631 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119476821 | Q2 | T3 EI FULTON-CALISTOGA 85 RPL ANCS | 44306735 | FULTON-CALISTOGA | 008/005 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-04-16 | 2021-04-12 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.54381 | 38.5882 | ETL.6880 | 40751159 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense |  | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119477063 | Q3 | T3 DONNELLS-MI-WUK 4/009 REPL INSS | 31511367 | DONNELLS-CURTIS | 004/009 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.052881 | 38.1826 | ETL.1400 | 44847691 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119477070 | Q3 | T2 EI BRIDGEVILLE-GARBERVILE 0/3 RPR JUM | 44300097 | BRIDGEVILLE-GARBERVILLE | 000/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.7835167 | 40.478 | ETL.6220 | 40679115 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119477135 | Q3 | T2 EI BRIDGEVILLE-GARBERVILE 0/2 RPR JUM | 44300097 | BRIDGEVILLE-GARBERVILLE | 000/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.7810647 | 40.4788 | ETL.6220 | 40713440 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119477227 | Not Scheduled | DI DRUM-SUMMIT #1 6/80R RPR GYWW | 44396376 | DRUM-SUMMIT #1 | 006/080 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.673553 | 39.3071 | ETL.1440 | 44765210 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119477228 | Not Scheduled | DI DRUM-SUMMIT #1 6/80L RPR GYWW | 44396376 | DRUM-SUMMIT #1 | 006/080 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.673553 | 39.3071 | ETL.1440 | 44765209 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119477317 | Not Scheduled | T2 EI DIVIDE-CABRILLO 06/75 RPR GYWW |  | DIVIDE-CABRILLO #2 | 006/075 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4333364 | 34.743 | ETL.1370 | 44283607 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119477691 | Not Scheduled | T3 EI MONTE RIO-FULTON 11/4 RPL STRW | 31509533 | MONTE RIO-FULTON | 011/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.965706 | 38.4836 | ETL.7630 | 40770570 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119477903 | Q2 | NT DI BRDGVLL-CTTNWD 41/332R INST MRKS | 44477511 | BRIDGEVILLE-COTTONWOOD | 041/332 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-20 | 2022-07-20 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-123.044968 | 40.388 | ETL.1110 | 44862874 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478085 | Mar | T3 EI DRUM-RIO OSO #2 1/11 RPL INSS | 31528394 | DRUM-RIO OSO #2 | 001/011 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.7877268 | 39.2564 | ETL.1430 | 40605312 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478087 | Mar | T3 EI DRUM-RIO OSO #2 1/13 RMV STEP | 44396373 | DRUM-RIO OSO #2 | 001/013 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791034 | 39.2563 | ETL.1430 | 40655126 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478092 | Mar | T3 EI DRUM-RIO OSO #2 0/9 RPL INSS | 31528394 | DRUM-RIO OSO #2 | 000/009 | 93K | E | 2020_(1a) PSPS |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.7849864 | 39.2565 | ETL.1430 | 40889172 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119478097 | Mar | T3 EI DRUM-RIO OSO #2 1/15 RPR STRT | 44397942 | DRUM-RIO OSO #2 | 001/015 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.794213 | 39.2562 | ETL.1430 | 40765123 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478101 | Mar | T3 EI DRUM-RIO OSO #2 1/11 RPR STRT | 44396373 | DRUM-RIO OSO #2 | 001/011 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.787714 | 39.2564 | ETL.1430 | 40581348 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478111 | Mar | T3 EI DRUM-RIO OSO #2 1/14 RPR STRT | 44396373 | DRUM-RIO OSO #2 | 001/014 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.792537 | 39.2562 | ETL.1430 | 40757248 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478156 | Q3 | T2 EI CARIBOU-PLUMAS JCT 03/011 RMV DEBR | 44408852 | CARIBOU-PLUMAS JCT | 003/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-20 | 2022-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.097088 | 40.052 | ETL.6290 | 40600663 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478157 | Q3 | T2 EI CARIBOU-PLUMAS JCT 03/011 REFRAME | 31507980 | CARIBOU-PLUMAS JCT | 003/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.097088 | 40.052 | ETL.6290 | 40600663 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478158 | Q3 | T2 EI CARIBOU-PLUMAS JCT 03/008 RMV DEBR | 44408852 | CARIBOU-PLUMAS JCT | 003/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-20 | 2022-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.100035 | 40.0536 | ETL.6290 | 40868071 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478160 | Q3 | T2 EI CARIBOU-PLUMAS JCT 03/011 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 003/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.097088 | 40.052 | ETL.6290 | 40600663 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478193 | Q3 | T2 EI CARIBOU-PLUMAS JCT 3/7 REFRAME | 31507980 | CARIBOU-PLUMAS JCT | 003/007 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.101411 | 40.0544 | ETL.6290 | 40809562 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478197 | Q3 | T2 EI CARIBOU-PLUMAS JCT 3/002 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 003/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.10529 | 40.057 | ETL.6290 | 40659852 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478203 | Q3 | T2 EI CARIBOU-PLUMAS JCT 3/005 RPL ANCHO | 31507980 | CARIBOU-PLUMAS JCT | 003/005 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.103265 | 40.0555 | ETL.6290 | 40758602 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478342 | Q3 | T2 EI CARIBOU #2 1/000 INST GYMW |  | CARIBOU #2 | 001/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-20 | 2022-07-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.160663 | 40.0789 | ETL.6280 | 40614758 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478344 | Not Scheduled | T2 EI CARIBOU #2 1/0 RMV VEG |  | CARIBOU #2 | 001/000 | HNA | E | 2020_(3) On high spread structure |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.160663 | 40.0789 | ETL.6280 | 40614758 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478524 | Q3 | T2 EI BRIDGEVILLE-CTTNWD 64/466 RPL DMPR | 44398374 | BRIDGEVILLE-COTTONWOOD | 064/466 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.439682 | 40.4048 | ETL.1110 | 44812807 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478540 | Q3 | T2 EI BRIDGEVILLE-CTTNWD 66/475 RPR DMPR | 44398374 | BRIDGEVILLE-COTTONWOOD | 066/475 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.456302 | 40.4155 | ETL.1110 | 40638308 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478592 | Not Scheduled | EI LOS BANOS-GATES #1 12/52 RPL INST | 31515417 | LOS BANOS-GATES #1 | 012/052 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.907799 | 36.9024 | ETL.6000 | 40680373 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119478847 | Q2 | DI GATES-PANOCHE #1 25/117 BENT STL | 44490730 | GATES-PANOCHE #1 | 025/117 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.380016 | 36.4299 | ETL.4720 | 40817994 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119478956 | Not Scheduled | EI LOS BANOS-MIDWAY #2 102/426 RMV VEG |  | LOS BANOS-MIDWAY #2 | 102/426 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.880551 | 35.9121 | ETL.6010 | 40812185 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119478985 | Q4 | T2 DI KESWICK-TRINITY 14/176B RMV DEBRIS |  | KESWICK-TRINITY | 014/176B | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-20 | 2022-07-20 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.662839 | 40.703 | ETL.7270 | 42621513 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478987 | Q4 | T2 DI KESWICK-TRINITY 14/176B RPR HRDD |  | KESWICK-TRINITY | 014/176B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-20 | 2021-07-20 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.662839 | 40.703 | ETL.7270 | 42621513 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478993 | Not Scheduled | EI T2NT BRIDGEVILLE-CTTNWD 59/433 RMV VE |  | BRIDGEVILLE-COTTONWOOD | 059/433 | HNA | F | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2022-07-20 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.35932 | 40.3716 | ETL.1110 | 40768277 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478996 | Q3 | T2 EI BRIDGEVILLE-CTTNWD 59/433 RPL DMPR | 44398374 | BRIDGEVILLE-COTTONWOOD | 059/433 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.35932 | 40.3716 | ETL.1110 | 40799052 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119478997 | Q3 | T2 EI BRIDGEVILLE-CTTNWD 60/435 RPL DMPR | 44398374 | BRIDGEVILLE-COTTONWOOD | 060/435 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.361221 | 40.3718 | ETL.1110 | 40611005 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119479015 | Q2 | DI GATES-PANOCHE #1 25/119 RPR FOND | 44571495 | GATES-PANOCHE #1 | 025/119 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.38455 | 36.4348 | ETL.4720 | 40863298 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119479031 | Q2 | DI GATES-PANOCHE #1 25/115 RPR STRT | 44571495 | GATES-PANOCHE #1 | 025/115 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.375612 | 36.425 | ETL.4720 | 40753542 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119479032 | Q2 | DI GATES-PANOCHE #1 25/115 RPR FOND | 44571495 | GATES-PANOCHE #1 | 025/115 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.375612 | 36.425 | ETL.4720 | 40753542 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119479106 | Mar | EI T3NT DRUM-HIGGINS 9/086 INST ACG | 31509477 | DRUM-HIGGINS | 009/086 | 93A | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.891897 | 39.1662 | ETL.4393 | 40814103 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119479118 | Mar | T2 DI DRUM-SUMMIT #2 9/103 RPR BENT STL | 44449511 | DRUM-SUMMIT #2 | 009/103 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.636384 | 39.3226 | ETL.1450 | 40602591 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119479210 | Not Scheduled | T2 DI DRUM-SUMMT #2 9/103 RPR SWTCH HRDW | 44449512 | DRUM-SUMMIT #2 | 009/103 | ICE | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.636384 | 39.3226 | ETL.1450 | 40602591 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119479369 | Q2 | NT DI GATES-PANOCHE #1 24/111 RPR FOND | 44571495 | GATES-PANOCHE #1 | 024/111 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2022-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.366668 | 36.4152 | ETL.4720 | 40587477 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119479496 | Not Scheduled | T2 EI ELK-GUALALA 60/009 RMV VEG |  | ELK-GUALALA | 060/009 | HNA | E | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.579926 | 38.8501 | ETL.8410 | 40876116 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119479536 | Q2 | EI GATES-PANOCHE #1 10/052 RPR TWR | 44490730 | GATES-PANOCHE #1 | 010/052 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.228409 | 36.2719 | ETL.4720 | 40663934 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119479958 | Not Scheduled | EI LOS BANOS-MIDWAY #2 -101/424 RMV VEG |  | LOS BANOS-MIDWAY #2 | 101/424 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.885846 | 35.9177 | ETL.6010 | 40754002 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119480200 | Not Scheduled | T2 DI DRUM-SUMMIT#2 9/112 RPL POLE | 44449514 | DRUM-SUMMIT #2 | 009/112 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.622018 | 39.321 | ETL.1450 | 44553510 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480271 | Q2 | T2 EI PHILO JCT-ELK 12/7 RPR GYWW | 44610684 | PHILO JCT-ELK | 012/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.343653 | 39.0234 | ETL.7780 | 40819511 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480292 | Mar | T3NT DI DRM-GRSS VLY-WMR 6/158 RMV BUTT | 44396744 | DRUM-GRASS VALLEY-WEIMAR | 006/158 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-20 | 2022-07-20 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.834543 | 39.2036 | ETL.6760 | 40693560 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480533 | Q2 | EI GATES-PANOCHE #1 - 12/58 RPR TWR | 44490730 | GATES-PANOCHE #1 | 012/058 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.240683 | 36.2877 | ETL.4720 | 40863636 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119480549 | Mar | T3NT DI DRUM-GRS VLY-WMR 7/168 RMV BUTT | 44401097 | DRUM-GRASS VALLEY-WEIMAR | 007/168 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.840027 | 39.1987 | ETL.6760 | 40603073 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480590 | Mar | T3 DI DRM-GRSS VLLY-WMR 1/42 RPR STRW | 44401096 | DRUM-GRASS VALLEY-WEIMAR | 001/042 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.769462 | 39.2416 | ETL.6760 | 42549844 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480680 | Not Scheduled | T3 EI MIDDLE FORK #1 4/73 RPR GYWW | 44402384 | MIDDLE FORK #1 | 004/073 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.660903 | 38.9996 | ETL.8405 | 40660040 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480699 | Feb | T2 EI PHILO JCT-ELK 21/5 RPL STRW | 31511245 | PHILO JCT-ELK | 021/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 | 2021-02-09 | 2021-02-11 | 2021-02-09 | 2021-02-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.468853 | 39.0848 | ETL.7780 | 40768482 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480720 | Mar | T3NT DI DRM-GRS VLY-WMR 7/168 INST MRKW | 44401097 | DRUM-GRASS VALLEY-WEIMAR | 007/168 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.840027 | 39.1987 | ETL.6760 | 40603073 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119480829 | Q2 | T3 MORAG-SAN LNDRO #3 4/31 INST INSUL |  | MORAGA-SAN LEANDRO #3 | 004/031 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 | 2021-04-01 |  | 2021-04-02 | 2021-04-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1283115 | 37.7954 | ETL.2790 | 40623971 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481265 | Q2 | T2 TRINITY-MAPLE CREEK 48/19 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 048/019 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.777644 | 40.7548 | ETL.8170 | 40876568 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481370 | Q3 | T2 EI CARIBOU-PLUMAS JCT -4/7 INST FBR R | 44408852 | CARIBOU-PLUMAS JCT | 004/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.086873 | 40.0459 | ETL.6290 | 40809564 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481733 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 7/154 REFRAM | 31512257 | HAT CREEK #1-WESTWOOD | 007/154 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.416955 | 40.879 | ETL.7030 | 40825571 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481767 | Q2 | EI GATES-PANOCHE #1 13/64 RPR TWR | 44490730 | GATES-PANOCHE #1 | 013/064 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.252957 | 36.3035 | ETL.4720 | 40753579 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119481780 | Q2 | MRG-SN LNDR #3 9/65 RPL INSUL | 31529960 | MORAGA-SAN LEANDRO #3 | 009/065 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 | 2021-04-01 |  | 2021-04-02 | 2021-04-01 | [5 empty] | Central | WSIP | [6 empty] | '-122.134982 | 37.7233 | ETL.2790 | 40745921 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481868 | Mar | T3 SOBRANTE-G #1 1/12 INST INSUL |  | SOBRANTE-"G" #1 | 001/012 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-19 | 2021-03-19 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2443556 | 37.9093 | ETL.3720 | 40704873 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481872 | Q3 | T2 DI BRIDGEVL-CTTNWD 72/520 RPR INSS | 44398374 | BRIDGEVILLE-COTTONWOOD | 072/520 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.541104 | 40.4686 | ETL.1110 | 40721777 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119481885 | Not Scheduled | DI GATES-PANOCHE #1 025/116 RPL INSS | 31514618 | GATES-PANOCHE #1 | 025/116 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [8 empty] | WECC | South | WSIP | [8 empty] | ETL.4720 | 44402059 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119481963 | Q2 | T3 EI MENDOCINO-WILLITS 10/007 RPL POLE | 31509535 | MENDOCINO-WILLITS | 010/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.311094 | 39.3568 | ETL.7540 | 40824382 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482012 | Q2 | T3 DI MENDOCINO-WILLITS 008/008 RPR STRW | 44610679 | MENDOCINO-WILLITS | 008/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.30139 | 39.3282 | ETL.7540 | 44660761 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482039 | Not Scheduled | T3 EI FULTON-CALISTOGA 6/6 INST ANCHW |  | FULTON-CALISTOGA | 006/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.516286 | 38.5737 | ETL.6880 | 40827213 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482071 | Not Scheduled | T3 EI FULTON-CALISTOGA 6/6 RPR GYWW |  | FULTON-CALISTOGA | 006/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.516286 | 38.5737 | ETL.6880 | 40827213 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482148 | Q2 | T3 IGNACIO-BOLINAS #1 8/95 RPL DAMPER | 44640733 | IGNACIO-BOLINAS #1 | 008/095 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.6556 | 38.004 | ETL.7140 | 40701396 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482308 | Mar | T3 DI POTTR VALLEY-WILLITS 10/2 RPR STRW | 44610689 | POTTER VALLEY-WILLITS | 010/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-08 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.292748 | 39.3792 | ETL.7820 | 40656751 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482325 | Q4 | T3 MAPLE CREEK-HOOPA 10/002 RPL POLE | 31509746 | MAPLE CREEK-HOOPA | 010/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.776258 | 40.8825 | ETL.7490 | 40662150 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482418 | Q2 | T2 TRINITY-MAPLE CREEK 48/19 RPL ANCHOR | 31512224 | TRINITY-MAPLE CREEK | 048/019 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.777644 | 40.7548 | ETL.8170 | 40876568 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482437 | Not Scheduled | DI GATES-PANOCHE #2 31/149 RPLC INSS | 31514619 | GATES-PANOCHE #2 | 031/149 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.455045 | 36.5079 | ETL.4730 | 40885730 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119482439 | Not Scheduled | DI GATES-PANOCHE #1 31/149 RPLC INSS | 31514618 | GATES-PANOCHE #1 | 031/149 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.455045 | 36.5079 | ETL.4720 | 40885728 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119482445 | Not Scheduled | T2 EI BRIDGEVILLE-COTTNWD 58/428 RPR STR | 44398374 | BRIDGEVILLE-COTTONWOOD | 058/423 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.327121 | 40.3779 | ETL.1110 | 40600521 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482490 | Not Scheduled | T2 EI SPAULDING-SUMMIT 17/552 RPR INSW | 44453252 | SPAULDING-SUMMIT | 017/552 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.356782 | 39.3093 | ETL.8060 | 40810185 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482539 | Mar | T3 DI POTTER VLLY-WLLTS 6/2 RPR WP HOLE | 44610689 | POTTER VALLEY-WILLITS | 006/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.228542 | 39.3859 | ETL.7820 | 40698182 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482640 | Mar | T3NT DI PTTR VALLEY-WILLITS 6/2 INS MRKW |  | POTTER VALLEY-WILLITS | 006/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.228542 | 39.3859 | ETL.7820 | 40698182 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482691 | Not Scheduled | T2NT SAN LUIS OBISP-CAYUCS 14/133 ROW1 |  | SAN LUIS OBISPO-CAYUCOS | 014/133 | CHR | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-21 | 2022-07-21 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.798229 | 35.3477 | ETL.9090 | 40814660 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482699 | Q2 | T2 EI ELK-GUALALA 55/008 RPL ANCHW | 31521863 | ELK-GUALALA | 055/008 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.637946 | 38.9031 | ETL.8410 | 40871841 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119482771 | Not Scheduled | T2 EI SPAULDING-SUMMIT 17/551 RPR STRW | 44453252 | SPAULDING-SUMMIT | 017/551 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.357311 | 39.3093 | ETL.8060 | 40770686 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483022 | Q2 | T3 DI POTTER VLLY-WILLITS 9/5 RPR POLE | 44610679 | MENDOCINO-WILLITS | 007/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.295081 | 39.3154 | ETL.7540 | 41113149 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483064 | Not Scheduled | T2 EI SPAULDING-SUMMIT 17/548 INST MRKW | 44453449 | SPAULDING-SUMMIT | 017/548 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2022-07-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.358964 | 39.3094 | ETL.8060 | 40702051 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483127 | Q2 | T2 EI ELK-GUALALA 56/001 RPL INSW | 31513489 | ELK-GUALALA | 056/001 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 |  |  | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6323026 | 38.8988 | ETL.8410 | 40628244 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483356 | Not Scheduled | T3 EI MONTE RIO-FLTN 12/4 iINST ARMOR RO |  | MONTE RIO-FULTON | 012/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.984226 | 38.485 | ETL.7630 | 40770566 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-05 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483361 | Not Scheduled | T3 DI UKH-HPLND-CLVRDL 13/5 RMV PL BUTT | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/005 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.998432 | 38.845 | ETL.4050 | 40750649 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483414 | Not Scheduled | T2 EI SPAULDING-SUMMIT 17/543 RPR WDPKR | 44453252 | SPAULDING-SUMMIT | 017/543 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.361509 | 39.3096 | ETL.8060 | 40826218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483448 | Not Scheduled | T3 EI DRM-GRSS VLLY-WMR B23/519 RPLUMB I | 44401096 | DRUM-GRASS VALLEY-WEIMAR | B023/519 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.0298261 | 39.1984 | ETL.6760 | 40719105 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483493 | Q3 | T2 EI CARIBOU #2 - 60 kV_009/024 RPL PL | 31509660 | CARIBOU #2 | 009/024 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.192238 | 40.0119 | ETL.6280 | 40769492 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483525 | Mar | T3 DI FULTON-HOPLAND 28/009 RPL STRW | 31509534 | FULTON-HOPLAND | 028/009 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.00303 | 38.8311 | ETL.6890 | 40875980 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119483544 | Q3 | T2 EI CARIBOU-PLUMAS JCT -4/5 RPL PL | 31511052 | CARIBOU-PLUMAS JCT | 004/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.087983 | 40.0466 | ETL.6290 | 40751784 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483588 | Not Scheduled | T3 EI DRM-GRSS VLLY-WMR B23/523 RPR STRW | 44401096 | DRUM-GRASS VALLEY-WEIMAR | B023/523 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.033197 | 39.1983 | ETL.6760 | 40824352 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483749 | Not Scheduled | DI GATES-PANOCHE #1 31/150 RPLC INSS | 31514618 | GATES-PANOCHE #1 | 031/150 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2021-07-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.457578 | 36.5108 | ETL.4720 | 40592411 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119483769 | Q3 | T2 EI CARIBOU-PLUMAS JCT 5/9 REFRAME | 31507980 | CARIBOU-PLUMAS JCT | 005/009 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.069199 | 40.0356 | ETL.6290 | 40867455 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483790 | Q3 | EI T2NT CARIBOU-PLUMAS JCT 5/009 RMV BUT | 44408852 | CARIBOU-PLUMAS JCT | 005/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.069199 | 40.0356 | ETL.6290 | 40867455 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483792 | Q3 | T2 EI CARIBOU-PLUMAS JCT 5/012 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 005/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.068396 | 40.0333 | ETL.6290 | 40659861 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119483869 | Not Scheduled | T3 EI FULTON-HOPLAND 27/13 REPLUMB INSW | 44579280 | FULTON-HOPLAND | 027/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.999123 | 38.8237 | ETL.6890 | 40667805 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484058 | Q3 | T2 EI CARIBOU #2 - 60 kV_008/004 RPL PL | 31509660 | CARIBOU #2 | 008/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.220506 | 40.0132 | ETL.6280 | 40758796 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484059 | Q3 | EI T2NT CARIBOU #2 8/023 RMV BUTT |  | CARIBOU #2 | 008/023 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.20978 | 40.017 | ETL.6280 | 40656539 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484060 | Q3 | T2 EI CARIBOU #2 - 9/2 RMV BUTT |  | CARIBOU #2 | 009/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.205365 | 40.0142 | ETL.6280 | 40698597 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484090 | Mar | T3 EI DRUM-RIO OSO #2 0/4 RPR FOND | 44397942 | DRUM-RIO OSO #2 | 000/004 | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.775559 | 39.2568 | ETL.1430 | 40765785 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484096 | Mar | T3 EI DRUM-RIO OSO #2 0/4 RMV CLIMB STEP | 44397942 | DRUM-RIO OSO #2 | 000/004 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.775559 | 39.2568 | ETL.1430 | 40765785 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484100 | Mar | T3 EI DRUM-RIO OSO #2 0/001 RPR STRT | 44396373 | DRUM-RIO OSO #2 | 000/001 | ICQ | E | 2020_(1a) PSPS |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.769289 | 39.2569 | ETL.1430 | 40590432 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119484102 | Mar | T3 EI DRM-RIO OSO #2 0/2 RPR FOND | 44397942 | DRUM-RIO OSO #2 | 000/002 | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.770926 | 39.2569 | ETL.1430 | 40672179 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484103 | Mar | T3 EI DRUM-RIO OSO #2 0/3 RMV CLIMB STEP | 44397942 | DRUM-RIO OSO #2 | 000/003 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.772477 | 39.2569 | ETL.1430 | 40655125 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484105 | Mar | T3 EI DRUM-RIO OSO #2 0/3 RPR FOND | 44397942 | DRUM-RIO OSO #2 | 000/003 | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.772477 | 39.2569 | ETL.1430 | 40655125 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484108 | Mar | T3 EI DRM-RIO OSO #2 0/2 RMV CLIMB STEP | 44397942 | DRUM-RIO OSO #2 | 000/002 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.770926 | 39.2569 | ETL.1430 | 40672179 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484120 | Not Scheduled | EI DRUM-HIGGINS 11/108 RMV VEG |  | DRUM-HIGGINS | 011/108 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.9180592 | 39.1758 | ETL.4393 | 44172301 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484122 | Not Scheduled | T3 EI DRUM-HIGGINS 11/108 RMV VEG |  | DRUM-HIGGINS | 011/108 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9180592 | 39.1758 | ETL.4393 | 44172300 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484132 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 37/713 RPR S |  | HAT CREEK #1-WESTWOOD | 037/713 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.060945 | 40.5549 | ETL.7030 | 40667971 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484817 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 12/338 BTT CNCL |  | COLGATE-ALLEGHANY | 012/338 | ICW | F | 2020_(1a) PSPS |  | 2020-07-08 | 2022-07-08 | [6 empty] | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-121.013388 | 39.4161 | ETL.6470 | 40818491 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119484847 | Mar | T3NT DI PTTR VLLY-WLLTS 4/4 INS MRKW |  | POTTER VALLEY-WILLITS | 004/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.203952 | 39.3713 | ETL.7820 | 40769296 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484911 | Q2 | T3 DI MENDOCINO-WILLITS 11/0 RPL POLE | 31509536 | MENDOCINO-WILLITS | 011/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.312516 | 39.3599 | ETL.7540 | 40614348 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484921 | Q2 | T2 DI TRINITY-MPL CRK 4/7 RPL POLE | 31512092 | TRINITY-MAPLE CREEK | 004/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.011268 | 40.735 | ETL.8170 | 40906308 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119484946 | Not Scheduled | EI DRUM-HIGGINS 27/210 RPL HRDWT | 44452914 | DRUM-HIGGINS | 027/210 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.090285 | 39.0443 | ETL.4393 | 40577412 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485083 | Not Scheduled | T3 DI FULTON-HOPLAND :26/7 RPR STRW | 44579280 | FULTON-HOPLAND | :026/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.98363 | 38.794 | ETL.6890 | 40808478 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485281 | Q2 | EI GATES-PANOCHE #1 14/68 BENT STL | 44490730 | GATES-PANOCHE #1 | 014/068 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.260797 | 36.3134 | ETL.4720 | 40863638 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119485351 | Q2 | T3 DI UKIAH-HPLAND-CLVRDL 10/9 RPR POLE | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 010/009 | ICW | E | 2020_(1a) PSPS |  | 2020-07-21 | 2021-01-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.988853 | 38.8047 | ETL.4050 | 40861034 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119485511 | Q2 | T2 EI LAKEVILLE #2 A7/141 RPR GYWW |  | LAKEVILLE #2 | A007/141 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.579572 | 38.1667 | ETL.7340 | 40754058 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485548 | Mar | T3 DI POTTER VLY-WLTS 9/8 RPR GYWW |  | POTTER VALLEY-WILLITS | 009/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-11 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.286267 | 39.3759 | ETL.7820 | 40876420 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485549 | Not Scheduled | T3 DI FULTON-HOPLAND 025/016 RPR GYWW | 44579280 | FULTON-HOPLAND | 025/016 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.98785 | 38.7996 | ETL.6890 | 43250137 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485645 | Q2 | T3NT DI UKIAH-HPLND-CLVRDL 16/5 INS MRKW |  | UKIAH-HOPLAND-CLOVERDALE | 016/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-21 | 2022-07-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.032747 | 38.878 | ETL.4050 | 40761341 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485680 | Not Scheduled | EI LOS BANOS-MIDWAY #2 19/083 INST RAPT | 31527298 | LOS BANOS-MIDWAY #2 | 019/083 | 93R | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.829529 | 36.816 | ETL.6010 | 40651926 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119485734 | Not Scheduled | EI LOS BANOS-MIDWAY #2 19/084 INST RAPTO | 31527298 | LOS BANOS-MIDWAY #2 | 019/084 | 93R | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.826794 | 36.8132 | ETL.6010 | 40753960 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119485765 | Q2 | T3 EI MENDOCINO-WILLITS 10/1 RPL STRW | 31509535 | MENDOCINO-WILLITS | 010/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-01-22 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.306749 | 39.347 | ETL.7540 | 40600417 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485800 | Q2 | T3 DI UKIAH-HPLND-CLVRDL 15/7 RPR STRW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.023918 | 38.8672 | ETL.4050 | 40808565 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485806 | Q2 | T3NT DI UKIAH-HPLND-CLVRDL 15/7 INS MRKW |  | UKIAH-HOPLAND-CLOVERDALE | 015/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-21 | 2022-07-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.023918 | 38.8672 | ETL.4050 | 40808565 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485825 | Not Scheduled | EI LOS BANOS-MIDWAY #2 20/85 INST RPTR G | 31527298 | LOS BANOS-MIDWAY #2 | 020/085 | 93R | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.824181 | 36.8106 | ETL.6010 | 40753888 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119485918 | Q2 | T2 EI LAKEVILLE #2 A7/135 RPR GYWW |  | LAKEVILLE #2 | A007/135 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.585569 | 38.1705 | ETL.7340 | 40601791 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485919 | Q2 | T2 EI LAKEVILLE #2 A7/135 REFRAME | 31512369 | LAKEVILLE #2 | A007/135 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.585569 | 38.1705 | ETL.7340 | 40601791 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485923 | Q2 | T2 DI TRINITY-MAPLE CRK 17/6 RPR WD HOLE | 44295371 | TRINITY-MAPLE CREEK | 017/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.215893 | 40.7419 | ETL.8170 | 40810477 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119485962 | Q2 | T3 DI UKIAH-HPLND-CLVRDL 13/1A RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/001A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.9953 | 38.8385 | ETL.4050 | 44846556 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486140 | Q2 | T2 EI LAKEVILLE #2 A7/137 RPL PL | 31511084 | LAKEVILLE #2 | A007/137 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.58331 | 38.1691 | ETL.7340 | 40876359 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486201 | Not Scheduled | T3 DI FULTON-HOPLAND 023/000 RPR GYWW | 44579280 | FULTON-HOPLAND | 023/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.94248 | 38.7577 | ETL.6890 | 40611015 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486251 | Not Scheduled | EI T3NT OLEUM-G #1 8/55 RPR ROAD |  | OLEUM-G #1 | 008/055 | CHS | F | 2020_(3) On high spread structure |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.271784 | 37.9449 | ETL.3150 | 40746976 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486498 | Not Scheduled | EI LOS BANOS-MIDWAY #2 21/90 INST RPTR G | 31527298 | LOS BANOS-MIDWAY #2 | 021/090 | 93R | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.807989 | 36.8008 | ETL.6010 | 40605014 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486578 | Q2 | T3 DI UKIAH-HOPLAND-CLOV 14/6 RPR STRW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 014/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.008801 | 38.8564 | ETL.4050 | 44660752 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486594 | Q2 | DI GATES-PANOCHE #1 26/121 MASTIC | 44571495 | GATES-PANOCHE #1 | 026/121 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-07-21 | 2022-07-21 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.389127 | 36.4399 | ETL.4720 | 40594747 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486745 | Not Scheduled | T3 DI FULTON-HOPLAND 27/13 RPR STRW | 44579280 | FULTON-HOPLAND | 027/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.999123 | 38.8237 | ETL.6890 | 40667805 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486782 | Q2 | T2 DI TRINITY-MAPLE CREEK 17/15 RPL HRDW | 44453151 | TRINITY-MAPLE CREEK | 017/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.22543 | 40.7388 | ETL.8170 | 40752258 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486792 | Mar | HMBLDT-TRINITY 105/1L RPL POLE |  | HUMBOLDT-TRINITY | 105/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.953181 | 40.7657 | ETL.1820 | 44557580 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486793 | Mar | HMBLDT-TRINITY 105/1R RPL POLE |  | HUMBOLDT-TRINITY | 105/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.953181 | 40.7657 | ETL.1820 | 44557620 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486853 | Q2 | EI GATES-PANOCHE #1 17/79 BENT STL | 44490730 | GATES-PANOCHE #1 | 017/079 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.290206 | 36.3372 | ETL.4720 | 40863294 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486904 | Not Scheduled | T3 EI MIDDLE FORK #1 5/79 REFRAME | 44402384 | MIDDLE FORK #1 | 005/079 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-01-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.673143 | 39.0017 | ETL.8405 | 40767427 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486928 | Not Scheduled | EI SPAULDING-SUMMIT 8/281 RPR GYWW | 44453252 | SPAULDING-SUMMIT | 008/281 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.508365 | 39.3139 | ETL.8060 | 44204516 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486937 | Not Scheduled | EI SPAULDING-SUMMIT 8/280 REFRAME | 31510883 | SPAULDING-SUMMIT | 008/280 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.509179 | 39.3139 | ETL.8060 | 40660143 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486938 | Not Scheduled | EI SPAULDING-SUMMIT 8/280 RPR GYWW | 44453252 | SPAULDING-SUMMIT | 008/280 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.509179 | 39.3139 | ETL.8060 | 40660143 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486939 | Not Scheduled | EI SPAULDING-SUMMIT 008/284 RPLC STRW | 31510882 | SPAULDING-SUMMIT | 008/284 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.506738 | 39.3137 | ETL.8060 | 40878064 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119486966 | Q3 | T2 EI CARIBOU-PLUMAS JCT 4/6 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.087467 | 40.0463 | ETL.6290 | 40826454 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119486976 | Q3 | T2 EI CARIBOU-PLUMAS JCT 4/4 RPL PL | 31511052 | CARIBOU-PLUMAS JCT | 004/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.088914 | 40.0471 | ETL.6290 | 40769623 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487004 | Q2 | EI GATES-PANOCHE #1 17/080 BENT STL | 44490730 | GATES-PANOCHE #1 | 017/080 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.293411 | 36.3392 | ETL.4720 | 40592393 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119487022 | Q2 | T3 DI UKIAH-HPLND-CLVRDL 15/0 RMV STUB | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 015/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.011925 | 38.8585 | ETL.4050 | 40603870 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487076 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 05/068A RPR JUM |  | DIVIDE-CABRILLO #2 | 005/068A | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436437 | 34.7541 | ETL.1370 | 43603714 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487094 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 05/068C RPR JUM |  | DIVIDE-CABRILLO #2 | 005/068C | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436496 | 34.754 | ETL.1370 | 43603716 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487102 | Q3 | T2 EI CARIBOU-PLUMAS JCT 4/003 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.089968 | 40.0477 | ETL.6290 | 40649929 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487103 | Not Scheduled | EI DRUM-GRASS VALLEY-WMR B18/412 RPL STR | 31512367 | DRUM-GRASS VALLEY-WEIMAR | B018/412 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.973599 | 39.1486 | ETL.6760 | 40757033 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487127 | Q3 | T2 EI CARIBOU #2 ;2/023 RPL PL | 31509660 | CARIBOU #2 | ;002/023 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.947645 | 39.9936 | ETL.6280 | 40649923 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487153 | Q3 | T2 EI BRIDGEVILLE-GRBRVLL 14/2 INS CTLGR | 44453320 | BRIDGEVILLE-GARBERVILLE | 014/002 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-22 | 2022-07-22 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.734817 | 40.3151 | ETL.6220 | 44920835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487209 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 05/068B RPR JUM |  | DIVIDE-CABRILLO #2 | 005/068B | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436466 | 34.754 | ETL.1370 | 43603715 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487314 | Q3 | T2 EI CARIBOU-PLUMAS JCT 4/2 RPR INSW | 44408852 | CARIBOU-PLUMAS JCT | 004/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.0914528 | 40.0486 | ETL.6290 | 40720971 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487343 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 06/080 RPL INSW | 31512150 | DIVIDE-CABRILLO #2 | 006/080 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4360043 | 34.7305 | ETL.1370 | 40856115 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487373 | Q2 | T2 DI BRDGVL-CTTNWD 43/342 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 043/342 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-22 | 2022-07-22 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.074173 | 40.3919 | ETL.1110 | 40661021 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487511 | Q3 | T2 EI CARIBOU-PLUMAS JCT 4/1 REFRAME | 31507980 | CARIBOU-PLUMAS JCT | 004/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.092217 | 40.0491 | ETL.6290 | 40591652 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487539 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 05/066 RPL INSW | 31513652 | DIVIDE-CABRILLO #2 | 005/066 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436832 | 34.7565 | ETL.1370 | 40618686 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487565 | Not Scheduled | T2 EI SPAULDING-SUMMIT 17/535 RPR WPKRW | 44453252 | SPAULDING-SUMMIT | 017/535 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.365586 | 39.3099 | ETL.8060 | 40869224 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487595 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 05/067 RPR JUMW |  | DIVIDE-CABRILLO #2 | 005/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436737 | 34.756 | ETL.1370 | 44296268 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487596 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 05/067 RPR POLE |  | DIVIDE-CABRILLO #2 | 005/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436737 | 34.756 | ETL.1370 | 44296268 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487628 | Mar | T3 DI POTTER VALL-WILLI 10/2A RPL STRW | 31509537 | POTTER VALLEY-WILLITS | 010/002A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-08 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.293673 | 39.3798 | ETL.7820 | 40577246 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-29 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487663 | Not Scheduled | EI SPAULDING-SUMMIT 8/286 RPL POLE | 31510882 | SPAULDING-SUMMIT | 008/286 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.505689 | 39.3137 | ETL.8060 | 40618198 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119487687 | Q3 | T2 EI CARIBOU-PLUMAS JCT 04/011 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.0804359 | 40.0422 | ETL.6290 | 44399522 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487688 | Q3 | T2 EI CARIBOU-PLUMAS JCT 04/011 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.0804359 | 40.0422 | ETL.6290 | 44399523 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487689 | Q3 | T2 EI CARIBOU-PLUMAS JCT 04/011 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.0804359 | 40.0422 | ETL.6290 | 44399521 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487714 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/482 RPL STRW | 31508176 | SPAULDING-SUMMIT | 015/482 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.390021 | 39.329 | ETL.8060 | 40771519 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487733 | Q3 | T2 EI CARIBOU-PLUMAS JCT 4/12 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 004/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.079486 | 40.0416 | ETL.6290 | 40698788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487815 | Mar | T3NT DI GEYSERS #3-CLVR 4/54 RMV PL BUTT | 44580896 | GEYSERS #3-CLOVERDALE | 004/054 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.887313 | 38.8119 | ETL.1650 | 44784149 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487819 | Mar | T3 DI GEYSERS #3-CLOVER 4/54 RPR STRW | 44580896 | GEYSERS #3-CLOVERDALE | 004/054 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.887313 | 38.8119 | ETL.1650 | 44784149 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119487875 | Q2 | T2 NEWARK-LIVERMORE 7/46 INST DAMPER | 44621457 | NEWARK-LIVERMORE | 007/046 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-12 | 2021-05-10 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.882508 | 37.5572 | ETL.7660 | 40825437 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488023 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 4/65 RPL INSW | 31513652 | DIVIDE-CABRILLO #2 | 004/065 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436986 | 34.7577 | ETL.1370 | 40591102 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488024 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 004/065 RPR JUM |  | DIVIDE-CABRILLO #2 | 004/065 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436986 | 34.7577 | ETL.1370 | 40591102 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488032 | Not Scheduled | EI LOS BANOS-MIDWAY #2 22/97 WASH INSU | 44623664 | LOS BANOS-MIDWAY #2 | 022/097 | ICI | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.7852559 | 36.7869 | ETL.6010 | 40845615 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119488088 | Not Scheduled | T2 EI SPAULDING-SUMMIT 17/529 RPL PL | 31510882 | SPAULDING-SUMMIT | 017/529 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.368774 | 39.3101 | ETL.8060 | 40650069 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488190 | Not Scheduled | T3 DI FULTON-HOPLAND 27/4 RPR STRW | 44579280 | FULTON-HOPLAND | 027/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-01-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.995205 | 38.8162 | ETL.6890 | 40759964 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488216 | Q2 | T2 DI TRINITY-MAPLE CRK 9/13 RMV HRDW | 44453151 | TRINITY-MAPLE CREEK | 009/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.087826 | 40.7669 | ETL.8170 | 44630140 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488288 | Q2 | T2 DI TRINTY-MAPLE CREEK 4/13 RPR SPLW | 44273074 | TRINITY-MAPLE CREEK | 004/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 40915983 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488437 | Not Scheduled | T2 DI DRUM-SUMMIT #1 6/78 CANCEL |  | DRUM-SUMMIT #1 | 006/078 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.676781 | 39.3068 | ETL.1440 | 44823750 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488438 | Not Scheduled | T2 DI DRUM-SUMMIT #1 6/78 CANCEL |  | DRUM-SUMMIT #1 | 006/078 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.676781 | 39.3068 | ETL.1440 | 44823751 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488589 | Not Scheduled | DI DRUM-SUMMIT #1 15/183 RPR GYWW | 44449508 | DRUM-SUMMIT #1 | 015/183 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.522253 | 39.3085 | ETL.1440 | 40654776 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119488673 | Q2 | DI GATES-PANOCHE #1 26/122 BENT STL | 44571495 | GATES-PANOCHE #1 | 026/122 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.391395 | 36.4424 | ETL.4720 | 40663960 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119488675 | Q2 | DI GATES-PANOCHE #1 26/122 RPR FOND | 44571495 | GATES-PANOCHE #1 | 026/122 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.391395 | 36.4424 | ETL.4720 | 40663960 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119488745 | Q2 | T2 DI TRINITY-MAPLE CREEK 8/12 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 008/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.067898 | 40.7611 | ETL.8170 | 40906373 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488747 | Q2 | T2 DI TRINITY-MAPLE CREEK 8/3 REFRAME | 31512366 | TRINITY-MAPLE CREEK | 008/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.062946 | 40.7542 | ETL.8170 | 40906364 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488762 | Not Scheduled | T3 EI MIDDLE FORK #1 6/092 REFRAME | 31509675 | MIDDLE FORK #1 | 006/092 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-01-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.692648 | 39.0023 | ETL.8405 | 40751862 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488768 | Feb | METCALF-MOSS LANDING #1 58/250 RPR INSU | 31483542 | METCALF-MOSS LANDING #1 | 058/250 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-02-25 |  |  | Likely MAT error - delink to correct |  |  | South | WSIP | [6 empty] | '-121.7235982 | 36.812 | ETL.5100 | 40622582 | Insulator-Steel | No Good/Out of Stdrd | Repair | srdy POST |  |  |  | PEND | LC | TLN | Maintenance | Capital | 628 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-29 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488787 | Mar | T3 DI DRUM-GRS VLY-WEIMAR 1/35 RPR SPLW | 44402126 | DRUM-GRASS VALLEY-WEIMAR | 001/035 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-01-22 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.765545 | 39.2452 | ETL.6760 | 40664655 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488816 | Q2 | T2 EI PHILO JCT-ELK 10/4 RPR WPKRW | 44610684 | PHILO JCT-ELK | 010/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.301464 | 39.0277 | ETL.7780 | 40763016 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119488817 | Q2 | T2 EI PHILO JCT-ELK 10/5 RPL PL | 31511245 | PHILO JCT-ELK | 010/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.302818 | 39.0278 | ETL.7780 | 40768520 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489001 | Not Scheduled | T2 SNTSLS-NWRK #2 95/622 INS INSS | 31484760 | STANISLAUS-NEWARK #2 (12KV) | 095/622 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.900723 | 37.5646 | ETL.3860 | 44942304 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy POST |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489011 | Q2 | T2 EI PHILO JCT-ELK 16/1 RPR WDPKR | 44610684 | PHILO JCT-ELK | 016/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.397652 | 39.0414 | ETL.7780 | 40600340 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489119 | Mar | T3NT DI GEYSERS #3-CLOVER 9/110 RMV BUTT | 44580896 | GEYSERS #3-CLOVERDALE | 009/110 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-22 | 2022-07-22 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.971252 | 38.8007 | ETL.1650 | 40750647 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489153 | Q2 | T3 EI LAURELES-OTTER 14/000 RPR ANCHOR | 44610149 | LAURELES-OTTER | 014/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-01-22 |  |  | 2021-04-02 | 2021-03-31 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.8729 | 36.3857 | ETL.7380 | 40617435 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489155 | Q2 | T3 EI LAURELES-OTTER 14/000 RPR GYWW | 44610149 | LAURELES-OTTER | 014/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-01-22 |  |  | 2021-04-02 | 2021-03-31 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.8729 | 36.3857 | ETL.7380 | 40617435 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489166 | Not Scheduled | STANISLAUS-NEWARK #1 88/585 RPR INS | 44645364 | STANISLAUS-NEWARK #1 (12KV) | 088/585 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.813038 | 37.6162 | ETL.3850 | 45016548 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489214 | Q2 | T3 DI FULTON-IGNACIO #1 18/93 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 018/093 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.592662 | 38.3592 | ETL.4680 | 40651565 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489280 | Mar | T3 DI GEYSERS #3-CLOVER 9/110 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 009/110 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-01-22 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.971252 | 38.8007 | ETL.1650 | 40750647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489283 | Q2 | T2 DI TRINITY-MAPLE CRK 3/16 RPR WP HOLE | 44295371 | TRINITY-MAPLE CREEK | 003/016 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.996319 | 40.7311 | ETL.8170 | 40906295 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489416 | Not Scheduled | DI SPAULDING-SUMMIT 8/301 RMV DEBRIS | 44440214 | SPAULDING-SUMMIT | 008/301 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.497696 | 39.3141 | ETL.8060 | 40770710 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119489417 | Not Scheduled | DI SPAULDING-SUMMIT 8/301 INST MRKW | 44440214 | SPAULDING-SUMMIT | 008/301 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.497696 | 39.3141 | ETL.8060 | 40770710 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119489663 | Not Scheduled | DI MENDOCINO-WILLITS 0/11 RMV PL BUTT | 44610679 | MENDOCINO-WILLITS | 000/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-22 | 2022-07-22 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.211299 | 39.2475 | ETL.7540 | 40584890 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489664 | Q2 | DI MENDOCINO-WILLITS 0/11 RPR WPKRW | 44610679 | MENDOCINO-WILLITS | 000/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.211299 | 39.2475 | ETL.7540 | 40584890 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489892 | Q2 | T2 DI BRDGVL-CTTNWD 38/305 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 038/305 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.986276 | 40.3678 | ETL.1110 | 44565819 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489894 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 19/616 RMV BUTT | 44453449 | SPAULDING-SUMMIT | 019/616 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3292 | 39.3167 | ETL.8060 | 40826231 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489895 | Q2 | T2 DI TRINITY-MAPLE CRK 3/9 RPR STRW | 44295371 | TRINITY-MAPLE CREEK | 003/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.990322 | 40.7309 | ETL.8170 | 40906289 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489930 | Q3 | T2 EI CARIBOU #2 :1/014 RPL PL | 31509660 | CARIBOU #2 | :001/014 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.047504 | 40.005 | ETL.6280 | 40769590 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489931 | Q3 | T2 EI CARIBOU #2 :01/016 RPR GYWW |  | CARIBOU #2 | :001/016 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.045029 | 40.0042 | ETL.6280 | 40826479 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489932 | Q3 | T2 EI CARIBOU #2 :1/015 RPR GYWW |  | CARIBOU #2 | :001/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.046575 | 40.0047 | ETL.6280 | 40751799 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119489973 | Q3 | T2 DI BRDGVL-CTTNWD 70/509 RPR GRWW | 44431445 | BRIDGEVILLE-COTTONWOOD | 070/509 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.514267 | 40.4646 | ETL.1110 | 44510547 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119490045 | Q3 | EI BRIDGEVELL_CTTNWD_069/500 RPR GRWW | 44431445 | BRIDGEVILLE-COTTONWOOD | 069/500 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.4960863 | 40.45 | ETL.1110 | 44510515 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119490047 | Q3 | T2 EI BRIDGEVILLE-COTTONWD 69/502 RPLC D | 44398374 | BRIDGEVILLE-COTTONWOOD | 069/502 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.500728 | 40.4537 | ETL.1110 | 40759211 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119490772 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 12/7 RPR W | 44299806 | BRIDGEVILLE-GARBERVILLE | 012/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-17 | 2021-07-17 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.724429 | 40.3377 | ETL.6220 | 40824488 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119490883 | Q2 | T2 IGNACIO-BOLINAS #2 05/064 RPL INSW | 31510884 | IGNACIO-BOLINAS #2 | 005/064 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.6295058 | 38.106 | ETL.7180 | 40628435 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119490931 | Not Scheduled | T2NT DI SPLDNG-SMMIT 18/565 RMV DBRIS | 44402132 | SPAULDING-SUMMIT | 018/565 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.35091 | 39.3077 | ETL.8060 | 40680234 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119491018 | Not Scheduled | T2NT DI SPLDING-SUMMIT 18/566 RMV PL BUT | 44402132 | SPAULDING-SUMMIT | 018/566 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.350613 | 39.3077 | ETL.8060 | 40668696 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119491091 | Not Scheduled | T2NT DI SPLDING-SUMMIT 18/566 RPLC GMKW | 44402132 | SPAULDING-SUMMIT | 018/566 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.350613 | 39.3077 | ETL.8060 | 40668696 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119491197 | Q2 | T2NT DI TRINITY-MAPLE CRK 6/13 RMV BUTT | 44401994 | TRINITY-MAPLE CREEK | 006/013 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-22 | 2022-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.053455 | 40.7384 | ETL.8170 | 40906340 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492062 | Not Scheduled | DI DRUM-SUMMIT #2 14/173B RPR GYWW | 44449908 | DRUM-SUMMIT #2 | 014/173B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538478 | 39.3115 | ETL.1450 | 42572808 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492099 | Q2 | EI GATES-PANOCHE #1 26/121 RPR STRT | 44490730 | GATES-PANOCHE #1 | 026/121 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.389127 | 36.4399 | ETL.4720 | 40594747 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492156 | Q2 | T2NT DI BRDGVL-CTTNWD 57/418 RMV DEBRIS | 43939216 | BRIDGEVILLE-COTTONWOOD | 057/418 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.310324 | 40.3757 | ETL.1110 | 40596845 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492157 | Not Scheduled | DI DRUM-SUMMIT #2 14/173C RPR GYWW | 44449908 | DRUM-SUMMIT #2 | 014/173C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538523 | 39.3115 | ETL.1450 | 42572809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492167 | Q2 | T2 DI TRINITY-MAPLE CREEK 11/4 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 011/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-07-21 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.116977 | 40.7679 | ETL.8170 | 41163311 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492315 | Feb | T3 EI MORAGA-CASTRO VALLEY 9/42 RMV STEP | 44623422 | MORAGA-CASTRO VALLEY | 009/042 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.070003 | 37.7428 | ETL.5250 | 40689988 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492328 | Not Scheduled | DI DRUM-SUMMIT #2 14/173C RPR WDPKR | 44449908 | DRUM-SUMMIT #2 | 014/173C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538523 | 39.3115 | ETL.1450 | 42572809 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492343 | Q2 | EI GATES-PANOCHE #1 26/120 RPR STRT | 44589058 | GATES-PANOCHE #1 | 026/120 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.386839 | 36.4374 | ETL.4720 | 40592402 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492368 | Q2 | T2 DI BRDGVLL-CTTNWD 42/337C RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 042/337 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44424600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492453 | Not Scheduled | EI T3NT DRUM-HIGGINS 16/142 RPR MASTIC | 44401859 | DRUM-HIGGINS | 016/142 | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2022-07-23 | [6 empty] | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492454 | Not Scheduled | T3 EI DRUM-HIGGINS 16/142 RMV STEP | 44401858 | DRUM-HIGGINS | 016/142 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492477 | Q2 | T2 DI BRDGVLL-CTTNWD 42/337R RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 042/337 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44424601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492536 | Not Scheduled | T3 EI MIDDLE FORK #1 6/98 RPR GYWW | 44402384 | MIDDLE FORK #1 | 006/098 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.702414 | 39.0027 | ETL.8405 | 40586052 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492615 | Not Scheduled | T2 DIVIDE-CABRILLO #2 6/76 RPL INSU | 31513652 | DIVIDE-CABRILLO #2 | 006/076 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.433481 | 34.7369 | ETL.1370 | 42574075 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492630 | Not Scheduled | T3 EI MIDDLE FORK #1 7/99 RPR GYWW | 44402384 | MIDDLE FORK #1 | 007/099 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.703495 | 39.0027 | ETL.8405 | 40589957 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492688 | Feb | T3 EI DRUM-HIGGINS 12/115L RPL STRW | 31522666 | DRUM-HIGGINS | 012/115 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9317298 | 39.1704 | ETL.4393 | 44172252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492691 | Not Scheduled | T2NT DI SPLDING-SUMMIT 17/555 RMV PL BUT | 44402132 | SPAULDING-SUMMIT | 017/555 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.355517 | 39.3092 | ETL.8060 | 40861954 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492702 | Not Scheduled | EI LOS BANOS-MIDWAY #2 26/111 WASH INSS | 44507667 | LOS BANOS-MIDWAY #2 | 026/111 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 | [6 empty] | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.7353526 | 36.7569 | ETL.6010 | 40617752 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492719 | Q2 | EI GATES-PANOCHE #1 25/119 BENT STL | 44490730 | GATES-PANOCHE #1 | 025/119 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.38455 | 36.4348 | ETL.4720 | 40863298 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492889 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 6/76 RPR WPKR |  | DIVIDE-CABRILLO #2 | 006/076 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4334808 | 34.7369 | ETL.1370 | 44283611 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492933 | Not Scheduled | T3 EI FULTON-CALISTOGA :4/1 RPR GYWW | 44597303 | FULTON-CALISTOGA | :004/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.593036 | 38.6457 | ETL.6880 | 44913375 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119492991 | Q2 | EI GATES-PANOCHE #1 25/118 BENT STL | 44490730 | GATES-PANOCHE #1 | 025/118 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.382263 | 36.4323 | ETL.4720 | 40863644 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119492997 | Not Scheduled | T2NT DI SPLDING-SUMMIT 19/614 RMV DEBRIS | 44440214 | SPAULDING-SUMMIT | 019/614 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329317 | 39.316 | ETL.8060 | 40751937 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493054 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 19/605 RMV BUTT | 44409175 | SPAULDING-SUMMIT | 019/605 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.331106 | 39.3125 | ETL.8060 | 40828159 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493059 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 19/605 INS MRKW | 44440214 | SPAULDING-SUMMIT | 019/605 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.331106 | 39.3125 | ETL.8060 | 40828159 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493061 | Not Scheduled | T2 DI DRUM-SUMMIT #2 18/219 CANCEL | 44449908 | DRUM-SUMMIT #2 | 018/219 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.477314 | 39.3178 | ETL.1450 | 44557532 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493064 | Not Scheduled | T2 DI DRUM-SUMMIT #2 18/219 CANCEL | 44449908 | DRUM-SUMMIT #2 | 018/219 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.477314 | 39.3178 | ETL.1450 | 44557533 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493101 | Q3 | T2NT DI CARIBOU #2 12/8 RMV BUTT |  | CARIBOU #2 | 012/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-22 | 2022-07-22 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.156967 | 40.0242 | ETL.6280 | 40868131 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493104 | Q3 | T2 DI CARIBOU #2 12/8 RPR GYWW |  | CARIBOU #2 | 012/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.156967 | 40.0242 | ETL.6280 | 40868131 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493126 | Not Scheduled | T2 DI DRUM-SUMMIT #1 24/285 RPL PL | 31498145 | DRUM-SUMMIT #1 | 024/285 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.377528 | 39.3109 | ETL.1440 | 44762496 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493138 | Q2 | T2 EI DIVIDE-CABRILLO #2 6/78L RPL STRW | 31513656 | DIVIDE-CABRILLO #2 | 006/078 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-29 | 2021-04-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4343354 | 34.7348 | ETL.1370 | 44336840 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493156 | Q2 | T2 DI BRDGVLLE-CTTNWOOD 37/299L RPR GRWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/299 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.974258 | 40.3657 | ETL.1110 | 44424085 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493158 | Q2 | T2 DI BRDGVLLE-CTTNWOOD 37/299R RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/299 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.974258 | 40.3657 | ETL.1110 | 44424086 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493224 | Not Scheduled | DI DRUM-SUMMIT #15/181B RPR GYWW | 44449913 | DRUM-SUMMIT #1 | 015/181 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525415 | 39.3069 | ETL.1440 | 42572684 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119493263 | Q2 | T3 EI LAURELES-OTTER 4/0 RPL POLE | 31521909 | LAURELES-OTTER | 004/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.727818 | 36.4377 | ETL.7380 | 40617446 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493298 | Not Scheduled | EI LOS BANOS-GATES #1 42/178 INST MRKS | 44507429 | LOS BANOS-GATES #1 | 042/178 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2022-07-23 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.570836 | 36.5618 | ETL.6000 | 40871601 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119493366 | Not Scheduled | DI DRUM-SUMMIT #2 15/183L REPL POLE |  | DRUM-SUMMIT #2 | 015/183 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [6 empty] | Likely MAT error - delink to correct |  | WECC | North Valley | WSIP | [6 empty] | '-120.527359 | 39.3071 | ETL.1450 | 44561348 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119493367 | Not Scheduled | DI DRUM-SUMMIT #2 15/183R RPL POLE | 44449908 | DRUM-SUMMIT #2 | 015/183 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.527359 | 39.3071 | ETL.1450 | 44561436 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119493371 | Q2 | T2 EI DIVIDE-CABRILLO #2 6/78C RPL STRW | 31513656 | DIVIDE-CABRILLO #2 | 006/078 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-29 | 2021-04-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4343354 | 34.7348 | ETL.1370 | 44336838 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493420 | Q2 | T2 EI DIVIDE-CABRILLO #2 6/78R RPL STRW | 31513656 | DIVIDE-CABRILLO #2 | 006/078 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-29 | 2021-04-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4343354 | 34.7348 | ETL.1370 | 44336839 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493512 | Q2 | GARBERVILLE-LAYTONVILLE 33/4 INST DAMPER | 44453326 | GARBERVILLE-LAYTONVILLE | 033/004 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5614311 | 39.8178 | ETL.8365 | 40779338 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493518 | Feb | T2 PHILO JCT-ELK 32/3 RPL ANCHOR | 31507982 | PHILO JCT-ELK | 032/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.634114 | 39.1341 | ETL.7780 | 40660586 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493542 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 6/79 RPR JUMPER |  | DIVIDE-CABRILLO #2 | 006/079 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.435477 | 34.7319 | ETL.1370 | 44820204 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493601 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 10/126L RMV BUTT | 44409006 | DRUM-SUMMIT #2 | 010/126 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.603803 | 39.3267 | ETL.1450 | 44558984 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493602 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 10/126R RMV BUTT | 44440202 | DRUM-SUMMIT #2 | 010/126 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.603803 | 39.3267 | ETL.1450 | 44558966 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493624 | Q2 | T2 DI TRINITY-MAPLE CREEK 0/11A RPL INSW | 31509759 | TRINITY-MAPLE CREEK | 000/011A | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420761 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119493892 | Not Scheduled | EI DISTRIBUTION RPR SPLW |  | FULTON-CALISTOGA | '-013/009 | 93C | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Coast | WSIP |  | 7/24 distribution |  |  |  |  | '-122.510149 | 38.4271 | ETL.6880 | 44916833 | Conductor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 531 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494112 | Q2 | T3 EGL RCK-FLTN-SLVRD 4/18 RPR REGRADE |  | EAGLE ROCK-FULTON-SILVERADO | 004/018 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.764133 | 38.671 | ETL.4392 | 41129321 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494328 | Before Feb | EI LOS BANOS-GATES #1 41/174 CANCEL | 31527294 | LOS BANOS-GATES #1 | 041/174 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 | 2020-07-06 | 2020-08-19 | 2020-08-19 | 2020-07-06 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | WSIP | [6 empty] | '-120.5836049 | 36.5695 | ETL.6000 | 40789226 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Before Feb | Found in 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119494415 | Not Scheduled | DI DRUM-SUMMIT #1 15/180 RPR GYWW | 44449508 | DRUM-SUMMIT #1 | 015/180 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.526299 | 39.3069 | ETL.1440 | 40595351 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119494425 | Not Scheduled | T2 TEMBLOR-SAN LUIS OBSP 55/306 RMV INSU |  | TEMBLOR-SAN LUIS OBISPO | 055/306 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.594324 | 35.2761 | ETL.3960 | 40852008 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494521 | Not Scheduled | T3 EI FULTON-CALISTOGA 05/001 RPL STRW | 31509532 | FULTON-CALISTOGA | 005/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.496555 | 38.5568 | ETL.6880 | 40585439 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494599 | Not Scheduled | DI DRUM-SUMMIT #1 15/181C RPR GYWW | 44449913 | DRUM-SUMMIT #1 | 015/181C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525388 | 39.3068 | ETL.1440 | 42572685 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119494601 | Not Scheduled | EI SPAULDING-SUMMIT A009/304 INST MKRW | 44453449 | SPAULDING-SUMMIT | A009/304 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2022-07-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.497118 | 39.3138 | ETL.8060 | 44213300 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119494608 | Q2 | T2 IGNACIO-BOLINAS #2 05/066 RPL INSW | 31510884 | IGNACIO-BOLINAS #2 | 005/066 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.6298122 | 38.1078 | ETL.7180 | 40678950 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494609 | Not Scheduled | DI DRUM-SUMMIT #1 23/279 RPL PL | 31498145 | DRUM-SUMMIT #1 | 023/279 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.386514 | 39.3113 | ETL.1440 | 40873397 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119494692 | Not Scheduled | DI DRUM-SUMMIT #1 15/181C RMV BUTT | 44409002 | DRUM-SUMMIT #1 | 015/181C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525388 | 39.3068 | ETL.1440 | 42572685 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119494706 | Q2 | T2 DI BRDGVL-CTTNWD 38/308 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 038/308 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.994107 | 40.3712 | ETL.1110 | 44550800 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494733 | Q2 | T2NT DI BRDGVL-CTTNWD 41/327 RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 041/327 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-22 | 2022-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.039927 | 40.3846 | ETL.1110 | 44424070 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494736 | Q2 | T2NT DI BRDGVL-CTTNWD 41/327 RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 041/327 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-22 | 2022-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.039927 | 40.3846 | ETL.1110 | 44424071 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494752 | Q2 | T2NT DI BRDGVLL-CTTNWD 41/328 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 041/328 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-22 | 2022-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.041318 | 40.3855 | ETL.1110 | 44424093 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494756 | Q2 | T2NT DI BRDGVLL-CTTNWD 41/328 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 041/328 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-22 | 2022-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.041318 | 40.3855 | ETL.1110 | 44424094 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494770 | Q3 | EI COTTONWOOD-HUMBOLDT 78/555L RPR GYWW | 44431445 | BRIDGEVILLE-COTTONWOOD | 078/555 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6412272 | 40.4824 | ETL.1110 | 44932591 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494771 | Q3 | EI COTTONWOOD-HUMBOLDT 78/555R RPR GYWW | 44431445 | BRIDGEVILLE-COTTONWOOD | 078/555 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6412272 | 40.4824 | ETL.1110 | 44932592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494780 | Q2 | T2 DI BRDGVL-CTTNWD 41/327 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 041/327 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.039927 | 40.3846 | ETL.1110 | 44424070 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119494842 | Q2 | T2 DI BRDGVLL-CTTNWD 41/328 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 041/328 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.041318 | 40.3855 | ETL.1110 | 44424093 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495049 | Q2 | T2 DI BRDGVL-CTTNWD 39/311L RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 039/311 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.999768 | 40.3743 | ETL.1110 | 44550723 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495076 | Not Scheduled | T2 EI CARIBOU-PALERMO 5/049 INS ATCG |  | CARIBOU-PALERMO | 005/049 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540447 | 39.5329 | ETL.3190 | 40870660 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495386 | Q3 | T2NT DI BRDGVL-CTTNWD 71/514 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 071/514 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-22 | 2022-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.527775 | 40.4681 | ETL.1110 | 44425581 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495422 | Q3 | T2 DI BRDGVLL-CTTNWD 070/507 RPR STRW | 44404493 | BRIDGEVILLE-COTTONWOOD | 070/507 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.512171 | 40.4629 | ETL.1110 | 44509664 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495424 | Q3 | T2 DI BRDGVLL-CTTNWD 72/521R RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 072/521 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.543463 | 40.4696 | ETL.1110 | 44512063 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495426 | Q3 | T2 DI BRDGVLL-CTTNWD 72/521L RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 072/521 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.543463 | 40.4696 | ETL.1110 | 44512062 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495429 | Q3 | T2 DI BRDGVLL-CTTNWD 72/521 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 072/521 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.543463 | 40.4696 | ETL.1110 | 44512063 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495452 | Q3 | T2NT DI BRDGVL-CTTNWD 71/514 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 071/514 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-22 | 2022-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.527775 | 40.4681 | ETL.1110 | 44425582 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495453 | Q3 | T2 DI BRDGVL-CTTNWD 71/514L RPL XARMS | 31526498 | BRIDGEVILLE-COTTONWOOD | 071/514 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.527775 | 40.4681 | ETL.1110 | 44425581 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495468 | Not Scheduled | T2 DI DRUM-SUMMIT #2 8/91 CANCEL | 44449908 | DRUM-SUMMIT #2 | 008/091 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.654548 | 39.3134 | ETL.1450 | 44551635 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495469 | Not Scheduled | T2 DI DRUM-SUMMIT #2 8/91 CANCEL | 44449908 | DRUM-SUMMIT #2 | 008/091 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.654548 | 39.3134 | ETL.1450 | 44551635 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495471 | Q4 | EI MIDDLE FORK-GOLD HILL 0/5 RPR SHLD | 44452455 | MIDDLE FORK-GOLD HILL | 000/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.5983204 | 39.0189 | ETL.5140 | 44552272 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495699 | Q4 | T2 EI MAPLE CREEK-HOOPA 25/9 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 025/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.648842 | 41.021 | ETL.7490 | 44145876 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495716 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 10/127 RMV BUTT | 44401845 | DRUM-SUMMIT #2 | 010/127 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44212219 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495843 | Not Scheduled | T2 DI CARIBOU-PALERMO :13/103 RMV DEBRIS |  | CARIBOU-PALERMO | :013/103 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278836 | 39.963 | ETL.3190 | 40738339 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495913 | Not Scheduled | T3 EI DRM-GRSS VLLY-WMR B22/486 RPL GYWW | 44402126 | DRUM-GRASS VALLEY-WEIMAR | B022/486 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008301 | 39.1892 | ETL.6760 | 40598617 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119495972 | Not Scheduled | T3 DI CRESTA-RIO OSO 13/108 RPR FOND |  | CRESTA-RIO OSO | 013/108 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.455727 | 39.7731 | ETL.4590 | 40910131 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496082 | Not Scheduled | DI DRUM-SUMMIT #2 014/174 INS MRKW | 44440202 | DRUM-SUMMIT #2 | 014/174 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538062 | 39.311 | ETL.1450 | 44558480 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119496085 | Not Scheduled | DI SPAULDING-SUMMIT 9/303 INS MRKW | 44440214 | SPAULDING-SUMMIT | 009/303 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.496822 | 39.3142 | ETL.8060 | 40618201 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119496142 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 24/286L INST MRKW | 44440200 | DRUM-SUMMIT #1 | 024/286 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44149467 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496199 | Mar | T3 DI DRUM-HIGGINS 009/086 RPR FOND | 44401857 | DRUM-HIGGINS | 009/086 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-23 | 2022-07-23 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.891897 | 39.1662 | ETL.4393 | 40814103 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496275 | Not Scheduled | T2NT DI CARIBOU-PLRMO :28/234 RMV DEBRIS |  | CARIBOU-PALERMO | :028/234 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451472 | 39.7995 | ETL.3190 | 40771764 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496357 | Mar | T3 EI LAURELES-OTTER 13/014 RPR ANCHOR | 44610149 | LAURELES-OTTER | 013/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.869953 | 36.3862 | ETL.7380 | 40771077 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496382 | Q2 | T2 DI BRDGVILLE-COTTONWD 41/329 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 041/329 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.043176 | 40.3868 | ETL.1110 | 44424407 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496445 | Not Scheduled | T2 DI DRUM-SUMMIT #2 9/105 CANCEL | 44449908 | DRUM-SUMMIT #2 | 009/105 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.632811 | 39.3219 | ETL.1450 | 44557471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119496446 | Not Scheduled | T2 DI DRUM-SUMMIT #2 009/105 CANCEL | 44449908 | DRUM-SUMMIT #2 | 009/105 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.632811 | 39.3219 | ETL.1450 | 44557642 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497529 | Q2 | T2 DI BRIDGVL-CTTNWD 45/355 RPR INSS | 44477511 | BRIDGEVILLE-COTTONWOOD | 045/355 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.123179 | 40.3993 | ETL.1110 | 42603488 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497572 | Not Scheduled | T3 EI COLGATE-CHALLENGE 1/30 RPL STRW | 31509852 | COLGATE-CHALLENGE | 001/030 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.184963 | 39.3478 | ETL.6480 | 40814415 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497613 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 13/239 RPR SPLW | 44402309 | FRENCH MEADOWS-MIDDLE FORK | 013/239 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.596084 | 39.024 | ETL.6870 | 43595443 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497626 | Not Scheduled | T2 DI SPAULDING-SUMMIT 001/038 RPL INSW | 31507463 | SPAULDING-SUMMIT | 001/038 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.626691 | 39.321 | ETL.8060 | 40610597 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497683 | Feb | T3 DI DRUM-HIGGINS 11/106 ANTI-SPLIT BLT | 44401855 | DRUM-HIGGINS | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.915226 | 39.1769 | ETL.4393 | 44172256 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497687 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 5/61B CANCEL | 44403356 | COLGATE-SMARTVILLE #2 | 005/061B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.262037 | 39.2838 | ETL.6520 | 42562738 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497803 | Not Scheduled | EI LOS BANOS-MIDWAY #2 27/117 RMV VEG |  | LOS BANOS-MIDWAY #2 | 027/117 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-24 | 2021-07-24 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.718497 | 36.7439 | ETL.6010 | 40821279 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119497885 | Q2 | T2 DI FULTON-CALISTOGA -12/2 REMV DEBRIS |  | FULTON-CALISTOGA | '-012/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.523093 | 38.4026 | ETL.6880 | 40658395 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497888 | Q2 | T2NT DI BRIDGEVILLE-CTTN 37/295 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 037/295 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.965504 | 40.3659 | ETL.1110 | 44515863 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119497906 | Not Scheduled | EI LOS BANOS-MIDWAY #2 28/118 RMV VEG |  | LOS BANOS-MIDWAY #2 | 028/118 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-24 | 2021-07-24 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.716746 | 36.7407 | ETL.6010 | 40871235 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119497913 | Not Scheduled | DI DRUM-SUMMIT #1 023/281 RPL PL |  | DRUM-SUMMIT #1 | 023/281 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.382924 | 39.3113 | ETL.1440 | 44767639 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119497976 | Q2 | EI GATES-PANOCHE #1 22/103 BENT STL | 44490730 | GATES-PANOCHE #1 | 022/103 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-24 | 2021-07-24 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.348429 | 36.3952 | ETL.4720 | 40651607 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119498023 | Q2 | T2 DI BRIDGEVLE-COTN 37/295 ANTI-SPL BLT | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/295 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.965504 | 40.3659 | ETL.1110 | 44561169 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498024 | Q2 | T2NT DI BRIDGVLLE-CTTN 39/312 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 039/312 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.001379 | 40.3751 | ETL.1110 | 44424594 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498075 | Feb | EI T3NT MORAGA-CASTRO VALLEY 9/38 INST | 31529482 | MORAGA-CASTRO VALLEY | 009/038 | 93A | F | 2020_(3) On high spread structure |  | 2020-07-24 | 2022-07-24 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.07905 | 37.7564 | ETL.5250 | 40866249 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498121 | Q2 | EI LOS BANOS-GATES #1 43/180 RPR FOUND | 44571722 | LOS BANOS-GATES #1 | 043/180 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-24 | 2021-07-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.564721 | 36.5581 | ETL.6000 | 40603194 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119498195 | Q2 | T3 DI UKIAH-HOPLAND-CLOVER 13/6 REPL INS |  | UKIAH-HOPLAND-CLOVERDALE | 013/006 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-21 | 2021-01-21 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.999197 | 38.8461 | ETL.4050 | 40819434 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498196 | Q2 | T2 DI BRIDGVL-CTTNWD 2/27 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 002/027 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.321036 | 40.3919 | ETL.1110 | 44424471 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498369 | Mar | T3 EI POTTER VALLEY-WILLIT 9/8A RPL STRW | 31509537 | POTTER VALLEY-WILLITS | 009/008A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 |  |  | 2021-03-11 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.287362 | 39.3763 | ETL.7820 | 40577247 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-29 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498395 | Not Scheduled | DI DRUM-SUMMIT #1 024/284 RMV PL BUTT | 44440200 | DRUM-SUMMIT #1 | 024/284 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.378934 | 39.311 | ETL.1440 | 44762494 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119498398 | Not Scheduled | T2 DI DRUM-SUMMIT #1 024/284 RPR PL | 44645316 | DRUM-SUMMIT #1 | 024/284 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378934 | 39.311 | ETL.1440 | 44762494 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498473 | Not Scheduled | T2NT DI SPAULDING-SMMT 16/507 RMV BUTT | 44409175 | SPAULDING-SUMMIT | 016/507 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.37884 | 39.3192 | ETL.8060 | 44565373 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498586 | Not Scheduled | T2NT DI COLGATE-SMRTVL #2 1/19 RMV BUTT | 44409114 | COLGATE-SMARTVILLE #2 | 001/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.212295 | 39.3234 | ETL.6520 | 40754751 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498588 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 1/19 RPR GYWW | 44452456 | COLGATE-SMARTVILLE #2 | 001/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.212295 | 39.3234 | ETL.6520 | 40754751 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498798 | Feb | EI T3NT MORAGA-CASTRO VALLEY 8/35 INST A | 31529482 | MORAGA-CASTRO VALLEY | 008/035 | 93A | F | 2020_(3) On high spread structure |  | 2020-07-24 | 2022-07-24 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.083608 | 37.7637 | ETL.5250 | 40756485 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498811 | Feb | EI T3NT MRGA-CSTRO VALLEY 8/035 RPR FOND | 44623422 | MORAGA-CASTRO VALLEY | 008/035 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-24 | 2022-07-24 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.083608 | 37.7637 | ETL.5250 | 40756485 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498899 | Q2 | T2 DI HAT CREEK #1-WSTWD 40/768 RPR GYWW | 44388736 | HAT CREEK #1-WESTWOOD | 040/768 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-07-24 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.034645 | 40.5182 | ETL.7030 | 40675716 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498916 | Not Scheduled | T2 DI CLGTE-SMRTVILL #2 5/61A CANCEL | 44403356 | COLGATE-SMARTVILLE #2 | 005/061A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.262025 | 39.2838 | ETL.6520 | 40754733 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498964 | Feb | EI T3NT MORAGA-CSTRO VALLY 8/036 INST A | 31529482 | MORAGA-CASTRO VALLEY | 008/036 | 93A | F | 2020_(3) On high spread structure |  | 2020-07-24 | 2022-07-24 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.082735 | 37.762 | ETL.5250 | 40816972 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119498965 | Mar | T3 EI MORAGA-CASTRO VALLEY 8/036 RPL INS | 31526489 | MORAGA-CASTRO VALLEY | 008/036 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.0827486 | 37.762 | ETL.5250 | 40844892 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119499065 | Not Scheduled | T2 DI DRUM-SUMMIT #2 26/314C RPL POLE | 31510143 | DRUM-SUMMIT #2 | 026/314C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.350722 | 39.3079 | ETL.1450 | 42572855 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119499066 | Not Scheduled | T2 DI DRUM-SUMMIT #2 26/314B RPL POLE | 31510143 | DRUM-SUMMIT #2 | 026/314B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.350703 | 39.308 | ETL.1450 | 42572854 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119499110 | Q2 | T2 DI HAT CRK #1-WSTWD 40/768 RPR GRNDW | 44388736 | HAT CREEK #1-WESTWOOD | 040/768 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-07-24 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.034645 | 40.5182 | ETL.7030 | 40675716 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119499210 | Not Scheduled | T3 EI FULTON-CALISTOGA 5/2 REPL INSW | 31509853 | FULTON-CALISTOGA | 005/002 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.497703 | 38.5577 | ETL.6880 | 40700663 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119499247 | Not Scheduled | T3 EI FULTON-CALISTOGA 5/4 REPL POLE | 31509728 | FULTON-CALISTOGA | 005/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.499933 | 38.56 | ETL.6880 | 40770510 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119499728 | Not Scheduled | EI LOS BANOS-GATES #1 044/185 INST MKRT | 44507429 | LOS BANOS-GATES #1 | 044/185 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-24 | 2022-07-24 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.548467 | 36.5481 | ETL.6000 | 40762680 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119500060 | Feb | EI T3NT MORAGA-CASTRO VALY 7/034 INST AC | 31529482 | MORAGA-CASTRO VALLEY | 007/034 | 93A | F | 2020_(3) On high spread structure |  | 2020-07-24 | 2022-07-24 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.085837 | 37.7678 | ETL.5250 | 40756555 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119500061 | Not Scheduled | T3 EI MORAGA-CASTRO VALLEY 7/034 OPGW DA | 44609778 | MORAGA-CASTRO VALLEY | 007/034 | ICS | F | 2020_(2) High fire spread TD |  | 2020-07-24 | 2022-07-24 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.085837 | 37.7678 | ETL.5250 | 40756555 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119500589 | Q2 | EI T2NT PHILO JCT-ELK 007/003 INST GMKW |  | PHILO JCT-ELK | 007/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-24 | 2022-07-24 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.251039 | 39.0476 | ETL.7780 | 40666580 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119501754 | Q2 | DI GATES-PANOCHE #2 24/113B RPR STRT | 44571496 | GATES-PANOCHE #2 | 024/113B | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.371084 | 36.4202 | ETL.4730 | 40740527 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119502190 | Not Scheduled | T2 EI CARIBOU-PALERMO 11/093 INST NUT |  | CARIBOU-PALERMO | 011/093 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119502444 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 19/603 RMV BUTT | 44453449 | SPAULDING-SUMMIT | 019/603 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.332025 | 39.3118 | ETL.8060 | 40771558 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119502449 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 19/603 INS MRKW | 44440214 | SPAULDING-SUMMIT | 019/603 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2022-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.332025 | 39.3118 | ETL.8060 | 40771558 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119503401 | Q2 | EI T3NT FULTON-CALISTOGA -014/003 RMV DE | 44597303 | FULTON-CALISTOGA | '-014/003 | ICW | F | 2020_(1a) PSPS |  | 2020-07-24 | 2022-07-24 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.507427 | 38.4311 | ETL.6880 | 40649312 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119503788 | Q4 | T3 EI MAPLE CREEK-HOOPA 22/011 RPR WPKR | 44192340 | MAPLE CREEK-HOOPA | 022/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.640275 | 40.986 | ETL.7490 | 44660734 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119503882 | Not Scheduled | T3 EI COLGATE-CHALLENGE 002/042 RPL SPLC | 44402124 | COLGATE-CHALLENGE | 002/042 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.176289 | 39.3546 | ETL.6480 | 40594209 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119504290 | Feb | T2NT DI COLGATE-GRS VLY 0/1 RMV BUTT | 44409113 | COLGATE-GRASS VALLEY | 000/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.18931 | 39.3314 | ETL.6490 | 40599624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119504495 | Q2 | DI LAKEVILLE-IGNACIO #1 005/026 RPR FOND | 43761675 | LAKEVILLE-IGNACIO #1 | 005/026 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-23 | 2022-07-23 |  |  | 2021-05-28 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.510826 | 38.1914 | ETL.4940 | 40819071 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119504497 | Q2 | DI LAKEVILLE-IGNACIO #1 005/026 INS MRKS |  | LAKEVILLE-IGNACIO #1 | 005/026 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-23 | 2022-07-23 |  |  | 2021-05-27 | 2021-05-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.510826 | 38.1914 | ETL.4940 | 40819071 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119504917 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/42 RPR SPLW | 44403403 | SPAULDING-SUMMIT | 001/042 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2021-07-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6257 | 39.3196 | ETL.8060 | 44420792 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119504929 | Not Scheduled | T3 EI COLGATE-CHALLENGE 02/045 RPR STRW | 44402124 | COLGATE-CHALLENGE | 002/045 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.173941 | 39.3564 | ETL.6480 | 40655133 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505009 | Q2 | T2NT DI TRINITY-MAPLE CREEK 8/0 RMV BUTT | 44401994 | TRINITY-MAPLE CREEK | 008/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-21 | 2022-07-21 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.06165 | 40.7529 | ETL.8170 | 40906361 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505013 | Not Scheduled | T3 EI DRUM-GRASS VALY-WMR B20/455 REFRAM | 31509748 | DRUM-GRASS VALLEY-WEIMAR | B020/455 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995295 | 39.1722 | ETL.6760 | 40756947 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505033 | Mar | T3 EI DRUM-HIGGINS 9/093 RPR GYWW | 44453178 | DRUM-HIGGINS | 009/093 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8911072 | 39.1763 | ETL.4393 | 44172113 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505069 | Not Scheduled | T3 EI COLGATE-CHALLENGE 2/47 RPR CNDW | 44402124 | COLGATE-CHALLENGE | 002/047 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.172475 | 39.3576 | ETL.6480 | 44422727 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505141 | Q2 | T2 DI BRIDGEVILLE-COTTONW 2/21 RPL STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 002/021 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.306754 | 40.3948 | ETL.1110 | 44423271 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505147 | Q2 | T2 DI BRIDGEVILLE-COTTON 2/28 RPL INSUL | 31515458 | BRIDGEVILLE-COTTONWOOD | 002/028 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.323387 | 40.3914 | ETL.1110 | 44423289 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505230 | Q2 | T2 DI BRIDGEVILLE-COTTON 2/28 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 002/028 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.323387 | 40.3914 | ETL.1110 | 44423289 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505296 | Not Scheduled | T2 EI CARIBOU-PALERMO 13/114 RPR STRT |  | CARIBOU-PALERMO | 013/114 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509255 | 39.6459 | ETL.3190 | 40762753 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119505329 | Not Scheduled | T2 DI DRUM-SUMMIT #2 009/107 RMV DEBRIS | 44449515 | DRUM-SUMMIT #2 | 009/107 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.62924 | 39.3213 | ETL.1450 | 44553570 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119506355 | Not Scheduled | T2 EI CARIBOU-PALERMO 6/055 RPR FOND |  | CARIBOU-PALERMO | 006/055 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.538613 | 39.5459 | ETL.3190 | 40765164 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119506374 | Not Scheduled | T2 EI SPAULDING-SUMMIT 13/441 RPL POLE | 31510882 | SPAULDING-SUMMIT | 013/441 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.420984 | 39.3276 | ETL.8060 | 40618262 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119507194 | Not Scheduled | T3 EI COLGATE-CHALLENGE 2/055 RPR SPLW | 44402124 | COLGATE-CHALLENGE | 002/055 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-25 | 2021-01-25 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.167405 | 39.3629 | ETL.6480 | 40664548 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119507201 | Not Scheduled | T3 EI COLGATE-CHALLENGE 03/064 INS HRDD | 44402124 | COLGATE-CHALLENGE | 003/064 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-25 | 2021-01-25 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.165636 | 39.3694 | ETL.6480 | 40766700 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119507302 | Q4 | T3 EI MAPLE CREEK-HOOPA 25/1 RPL STRW | 31509746 | MAPLE CREEK-HOOPA | 025/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-25 | 2021-01-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.646695 | 41.0132 | ETL.7490 | 40602138 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119507303 | Q4 | EI T3NTAPLE CRK-HPA 24/010 RMV PL BUT | 44301081 | MAPLE CREEK-HOOPA | 024/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-25 | 2022-07-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.64646 | 41.0098 | ETL.7490 | 40617838 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119507324 | Q4 | T3 EI MAPLE CREEK-HOOPA 24/10 RPR WDPKR | 44192340 | MAPLE CREEK-HOOPA | 024/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-25 | 2021-01-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.64646 | 41.0098 | ETL.7490 | 40617838 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119508528 | Q4 | EI T3NT MAPLE CREEK-HOOPA 25/7 RMV BUTT | 44593017 | MAPLE CREEK-HOOPA | 025/007 | ICW | F | 2020_(2) High fire spread TD |  | 2020-07-25 | 2022-07-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.645853 | 41.0181 | ETL.7490 | 44145875 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119508801 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/084 REPL INSS |  | CARIBOU-PALERMO | 010/084 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.524512 | 39.5921 | ETL.3190 | 40755650 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119508802 | Not Scheduled | T2 EI CARIBOU-PALERMO 10/084 INST STEP |  | CARIBOU-PALERMO | 010/084 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.524512 | 39.5921 | ETL.3190 | 40755650 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119508803 | Not Scheduled | T2 EI CARIBOU-PALERMO 8/070 RPR FOND |  | CARIBOU-PALERMO | 008/070 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53037 | 39.5727 | ETL.3190 | 40599260 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119509034 | Not Scheduled | T3 EI DRM-GRSS VLLY-WMR B22/501 RPR INSW | 44403357 | DRUM-GRASS VALLEY-WEIMAR | B022/501 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.01702 | 39.1954 | ETL.6760 | 40815108 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119509103 | Not Scheduled | DI GATES-PANOCHE #1 9/40 RPLC DAMS | 44402449 | GATES-PANOCHE #1 | 009/040 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 | [8 empty] | WECC | South | WSIP | [8 empty] | ETL.4720 | 44402039 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119509104 | Not Scheduled | DI GATES-PANOCHE #1 9/40 RPLC DAMS | 44402451 | GATES-PANOCHE #2 | 009/040 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 | [8 empty] | WECC | South | WSIP | [8 empty] | ETL.4730 | 44402089 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119509110 | Q2 | T2 DI BRIDGVLLE-CTTONWD 40/321 RPR INSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 040/321 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.026791 | 40.3822 | ETL.1110 | 40796892 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119509671 | Not Scheduled | T3 DI DRUM-HIGGINS RPL STRW | 31509929 | DRUM-HIGGINS | 011/110 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.920806 | 39.1747 | ETL.4393 | 44172316 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119509802 | Not Scheduled | T3 DI DRM-GRS VLY-WMR 5/124 CANCEL | 44403357 | DRUM-GRASS VALLEY-WEIMAR | 005/124 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.812177 | 39.2139 | ETL.6760 | 40693557 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119509804 | Not Scheduled | T3 DI DRM-GRS VLY-WMR 5/124 CANCEL | 44403357 | DRUM-GRASS VALLEY-WEIMAR | 005/124 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.812177 | 39.2139 | ETL.6760 | 40693557 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510024 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/521 RPR INSW | 44453252 | SPAULDING-SUMMIT | 016/521 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3729676 | 39.3119 | ETL.8060 | 40834379 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510456 | Not Scheduled | T3 EI FULTON-CALISTOGA :2/2 RMV LADDER | 44597303 | FULTON-CALISTOGA | :002/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.587195 | 38.6238 | ETL.6880 | 44310678 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510462 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/519 RPL POLE | 31510882 | SPAULDING-SUMMIT | 016/519 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.374288 | 39.3129 | ETL.8060 | 40770684 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510701 | Not Scheduled | T3 EI DRM-GRSS VLLY-WMR B21/467 REFRAME | 31509748 | DRUM-GRASS VALLEY-WEIMAR | B021/467 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.999387 | 39.1786 | ETL.6760 | 40693415 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510707 | Q2 | EI VC-VCVLLE-JMESN-NRTH TO 23/162 RPR HR | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/162 | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-27 | 2021-07-27 |  |  | 2021-06-04 | 2021-06-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.170041 | 38.144 | ETL.4100 | 40581672 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510772 | Q2 | T2 DI TRINITY-MAPLE CRK 17/7 RMV PL BUTT | 44401994 | TRINITY-MAPLE CREEK | 017/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-21 | 2022-07-21 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.217174 | 40.7417 | ETL.8170 | 40809959 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510836 | Not Scheduled | EI SPAULDING-SUMMIT 9/306 RPR STRW | 44453252 | SPAULDING-SUMMIT | 009/306 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.495078 | 39.3144 | ETL.8060 | 40668671 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119510888 | Not Scheduled | DI DRUM-SUMMIT #2 13/160L RPR GYWW | 44449908 | DRUM-SUMMIT #2 | 013/160 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44212076 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119510889 | Not Scheduled | T2 DI DRUM-SUMMIT #2 13/160C RPR GYWW | 44449908 | DRUM-SUMMIT #2 | 013/160 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44212077 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510893 | Mar | T3 EI SAN RAMON-MORAGA 5/26 RPL INSULS | 31526414 | SAN RAMON-MORAGA | 005/026 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.0999311 | 37.7964 | ETL.5660 | 40637914 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510900 | Mar | T3 EI MORAGA-CASTRO VALLEY 5/26 RPL INSU | 31526489 | MORAGA-CASTRO VALLEY | 005/026 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.0999311 | 37.7964 | ETL.5250 | 40842335 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510924 | Not Scheduled | T3 EI FULTON-CALISTOGA 5/5 WASH INSW |  | FULTON-CALISTOGA | 005/005 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.500601 | 38.5611 | ETL.6880 | 40769669 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510966 | Not Scheduled | EI T2NT SPAULDING-SUMMIT 16/517 INST MRK | 44453449 | SPAULDING-SUMMIT | 016/517 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2022-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.375736 | 39.3138 | ETL.8060 | 40650068 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119510974 | Not Scheduled | EI SPAULDING-SUMMIT 009/308 RPLC STRW | 31510882 | SPAULDING-SUMMIT | 009/308 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.494066 | 39.3146 | ETL.8060 | 40770712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119511074 | Not Scheduled | EI SPAULDING-SUMMIT 9/309 INST GMKW | 44439439 | SPAULDING-SUMMIT | 009/309 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2022-07-27 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.493589 | 39.3146 | ETL.8060 | 44349532 | Guy Wire-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119511154 | Not Scheduled | DI DRUM-SUMMIT #2 14/173A RPR GYWW | 44449908 | DRUM-SUMMIT #2 | 014/173A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538438 | 39.3116 | ETL.1450 | 40682565 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119511216 | Q4 | DI MIDDLE FRK-GLD HLL 11/91L RPL POLE |  | MIDDLE FORK-GOLD HILL | 011/091 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.764882 | 38.9769 | ETL.5140 | 44553642 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511300 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/515 RPR STRW | 44453252 | SPAULDING-SUMMIT | 016/515 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.377011 | 39.3147 | ETL.8060 | 40602278 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511374 | Not Scheduled | DI GATES-PANOCHE #1 029/140 RPL INSS | 31514618 | GATES-PANOCHE #1 | 029/140 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.434396 | 36.4872 | ETL.4720 | 40631591 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119511576 | Not Scheduled | EI T2NT SPAULDING-SUMMIT 16/513 RMV BUTT | 44409175 | SPAULDING-SUMMIT | 016/513 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2022-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378239 | 39.3156 | ETL.8060 | 40876713 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511649 | Not Scheduled | T3 EI FULTON-CALISTOGA 5/9 RPR STRW |  | FULTON-CALISTOGA | 005/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.504378 | 38.5661 | ETL.6880 | 44647529 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511791 | Not Scheduled | EI T3NT FULTON-CALISTOGA 6/0 RMV DEBRIS |  | FULTON-CALISTOGA | 006/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-27 | 2022-07-27 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.505916 | 38.5661 | ETL.6880 | 40588911 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511855 | Mar | T3 EI SAN RAMON-MORAGA 15/69 RPL INST | 31526414 | SAN RAMON-MORAGA | 015/069 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-03-19 | 2021-03-19 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.0906781 | 37.7874 | ETL.5660 | 40888254 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511860 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/511 RPR GYWW | 44453252 | SPAULDING-SUMMIT | 016/511 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378442 | 39.3169 | ETL.8060 | 40809675 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511867 | Feb | EI T3NT MORAGA-CASTRO VALLEY 6/29 RPR FO | 44623422 | MORAGA-CASTRO VALLEY | 006/029 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-27 | 2022-07-27 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.090665 | 37.7874 | ETL.5250 | 40865513 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119511880 | Not Scheduled | T2 EI CARIBOU-PALERMO 15/121 INST STEP B |  | CARIBOU-PALERMO | 015/121 | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512078 | Q4 | T3 DI MIDDLE FORK-GLD HILL 9/76 RPR SHLS | 44453126 | MIDDLE FORK-GOLD HILL | 009/076 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.5140 | 44236773 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512402 | Not Scheduled | T3 EI FULTON-CALISTOGA 6/1 REFRAME STRW | 31509848 | FULTON-CALISTOGA | 006/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.506421 | 38.5665 | ETL.6880 | 40585441 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512479 | Q3 | EI TESLA-NEWARK #2 10/069 RPR FOND |  | TESLA-NEWARK #2 | 010/069 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 |  |  | 2021-07-23 | 2021-07-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.734695 | 37.6563 | ETL.5354 | 41152614 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512515 | Q3 | EI TESLA-NEWARK #2 9/67 RPR FOND |  | TESLA-NEWARK #2 | 009/067 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 |  |  | 2021-07-23 | 2021-07-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.730927 | 37.6583 | ETL.5354 | 41152612 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512531 | Q3 | EI TESLA-NEWARK #2 10/73 RPL HRDT |  | TESLA-NEWARK #2 | 010/073 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 |  |  | 2021-07-23 | 2021-07-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.742941 | 37.6519 | ETL.5354 | 41152618 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512819 | Q2 | EI T2NT BRIDGEVILLE-COTTONWD 45/3 INS GM | 44477511 | BRIDGEVILLE-COTTONWOOD | 045/353C | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-27 | 2022-07-27 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.108201 | 40.3967 | ETL.1110 | 42603429 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119512860 | Not Scheduled | T2 EI BRIDGEVILLE-COTTONWOOD 45/3 RPR FO |  | BRIDGEVILLE-COTTONWOOD | 045/353 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.108221 | 40.3967 | ETL.1110 | 42603428 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119513399 | Q2 | WV LOS BANOS-GATES #1 43/182 RETAIN WALL | 31521882 | LOS BANOS-GATES #1 | 043/182 | 93Z | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.558023 | 36.5541 | ETL.6000 | 40679555 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119513457 | Not Scheduled | EI T2NT SPAULDING-SUMMIT 13/447 RPL GMK | 44453449 | SPAULDING-SUMMIT | 013/447 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2022-07-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.41679 | 39.3281 | ETL.8060 | 44145239 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119513666 | Mar | T3 EI POTTER VALLEY-WILLITS 5/8 RPL POLE | 31509537 | POTTER VALLEY-WILLITS | 005/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.218048 | 39.3838 | ETL.7820 | 40861071 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-29 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514094 | Mar | T3 EI SN RMN- MRGA 8/36 RPL INSS | 31526414 | SAN RAMON-MORAGA | 008/036 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 |  |  | 2021-03-19 | 2021-03-19 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.082371 | 37.762 | ETL.5660 | 40718490 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514184 | Q2 | T2 DI BRDGVLL-CTTNWD 41/323 RPR INSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 041/323 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.031588 | 40.3828 | ETL.1110 | 40636965 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514233 | Not Scheduled | EI SPAULDING-SUMMIT 9/317 RPL POLE | 31510882 | SPAULDING-SUMMIT | 009/317 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-27 | 2021-07-27 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.490184 | 39.3155 | ETL.8060 | 40771509 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119514264 | Q2 | T2 DI BRDGVLL-CTTNWD 58/425A RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 058/425A | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.337168 | 40.3784 | ETL.1110 | 40676686 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514588 | Q2 | DI WEIMAR #1 4/66L RMV PL BUTT | 44440215 | WEIMAR #1 | 004/066 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-08 | 2021-03-22 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.7560 | 44414828 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514812 | Q2 | DI WEIMAR #1 4/66R RMV PL BUTT | 44449612 | WEIMAR #1 | 004/066 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-08 | 2021-03-22 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.7560 | 44414830 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514816 | Q2 | T2 DI WEIMAR #1 4/66 RPLC INSW | 31512497 | WEIMAR #1 | 004/066 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.923534 | 39.0203 | ETL.7560 | 42568959 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514904 | Q3 | T2NT DI CARIBOU #2 15/6 RMV BUTT |  | CARIBOU #2 | 015/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-23 | 2022-07-23 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.107722 | 40.0231 | ETL.6280 | 40826428 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119514907 | Q3 | T2 DI CARIBOU #2 15/6 RPR GYWW |  | CARIBOU #2 | 015/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-23 | 2021-07-23 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.107722 | 40.0231 | ETL.6280 | 40826428 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515012 | Q2 | T2 DI BRDGVLL-CTTNWD 037/296 RPR WPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/296 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.96706 | 40.3657 | ETL.1110 | 44561172 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515013 | Q2 | T2 DI BRDGVLL-CTTNWD 037/296 RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/296 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.96706 | 40.3657 | ETL.1110 | 44561171 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515016 | Q2 | T2 DI BRDGVLL-CTTNWD 037/296 RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/296 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.96706 | 40.3657 | ETL.1110 | 44561172 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515037 | Q3 | EI HAMILTON BRANCH-CHESTER 10/209 RPR IN | 44586070 | HAMILTON BRANCH-CHESTER | 010/209 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-08-31 | 2021-08-30 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-121.1956434 | 40.3116 | ETL.7000 | 40628282 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515044 | Mar | T3 EI MORAGA-CASTRO VALLEY 4/21 RPL INS | 31526489 | MORAGA-CASTRO VALLEY | 004/021 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1092318 | 37.8133 | ETL.5250 | 40615159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515079 | Mar | T3 EI MORAGA-CASTRO VALLE 15/69 RPL INST | 31526489 | MORAGA-CASTRO VALLEY | 006/029 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.090596 | 37.7874 | ETL.5250 | 40888256 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515093 | Q2 | T2 DI BRDGVLL-CTTNWD 037/296 RPR CRSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/296 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.96706 | 40.3657 | ETL.1110 | 44561171 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515094 | Q2 | T2NT DI BRDGVLL-CTTNWD 037/296 INST MRKW | 44404807 | BRIDGEVILLE-COTTONWOOD | 037/296 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.96706 | 40.3657 | ETL.1110 | 44561171 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515096 | Q2 | T3NT DI KNOCTI-EGLE RCK 7/8 RMV PL BUTT | 44610613 | KONOCTI-EAGLE ROCK | 007/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2022-07-28 |  |  | 2021-05-07 | 2021-05-07 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.763855 | 38.9108 | ETL.6861 | 40876732 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515296 | Q3 | T3 DI BRDGVLL-GRBERVLL 10/0 RPR SPLW | 44300097 | BRIDGEVILLE-GARBERVILLE | 010/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.730073 | 40.3661 | ETL.6220 | 40591074 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515321 | Q3 | T3 DI BRDGVL-GRBRVL 5/1 RPR SPLW | 44300097 | BRIDGEVILLE-GARBERVILLE | 005/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.763672 | 40.4291 | ETL.6220 | 40600503 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515421 | Q3 | T3 DI BRDGVLL-GRBERVLL 010/008 RPL DAMW | 44300097 | BRIDGEVILLE-GARBERVILLE | 010/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-24 | 2021-01-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.725082 | 40.3624 | ETL.6220 | 40862836 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515556 | Q4 | EI LOS BANOS-MIDWAY #2 137/566 RMV VEG |  | LOS BANOS-MIDWAY #2 | 137/566 | HNA | F | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2022-07-28 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.521636 | 35.486 | ETL.6010 | 40818583 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119515572 | Q3 | T3NT DI BRDGVL-GRBRVL 8/5 RMV DEBRIS | 44299809 | BRIDGEVILLE-GARBERVILLE | 008/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-27 | 2022-07-27 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.742676 | 40.3888 | ETL.6220 | 40768707 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515733 | Not Scheduled | EI T3NT MORAGA-CASTRO VALLEY 4/20 PAINT | 43744386 | MORAGA-CASTRO VALLEY | 004/020 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2022-07-28 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.111109 | 37.8173 | ETL.5250 | 40596489 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515753 | Q4 | MAPLE CREEK-HOOPA 003/009 RPR INSS | 44453324 | MAPLE CREEK-HOOPA | 003/009 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-07-28 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.828095 | 40.8057 | ETL.7490 | 44838168 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515799 | Q2 | T2 DI BRDGVLL-CTTNWD 42/339C RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 042/339C | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.06425 | 40.3909 | ETL.1110 | 42603425 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515864 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/507 INST MRKW | 44461263 | SPAULDING-SUMMIT | 016/507 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2022-07-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.37884 | 39.3192 | ETL.8060 | 44565373 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119515934 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/507 INST MRKW | 44461263 | SPAULDING-SUMMIT | 016/507 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2022-07-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.37884 | 39.3192 | ETL.8060 | 44565382 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516160 | Q2 | T2 DI BRDGVLL-CTTNWD 42/339B RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 042/339B | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.064259 | 40.3909 | ETL.1110 | 42603424 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516425 | Not Scheduled | T2 DI CLGT-SMRTVL #2 0/7A RMV PL BUTT | 44439115 | COLGATE-SMARTVILLE #2 | 000/007A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-23 | 2022-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.193705 | 39.3291 | ETL.6520 | 40826819 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516429 | Mar | T2 DI SPAULDING-SUMMIT 18/593 BENT STL | 44453004 | SPAULDING-SUMMIT | 018/593 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.337964 | 39.3103 | ETL.8060 | 40618244 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516522 | Not Scheduled | T2 EI SPAULDING-SUMMIT 16/504 RMV ANCW | 44461262 | SPAULDING-SUMMIT | 016/504 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2021-07-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379007 | 39.3208 | ETL.8060 | 40602277 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516647 | Mar | EI NEWARK-JARVIS #1 5/36 RMV STEP |  | NEWARK-JARVIS #1 | 005/036 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.905256 | 37.533 | ETL.3020 | 40819647 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516651 | Mar | EI NEWARK-JARVIS #1 5/37 RMV STEP |  | NEWARK-JARVIS #1 | 005/037 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.902169 | 37.5354 | ETL.3020 | 40805694 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516652 | Mar | EI NEWARK-JARVIS #1 5/35 RMV STEP |  | NEWARK-JARVIS #1 | 005/035 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.906426 | 37.5321 | ETL.3020 | 40745974 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119516827 | Q2 | T3 DI KONOCTI-EAGLE RCK 7/7 RMV PL BUTT | 44610613 | KONOCTI-EAGLE ROCK | 007/007 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2021-01-28 |  |  | 2021-05-07 | 2021-05-07 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.764858 | 38.9105 | ETL.6861 | 40808796 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517324 | Not Scheduled | EI T3NT MORAGA-CASTRO VALLEY 5/23 PAINT | 43744386 | MORAGA-CASTRO VALLEY | 005/023 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-28 | 2022-07-28 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.104971 | 37.8044 | ETL.5250 | 40654420 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517326 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/083 REPLUMB | 44409109 | COLGATE-CHALLENGE | 004/083 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.162487 | 39.3822 | ETL.6480 | 40655138 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517422 | Q3 | T3 DI BRDGVLL-GRBRVLL 9/11 RPR SPLW | 44300097 | BRIDGEVILLE-GARBERVILLE | 009/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-01-28 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.744594 | 40.4048 | ETL.6220 | 40611410 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517441 | Not Scheduled | T3 EI FULTON-CALISTOGA 8/9 RPR GYWW | 44597303 | FULTON-CALISTOGA | :008/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.604334 | 38.7105 | ETL.6880 | 44928868 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517497 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/084 RPR POLE | 44409109 | COLGATE-CHALLENGE | 004/084 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.162308 | 39.3829 | ETL.6480 | 44695489 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517684 | Q2 | EI LOS BANOS-GATES #1 1/6 BENT STL | 44571722 | LOS BANOS-GATES #1 | 001/006 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2021-07-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-121.011433 | 37.035 | ETL.6000 | 40815929 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119517702 | Q2 | T2 DI BRDGEVLLE-CTTONWD 57/422B RPR GYWS | 44143775 | BRIDGEVILLE-COTTONWOOD | 057/422 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.321428 | 40.3765 | ETL.1110 | 42603440 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517761 | Q2 | T2 DI BRDGVLLE-CTTNWD 57/422A RPR GYWS | 44143775 | BRIDGEVILLE-COTTONWOOD | 057/422A | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.321469 | 40.3764 | ETL.1110 | 40761791 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119517865 | Q2 | EI LOS BANOS-GATES #1 1/7 BENT STL | 44571722 | LOS BANOS-GATES #1 | 001/007 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2021-07-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-121.008365 | 37.0303 | ETL.6000 | 40819230 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119517896 | Not Scheduled | T2 DI DRUM-SUMMIT #1 23/276 RPL INSS | 31521959 | DRUM-SUMMIT #1 | 023/276 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.391749 | 39.3112 | ETL.1440 | 40784572 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518203 | Q4 | T3 DI MIDDLE FRK-GLD HLL 8/68 RPR SHLS | 44403355 | MIDDLE FORK-GOLD HILL | 008/068 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-01-23 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.724256 | 39.0014 | ETL.5140 | 40870401 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518838 | Q3 | EI TESLA-NEWARK #2 11/80 MASTIC |  | TESLA-NEWARK #2 | 011/080 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2022-07-28 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.758608 | 37.6435 | ETL.5354 | 41152625 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518839 | Q3 | EI TESLA-NEWARK #2 11/81 RPR FOND |  | TESLA-NEWARK #2 | 011/081 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-07-23 | 2021-07-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.761181 | 37.6421 | ETL.5354 | 41152626 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518843 | Q3 | EI TESLA-NEWARK #2 11/081 BENT STL |  | TESLA-NEWARK #2 | 011/081 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.761181 | 37.6421 | ETL.5354 | 41152626 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518848 | Q3 | EI TESLA-NEWARK #2 17/113 MASTIC | 44226389 | TESLA-NEWARK #2 | 017/113 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-28 | 2022-07-28 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.836768 | 37.599 | ETL.5354 | 41152659 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518860 | Q3 | EI TESLA-NEWARK #2 12/82 MASTIC |  | TESLA-NEWARK #2 | 012/082 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2022-07-28 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.763454 | 37.6409 | ETL.5354 | 41152627 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518870 | Q3 | EI TESLA-NEWARK #2 17/114 MASTIC | 44226389 | TESLA-NEWARK #2 | 017/114 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-28 | 2022-07-28 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.838934 | 37.5977 | ETL.5354 | 41152660 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119518946 | Mar | T3 EI LAURELES-OTTER 11/005 RPR ANCHOR | 44438214 | LAURELES-OTTER | 011/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.838869 | 36.3981 | ETL.7380 | 40770270 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119519102 | Q2 | WV HUMBOLDT #1 10/9 INS INSW | 31492627 | HUMBOLDT #1 | 010/009 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-04-17 | 2021-04-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-124.0593263 | 40.8983 | ETL.7113 | 40900386 | Insulator-Wood | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119519191 | Not Scheduled | T2 FULTON-PUEBLO 38/196 INST JUMS INSS | 31505500 | FULTON-PUEBLO | 038/196 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.6812942 | 38.4966 | ETL.1600 | 40835398 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119519909 | Not Scheduled | T2 EI SPAULDING-SUMMIT 14/463 RPLC STRW | 31508176 | SPAULDING-SUMMIT | 014/463 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-28 | 2021-07-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.404566 | 39.3285 | ETL.8060 | 40826206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119519927 | Q3 | EI HAMILTON BRNCH-CHSTR 10/210 INSU WASH |  | HAMILTON BRANCH-CHESTER | 010/210 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-08-31 | 2021-08-30 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-121.1967064 | 40.312 | ETL.7000 | 40735131 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119520342 | Mar | T3 EI SAN RAMON-MORAGA 17/77 RPL INSS | 31526414 | SAN RAMON-MORAGA | 017/077 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-19 | 2021-03-19 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.108903 | 37.813 | ETL.5660 | 40615158 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119520433 | Q3 | T3 DI BRDGVLL-GRBRVLL 2/6 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 002/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.796121 | 40.4536 | ETL.6220 | 40810909 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119520965 | Feb | EI RIO DELL JCT-BRIDGEVILE 36/6 RPR GYWW | 44261478 | RIO DELL JCT-BRIDGEVILLE | 036/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.844658 | 40.4626 | ETL.7850 | 40826290 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522193 | Q2 | EI LOS BANOS-MIDWAY #2 131/540 INS MKRT | 44630410 | LOS BANOS-MIDWAY #2 | 131/540 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2022-07-29 |  |  | 2021-05-20 | 2021-05-20 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.584802 | 35.5636 | ETL.6010 | 40592990 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119522306 | Feb | EI RIO DELL JCT-BRIDGEVILL 37/1 RPR GYWW | 44261478 | RIO DELL JCT-BRIDGEVILLE | 037/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.838483 | 40.4638 | ETL.7850 | 40584732 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522549 | Q2 | T2 EI PHILO JCT-ELK 13/5 RPR WDPKR | 44610684 | PHILO JCT-ELK | 013/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.36 | 39.0224 | ETL.7780 | 40762796 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522656 | Mar | EI FULTON-HOPLAND 009/008 RPLC STRW | 31512495 | FULTON-HOPLAND | 009/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.84408 | 38.6109 | ETL.6890 | 40861100 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522671 | Not Scheduled | EI E1 FULTON-HOPLAND 010/000 RPLC STRW | 31512495 | FULTON-HOPLAND | :010/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.843665 | 38.614 | ETL.6890 | 40587774 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522674 | Mar | T2 EI FULTON-HOPLAND 009/009 RPLC STRW | 31512495 | FULTON-HOPLAND | 009/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.844037 | 38.6119 | ETL.6890 | 40875978 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522723 | Not Scheduled | T2 EI MDWY-WHRLWND 51/210 INST FNC AND | 31510049 | MIDWAY-WHIRLWIND | 051/210 | 71Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2021-07-29 |  |  |  | 2021-03-22 |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.700503 | 35.078 | ETL.6030 | 40586574 | Fence / Gate | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522730 | Not Scheduled | T2NT EI MIDWAY-WHIRLWIND 51/209 RPR ROAD | 44644398 | MIDWAY-WHIRLWIND | 051/209 | CHS | F | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2022-07-29 |  |  |  | 2021-05-01 |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.702835 | 35.0797 | ETL.6030 | 40871795 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119522962 | Q2 | EI MUSTANG SW STA-GREGG 14/61A RPR FOND | 44571493 | GATES-GREGG | 014/061A | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2021-07-29 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900684 | 36.2423 | ETL.4700 | 44190845 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119522963 | Not Scheduled | EI MUSTANG SW STA-GREGG 14/61A PAINT | 44507420 | GATES-GREGG | 014/061A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2022-07-29 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.900684 | 36.2423 | ETL.4700 | 44190845 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119523426 | Not Scheduled | EI MUSTANG SW STA-GREGG 14/61B PAINT | 44507420 | GATES-GREGG | 014/061B | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2022-07-29 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.900682 | 36.2423 | ETL.4700 | 44191211 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119523427 | Q2 | EI MUSTANG SW STA-GREGG 14/61B RPR FOND | 44571493 | GATES-GREGG | 014/061B | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2022-07-29 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900682 | 36.2423 | ETL.4700 | 44191211 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119523534 | Not Scheduled | EI DIVIDE-CABRILLO #2 3/52 RPL INSW |  | DIVIDE-CABRILLO #2 | 003/052 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-07-29 | [9 empty] | South | WSIP | [6 empty] | '-120.439306 | 34.7725 | ETL.1370 | 40618680 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119523558 | Not Scheduled | EI MUSTANG SW STA-GREGG 14/61C PAINT | 44507420 | GATES-GREGG | 014/061C | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2022-07-29 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.90068 | 36.2422 | ETL.4700 | 44190853 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119523559 | Q2 | EI MUSTANG SW STA-GREGG 14/61C RPR FOND | 44571493 | GATES-GREGG | 014/061C | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2021-07-29 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.90068 | 36.2422 | ETL.4700 | 44190853 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119523661 | Not Scheduled | T3 EGLE RCK-FLTN-SLVRDO 18/77 INST DMPS |  | EAGLE ROCK-FULTON-SILVERADO | 018/077 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 | [5 empty] | TLN/TLQ - should be TLN |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62968 | 38.5194 | ETL.4392 | 41129271 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119523706 | Feb | T3 EAGLE ROCK-FLTN-SLVRDO 3/0 INST JMPRS | 31445553 | EAGLE ROCK-FULTON-SILVERADO | 003/016B | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-02-28 | 2021-02-28 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.803694 | 38.8034 | ETL.4392 | 40740504 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119523830 | Feb | T2 WV DRUM-RIO OSO #1 21/163 INST JUMP | 31505600 | DRUM-RIO OSO #1 | 021/163 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.097305 | 39.1054 | ETL.1420 | 40659461 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119523893 | Feb | T2 WV DRUM-RIO OSO #1 18/144 INST JUMP | 31505600 | DRUM-RIO OSO #1 | 018/144 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.048021 | 39.1249 | ETL.1420 | 40764900 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524056 | Not Scheduled | T3 DIABLO-MIDWAY #2 26/106 RPR INSS |  | DIABLO-MIDWAY #2 | 026/106 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.398113 | 35.1631 | ETL.5970 | 40818890 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524165 | Not Scheduled | EI SPAULDING-SUMMIT 8/278 RPR GYWW | 44470932 | SPAULDING-SUMMIT | 008/278 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2021-07-29 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.511695 | 39.3142 | ETL.8060 | 40618268 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119524252 | Mar | EI LAURELES-OTTER 10/2A RPL ANCW | 31513712 | LAURELES-OTTER | 010/002A | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-07-29 |  |  | 2021-03-30 | 2021-03-30 | [5 empty] | South | WSIP | [6 empty] | '-121.8266175 | 36.4068 | ETL.7380 | 44562892 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524253 | Mar | EI LAURELES-OTTER 10/2A RPL ANCW | 31513712 | LAURELES-OTTER | 010/002A | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-07-29 |  |  | 2021-03-30 | 2021-03-30 | [5 empty] | South | WSIP | [6 empty] | '-121.8266175 | 36.4068 | ETL.7380 | 44562702 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524279 | Not Scheduled | EI TESLA-NEWARK #2 13/88 REPAINT | 43753285 | TESLA-NEWARK #2 | 013/088 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-29 | 2022-07-29 | [9 empty] | Central | WSIP | [6 empty] | '-121.781421 | 37.6312 | ETL.5354 | 41152633 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524338 | Q3 | EI SPAULDING-SUMMIT 8/277 RMV VEG |  | SPAULDING-SUMMIT | 008/277 | HNA | E | 2020_(1b) Lines with special commitments | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 |  |  | 2021-07-29 | 2021-07-01 |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.512754 | 39.3144 | ETL.8060 | 40876689 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119524743 | Feb | T2 WV DRUM-RIO OSO #1 26/193 RPR INSS | 44461298 | DRUM-RIO OSO #1 | 026/193 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.182912 | 39.0711 | ETL.1420 | 40654200 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524806 | Not Scheduled | EI T3NT FRNCH MDWS-MDDLE FRK 4/80 INST G | 44409118 | FRENCH MEADOWS-MIDDLE FORK | 004/080 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-29 | 2022-07-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.46472 | 39.0447 | ETL.6870 | 40664841 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524811 | Not Scheduled | T3 EI FRNCH MDWS-MDDL FRK 4/0 CANCEL | 44409116 | FRENCH MEADOWS-MIDDLE FORK | 004/082 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-29 | 2021-01-29 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.466787 | 39.0446 | ETL.6870 | 40751842 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524812 | Not Scheduled | T3 EI FRNCH MDWS-MDDL FRK 4/0 RMV VEG |  | FRENCH MEADOWS-MIDDLE FORK | 004/080 | HNA | E | 2020_(3) On high spread structure |  | 2020-07-29 | 2021-01-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.46472 | 39.0447 | ETL.6870 | 40664841 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524872 | Feb | T3 EAGLE RCK-FLTN-SLVRDO 7/32 RPL JUMS |  | EAGLE ROCK-FULTON-SILVERADO | 007/032 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-29 | 2021-01-29 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.751686 | 38.6296 | ETL.4392 | 44951587 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524937 | Feb | T3 COLGATE-GRASS VALLEY 05/132 REFRAME | 31423045 | COLGATE-GRASS VALLEY | 005/132 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-01-29 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.107617 | 39.3018 | ETL.6490 | 40823557 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524938 | Feb | T3 COLGATE-GRASS VALLEY - 60 kV_006/157 | 44409111 | COLGATE-GRASS VALLEY | 006/157 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.096818 | 39.2859 | ETL.6490 | 40612744 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119524969 | Q2 | T2 WV BRDGVLLE-CTTNWD 23/203 INST JUMP | 31515458 | BRIDGEVILLE-COTTONWOOD | 023/203 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.7049872 | 40.3734 | ETL.1110 | 44820253 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119525000 | Q2 | T2 WV BRDGVLLE-CTTNWD 23/203 INST ANCW |  | BRIDGEVILLE-COTTONWOOD | 023/203 | 93E | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-29 | 2021-07-29 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.704974 | 40.3734 | ETL.1110 | 44820330 | Anchor-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-16 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119526143 | Not Scheduled | T2 EI CARIBOU-PALERMO 6/046 RPR MEMBR |  | CARIBOU-PALERMO | :006/046 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219048 | 40.0305 | ETL.3190 | 40910288 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119526657 | Q3 | T3 DI BRDGVLL-GRBRVLL 8/10 RPR STRW WDPK | 44299806 | BRIDGEVILLE-GARBERVILLE | 008/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742211 | 40.3847 | ETL.6220 | 40591068 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119527634 | Feb | EI RIO DELL JCT-BRIDGEVILL 37/5 RPR GYWW | 44261478 | RIO DELL JCT-BRIDGEVILLE | 037/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-02-16 | 2021-02-16 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.834831 | 40.4673 | ETL.7850 | 40750382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119527739 | Not Scheduled | EI T3NT CASTRO VLLY-NWRK 8/48 RMV VEG RD |  | CASTRO VALLEY-NEWARK | 008/048 | CHS | F | 2020_(3) On high spread structure |  | 2020-07-30 | 2022-07-30 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-121.952818 | 37.6102 | ETL.4450 | 40599996 | Road | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119527745 | Q2 | EI T3NT TSSJR-NWRK 18/087 RPR FOND | 44624394 | TASSAJARA-NEWARK | 018/087 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-30 | 2022-07-30 |  |  | 2021-06-19 | 2021-06-14 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.9528307 | 37.6102 | ETL.5920 | 40634572 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119527802 | Not Scheduled | EI DIVIDE-CABRILLO #1 14/200 RPR SPLW |  | DIVIDE-CABRILLO #1 | 014/200 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.4387144 | 34.6437 | ETL.1380 | 40578907 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119527947 | Q3 | T2 DI CARIBOU-PLUMAS JCT ;9/1 RMV DEBRIS | 44408852 | CARIBOU-PLUMAS JCT | ;009/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-30 | 2022-07-30 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.934023 | 39.9402 | ETL.6290 | 44168157 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528042 | Q2 | T2 EI CRESTA-RIO OSO_029/240 RPL INSS | 31500129 | CRESTA-RIO OSO | 029/240 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.53482 | 39.5491 | ETL.4590 | 41083101 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528190 | Not Scheduled | T2 DRUM-SUMMIT #1 21/249L RPL POLE | 31453474 | DRUM-SUMMIT #1 | 021/249 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.428923 | 39.3174 | ETL.1440 | 44762485 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528200 | Not Scheduled | DRUM-SUMMIT #2 13/159L RPL POLE | 31521945 | DRUM-SUMMIT #2 | 013/159 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556835 | 39.3203 | ETL.1450 | 44561430 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119528210 | Not Scheduled | T2 DRUM-SUMMIT #2 27/324L RPL POLE | 31471241 | DRUM-SUMMIT #2 | 027/324 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.335204 | 39.3114 | ETL.1450 | 44552577 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528325 | Feb | EI RIO DLL JCT-BRIDGEVILL 38/1R RPL POLE | 31508280 | RIO DELL JCT-BRIDGEVILLE | 038/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.825885 | 40.4688 | ETL.7850 | 44403577 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528350 | Feb | EI RIO DELL JCT-BRIDGEVILL 38/1C RPL PO | 31508280 | RIO DELL JCT-BRIDGEVILLE | 038/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.825885 | 40.4688 | ETL.7850 | 44403576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528461 | Not Scheduled | EI DIVIDE-CABRILLO #2 2/37 RPL INSW | 31513655 | DIVIDE-CABRILLO #2 | 002/037 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.442261 | 34.7912 | ETL.1370 | 40757612 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528502 | Not Scheduled | EI NT _001/055 RMV VEG |  | SPAULDING-SUMMIT | 001/055 | HNA | F | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2022-07-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.6232641 | 39.3163 | ETL.8060 | 44420797 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119528515 | Not Scheduled | T2NT DI COLGATE-CHALLENGE 1/23 RMV BUTT | 44461285 | COLGATE-CHALLENGE | 001/023 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2022-07-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.189466 | 39.3444 | ETL.6480 | 40594206 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528570 | Not Scheduled | EI DIVIDE-CABRILLO #1 2/35 RPL INSW | 31513649 | DIVIDE-CABRILLO #1 | 002/035 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.442411 | 34.7912 | ETL.1380 | 40757625 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528662 | Not Scheduled | T2 EI DRUM-SUMMIT #2 27/324R RPL POLE |  | DRUM-SUMMIT #2 | 027/324 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.335204 | 39.3114 | ETL.1450 | 44552398 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528677 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/94 RPR CONDW | 44409109 | COLGATE-CHALLENGE | 004/094 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.1606468 | 39.3899 | ETL.6480 | 40787321 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528679 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/94 REFRAME | 44409109 | COLGATE-CHALLENGE | 004/094 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.160634 | 39.3899 | ETL.6480 | 40757260 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528681 | Not Scheduled | DRUM-SUMMIT #2 13/159R RPL POLE | 31521945 | DRUM-SUMMIT #2 | 013/159 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556835 | 39.3203 | ETL.1450 | 44561376 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119528685 | Not Scheduled | DRUM-SUMMIT #2 13/159C RPL POLE | 31521945 | DRUM-SUMMIT #2 | 013/159 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556835 | 39.3203 | ETL.1450 | 44561344 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119528687 | Not Scheduled | T2 DRUM-SUMMIT #1 21/249R RPL POLE | 31453474 | DRUM-SUMMIT #1 | 021/249 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.428923 | 39.3174 | ETL.1440 | 44762486 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528690 | Not Scheduled | T2 DRUM-SUMMIT #1 21/249C RPL POLE | 31453474 | DRUM-SUMMIT #1 | 021/249 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.428923 | 39.3174 | ETL.1440 | 44762487 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528696 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/95 RPR GYWW | 44409109 | COLGATE-CHALLENGE | 004/095 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.160378 | 39.3906 | ETL.6480 | 40766537 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528766 | Q2 | T3 DI KONOCTI-EAGLE ROCK 7/1 RPR STRW | 44610613 | KONOCTI-EAGLE ROCK | 007/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-05-07 | 2021-05-07 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.770075 | 38.9083 | ETL.6861 | 40600722 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119528987 | Q2 | EI MUSTNG SW STA-GREGG 24/103 BENT STEEL | 44571494 | GATES-GREGG | 024/103 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.889539 | 36.3665 | ETL.4700 | 40659469 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119529027 | Q4 | T2 EI MAPLE CREEK-HOOPA 03/1 RPR STRW | 44453147 | MAPLE CREEK-HOOPA | 003/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.833985 | 40.7956 | ETL.7490 | 40586842 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529028 | Not Scheduled | EI DIVIDE-CABRILLO #1 3/53 RPL INSW | 31513651 | DIVIDE-CABRILLO #1 | 003/053 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.439464 | 34.7725 | ETL.1380 | 40668990 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529029 | Q4 | EI T2NT MAPLE CREEK-HOOPA 003/001 RMV BU | 44301081 | MAPLE CREEK-HOOPA | 003/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-30 | 2022-07-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.833985 | 40.7956 | ETL.7490 | 40586842 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529053 | Mar | EI FULTON-HOPLAND 11/8 RPR WDPKR | 44579280 | FULTON-HOPLAND | 011/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.85745 | 38.6314 | ETL.6890 | 40874585 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529177 | Not Scheduled | EI DIVIDE-CABRILLO #1 2/40 RPL INSW | 31513651 | DIVIDE-CABRILLO #1 | 002/040 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.441583 | 34.7855 | ETL.1380 | 40598008 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529402 | Not Scheduled | EI DIVIDE-CABRILLO #1 3/41 RPL INSW | 31513651 | DIVIDE-CABRILLO #1 | 003/041 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.441438 | 34.7849 | ETL.1380 | 40602558 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529517 | Q2 | EI MUSTANG SW STA-GREGG 25/105 RPR FOND | 44571494 | GATES-GREGG | 025/105 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.889544 | 36.3733 | ETL.4700 | 40746607 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119529657 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/97 RPR HRDWW | 44409109 | COLGATE-CHALLENGE | 004/097 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.159607 | 39.3936 | ETL.6480 | 40866891 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529674 | Not Scheduled | T3 EI COLGATE-CHALLENGE 4/97 RPR CONDW | 44409109 | COLGATE-CHALLENGE | 004/097 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.1596202 | 39.3936 | ETL.6480 | 40891309 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529801 | Q3 | EI MIDWAY-WHIRLWIND 20/084 TRIM VEGN |  | MIDWAY-WHIRLWIND | 020/084 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-30 | 2021-07-30 |  |  | 2021-07-15 | 2021-07-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.159147 | 35.2839 | ETL.6030 | 40749769 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119529826 | Q3 | T2 DI BRDGVL-GRBRVL 12/1 RMV DEBRIS | 44470704 | BRIDGEVILLE-GARBERVILLE | 012/001 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-30 | 2022-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.72264 | 40.3419 | ETL.6220 | 40600497 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529833 | Q3 | EI BRIDGEVILLE-GARBERVILLE 0/7 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 000/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.791454 | 40.4753 | ETL.6220 | 40810318 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529835 | Q3 | EI BRIDGEVLE-GRBRVIL 00/09 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 000/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.795594 | 40.4741 | ETL.6220 | 40862501 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529836 | Q3 | EI BRIDGEVILLE-GARBERVLLE 0/006 RPR HDRW | 44453320 | BRIDGEVILLE-GARBERVILLE | 000/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.789077 | 40.4761 | ETL.6220 | 40810905 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529928 | Feb | T3 EI RND MTN-CTTNWD #3 27/224 RPL INSUL | 31504993 | ROUND MTN-COTTONWOOD #3 | 027/224 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940901 | 40.789 | ETL.5650 | 40755447 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119529929 | Not Scheduled | T3 EI RND MTN-CTTNWD #3 027/2 RMV CLMB S | 43932111 | ROUND MTN-COTTONWOOD #3 | 027/224 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940901 | 40.789 | ETL.5650 | 40755447 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119530046 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 27/2 RPL HRDWT | 43932111 | ROUND MTN-COTTONWOOD #3 | 027/225 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.941724 | 40.788 | ETL.5650 | 40755338 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119530047 | Not Scheduled | EI T3NT RND MTN-CTTNWD #3 27/225 RPR REP | 43755801 | ROUND MTN-COTTONWOOD #3 | 027/225 | ICQ | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-30 | 2022-07-30 | [6 empty] | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.941724 | 40.788 | ETL.5650 | 40755338 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119530062 | Feb | T3 EI RND MTN-CTTNWD #3 27/225 RPR HRD | 44624619 | ROUND MTN-COTTONWOOD #3 | 027/225 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.941724 | 40.788 | ETL.5650 | 40755338 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119530063 | Not Scheduled | T3 EI RND MTN-CTTNWD #3 27/225 RMV CLB S | 43932111 | ROUND MTN-COTTONWOOD #3 | 027/225 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.941724 | 40.788 | ETL.5650 | 40755338 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119530826 | Q4 | T2 WV MAPLE CREEK-HOOPA 0/12 INS DMPRS | 44453324 | MAPLE CREEK-HOOPA | 000/012 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.859778 | 40.772 | ETL.7490 | 44969780 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119531065 | Q2 | T2 EI HAT CREEK #1-WSTWD 35/688 REFRAME | 31514136 | HAT CREEK #1-WESTWOOD | 035/688 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.075093 | 40.5703 | ETL.7030 | 40815872 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533518 | Mar | T2 DI KILARC-DESCHUTES 15/317 RPR SPLW | 44406470 | KILARC-DESCHUTES | 015/317 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.095541 | 40.5639 | ETL.7300 | 40770413 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533519 | Mar | T2 DI KILARC-DESCHUTES 15/317 RMV BUTT | 44406470 | KILARC-DESCHUTES | 015/317 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2022-07-28 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.095541 | 40.5639 | ETL.7300 | 40770413 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533669 | Q3 | T3NT DI BRDGVLE-GRBRVLE 6/14 RMV DEBRIS | 44299809 | BRIDGEVILLE-GARBERVILLE | 006/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-30 | 2022-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.747542 | 40.4068 | ETL.6220 | 40769370 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533704 | Q2 | T3NT DI KONOCTI MIDDLTWN 27/9 RMV DEBRIS | 44610651 | KONOCTI-MIDDLETOWN | 027/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-30 | 2022-07-30 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.65038 | 38.9078 | ETL.6380 | 40875523 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533774 | Mar | T2 DI EAGLE RCK-CRTN :13/15 REFRAME | 31513195 | EAGLE ROCK-CORTINA | :013/015 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.611238 | 38.919 | ETL.1470 | 40801997 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533783 | Q4 | T3 DI MAPLE CREK-HOPA 25/3 RPL POLE | 31510885 | MAPLE CREEK-HOOPA | 025/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.646872 | 41.0148 | ETL.7490 | 40679298 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533787 | Q2 | T3 DI UKH-HPLND-CLOVERDLE 15/4 RPR STRW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 015/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.01863 | 38.8634 | ETL.4050 | 43250126 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533794 | Q2 | EI MUSTANG SW STA-GREGG 25/106 RPR FOND | 44571494 | GATES-GREGG | 025/106 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-07-31 | 2022-07-31 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.889546 | 36.3768 | ETL.4700 | 40805372 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119533879 | Feb | EI RIO DELL JCT-BRIDGEVILE 39/7 RPL PL | 31514233 | RIO DELL JCT-BRIDGEVILLE | 039/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.797157 | 40.4737 | ETL.7850 | 40808362 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-12-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533912 | Q3 | T3NT DI BRDGVL-GRBRVL 1/9 RMV BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 001/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-30 | 2022-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.801585 | 40.4628 | ETL.6220 | 40862503 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533931 | Mar | T2NT DI EGL ROCK-CORTINA :12/3 INS MRKW |  | EAGLE ROCK-CORTINA | :012/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-30 | 2022-07-30 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.618203 | 38.9133 | ETL.1470 | 41176415 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119533936 | Q2 | T3 DI KONOCTI MIDDLETOWN 24/1A RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 024/001A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-01-30 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.713601 | 38.9219 | ETL.6380 | 40577273 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534065 | Feb | EI RIO DELL JCT-BRIDGEVILE 39/8 RPR GYWW | 44261478 | RIO DELL JCT-BRIDGEVILLE | 039/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.795674 | 40.4741 | ETL.7850 | 40861026 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534176 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 0/14B REPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 000/014 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.203254 | 39.3277 | ETL.6520 | 42562718 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534247 | Q4 | T3 DI MAPLE CREEK-HOOPA 23/1 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 023/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.639747 | 40.9883 | ETL.7490 | 40586865 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534333 | Not Scheduled | T2 DI CLGTE-SMRTVILLE #2 0/14A RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 000/014A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.203227 | 39.3277 | ETL.6520 | 40772189 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534445 | Q4 | T3 DI MAPLE CREEK-HOOPA 22/11 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 022/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.640275 | 40.986 | ETL.7490 | 44660734 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534559 | Not Scheduled | T3 EI DRM-GRSS VLLY-WMR B021/481 RPR GYW | 44410419 | DRUM-GRASS VALLEY-WEIMAR | B021/481 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.004732 | 39.1871 | ETL.6760 | 40824338 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534578 | Not Scheduled | T2 DI CLGTE-SMRTVILLE #2 0/14C RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 000/014C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-23 | 2021-07-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.203277 | 39.3277 | ETL.6520 | 42562719 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534689 | Q2 | EI LOS BANOS-MDWAY #2 124/512 INST MRKS | 44612466 | LOS BANOS-MIDWAY #2 | 124/512 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-31 | 2022-07-31 |  |  | 2021-05-20 | 2021-05-20 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.65337 | 35.6485 | ETL.6010 | 40684247 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 37 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119534763 | Q3 | T3NT EI DRUM HIGGINS 4/48 RMV ROAD VEGN | 44591221 | DRUM-HIGGINS | 004/048 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2022-07-31 |  |  | 2021-08-31 | 2021-08-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8316966 | 39.2144 | ETL.4393 | 44172174 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534834 | Q4 | EI NT LOS BANOS-MIDWAY #2 124/511 RMV VE |  | LOS BANOS-MIDWAY #2 | 124/511 | HNA | F | 2020_(1b) Lines with special commitments |  | 2020-07-31 | 2022-07-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.655489 | 35.6511 | ETL.6010 | 40587776 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119534835 | Not Scheduled | EI T2NT SPAULDING-SUMMIT 15/493 CANCEL | 44440214 | SPAULDING-SUMMIT | 015/493 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-31 | 2022-07-31 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380982 | 39.3277 | ETL.8060 | 40770700 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534882 | Not Scheduled | T2 DI CARIBOU-PALERMO :004/037 INS HRDT |  | CARIBOU-PALERMO | :004/037 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.216388 | 40.0451 | ETL.3190 | 40907002 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119534973 | Q3 | T2 DI BRDGVL-GRBRVL 11/12 RPR SPLW | 44453320 | BRIDGEVILLE-GARBERVILLE | 011/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.720529 | 40.3445 | ETL.6220 | 40698440 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535343 | Q3 | EI BRIDGEVILLE-GARBERVLLE 15/7 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.73589 | 40.2978 | ETL.6220 | 44415544 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535344 | Q3 | EI BRIDGEVILLE-GARBERVILLE 14/12 REFRAME | 31514123 | BRIDGEVILLE-GARBERVILLE | 014/012 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.736491 | 40.3058 | ETL.6220 | 40698372 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535352 | Not Scheduled | T2 DI CARIBOU-PALERMO :025/205 RPR FOND |  | CARIBOU-PALERMO | :025/205 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.414992 | 39.8439 | ETL.3190 | 40758492 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535380 | Mar | T3 EI MORAGA-SAN LEANDRO #3 5/41 RPR STR |  | MORAGA-SAN LEANDRO #3 | 005/041 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40580825 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535395 | Not Scheduled | T2NT DI CARIBOU-PLRMO :24/200 RMV DEBRIS |  | CARIBOU-PALERMO | :024/200 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-31 | 2021-07-31 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.40384 | 39.85 | ETL.3190 | 40599288 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535399 | Q2 | T3 DI CARIBOU-TABLE MTN 14/108 RPLC HRDT | 44634441 | CARIBOU-TABLE MTN | 014/108 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.226747 | 40.0126 | ETL.4440 | 40871501 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119535646 | Mar | DI EAGLE ROCK-CORTINA :17/12 REFRAME | 31513195 | EAGLE ROCK-CORTINA | :017/012 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.611945 | 38.9763 | ETL.1470 | 40710979 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119536279 | Q2 | EI MUSTANG SW STA-GREGG X56/237 RPR FOND | 44571494 | GATES-GREGG | X056/237 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-31 | 2021-07-31 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900749 | 36.823 | ETL.4700 | 40805365 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119536305 | Feb | T3 EI ROUND MTN-CTTNWD #3 34/292 RPL INS | 31504993 | ROUND MTN-COTTONWOOD #3 | 034/292 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.010493 | 40.7057 | ETL.5650 | 40729447 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119536512 | Mar | T2 DI KONOCTI-MDDLTWN 12/11 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 012/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.602627 | 38.7602 | ETL.6380 | 40586655 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119536570 | Not Scheduled | T2 DI KNCTI-MDDLTWN 21/3 RPR WDPKR | 44610651 | KONOCTI-MIDDLETOWN | 021/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-07-31 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.597548 | 38.8698 | ETL.6380 | 40666985 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119536599 | Not Scheduled | T3 EI COLGATE-CHALLENGE 5/105 RPL STRW | 31509852 | COLGATE-CHALLENGE | 005/105 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.168533 | 39.3982 | ETL.6480 | 40815345 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119536604 | Not Scheduled | T3 EI COLGATE-CHALLENGE 5/105 RPR SPLW | 44410417 | COLGATE-CHALLENGE | 005/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.168533 | 39.3982 | ETL.6480 | 40815345 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537115 | Not Scheduled | T3 EI COLGATE-CHALLENGE 5/107 RPR SPLW | 44410417 | COLGATE-CHALLENGE | 005/107 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.171924 | 39.3987 | ETL.6480 | 44695494 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537219 | Not Scheduled | T3 EI COLGATE-CHALLENGE 5/108 REFRAME | 31510988 | COLGATE-CHALLENGE | 005/108 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.17357 | 39.399 | ETL.6480 | 40866299 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537320 | Q2 | T2 DI EAGLE ROCK-CORTNA :13/21 RPR WDPKR | 44563383 | EAGLE ROCK-CORTINA | :013/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.609054 | 38.9233 | ETL.1470 | 41176302 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537533 | Q2 | T2 EI CRESTA-RIO OSO_027/217 RMV NEST |  | CRESTA-RIO OSO | 027/217 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2021-07-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.526562 | 39.5859 | ETL.4590 | 41083078 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537553 | Q2 | T2 EI CRESTA-RIO OSO_027/217 WASH INSS |  | CRESTA-RIO OSO | 027/217 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.526562 | 39.5859 | ETL.4590 | 41083078 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537559 | Mar | T2 EI FULTON-HOPLAND 11/0 INST GMKR | 44579280 | FULTON-HOPLAND | 011/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2022-07-31 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.850505 | 38.6246 | ETL.6890 | 40587777 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537773 | Not Scheduled | T3 EI COLGATE-CHALLENGE 5/110 RPL SPLW | 44410417 | COLGATE-CHALLENGE | 005/110 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.176135 | 39.3994 | ETL.6480 | 44695496 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537889 | Q3 | T2 DI BRDGVL-GRBRVL 11/9 RPL STRW | 31513483 | BRIDGEVILLE-GARBERVILLE | 011/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.718346 | 40.3471 | ETL.6220 | 40875304 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119537982 | Q2 | T2 DI KONOCTI-MDDLTWN 25/3 RMV PL BUTT | 44610651 | KONOCTI-MIDDLETOWN | 025/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2021-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.6929 | 38.9161 | ETL.6380 | 40648319 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119538062 | Mar | T3 EI LAURELES-OTTER 8/014 RPR ANCW | 44587870 | LAURELES-OTTER | 008/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.801512 | 36.4182 | ETL.7380 | 40771071 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119538227 | Mar | T3 EI LAURELES-OTTER_009/013 RPR ANCHOR | 44587870 | LAURELES-OTTER | 009/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.816887 | 36.4181 | ETL.7380 | 44562839 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119538234 | Mar | T3 EI LAURELES-OTTER 09/013 RPR ANCHOR | 44587870 | LAURELES-OTTER | 009/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.816887 | 36.4181 | ETL.7380 | 44562662 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119538235 | Mar | T3 EI LAURELES-OTTER 09/013 RPR ANCHOR | 44587870 | LAURELES-OTTER | 009/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.816887 | 36.4181 | ETL.7380 | 44562837 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119538266 | Mar | T3 EI LAURELES-OTTER 09/014 RPR ANCHOR | 44587870 | LAURELES-OTTER | 009/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-29 | 2021-03-29 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.819027 | 36.4156 | ETL.7380 | 44563001 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119538269 | Mar | T3 EI LAURELES-OTTER 09/014 RPR ANCHOR | 44587870 | LAURELES-OTTER | 009/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-03-29 | 2021-03-29 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.819027 | 36.4156 | ETL.7380 | 44562890 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539109 | Q2 | T2 DI KONOCTI-MIDDLETOWN 26/2 RPR WDPKR | 44610651 | KONOCTI-MIDDLETOWN | 026/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.677426 | 38.9098 | ETL.6380 | 40699027 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539146 | Q2 | T2 DI KONOCTI-MIDDLTWN 26/2 RMV PL BUTT | 44610651 | KONOCTI-MIDDLETOWN | 026/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2022-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.677426 | 38.9098 | ETL.6380 | 40699027 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539631 | Q2 | EI GARBERVILLE-LAYTONVILLE 61/5 RPL INSW | 31505611 | GARBERVILLE-LAYTONVILLE | 061/005 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7673818 | 40.1126 | ETL.8365 | 40922503 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539632 | Q2 | EI GARBERVILLE-LAYTONVILLE 61/007 RPL PL | 31511613 | GARBERVILLE-LAYTONVILLE | 061/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.768494 | 40.1119 | ETL.8365 | 40912696 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539635 | Q2 | EI GARBERVILLE-LAYTONVILLE 61/4 RMV DMPR | 44453316 | GARBERVILLE-LAYTONVILLE | 061/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7662917 | 40.1135 | ETL.8365 | 40922502 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539652 | Q2 | EI GARBERVILLE-LAYTONVILLE 61/9 RPL PL | 31511613 | GARBERVILLE-LAYTONVILLE | 061/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.771417 | 40.1111 | ETL.8365 | 40912698 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119539657 | Q2 | EI GARBERVILLE-LAYTNVILLE 61/3 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 061/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-07-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.76446 | 40.115 | ETL.8365 | 44895584 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119542150 | Q3 | EI TESLA-NEWARK #2 15/104 RPR FOND | 44226389 | TESLA-NEWARK #2 | 015/104 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.81788 | 37.6103 | ETL.5354 | 41152649 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119546499 | Q4 | T2 EI MAPLE CREEK- HOOPA 5/4 RPR GYWW | 44453147 | MAPLE CREEK-HOOPA | 005/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-02 | 2021-08-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.8270997 | 40.8254 | ETL.7490 | 44779054 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547164 | Not Scheduled | T2 DI KONOCTI-MIDDLETOWN 21/7 RPR WDPKR | 44610651 | KONOCTI-MIDDLETOWN | 021/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-07-31 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.599026 | 38.8738 | ETL.6380 | 40810257 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547182 | Feb | T3 EI ROUND MTN-CTTNWD #3 33/284 RPL INS | 31504993 | ROUND MTN-COTTONWOOD #3 | 033/284 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.0021815 | 40.7157 | ETL.5650 | 40789059 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547189 | Not Scheduled | T3 EI ROUND MTN-CTTNWD 032/272 RPR STRT | 43932111 | ROUND MTN-COTTONWOOD #3 | 032/272 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98922 | 40.7312 | ETL.5650 | 40668248 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547201 | Q2 | T2 EI HAT CRK #1-WESTWD 35/676 REFRAME | 31514136 | HAT CREEK #1-WESTWOOD | 035/676 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.081725 | 40.5774 | ETL.7030 | 40759043 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547202 | Feb | T3 EI ROUND MTN-CTTNWD #3 33/277 RPR INS | 44624619 | ROUND MTN-COTTONWOOD #3 | 033/277 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9944539 | 40.7249 | ETL.5650 | 40846050 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547204 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 32/276 RPR STR | 43932111 | ROUND MTN-COTTONWOOD #3 | 032/276 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.993279 | 40.7263 | ETL.5650 | 40816918 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547210 | Feb | T3 EI ROUND MTN-CTTNWD #3 32/274 RPR INS | 44624619 | ROUND MTN-COTTONWOOD #3 | 032/274 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9910707 | 40.729 | ETL.5650 | 40791625 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547442 | Q2 | EI MSTNG SW STA-GREGG X049/206 RPR FOND | 44571494 | GATES-GREGG | X049/206 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2021-08-03 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897204 | 36.7298 | ETL.4700 | 40815319 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119547492 | Mar | T2 DI EAGLE ROCK-CORTINA :18/3 RPR IBWW | 44563383 | EAGLE ROCK-CORTINA | :018/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.613086 | 38.9836 | ETL.1470 | 41176386 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119547614 | Q2 | T2 EI IGNACIO-BOLINAS #1 7/77 REFRAME | 31511096 | IGNACIO-BOLINAS #1 | 007/077 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.647148 | 38.0154 | ETL.7140 | 40601725 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119549380 | Q2 | EI MSTNG SW STA-GREGG X049/207 RPR FOND | 44571494 | GATES-GREGG | X049/207 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2022-08-03 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897281 | 36.7328 | ETL.4700 | 40805361 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119549481 | Q2 | T2 DI KONOCTI-MIDDLETOWN 18/0 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 018/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.576931 | 38.8231 | ETL.6380 | 40590977 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119549488 | Q2 | T2 DI KONOCTI-MIDDLETWN 24/8 RMV PL BUTT | 44610651 | KONOCTI-MIDDLETOWN | 024/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2022-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.702709 | 38.919 | ETL.6380 | 40860830 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119549719 | Q2 | EI MUSTANG SW S-GREG X049/208 RPR FOND | 44571494 | GATES-GREGG | X049/208 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2021-08-03 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.89742 | 36.7357 | ETL.4700 | 40873446 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119549979 | Q2 | T2 EI PHILO JCT-ELK 6/001 RPR STRW | 44610684 | PHILO JCT-ELK | 006/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.240081 | 39.0581 | ETL.7780 | 40595267 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119550099 | Q2 | EI MUSTANG SW STA-GREGG X50/209 RPR FOND | 44571494 | GATES-GREGG | X050/209 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2021-08-03 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897497 | 36.7387 | ETL.4700 | 40858236 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119550236 | Q2 | EI MUSTANG SW STA-GREGG X50/210 RPR FOND | 44571494 | GATES-GREGG | X050/210 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2021-08-03 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897507 | 36.7417 | ETL.4700 | 40597542 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119550261 | Q2 | T2NT DI KNCTI-MIDDLETOWN 27/0 RMV DEBRIS | 44610651 | KONOCTI-MIDDLETOWN | 027/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-03 | 2022-08-03 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.666201 | 38.9055 | ETL.6380 | 40587058 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119550267 | Q3 | BEARDSLEY TAP 2/3 RPR WDPRK |  | BEARDSLEY TAP | 002/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2021-05-04 |  |  | 2021-09-04 | 2021-09-03 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.060383 | 38.1801 | ETL.1401 | 44390893 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119550596 | Q2 | EI BRIDGEVILLE-CTTNWD 9/86 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/086 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.441963 | 40.3891 | ETL.1110 | 44423427 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119550598 | Q2 | T3 SNTH LN-HLF MN BY ?6/0 RPR GYWW | 44621947 | SNEATH LANE-HALF MOON BAY | ?006/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.448776 | 37.5454 | ETL.7212 | 40601798 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | Scarper Ridge | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119551115 | Not Scheduled | T3 EI TIGER CRK-VLLY SPRINGS 8/0 RPR STR |  | TIGER CREEK-VALLEY SPRINGS | 008/066 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.627044 | 38.3947 | ETL.5790 | 40818865 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119551375 | Not Scheduled | T3 GEYSERS #9-LAKEVILLE 17/72 RPL INSUL |  | GEYSERS #9-LAKEVILLE | 017/072 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.6530841 | 38.5305 | ETL.4780 | 40716254 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119551416 | Q2 | EI GARBERVILLE-LAYTONVILLE 60/5 RPR DAMP | 44453316 | GARBERVILLE-LAYTONVILLE | 060/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.757467 | 40.1153 | ETL.8365 | 40912683 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119552004 | Q3 | EI BRIDGVILLE-GRBRVLLE 17/3 RMV PL BUTT | 44476761 | BRIDGEVILLE-GARBERVILLE | 017/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-03 | 2022-08-03 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7522 | 40.2778 | ETL.6220 | 40650768 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119552006 | Q3 | EI BRIDGVILLE-GRBRVLLE 17/2 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 017/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.751792 | 40.2783 | ETL.6220 | 40698427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119552013 | Q3 | EI BRIDGVILLE-GRBRVLLE 17/3 RPR WDPK | 44299806 | BRIDGEVILLE-GARBERVILLE | 017/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7522 | 40.2778 | ETL.6220 | 40650768 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119552016 | Q3 | EI BRIDGEVILLE-GARBERVILLE 17/4 RPR GYWW | 44476628 | BRIDGEVILLE-GARBERVILLE | 017/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.753453 | 40.2764 | ETL.6220 | 40769357 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119552064 | Not Scheduled | T3NT DI DRUM-RIO OSO #2 0/1 PNT STRT | 44410116 | DRUM-RIO OSO #2 | 000/001 | ICX | F | 2020_(1a) PSPS |  | 2020-08-03 | 2022-08-03 | [6 empty] | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-120.769289 | 39.2569 | ETL.1430 | 40590432 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119552065 | Q4 | T3 DI DRUM-RIO OSO #2 0/1 RMV GYWS | 44410112 | DRUM-RIO OSO #2 | 000/001 | ICS | E | 2020_(1a) PSPS |  | 2020-08-03 | 2021-02-03 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.769289 | 39.2569 | ETL.1430 | 40590432 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119552384 | Q3 | EI TESLA-NEWARK #2 17/115 RPR FOND |  | TESLA-NEWARK #2 | 017/115 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2020-10-03 |  |  | 2021-07-30 | 2021-07-26 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.840969 | 37.5964 | ETL.5354 | 41152661 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119552400 | Q3 | EI TESLA-NEWARK #2 19/128 RPR FOND |  | TESLA-NEWARK #2 | 019/128 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2022-08-03 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.868441 | 37.5733 | ETL.5354 | 41152674 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553201 | Mar | T2 EI FULTON-HOPLAND 12/4 RPL POLE | 31514314 | FULTON-HOPLAND | 012/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.856398 | 38.644 | ETL.6890 | 40770420 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553204 | Mar | T2 EI FULTON-HOPLAND 12/3 RPR WDPKR | 44579280 | FULTON-HOPLAND | 012/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.85659 | 38.6432 | ETL.6890 | 40648702 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553206 | Mar | EI FULTON-HOPLAND 13/7 REFRAME | 31509679 | FULTON-HOPLAND | 013/007 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.854045 | 38.6639 | ETL.6890 | 44860857 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553456 | Not Scheduled | T2 EI SPAULDING-SUMMIT 14/475 REPL INSW | 31514138 | SPAULDING-SUMMIT | 014/475 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2021-08-03 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.394617 | 39.3289 | ETL.8060 | 40876702 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553729 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 30/256 RMV STE | 43932111 | ROUND MTN-COTTONWOOD #3 | 030/256 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.972989 | 40.7506 | ETL.5650 | 40813494 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553801 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 31/2 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/259 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.976159 | 40.7468 | ETL.5650 | 40864681 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553802 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 30/255 RMV STE | 43932111 | ROUND MTN-COTTONWOOD #3 | 030/255 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.972041 | 40.7517 | ETL.5650 | 40762206 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553804 | Feb | T3 EI ROUND MTN-CTTNWD #3 30/256 RPL ISU | 31504993 | ROUND MTN-COTTONWOOD #3 | 030/256 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9730028 | 40.7506 | ETL.5650 | 40840954 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553805 | Not Scheduled | EI T3NT RND MTN-CTTNWD #3 31/260 RPR FON | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/260 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2022-08-03 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.977131 | 40.7456 | ETL.5650 | 40595001 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553807 | Feb | T3 EI ROUND MTN-CTTNWD #3 31/262 RPR INS | 44624619 | ROUND MTN-COTTONWOOD #3 | 031/262 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9791727 | 40.7432 | ETL.5650 | 40725722 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553808 | Feb | T3 EI ROUND MTN-CTTNWD #3 32/270 RPL INS | 31504993 | ROUND MTN-COTTONWOOD #3 | 032/270 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9868641 | 40.734 | ETL.5650 | 40637083 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553811 | Feb | T3 EI ROUND MTN-CTTNWD #3 30/256 RPR SPL | 44624619 | ROUND MTN-COTTONWOOD #3 | 030/256 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9730028 | 40.7506 | ETL.5650 | 40840954 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553812 | Feb | T3 EI ROUND MTN-CTTNWD #3 31/261 RPR SPL | 44624619 | ROUND MTN-COTTONWOOD #3 | 031/261 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9782043 | 40.7444 | ETL.5650 | 40619622 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553813 | Not Scheduled | T3 EI ROUND MTN-COTTONWD #3 31/264 RPR S | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/264 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980338 | 40.7418 | ETL.5650 | 40755441 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119553814 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 31/265 RMV STE | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/265 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980899 | 40.7411 | ETL.5650 | 40760997 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554221 | Mar | EI LAURELES-OTTER 10/0C RPR ANCW | 44587870 | LAURELES-OTTER | 010/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-03-29 | 2021-03-29 | [5 empty] | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44563002 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554251 | Mar | EI LAURELES-OTTER 10/0R RPR ANCW | 44587870 | LAURELES-OTTER | 010/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-03-29 | 2021-03-29 | [5 empty] | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44562891 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554252 | Mar | EI LAURELES-OTTER 10/0L RPR ANCW | 44587870 | LAURELES-OTTER | 010/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-03-29 | 2021-03-29 | [5 empty] | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44562938 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554254 | Mar | T3 EI LAURELES-OTTER 8/001 RPR ANCHOR | 44587870 | LAURELES-OTTER | 008/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.788465 | 36.4184 | ETL.7380 | 40601892 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554473 | Not Scheduled | EI DIVIDE-CABRILLO #1 1/22 RPR GYWW |  | DIVIDE-CABRILLO #1 | 001/022 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.445272 | 34.808 | ETL.1380 | 40828450 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554488 | Not Scheduled | EI DIVIDE-CABRILLO #1 1/23 RPR GYWW |  | DIVIDE-CABRILLO #1 | 001/023 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-120.445093 | 34.807 | ETL.1380 | 40826474 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554492 | Q3 | T2 DI BRDGVL-GRBRVL 0/4 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.784801 | 40.4775 | ETL.6220 | 40752600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554560 | Q2 | DI DRUM-SPAULDING 000/005 RPL POLE | 31514145 | DRUM-SPAULDING | 000/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.763389 | 39.2566 | ETL.6770 | 40751868 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554596 | Not Scheduled | T3 DI MONTE RIO-FLTN 14/10 CLN INSW |  | MONTE RIO-FULTON | 014/010 | ICD | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.011615 | 38.4764 | ETL.7630 | 40587320 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-05 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554700 | Q2 | T2 DI KONOCTI-MIDDLETOWN ;24/9 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | ;024/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.617401 | 38.9092 | ETL.6380 | 40862467 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554703 | Q2 | T2 DI TRINITY-MAPLE CRK 22/3 RPLC STRW | 31510696 | TRINITY-MAPLE CREEK | 022/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.303195 | 40.707 | ETL.8170 | 40650361 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554704 | Q4 | T3NT DI DRUM-RIO OSO #2 0/2 RMV DEBRIS | 44410114 | DRUM-RIO OSO #2 | 000/002 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-03 | 2022-08-03 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.770926 | 39.2569 | ETL.1430 | 40672179 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554708 | Feb | T3 DI RND MTN-CTTNWD #3 29/243 RPLC INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 029/243 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.960503 | 40.7656 | ETL.5650 | 40693167 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554729 | Q2 | T2 DI TRINITY-MAPLE CREEK 43/5 RPR CRSW | 44453151 | TRINITY-MAPLE CREEK | 043/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.684444 | 40.7358 | ETL.8170 | 40770474 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554784 | Q2 | EI GARBERVILLE-LAYTONVILLE 60/2 REPULL G | 44453316 | GARBERVILLE-LAYTONVILLE | 060/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.749815 | 40.1129 | ETL.8365 | 44913382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554792 | Q2 | EI GARBERVILLE-LAYTONVILLE 58/2 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 058/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-03 | 2022-08-03 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.711895 | 40.1055 | ETL.8365 | 40912655 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554794 | Q2 | EI GARBERVILLE-LAYTONVILLE 58/1 REPL POL | 31512220 | GARBERVILLE-LAYTONVILLE | 058/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.710705 | 40.1049 | ETL.8365 | 40912654 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554795 | Q2 | EI GARBERVILLE-LAYTONVILLE 60/3 REPL INS | 31513498 | GARBERVILLE-LAYTONVILLE | 060/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.751681 | 40.1134 | ETL.8365 | 40912681 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554800 | Mar | T3 DI LAURELES-OTTER 13/15 RPR GYWW | 44610149 | LAURELES-OTTER | 013/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.870997 | 36.3864 | ETL.7380 | 44870751 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119554802 | Q2 | T3 DI KONOCTI-EAGLE ROCK 4/12 RPLC POLE | 31510990 | KONOCTI-EAGLE ROCK | 004/012 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-05-06 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.786463 | 38.88 | ETL.6861 | 40698967 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119555151 | Q2 | T3NT DI IGNCIO-BOLNAS #2 22/252 RMV BUTT | 44640732 | IGNACIO-BOLINAS #2 | 022/252 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-04 | 2022-08-04 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.74205 | 37.9911 | ETL.7180 | 40808623 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119555729 | Q4 | T3 EI MAPLE CREEK-HOOPA 19/007 REFRAME | 44394730 | MAPLE CREEK-HOOPA | 019/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.647963 | 40.9488 | ETL.7490 | 40810438 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119555792 | Q2 | EI LOS BANOS-GATES #1 6/27 RPL TURNBUCKL |  | LOS BANOS-GATES #1 | 006/027 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.970682 | 36.9758 | ETL.6000 | 40819424 | Guy Wire-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119555797 | Q4 | EI T3NT MAPLE CREEK-HOOPA 19/8 RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 019/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2022-08-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.645863 | 40.9478 | ETL.7490 | 40877970 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119555799 | Q4 | T3 EI MAPLE CREEK-HOOPA 19/8 REFRAME | 31510992 | MAPLE CREEK-HOOPA | 019/008 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.645863 | 40.9478 | ETL.7490 | 40877970 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556005 | Not Scheduled | T3 EI TGR CRK-VLLY SPRNGS 7/59 RPR SEC M |  | TIGER CREEK-VALLEY SPRINGS | 007/059 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.612638 | 38.405 | ETL.5790 | 40591656 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556862 | Q2 | T2 DI TRNTY-MPLE CREEK 25/3 RPR STRW | 44295371 | TRINITY-MAPLE CREEK | 025/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.365738 | 40.7038 | ETL.8170 | 40906421 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556897 | Q2 | T2 DI TRINITY-MAPLE CRK 43/2 REFRAME | 44401954 | TRINITY-MAPLE CREEK | 043/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.681931 | 40.734 | ETL.8170 | 40701832 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556898 | Not Scheduled | T3NT DI SNTH LN-HLF MN 3/2 RMV DEBRIS | 44621950 | SNEATH LANE-HALF MOON BAY | ?003/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-03 | 2022-08-03 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.486331 | 37.5598 | ETL.7212 | 40674734 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556899 | Q2 | T3 DI SNTH LN-HLF MN BY ?3/2 RPR GYWW | 44621670 | SNEATH LANE-HALF MOON BAY | ?003/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.486331 | 37.5598 | ETL.7212 | 40674734 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556955 | Mar | T3 MORAGA-OAKLAND #3 1/9 REPL BOLT | 44623421 | MORAGA-OAKLAND #3 | 001/009 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.178464 | 37.8431 | ETL.2740 | 40857636 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119556983 | Feb | T3 MORAGA-OAKLAND #1 1/8 REPL BOLT | 44611129 | MORAGA-OAKLAND #1 | 001/008 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.178678 | 37.8431 | ETL.2720 | 40870714 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557094 | Q2 | EI MI-WUK-CURTIS 19/6 RPR HRDW | 44623519 | ETL.1073.POLE.WDPS | 019/006 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.2374101 | 38.0477 | ETL.1073 | 44779570 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557196 | Q2 | T3 DI IGNACIO-BOLINAS #2 2/27 REFRAME | 44640732 | IGNACIO-BOLINAS #2 | 002/027 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.581246 | 38.0719 | ETL.7180 | 40760169 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557406 | Q2 | T2 DI TRINITY-MAPLE CRK 44/8 RPR WDPK | 44295371 | TRINITY-MAPLE CREEK | 044/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.704593 | 40.7475 | ETL.8170 | 40877937 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557605 | Q2 | T2 DI TRNTY-MPLE CREEK 48/25 RPR CNDW | 44453151 | TRINITY-MAPLE CREEK | 048/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.78105 | 40.7559 | ETL.8170 | 40770542 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557647 | Q2 | T3 DI IGNCIO-BOLNAS #2 3/46 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 003/046 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.603813 | 38.0823 | ETL.7180 | 40601744 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557712 | Q2 | T3 DI IGNCIO-BOLNAS #2 21/45 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 021/245 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.748615 | 38.0011 | ETL.7180 | 40668084 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557727 | Not Scheduled | EI BRIDGEVILLE-GARBERVLE 31/2 TIE WIRE | 44453320 | BRIDGEVILLE-GARBERVILLE | 031/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 | [6 empty] | CANCEL/CNCL |  |  | North Coast | WSIP | [6 empty] | '-123.708473 | 40.1126 | ETL.6220 | 40698342 | Tie Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119557733 | Not Scheduled | EI BRIDGEVILLE-GARBERVILLE 31/2 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 031/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 | [6 empty] | CANCEL/CNCL |  |  | North Coast | WSIP | [6 empty] | '-123.708473 | 40.1126 | ETL.6220 | 40698342 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558000 | Q2 | T2 DI PHILO JCT-ELK 11/11 RPL PL | 31515022 | PHILO JCT-ELK | 011/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.329232 | 39.0239 | ETL.7780 | 40600383 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558245 | Q4 | T3 EI MAPLE CREEK-HOOPA 22/006 RPL STRW | 31509746 | MAPLE CREEK-HOOPA | 022/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.641606 | 40.9797 | ETL.7490 | 40827972 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558259 | Q4 | T3 EI MAPLE CREEK-HOOPA 22/007 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 022/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.64113 | 40.9824 | ETL.7490 | 40810442 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558330 | Q4 | T3 EI MAPLE CRK-HP 22/4 RPR REFRAME | 44394730 | MAPLE CREEK-HOOPA | 022/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.641987 | 40.9776 | ETL.7490 | 40771311 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558574 | Q4 | T3 EI MAPLE CREEK-HP 22/2 RPR WDPK | 44192340 | MAPLE CREEK-HOOPA | 022/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.642326 | 40.976 | ETL.7490 | 40662189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558576 | Q4 | EI T3NT MAPLE CREEK-HP 22/002 RMV DEBRIS | 44301081 | MAPLE CREEK-HOOPA | 022/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-04 | 2022-08-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.642326 | 40.976 | ETL.7490 | 40662189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558637 | Feb | T2 EI COLGATE-GRASS VALLY 3/082 RPR STRW | 44473099 | COLGATE-GRASS VALLEY | 003/082 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.12874 | 39.3207 | ETL.6490 | 40679372 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558739 | Q4 | EI T3NT MAPLE CREEK-HPA 22/1 RMV BUTT | 44593017 | MAPLE CREEK-HOOPA | 022/001 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2022-08-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.64156 | 40.975 | ETL.7490 | 44735744 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558746 | Feb | T2 EI COLGATE-GRASS VALLEY 0/3B RPR GYWW | 44461286 | COLGATE-GRASS VALLEY | 000/003B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.188488 | 39.3294 | ETL.6490 | 44190861 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558773 | Feb | T2 EI COLGATE-GRASS VLLEY 0/007 RPR STRW | 44473099 | COLGATE-GRASS VALLEY | 000/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.185435 | 39.3287 | ETL.6490 | 40825238 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558775 | Feb | T3 EI CLGT-GRSS VLLY 5/129 RPL CROSSARM | 31508498 | COLGATE-GRASS VALLEY | 005/129 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.108678 | 39.3033 | ETL.6490 | 40768370 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558780 | Feb | T2 EI COLGATE-GRASS VALLEY 0/4 RPR STRW | 44473099 | COLGATE-GRASS VALLEY | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.187827 | 39.3292 | ETL.6490 | 40655407 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119558782 | Feb | T3 EI COLGATE-GRSS VLLY 5/130 RPL POLE | 31510989 | COLGATE-GRASS VALLEY | 005/130 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.108428 | 39.3029 | ETL.6490 | 40767586 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559106 | Q4 | T3 EI MAPLE CREEK-HOOPA 22/000 RPR POLE | 44192340 | MAPLE CREEK-HOOPA | 022/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.640519 | 40.9734 | ETL.7490 | 40617930 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559158 | Q4 | T3 EI MAPLE CREEK-HOOPA 20/14 RPR STRW | 44192340 | MAPLE CREEK-HOOPA | 020/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.643038 | 40.9566 | ETL.7490 | 40752771 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559167 | Q4 | T3 EI MAPLE CREEK-HOOPA 20/014 INST JUMP | 44394730 | MAPLE CREEK-HOOPA | 020/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.643052 | 40.9566 | ETL.7490 | 40781966 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559606 | Q2 | EI GARBERVILLE-LAYTONVILLE 57/2 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 057/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2022-08-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.692292 | 40.103 | ETL.8365 | 40912646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559608 | Q2 | EI GARBERVILLE-LAYTONVIL 56/18 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 056/018 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.688983 | 40.1015 | ETL.8365 | 40912640 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559609 | Q2 | EI GARBERVILLE-LAYTONVILLE 57/0 RMV HRDW | 44476763 | GARBERVILLE-LAYTONVILLE | 057/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2021-08-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.689842 | 40.1022 | ETL.8365 | 40912641 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119559650 | Q2 | EI GARBERVILLE-LAYTONVILLE 57/0 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 057/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.689842 | 40.1022 | ETL.8365 | 40912641 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560175 | Q2 | T3 DI IGNACIO-BOLINAS #2 22/254 BOND GUY | 44640732 | IGNACIO-BOLINAS #2 | 022/254 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.740515 | 37.9888 | ETL.7180 | 40750720 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560176 | Q3 | T2 DI CARIBOU-WESTWOOD 16/339 RPL STRW | 31513338 | CARIBOU-WESTWOOD | 016/339 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.073688 | 40.289 | ETL.6300 | 40769695 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560179 | Q3 | T2 DI CARIBOU-WESTWOOD 15/317 RPR CONW |  | CARIBOU-WESTWOOD | 015/317 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.082933 | 40.2751 | ETL.6300 | 40787960 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560346 | Q2 | T3 DI IGNCIO-BOLNAS #2 21/243 RPR STRW | 44640732 | IGNACIO-BOLINAS #2 | 021/243 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.750189 | 38.0031 | ETL.7180 | 40750722 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560348 | Q2 | T3 DI IGNCO-BLNAS #2 21/243 GRD WAS INSU | 44640989 | IGNACIO-BOLINAS #2 | 021/243 | ICD | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.752116 | 38.005 | ETL.7180 | 40778801 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560349 | Q2 | T3 DI IGNACIO-BOLINAS #2 21/243 RPR SPLW | 44640732 | IGNACIO-BOLINAS #2 | 021/243 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.750189 | 38.0031 | ETL.7180 | 40750722 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560383 | Q2 | T2 DI TRINITY-MAPLE CREEK 48/15 RPR SPLW | 44401954 | TRINITY-MAPLE CREEK | 048/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.775275 | 40.754 | ETL.8170 | 40751108 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560438 | Q2 | T2 DI PHILO JCT-ELK 15/0 RPLC INSW | 31513412 | PHILO JCT-ELK | 015/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.37873 | 39.035 | ETL.7780 | 40640240 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119560484 | Q2 | T3NT DI WSHN-SN JOAQUIN #3 7/3 RMV BUTT | 44429040 | WISHON-SAN JOAQUIN #3 | 007/003 | ICW | F | 2020_(1a) PSPS |  | 2020-08-04 | 2022-08-04 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-119.506676 | 37.1566 | ETL.9340 | 44655747 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119560486 | Q2 | T3 DI LAKEVILLE #1 8/5 RPLC STRW | 31510991 | LAKEVILLE #1 | 008/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-06-01 | 2021-05-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.560403 | 38.3623 | ETL.7360 | 40770230 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561161 | Q2 | TRINITY-MAPLE CREEK 40/0R RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 040/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.626398 | 40.72 | ETL.8170 | 44769587 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561172 | Q4 | T2 DI MAPLE CREEK-HOOPA 21/2 RMV STEP | 44453147 | MAPLE CREEK-HOOPA | 021/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.641807 | 40.9632 | ETL.7490 | 40701854 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561173 | Q4 | T2 DI MAPLE CREEK-HOOPA 21/2 RPR STRW | 44192340 | MAPLE CREEK-HOOPA | 021/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.641807 | 40.9632 | ETL.7490 | 40701854 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561181 | Q2 | TRINITY-MAPLE CREEK 40/0L RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 040/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.626398 | 40.72 | ETL.8170 | 44769585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561288 | Q2 | TRINITY-MAPLE CREEK 45/007C RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 045/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.725618 | 40.7499 | ETL.8170 | 44565377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561312 | Q2 | T2 DI TRINITY-MAPLE CRK 17/12R RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 017/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2224114 | 40.741 | ETL.8170 | 44420621 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561324 | Q2 | T2 DI TRINITY-MAPLE CRK 17/12L RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 017/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.2224136 | 40.741 | ETL.8170 | 44420619 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561342 | Q3 | T2 DI CARIBOU-WESTWOOD 9/184 RPR GYWW |  | CARIBOU-WESTWOOD | 009/184 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.072508 | 40.1968 | ETL.6300 | 44190956 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561345 | Q3 | T2 DI CARIBOU-WESTWOOD 9/184 RMV BUTT |  | CARIBOU-WESTWOOD | 009/184 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2022-08-04 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.072508 | 40.1968 | ETL.6300 | 44190956 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561466 | Q2 | T3 DI IGNACIO-BOLINAS #2 2/38 RPR STRW | 44640732 | IGNACIO-BOLINAS #2 | 002/038 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.590615 | 38.0804 | ETL.7180 | 40668139 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561467 | Q2 | T3 DI IGNACIO-BOLINAS #2 2/38 RPR HRDW | 44640732 | IGNACIO-BOLINAS #2 | 002/038 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.590615 | 38.0804 | ETL.7180 | 40668139 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561590 | Q3 | EI BRIDGEVILLE-GARBERVILLE 16/2 REPL POL | 31508614 | BRIDGEVILLE-GARBERVILLE | 016/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.740136 | 40.2899 | ETL.6220 | 40661856 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-08-12 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561828 | Q3 | T2 DI CARIBOU-PLUMAS JCT 11/7 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 011/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.999167 | 39.9827 | ETL.6290 | 40824653 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561920 | Q3 | T2 DI CARIBOU-PLUMAS JCT 0/2B RPL INSW | 44408852 | CARIBOU-PLUMAS JCT | 000/002B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.147369 | 40.0856 | ETL.6290 | 42721991 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561923 | Q3 | T2 DI CARIBOU-WESTWOOD 8/149 RMV BUTT |  | CARIBOU-WESTWOOD | 008/149 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2022-08-04 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08106 | 40.1734 | ETL.6300 | 40591691 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119561926 | Q3 | T2 DI CARIBOU-WESTWOOD 8/149 RPR GYWW |  | CARIBOU-WESTWOOD | 008/149 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.08106 | 40.1734 | ETL.6300 | 40591691 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119562338 | Not Scheduled | T2 DRUM-SUMMIT #2 26/312L RPL POLE | 31521951 | DRUM-SUMMIT #2 | 026/312 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.353954 | 39.309 | ETL.1450 | 44553702 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119562380 | Not Scheduled | T2 DRUM-SUMMIT #2 26/313L RPL POLE | 31510143 | DRUM-SUMMIT #2 | 026/313 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.352399 | 39.3085 | ETL.1450 | 44553604 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119562419 | Not Scheduled | T3 DRUM-HIGGINS 00/002L RPL POLE | 31507649 | DRUM-HIGGINS | 000/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.093586 | 37.4224 | ETL.4393 | 44199668 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119562550 | Mar | T3 EI WEST PNT-VLLY SPRINGS 3/40 RPR STR |  | WEST POINT-VALLEY SPRINGS | 003/040 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.598862 | 38.4146 | ETL.8350 | 40697098 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119562917 | Not Scheduled | T2 DRUM-SUMMIT #2 26/312R REPL POLE | 31521951 | DRUM-SUMMIT #2 | 026/312 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.353954 | 39.309 | ETL.1450 | 44553633 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119562919 | Not Scheduled | T2 DRUM-SUMMIT #2 26/313R REPL POLE | 31510143 | DRUM-SUMMIT #2 | 026/313 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.352399 | 39.3085 | ETL.1450 | 44553671 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119563353 | Not Scheduled | T3 DRUM-HIGGINS 0/002R REPL POLE | 31507649 | DRUM-HIGGINS | 000/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.093586 | 37.4224 | ETL.4393 | 44199669 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119563514 | Q2 | T2NT DI BRDGVL-CTTNWD 47/363 RPR FOND | 44634172 | BRIDGEVILLE-COTTONWOOD | 047/363 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-05 | 2022-08-05 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.146351 | 40.4076 | ETL.1110 | 40657057 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119563515 | Q2 | T2 DI BRDGVL-CTTNWD 47/363 INST DMPR | 44477511 | BRIDGEVILLE-COTTONWOOD | 047/363 | ICS | E | 2020_(3) On high spread structure |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.146351 | 40.4076 | ETL.1110 | 40657057 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119563793 | Q4 | T2 EI MAPLE CREEK-HOOPA 20/15 RPL PL | 31515576 | MAPLE CREEK-HOOPA | 020/015 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.642895 | 40.9577 | ETL.7490 | 40752760 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119564213 | Not Scheduled | EI FULTON-HOPLAND 28/000 RPR POLE | 44579280 | FULTON-HOPLAND | 028/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.000128 | 38.8256 | ETL.6890 | 40616424 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119564242 | Not Scheduled | EI FULTON-HOPLAND 28/000 RPL HRDW | 44579280 | FULTON-HOPLAND | 028/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.000128 | 38.8256 | ETL.6890 | 40616424 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566343 | Q3 | T2 DI CARIBOU-WESTWOOD 13/275 RPR CRSW |  | CARIBOU-WESTWOOD | 013/275 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.077767 | 40.2516 | ETL.6300 | 40876710 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566467 | Q2 | T3 DI IGNACIO-BOLINAS #2 19/224 RPR SPLW | 44640732 | IGNACIO-BOLINAS #2 | 019/224 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.770315 | 38.0263 | ETL.7180 | 40827634 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566473 | Q3 | T2 DI CARIBOU #2 ;004/026 REFRAME | 31513486 | CARIBOU #2 | ;004/026 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.950305 | 39.9647 | ETL.6280 | 40813521 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566487 | Q2 | EI GARBERVILLE-LYTNVLLE 32/10 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 032/010 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2022-08-05 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.551915 | 39.8112 | ETL.8365 | 40587732 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566488 | Q2 | EI GARBERVILLE-LAYTNVILLE 32/10 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 032/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.551915 | 39.8112 | ETL.8365 | 40587732 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566596 | Not Scheduled | T2 DI DRUM-SUMMIT #2 20/241 RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/241 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.445351 | 39.3186 | ETL.1450 | 44558962 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566598 | Not Scheduled | T2 DI DRUM-SUMMIT #2 20/241 RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/241 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.445351 | 39.3186 | ETL.1450 | 44559067 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566613 | Q2 | T2 DI BRIDGVILLE-CTTNWD 52/395 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 052/395 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.239539 | 40.4049 | ETL.1110 | 40785964 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566614 | Not Scheduled | T2 DI DRM-SMIT #2 21/249L REPL POLE |  | DRUM-SUMMIT #2 | 021/249 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.433994 | 39.3245 | ETL.1450 | 44552355 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566616 | Not Scheduled | T2 DI DRUM-SUMMIT #2 21/249 REPL POLE |  | DRUM-SUMMIT #2 | 021/249 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.433994 | 39.3245 | ETL.1450 | 44552356 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566619 | Q3 | T2 DI CARIBOU #2 ;003/024 RMV BUTT |  | CARIBOU #2 | ;003/024 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-05 | 2022-08-05 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.9463 | 39.9797 | ETL.6280 | 40769569 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566665 | Q2 | T2 DI BRDGVL-CTTNWD 47/364 RPR INSS | 44477511 | BRIDGEVILLE-COTTONWOOD | 047/364 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.147944 | 40.4082 | ETL.1110 | 40789516 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566750 | Q2 | T2NT DI PHILO JCT-ELK 3/4 RMV BUTT | 44610684 | PHILO JCT-ELK | 003/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2022-08-05 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.208877 | 39.0881 | ETL.7780 | 40763007 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566753 | Q2 | T2 DI PHILO JCT-ELK 3/4 RPR STRW | 44610684 | PHILO JCT-ELK | 003/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.208877 | 39.0881 | ETL.7780 | 40763007 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566821 | Q2 | T3NT DI TGR CRK-VLY SPRNGS 0/2 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 000/002 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-05 | 2022-08-05 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.493319 | 38.4516 | ETL.5790 | 40664027 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566865 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 21/249 RMV DEBRIS | 44420921 | DRUM-SUMMIT #1 | 018/212 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.48067 | 39.3173 | ETL.1440 | 44338215 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566922 | Q3 | T2 DI CARIBOU-WESTWOD 12/242 RMV PL BUT |  | CARIBOU-WESTWOOD | 012/242 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2022-08-05 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.075385 | 40.2314 | ETL.6300 | 40862089 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566926 | Q3 | T2 DI CARIBOU-WESTWOOD 12/242 RPLC INSW | 31513339 | CARIBOU-WESTWOOD | 012/242 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.075405 | 40.2313 | ETL.6300 | 40885479 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119566929 | Q3 | T2 DI CARIBOU-WESTWOOD 12/242 RPR GYWW |  | CARIBOU-WESTWOOD | 012/242 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.075385 | 40.2314 | ETL.6300 | 40862089 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567319 | Not Scheduled | T2NT DI DRM-SMMT #1 18/211 RMV PL BUTT | 44434590 | DRUM-SUMMIT #1 | 018/211 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2022-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.481891 | 39.3172 | ETL.1440 | 44338207 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567395 | Mar | T3 EI WEST POINT-VALLY SPRINGS 2/36 REPL |  | WEST POINT-VALLEY SPRINGS | 002/036 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.5947457 | 38.4176 | ETL.8350 | 40603544 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567406 | Mar | T3 EI WEST POINT-VLLY SPRINGS 2/3 RPR GY |  | WEST POINT-VALLEY SPRINGS | 002/036 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.594733 | 38.4176 | ETL.8350 | 40579950 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567434 | Q2 | T2 DI PHILO JCT-ELK 3/6 REFRAME | 31507080 | PHILO JCT-ELK | 003/006 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.209832 | 39.086 | ETL.7780 | 40820699 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567498 | Q2 | T2 DI FORT ROSS-GUALALA 030/008 RPR STRW |  | GUALALA-MONTE RIO | 030/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.245435 | 38.5492 | ETL.6980 | 44942620 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567667 | Q2 | T2 DI PHILO JCT-ELK 017/001 RPR GYWW | 44610684 | PHILO JCT-ELK | 017/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.413272 | 39.0519 | ETL.7780 | 44837852 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567792 | Q4 | T3 MIDDLE FORK-GLD HLL 11/091R RPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 011/091 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.764882 | 38.9769 | ETL.5140 | 44553679 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567795 | Q4 | T3 MIDDLE FORK-GOLD HILL 12/101L RPL PL | 31510070 | MIDDLE FORK-GOLD HILL | 012/101 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.787319 | 38.9649 | ETL.5140 | 44553578 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567805 | Q4 | T3 MIDDLE FORK-GOLD HILL 12/101R RPL PL | 31510070 | MIDDLE FORK-GOLD HILL | 012/101 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.787319 | 38.9649 | ETL.5140 | 44553548 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567831 | Q4 | T3 MIDDLE FORK-GOLD HILL 13/113R RPL PL | 31510070 | MIDDLE FORK-GOLD HILL | 013/113 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.808918 | 38.9501 | ETL.5140 | 44553518 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567840 | Q4 | T3 MIDDLE FORK-GOLD HILL 13/113L RPL PL | 31510070 | MIDDLE FORK-GOLD HILL | 013/113 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.808918 | 38.9501 | ETL.5140 | 44553582 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567865 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/252 RPL STRW | 31521951 | DRUM-SUMMIT #2 | 021/252 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.429206 | 39.3262 | ETL.1450 | 44553748 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119567934 | Not Scheduled | EI PIT #1-COTTONWOOD 9/80 RPL STRT |  | PIT #1-COTTONWOOD | 009/080 | 70S | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.651337 | 40.9098 | ETL.5390 | 40601037 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568043 | Mar | T3 EI WEST POINT-VLLY SPRINGS 2/29 RPR S |  | WEST POINT-VALLEY SPRINGS | 002/029 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.5886322 | 38.422 | ETL.8350 | 40800418 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568054 | Mar | T3 EI WEST POINT-VLLY SPRNGS 2/30 RPR SP |  | WEST POINT-VALLEY SPRINGS | 002/030 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.589342 | 38.4215 | ETL.8350 | 40772139 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568183 | Q4 | T3 DI MDDLE FRK-GLD HLL 11/94L REPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 011/094 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.773631 | 38.9722 | ETL.5140 | 44553576 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568184 | Q4 | T3 DI MDDLE FRK-GLD HLL 11/94R REPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 011/094 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-08 | 2021-01-08 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.773631 | 38.9722 | ETL.5140 | 44553577 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568192 | Not Scheduled | T3 DI FULTON-CALISTOGA 5/5 RPR STRW |  | FULTON-CALISTOGA | 005/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.500601 | 38.5611 | ETL.6880 | 40769669 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568225 | Not Scheduled | T3NT DI FULTON-CALISTOGA 5/5 RMV DEBRIS |  | FULTON-CALISTOGA | 005/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.500601 | 38.5611 | ETL.6880 | 40769669 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568267 | Q2 | T3 DI FULTON-CALISTOGA :4/3 RPLC STRW | 31510986 | FULTON-CALISTOGA | :004/003 | 70Y | E | 2020_(1a) PSPS |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.592727 | 38.6477 | ETL.6880 | 40912446 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119568270 | Feb | T2 EI COLGATE-GRASS VALLY 1/42 INST MRKW | 44477156 | COLGATE-GRASS VALLEY | 001/042 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2022-08-06 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.157797 | 39.3234 | ETL.6490 | 40874460 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568276 | Not Scheduled | NEWARK-LAWRENCE LAB 6/43 REPL INSS | 31507589 | NEWARK-LAWRENCE LAB | 006/043 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 | [9 empty] | Central | WSIP | [6 empty] | '-121.8901123 | 37.5486 | ETL.3060 | 40671137 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568492 | Q3 | T2 DI CARIBOU-WESTWOOD 018/364 RPL PL | 31513338 | CARIBOU-WESTWOOD | 018/364 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.051627 | 40.2912 | ETL.6300 | 40599588 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119568494 | Not Scheduled | T2 DI DRUM-SUMMIT #2 018/216L REPL POLE |  | DRUM-SUMMIT #2 | 018/216 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.481913 | 39.3173 | ETL.1450 | 44552256 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569025 | Q3 | T2NT DI CARIBOU #2 ;004/019 RMV BUTT |  | CARIBOU #2 | ;004/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.948948 | 39.9683 | ETL.6280 | 40864715 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569087 | Q4 | T3 EI MAPLE CREEK-HOOPA 18/0 RPR GRWS | 44453324 | MAPLE CREEK-HOOPA | 018/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.672624 | 40.9376 | ETL.7490 | 40617820 | Ground Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569135 | Q3 | EI BRIDGEVILLE-GARBERVILLE 24/1 RMV BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 024/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 |  |  | 2021-08-28 | 2021-08-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.724367 | 40.2049 | ETL.6220 | 40586749 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569137 | Q3 | EI BRIDGEVILLE-GARBERVILLE 24/1 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 024/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.724367 | 40.2049 | ETL.6220 | 40586749 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569145 | Q3 | EI BRIDGEVILLE-GARBERVILLE 24/3 RPR GYWW | 44476628 | BRIDGEVILLE-GARBERVILLE | 024/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.72117 | 40.2041 | ETL.6220 | 40666729 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569299 | Mar | T2 EI FULTON-HOPLAND 12/000 REFRAME | 31509679 | FULTON-HOPLAND | 012/000 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.858097 | 38.6373 | ETL.6890 | 40587783 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569300 | Not Scheduled | T2 DI DRUM-SUMMIT #2 022/262 RPL INSW | 31522060 | DRUM-SUMMIT #2 | 022/262 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.413806 | 39.3284 | ETL.1450 | 40619939 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569306 | Not Scheduled | T2 DI DRUM-SUMMIT #2 020/246 RPR STRW | 44470921 | DRUM-SUMMIT #2 | 020/246 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.437634 | 39.3228 | ETL.1450 | 44549972 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569327 | Q2 | T3NT DI FULTON-CALISTOGA :5/6 RMV BUTT | 44597303 | FULTON-CALISTOGA | :005/006 | ICW | F | 2020_(1a) PSPS |  | 2020-08-06 | 2022-08-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.588821 | 38.6653 | ETL.6880 | 40912463 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119569383 | Q2 | T3 DI FULTON-CALISTOGA :5/6 REFRAME | 31510987 | FULTON-CALISTOGA | :005/006 | 93E | E | 2020_(1a) PSPS |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588821 | 38.6653 | ETL.6880 | 40912463 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119569410 | Q2 | T3 DI FULTON-CALISTOGA :5/6 RPR STRW | 44597303 | FULTON-CALISTOGA | :005/006 | ICW | E | 2020_(1a) PSPS |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588821 | 38.6653 | ETL.6880 | 40912463 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119569443 | Q2 | EI SNEATH LANE-HALF MN BY ?0/19 RPR POLE | 44620196 | SNEATH LANE-HALF MOON BAY | ?000/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.496864 | 37.5854 | ETL.7212 | 40862852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569504 | Not Scheduled | T3NT DI FULTON-CALISTOGA :6/4 RMV DEBRIS | 44597303 | FULTON-CALISTOGA | :006/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2022-08-05 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.588338 | 38.675 | ETL.6880 | 40912474 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569560 | Q4 | T3 EI MAPLE CREEK-HOOPA 9/10 RPR STRW | 44394730 | MAPLE CREEK-HOOPA | 009/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779855 | 40.8799 | ETL.7490 | 40617814 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569606 | Mar | EI T3NT MORAGA-SAN LNDRO #3 2/17 RPR FON | 44303862 | MORAGA-SAN LEANDRO #3 | 002/017 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-06 | 2022-08-06 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.143163 | 37.8194 | ETL.2790 | 40808549 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569670 | Q4 | T3 EI MAPLE CREEK-HOOPA 10/0 RPL POLE | 31516371 | MAPLE CREEK-HOOPA | 010/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324521 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569762 | Q2 | T2 DI FORT ROSS-GUALALA 43/9 RPL STRW | 31514146 | GUALALA-MONTE RIO | 043/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.316716 | 38.6942 | ETL.6980 | 40860815 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569772 | Mar | EI T3NT MORAGA-SAN LEANDRO #3 2/18 RPR F | 44303862 | MORAGA-SAN LEANDRO #3 | 002/018 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-06 | 2022-08-06 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.141566 | 37.8182 | ETL.2790 | 40857659 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569873 | Not Scheduled | T3 DI FULTON-CALISTOGA 3/0 RPR SPLW |  | FULTON-CALISTOGA | 003/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.481151 | 38.53 | ETL.6880 | 40640977 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569921 | Not Scheduled | T3NT DI FULTON-CALISTOGA 3/0 RMV DEBRIS |  | FULTON-CALISTOGA | 003/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.481151 | 38.53 | ETL.6880 | 40616384 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569927 | Not Scheduled | T3 DI FULTON-CALISTOGA 3/0 RPR STRW |  | FULTON-CALISTOGA | 003/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.481151 | 38.53 | ETL.6880 | 40616384 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119569931 | Q2 | EI SNEATH LANE-HALF MN BY ?0/8 RPR INSS | 44620197 | SNEATH LANE-HALF MOON BAY | ?000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.493164 | 37.5915 | ETL.7212 | 40863180 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570028 | Not Scheduled | T3 DI FULTON-CALISTOGA 8/2 RPR STRW |  | FULTON-CALISTOGA | 008/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.53998 | 38.5839 | ETL.6880 | 40700650 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570066 | Not Scheduled | T3NT DI FULTON-CALSTGA :009/004 INS MRKW |  | FULTON-CALISTOGA | :009/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.606174 | 38.7189 | ETL.6880 | 40905741 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570069 | Not Scheduled | T3 DI FULTON-CALISTOGA :009/004 RPR STRW | 44597303 | FULTON-CALISTOGA | :009/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.606174 | 38.7189 | ETL.6880 | 40905741 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570181 | Not Scheduled | T3 DI FULTON-CALISTOGA 005/006 RPR STRW |  | FULTON-CALISTOGA | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.501874 | 38.5631 | ETL.6880 | 40827278 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570207 | Q2 | T2 EI TRINITY-MAPLE CREEK_012/003L RPL P | 31510696 | TRINITY-MAPLE CREEK | 012/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.135178 | 40.7675 | ETL.8170 | 44769647 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570291 | Q2 | T2 EI TRINITY-MAPLE CREEK_012/003R RPL P | 31510696 | TRINITY-MAPLE CREEK | 012/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.135178 | 40.7675 | ETL.8170 | 44769655 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570331 | Q2 | DI RIO BRAVO-KERN OIL 15/4 RPR GYWW | 44612467 | RIO BRAVO-KERN OIL (IDLE) | 015/004 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.200822 | 35.4415 | ETL.1922 | 44182538 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119570389 | Q2 | DI RIO BRAVO-KERN OIL 12/8 INST MRKS | 44612468 | RIO BRAVO-KERN OIL (IDLE) | 012/008 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.247296 | 35.4416 | ETL.1922 | 44182447 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119570408 | Q2 | T3 DI SNEATH LANE-PACIFICA 6/64 RPL STRW | 31510922 | SNEATH LANE-PACIFICA | 006/064 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.469911 | 37.6017 | ETL.7575 | 40599267 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119570665 | Q2 | DI RIO BRAVO-KERN OIL 14/1 INST MRKS | 44612470 | RIO BRAVO-KERN OIL (IDLE) | 014/001 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.22504 | 35.4416 | ETL.1922 | 44182524 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119571315 | Q2 | T2 DI FORT ROSS-GUALALA 50/8 RPR SPLW |  | GUALALA-MONTE RIO | 050/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.416662 | 38.726 | ETL.6980 | 40884118 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119571403 | Q3 | T2 DI CARIBOU-WESTWOOD 015/309 RPL PL | 31513338 | CARIBOU-WESTWOOD | 015/309 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.08645 | 40.2699 | ETL.6300 | 40824715 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119571584 | Feb | T2 EI COLGATE-GRASS VALLEY 8/186 REFRAME | 31510691 | COLGATE-GRASS VALLEY | 008/186 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.089112 | 39.2665 | ETL.6490 | 40613018 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573577 | Not Scheduled | T3NT DI FULTON-CALISTOGA :6/3 INST MRKW |  | FULTON-CALISTOGA | :006/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.587414 | 38.6737 | ETL.6880 | 40912473 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573584 | Not Scheduled | T3 EI PIT #1-COTTONWOOD 25/199 |  | PIT #1-COTTONWOOD | 025/199 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-02-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.891633 | 40.8041 | ETL.5390 | 40856773 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573657 | Feb | T2 EI COLGATE-GRASS VALLY 3/72 INST MRKW | 44477156 | COLGATE-GRASS VALLEY | 003/072 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2022-08-06 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.135423 | 39.3213 | ETL.6490 | 40590716 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573663 | Q4 | T2 DI KESWICK-TRINITY 23/371 RPR WPKR |  | KESWICK-TRINITY | 023/371 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [8 empty] | ETL.7270 | 44421168 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573668 | Q4 | T2 DI KESWICK-TRINITY 23/371 RPL HRDD |  | KESWICK-TRINITY | 023/371 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [8 empty] | ETL.7270 | 44421167 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573669 | Q4 | T2 DI KESWICK-TRINITY 23/371 RPL HRDD |  | KESWICK-TRINITY | 023/371 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-09 | 2021-07-09 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [8 empty] | ETL.7270 | 44421169 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573677 | Feb | T2 EI COLGATE-GRASS VALLY 3/73 RPR WDPKR | 44476724 | COLGATE-GRASS VALLEY | 003/073 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.134833 | 39.3212 | ETL.6490 | 40695676 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573754 | Q2 | T3 DI FULTON-CALISTOGA 8/4 RPL GYWW | 44597303 | FULTON-CALISTOGA | 008/004 | ICW | E | 2020_(1a) PSPS |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.541219 | 38.5852 | ETL.6880 | 40770412 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119573755 | Not Scheduled | T3 DI FULTON-CALISTOGA :9/6 RPR GYWW | 44597303 | FULTON-CALISTOGA | :009/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.606512 | 38.7211 | ETL.6880 | 40905743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573756 | Q2 | T2 DI FORT ROSS-GUALALA 046/010 RPR STRW |  | GUALALA-MONTE RIO | 046/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-08-06 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.356673 | 38.7173 | ETL.6980 | 40616634 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573757 | Q2 | T2NT DI FORT ROSS-GLALA 46/10 RMV DEBRIS |  | GUALALA-MONTE RIO | 046/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-06 | 2022-08-06 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.356673 | 38.7173 | ETL.6980 | 40616634 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573758 | Q2 | T2 DI FORT ROSS-GUALALA 050/012 RPR GYWW |  | GUALALA-MONTE RIO | 050/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.42071 | 38.7276 | ETL.6980 | 40701004 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573910 | Q2 | T2 DI FORT ROSS-GUALALA 41/5 RPR STRW |  | GUALALA-MONTE RIO | 041/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-08-06 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.309038 | 38.6613 | ETL.6980 | 40750307 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119573923 | Not Scheduled | T2NT DI FORT RSS-GLLA 52/12 RMV PL BUT |  | GUALALA-MONTE RIO | 052/012 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.453173 | 38.7385 | ETL.6980 | 40656415 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574014 | Q2 | DONNELLS-CURTIS 021/6 RMV DEBRIS | 44623580 | ETL.1073.POLE.STPS | 021/006 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-06 | 2022-08-06 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.2538415 | 38.0207 | ETL.1073 | 44385267 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574063 | Q2 | T2 DI IGNACIO-BOLINAS #2 5/59 RPLC STRW | 31514228 | IGNACIO-BOLINAS #2 | 005/059 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-08-06 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.624681 | 38.099 | ETL.7180 | 40770135 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574066 | Q2 | T2 DI IGNACIO-BOLINAS #2 13/159 RMV BUTT | 44640732 | IGNACIO-BOLINAS #2 | 013/159 | ICW | E | 2020_(3) On high spread structure |  | 2020-08-06 | 2021-08-06 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.718793 | 38.0655 | ETL.7180 | 40809520 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574132 | Q2 | T2 EI TRINITY-MAPLE CREEK 7/16 RPR INSW | 44453151 | TRINITY-MAPLE CREEK | 007/016 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-08-06 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 40916028 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574181 | Feb | T2 EI COLGATE-GRASS VALLEY 10/242 REPLUM | 44429531 | COLGATE-GRASS VALLEY | 010/242 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079255 | 39.2316 | ETL.6490 | 40593248 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574409 | Feb | T3 EI BRIDGVILLE-GARBRVILLE 7/3 RPL ANCW | 31510984 | BRIDGEVILLE-GARBERVILLE | 007/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-04-18 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743956 | 40.4039 | ETL.6220 | 40666713 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574454 | Not Scheduled | T2 EI CARIBOU-PALERMO 1/014 RMV STEP |  | CARIBOU-PALERMO | :001/014 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.171253 | 40.0708 | ETL.3190 | 40910259 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574517 | Q2 | EI GARBERVILLE-LAYTONVILLE 32/7 RMV DEBR | 44311203 | GARBERVILLE-LAYTONVILLE | 032/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.547036 | 39.8103 | ETL.8365 | 40824434 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574600 | Q2 | EI GARBERVILLE-LAYTONVILLE 32/8 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 032/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.54908 | 39.811 | ETL.8365 | 40861087 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119574710 | Feb | T3 EI KILARC-CEDAR CREEK 0/8 RPL STRW | 31512795 | KILARC-CEDAR CREEK | 000/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-23 | 2020-11-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87882 | 40.68 | ETL.7290 | 40590481 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575036 | Mar | EI T3NT MORAGA-SAN LEANDRO #3 3/23 RPR F | 44303862 | MORAGA-SAN LEANDRO #3 | 003/023 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-07 | 2022-08-07 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.136734 | 37.8119 | ETL.2790 | 40648780 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575376 | Not Scheduled | T3 DI RND MTN-CTTNWD #3 28/228 RPR STRT | 43932111 | ROUND MTN-COTTONWOOD #3 | 028/228 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.944952 | 40.7841 | ETL.5650 | 40865161 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575422 | Not Scheduled | T3 DI RND MTN-CTTNWD #3 31/259 RPR STRT | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/259 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.976159 | 40.7468 | ETL.5650 | 40864681 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575423 | Not Scheduled | T3 DI RND MTN-CTTNWD #3 31/259 INST STEP | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/259 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.976159 | 40.7468 | ETL.5650 | 40864681 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575426 | Q2 | T2 DI PT #5-RND MTN #1 12/121A RMV BUTT |  | PIT #5-ROUND MTN #1 | 012/121A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2022-08-05 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.933899 | 40.8231 | ETL.5420 | 44150347 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575431 | Q2 | T3 DI FULTON-CALISTOGA :002/0 RPR CNDW | 44597303 | FULTON-CALISTOGA | :002/000 | ICW | E | 2020_(1a) PSPS |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585691 | 38.6206 | ETL.6880 | 44286127 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119575434 | Q2 | T3NT DI FULTON-CALISTOGA :2/0 INS MRKW | 44597303 | FULTON-CALISTOGA | :002/000 | ICW | F | 2020_(1a) PSPS |  | 2020-08-06 | 2022-08-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.585691 | 38.6206 | ETL.6880 | 40912423 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119575551 | Mar | EI T3NT MORAGA-SAN LEANDRO #3 3/21 RPR F | 44303862 | MORAGA-SAN LEANDRO #3 | 003/021 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-07 | 2022-08-07 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.138206 | 37.8142 | ETL.2790 | 40580824 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575794 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 22/196R RPL PL | 31526498 | BRIDGEVILLE-COTTONWOOD | 022/196 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.687411 | 40.3746 | ETL.1110 | 44424092 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575832 | Q2 | EI LOS BANOS-MIDWAY #2 5/026 BENT STL | 44490736 | LOS BANOS-MIDWAY #2 | 005/026 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-04 | 2021-08-04 |  |  | 2021-04-15 | 2021-02-16 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | WSIP | [6 empty] | '-120.971043 | 36.9772 | ETL.6010 | 40812136 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119575887 | Not Scheduled | EI T3NT RND MTN-CTTNWD #3 29/242 RPR FON | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/242 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2022-08-07 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.959932 | 40.7662 | ETL.5650 | 40668240 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119575990 | Mar | EI T3NT MORAGA-SAN LEANDRO #3 2/20 CNCL |  | MORAGA-SAN LEANDRO #3 | 002/020 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-07 | 2022-08-07 |  |  | 2021-03-12 |  |  |  | CANCEL/CNCL | TR3 |  | Central | WSIP | [6 empty] | '-122.139234 | 37.8158 | ETL.2790 | 40587930 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576096 | Not Scheduled | T3 DI RND MTN-CTTNWD #3 30/256 RPR STRT | 43932111 | ROUND MTN-COTTONWOOD #3 | 030/256 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.972989 | 40.7506 | ETL.5650 | 40813494 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576099 | Q2 | T3NT DI EAGLE ROCK-REDBUD :0/3 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :000/003 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-07 | 2022-08-07 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.804759 | 38.8323 | ETL.1480 | 40648890 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576402 | Q2 | T2 EI BRDGVLL-CTTNWD 22/198 INST SPLT BL | 44404807 | BRIDGEVILLE-COTTONWOOD | 022/198 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.691523 | 40.3744 | ETL.1110 | 44424383 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576405 | Q2 | T2 DI IGNACIO-BOLINAS #2 9/117 RPL POLE | 31514228 | IGNACIO-BOLINAS #2 | 009/117 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.678147 | 38.1129 | ETL.7180 | 40825741 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576408 | Q2 | T2 DI IGNACIO-BOLINAS #2 18/210 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 018/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.786163 | 38.0419 | ETL.7180 | 40588078 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576433 | Q2 | T2 DI IGNACIO-BOLINAS #2 9/115 RPR STRW | 44640732 | IGNACIO-BOLINAS #2 | 009/115 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.675554 | 38.1143 | ETL.7180 | 40751191 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576499 | Not Scheduled | EI T3NT RND MTN-CTTNWD #3 29/243 RPR FON | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/243 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2022-08-07 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.960782 | 40.7652 | ETL.5650 | 40662306 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576522 | Not Scheduled | T3 EI ROUND MTN-CTTNWD #3 29/245 RPR FON | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/245 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.96243 | 40.7632 | ETL.5650 | 40755330 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576600 | Q2 | EI DONNELLS-CURTIS 22/2L RMV BUTT | 44623581 | ETL.1073.POLE.STPS | 022/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-07 | 2022-08-07 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.258245 | 38.0149 | ETL.1073 | 44385270 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576700 | Q2 | EI DONNELLS-CURTIS 22/002C RMV BUTT | 44623582 | ETL.1073.POLE.STPS | 022/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-07 | 2022-08-07 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.258245 | 38.0149 | ETL.1073 | 44385271 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576708 | Q2 | EI MI WUK CURTIS 22/2 RPR GYWS | 44623583 | ETL.1073.POLE.STPS | 022/002 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.258245 | 38.0149 | ETL.1073 | 44385272 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119576711 | Q2 | EI DONNELLS-CURTIS 22/002R RMV BUTT | 44623584 | ETL.1073.POLE.STPS | 022/002 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-07 | 2022-08-07 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.258245 | 38.0149 | ETL.1073 | 44385272 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577068 | Feb | EI RUND MTN-CTNWD #3 49/430 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 049/430 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-02-19 | 2021-02-15 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.1600281 | 40.526 | ETL.5650 | 40634942 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577069 | Feb | T2 EI COLGATE-GRASS VALLEY 4/112 RMV BUT | 44429532 | COLGATE-GRASS VALLEY | 004/112 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-07 | 2022-08-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.114348 | 39.3132 | ETL.6490 | 40767732 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577096 | Q2 | T3 DI CRESTA-RIO OSO 14/118 RPLC INSS | 31500129 | CRESTA-RIO OSO | 014/118 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.4590 | 40921060 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577098 | Q2 | T2 DI IGNACIO-BOLINAS #2 5/62 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 005/062 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.627339 | 38.1029 | ETL.7180 | 40862724 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577202 | Q2 | EI GARBERVILLE-LAYTONVILLE 57/5 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 057/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.699282 | 40.1035 | ETL.8365 | 40912649 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577291 | Q2 | T2 DI ELK-GUALALA 41/2 RPLC INSW | 31506140 | ELK-GUALALA | 041/002 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.690156 | 39.0744 | ETL.8410 | 40734950 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577295 | Q2 | T3 DI SNTH LN-HLF MN BY ?2/5 RPR SPLW | 44621669 | SNEATH LANE-HALF MOON BAY | ?002/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.494267 | 37.5677 | ETL.7212 | 44865989 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | MSB | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577517 | Q2 | EI GARBERVIL-LAYTONVIL 56/009 RPR POLE | 44449697 | GARBERVILLE-LAYTONVILLE | 056/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.68307 | 40.097 | ETL.8365 | 40912631 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577519 | Q2 | EI GARBERVILLE-LAYTONVILLE 33/5 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 033/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.561641 | 39.8184 | ETL.8365 | 40750497 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577551 | Q2 | EI GARBERVILLE-LAYTONVILLE 56/9 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 056/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.68307 | 40.097 | ETL.8365 | 40912631 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577554 | Q2 | EI GARBERVILLE-LAYTONVILLE 33/004 RMV BU | 44311203 | GARBERVILLE-LAYTONVILLE | 033/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.561417 | 39.8178 | ETL.8365 | 40750535 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577555 | Q2 | EI GARBERVILLE-LAYTONVILLE 57/3 RMV BUTT | 44311204 | GARBERVILLE-LAYTONVILLE | 057/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-07 | 2022-08-07 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.69466 | 40.1031 | ETL.8365 | 40912647 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577557 | Q2 | EI GARBERVILLE-LAYTONVILLE 57/3 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 057/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.69466 | 40.1031 | ETL.8365 | 40912647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577562 | Q2 | EI GARBERVILLE-LAYTONVILLE 58/006 RPL PL | 31511613 | GARBERVILLE-LAYTONVILLE | 058/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.716198 | 40.1075 | ETL.8365 | 40912659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577567 | Q2 | EI GARBERVILLE-LAYTNVLL 33/005 RPR JUMW | 44476763 | GARBERVILLE-LAYTONVILLE | 033/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.561641 | 39.8184 | ETL.8365 | 40750497 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119577648 | Not Scheduled | T2NT MENDCINO-WLITS-FT BRG 40/3 RPL ROAD | 31512631 | MENDOCINO-WILLITS-FORT BRAGG | 040/003 | 71Y | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-03 | 2022-08-03 |  |  |  | 2021-10-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.761326 | 39.4222 | ETL.7550 | 40666502 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578061 | Q2 | T2 SNEATH LANE-HALF MN BY ?11/9 RPL INSS | 31474364 | SNEATH LANE-HALF MOON BAY | ?011/009 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.425539 | 37.4714 | ETL.7212 | 40732015 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578086 | Not Scheduled | T3 EI PIT #1-COTTONWOOD 31/259 REPLUMB |  | PIT #1-COTTONWOOD | 031/259 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9761311 | 40.7465 | ETL.5390 | 40891155 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578120 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/006 RPL STRW | 31514054 | MAPLE CREEK-HOOPA | 012/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.757625 | 40.9071 | ETL.7490 | 44743798 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578190 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/006 RPL STRW | 31514054 | MAPLE CREEK-HOOPA | 012/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.757625 | 40.9071 | ETL.7490 | 44743797 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578222 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/006 RPL STRW | 31514054 | MAPLE CREEK-HOOPA | 012/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.757625 | 40.9071 | ETL.7490 | 44743796 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578276 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/5 RPL POLE | 31511017 | MAPLE CREEK-HOOPA | 012/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.75827 | 40.9067 | ETL.7490 | 40770516 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578305 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/4 RPL INSW | 31511251 | MAPLE CREEK-HOOPA | 012/004 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.75924 | 40.9063 | ETL.7490 | 40752759 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578308 | Q4 | EI T3NT MAPLE CREEK-HOOPA 12/3 RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 012/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.759972 | 40.906 | ETL.7490 | 40668477 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578342 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/3 RPL INSS | 31511251 | MAPLE CREEK-HOOPA | 012/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.759972 | 40.906 | ETL.7490 | 40668477 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578370 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/2 RPL INSS | 31511251 | MAPLE CREEK-HOOPA | 012/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.762235 | 40.905 | ETL.7490 | 40662163 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578376 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/1 RPL INSS | 31511251 | MAPLE CREEK-HOOPA | 012/001 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.762882 | 40.9047 | ETL.7490 | 40586849 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578403 | Q4 | EI MAPLE CREEK-HOOPA 12/000 INST JMP SPP | 44453324 | MAPLE CREEK-HOOPA | 012/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.763465 | 40.9044 | ETL.7490 | 40591312 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578407 | Feb | T3 EI COLGATE-GRASS VALLEY 5/134 REPLUMB | 44429534 | COLGATE-GRASS VALLEY | 005/134 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.107078 | 39.301 | ETL.6490 | 40874470 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578408 | Feb | T3 EI COLGATE-GRASS VALLEY 5/135 REPLUMB | 44429534 | COLGATE-GRASS VALLEY | 005/135 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.106738 | 39.3005 | ETL.6490 | 40602476 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578409 | Feb | T3 EI COLGATE-GRASS VALLEY 5/144 REPLUMB | 44429534 | COLGATE-GRASS VALLEY | 005/144 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.103158 | 39.2952 | ETL.6490 | 40874472 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578432 | Feb | T2 EI COLGATE-GRASS VALEY 6/147 RPL INSW | 31514058 | COLGATE-GRASS VALLEY | 006/147 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.1023002 | 39.294 | ETL.6490 | 40636160 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119578580 | Not Scheduled | T2 DI FULTON-CALISTOGA :011/006 RPR STRW | 44597303 | FULTON-CALISTOGA | :011/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.610405 | 38.748 | ETL.6880 | 40911340 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119579350 | Q3 | EI GATES-GREGG 3/015 BENT MEMB | 44490873 | SPARE T-LINE RECORD | 003/015 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-08 | 2021-08-08 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.077199 | 36.1595 | ETL.2604 | 40751524 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119580281 | Not Scheduled | EI STANISLAUS-NEWARK #2 96/624 RPL INSS |  | STANISLAUS-NEWARK #2 (12KV) | 096/624 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-08-08 | [9 empty] | Central | WSIP | [6 empty] | '-121.9085783 | 37.5615 | ETL.3860 | 40803213 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119580528 | Q4 | T3 EI MAPLE CREEK-HOPA 12/013C RPL PL | 31514224 | MAPLE CREEK-HOOPA | 012/013 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-02-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7496935 | 40.9067 | ETL.7490 | 44145849 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119580548 | Q4 | T3 EI MAPLE CREEK-HOOPA 012/013R RPL PL | 31514224 | MAPLE CREEK-HOOPA | 012/013 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-02-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7496935 | 40.9067 | ETL.7490 | 44145850 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119580647 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/10 RPR CNDW | 44394730 | MAPLE CREEK-HOOPA | 012/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-02-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.752102 | 40.9076 | ETL.7490 | 40591315 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119580675 | Q4 | T3 EI MAPLE CREEK-HOOPA 12/9 RPL POLE | 31511017 | MAPLE CREEK-HOOPA | 012/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-02-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.752995 | 40.9079 | ETL.7490 | 40862590 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119580968 | Not Scheduled | EI STANISLAUS-NEWARK #2 95/623 RPL INSS |  | STANISLAUS-NEWARK #2 (12KV) | 095/623 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-08-08 | [9 empty] | Central | WSIP | [6 empty] | '-121.9036195 | 37.5622 | ETL.3860 | 40701171 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119580980 | Not Scheduled | EI STANISLAUS-NEWARK #2 94/616 RPL INSS |  | STANISLAUS-NEWARK #2 (12KV) | 094/616 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-08 | 2021-08-08 | [9 empty] | Central | WSIP | [6 empty] | '-121.885579 | 37.5728 | ETL.3860 | 40856327 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119590924 | Q2 | T2 DI IGNACIO-BOLINAS #2 18/211 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 018/211 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.784347 | 38.0411 | ETL.7180 | 40861081 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119591114 | Mar | T3 DI WST PNT-VLY SPRNGS 0/3 RPR WDPKR | 44631078 | WEST POINT-VALLEY SPRINGS | 000/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-02-10 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.548943 | 38.4217 | ETL.8350 | 40643805 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119591422 | Q2 | T2 DI LAKEVILLE #2 A006/125A RPR INSW |  | LAKEVILLE #2 | A006/125A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.7340 | 43603674 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119591424 | Mar | T3 DI WST PNT-VLY SPRNGS 0/1A RPR GYWW |  | WEST POINT-VALLEY SPRINGS | 000/001A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-02-10 |  |  | 2021-03-27 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.549598 | 38.4213 | ETL.8350 | 41167107 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119591828 | Q3 | T3 EI DONNELLS-MI-WUK 015/003 RPR STRW | 44623585 | DONNELLS-CURTIS | 015/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.172159 | 38.0796 | ETL.1400 | 40661820 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119591840 | Q2 | DI LAKEVILLE #2 013/287 GRD WAS INSU |  | LAKEVILLE #2 | 013/287 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-21 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.719753 | 38.3032 | ETL.7340 | 40900835 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119591843 | Q2 | T2 DI IGNACIO-BOLINAS #2 11/137 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 011/137 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.691582 | 38.091 | ETL.7180 | 40770925 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119592116 | Feb | T2 EI COLGATE-GRASS VALLEY 5/125 RPL PL | 31514628 | COLGATE-GRASS VALLEY | 005/125 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-08-10 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.110397 | 39.3058 | ETL.6490 | 40603836 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119592312 | Mar | T3 DI WST PNT-VLLY SPRNGS 0/4 RPR SPLW | 44589647 | WEST POINT-VALLEY SPRINGS | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-02-10 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.549222 | 38.4217 | ETL.8350 | 40643229 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | CalTrans | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119592599 | Mar | T3 EI WEST PNT-VLLY SPRNGS 1/23 RPR WKPK | 44595506 | WEST POINT-VALLEY SPRINGS | 001/023 | ICW | E | 2020_(3) On high spread structure |  | 2020-08-07 | 2021-02-07 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.579364 | 38.4247 | ETL.8350 | 40856862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119592622 | Mar | T3 EI WEST POINT-VLLY SPRINGS 1/27 RPL S | 44631079 | WEST POINT-VALLEY SPRINGS | 001/027 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.586356 | 38.423 | ETL.8350 | 40697166 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119592841 | Not Scheduled | T3 EI COLGATE-CHALLENGE 6/111 RPL SPLW | 44435039 | COLGATE-CHALLENGE | 006/111 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.177967 | 39.3997 | ETL.6480 | 44695497 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119593028 | Q2 | T3 DI FULTON-CALISTOGA -13/8 RPR CNDW |  | FULTON-CALISTOGA | '-013/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.511195 | 38.4256 | ETL.6880 | 40861561 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119593067 | Not Scheduled | T2 EI FULTON-HOPLAND 18/9 RPL PL | 31514632 | FULTON-HOPLAND | 018/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-08-10 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.882493 | 38.7234 | ETL.6890 | 40860943 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119593430 | Not Scheduled | T3 EI COLGATE-CHALLENGE 6/114 REFRAME | 31511247 | COLGATE-CHALLENGE | 006/114 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18301 | 39.4004 | ETL.6480 | 40664715 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119593557 | Q3 | EI BRIDGEVILLE-GARBERVILLE 24/2 RPR GYWW | 44476628 | BRIDGEVILLE-GARBERVILLE | 024/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-08-10 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.721807 | 40.2043 | ETL.6220 | 40698359 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119594565 | Mar | T2 EI FULTON-HOPLAND 10/001 RPL PL | 31514632 | FULTON-HOPLAND | 010/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-08-10 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.843602 | 38.6156 | ETL.6890 | 40601387 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119594889 | Mar | T3 DI WST PNT-VLLY SPRNGS 0/1 RPR GYWW |  | WEST POINT-VALLEY SPRINGS | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-02-10 |  |  | 2021-03-27 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.549223 | 38.4211 | ETL.8350 | 41123026 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119594918 | Q2 | T2 IGNACIO-BOLINAS #2 4/053 RPL PL | 31511246 | IGNACIO-BOLINAS #2 | 004/053 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-08-10 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.616028 | 38.0929 | ETL.7180 | 40810762 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119594925 | Not Scheduled | T3 EI COLGATE-CHALLENGE 6/119 RPL CONN | 44435037 | COLGATE-CHALLENGE | 006/119 | ICM | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.189505 | 39.4015 | ETL.6480 | 44695499 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119595300 | Q2 | T3 EI PITTSBURG-SAN MATEO 13/52 INST HRD |  | PITTSBURG-SAN MATEO | 013/052 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-10 | 2021-02-10 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.888964 | 37.8575 | ETL.5463 | 40805055 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119595306 | Not Scheduled | T3 EI COLGATE-CHALLENGE 6/120 RPL SPLW | 44435039 | COLGATE-CHALLENGE | 006/120 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.189772 | 39.4019 | ETL.6480 | 44695500 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119595367 | Q2 | T3 DI FULTON-CALISTOGA -13/7 RPL POLE | 31511018 | FULTON-CALISTOGA | '-013/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.512014 | 38.4245 | ETL.6880 | 40808987 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596389 | Not Scheduled | T3 EI COLGATE-GRASS VALLY 6/150 RPLC PL | 31530141 | COLGATE-GRASS VALLEY | 006/150 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.099622 | 39.29 | ETL.6490 | 40655415 | Structure-Wood | Rotten | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596848 | Not Scheduled | T2 EI COLGATE-SMARTVILLE #2 0/009 RPL PL | 44478904 | COLGATE-SMARTVILLE #2 | 000/009 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-10 | 2021-08-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.199155 | 39.3292 | ETL.6520 | 42562716 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596875 | Not Scheduled | T2 EI COLGATE-SMARTVILLE #2 0/009 RPL PL |  | COLGATE-SMARTVILLE #2 | 000/009C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-08-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.199172 | 39.3292 | ETL.6520 | 42562717 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596884 | Not Scheduled | EI ROUND MTN-COTTONWD #3 55/496 RMV HRDW | 43932111 | ROUND MTN-COTTONWOOD #3 | 055/496 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.223248 | 40.4495 | ETL.5650 | 40817529 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596893 | Not Scheduled | T2 EI DRUM-SUMMIT#2 27/330C RPR AGSW | 44476655 | DRUM-SUMMIT #2 | 027/330 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-10 | 2021-08-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553673 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596905 | Q2 | COTTONWOOD #1 18/127 RPR BENT STL | 44498830 | COTTONWOOD #1 | 018/127 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-08-11 |  |  | 2021-05-13 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.25587 | 40.1231 | ETL.6620 | 40911124 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119596922 | Feb | EI RUND MTN-CTNWD #3 55/496 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 055/496 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-02-19 | 2021-02-15 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.223262 | 40.4495 | ETL.5650 | 40845460 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119597234 | Q2 | EI LOS BANOS-MIDWAY #2 19/081 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 019/081 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-10 | 2021-08-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.834745 | 36.8213 | ETL.6010 | 40594796 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119597235 | Q2 | EI LOS BANOS-MIDWAY #2 18/078 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 018/078 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-10 | 2021-08-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.843493 | 36.8302 | ETL.6010 | 40868518 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119597290 | Q2 | T2NT DI IGNCIO-BLNAS#2 26/292 INST MRKW | 44640732 | IGNACIO-BOLINAS #2 | 026/292 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.705774 | 37.9415 | ETL.7180 | 40743051 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119597542 | Not Scheduled | T2NT DI BRDGVL-CTTNWD 55/412 RPR MASTIC |  | BRIDGEVILLE-COTTONWOOD | 055/412 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2022-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.294441 | 40.3889 | ETL.1110 | 40765107 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119597738 | Not Scheduled | EI T2NT COLGATE-SMRTVLL #2 1/015A INS MK | 44453373 | COLGATE-SMARTVILLE #2 | 001/015A | ICW | F | 2020_(1a) PSPS |  | 2020-08-11 | 2022-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.208679 | 39.3251 | ETL.6520 | 40594220 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119598066 | Q2 | T3 DI SNTH LN-HLF MN BY ?3/5 RPR WDPKR | 44621670 | SNEATH LANE-HALF MOON BAY | ?003/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-02-11 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.479956 | 37.5588 | ETL.7212 | 40767321 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119598094 | Q2 | EI T3NT PITTSBURG-SAN MATO 011/044 RPR F |  | PITTSBURG-SAN MATEO | 011/044 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2022-08-11 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.877921 | 37.8862 | ETL.5463 | 40857948 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119598349 | Feb | EI T2NT LAURELES-OTTER 3/001 RPR ROAD | 44627165 | LAURELES-OTTER | 003/001 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-11 | 2022-08-11 |  |  | 2021-02-19 | 2021-02-11 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71788 | 36.4449 | ETL.7380 | 40585835 | Road | Grade Change | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | CH | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119598365 | Q3 | T2 EI LAURELES-OTTER 3/001 RMV VEG |  | LAURELES-OTTER | 003/001 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-11 | 2021-08-11 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71788 | 36.4449 | ETL.7380 | 40585835 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119598944 | Q2 | T3 UKIAH-HOPLAND-CLOVERDAL 12/6 RPL POLE | 31511019 | UKIAH-HOPLAND-CLOVERDALE | 012/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.992779 | 38.8329 | ETL.4050 | 40808990 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599030 | Q2 | EI GARBERVIL-LAYTONVIL 35/08 INST MRKW | 44476763 | GARBERVILLE-LAYTONVILLE | 035/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-11 | 2022-08-11 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.581516 | 39.8392 | ETL.8365 | 40906588 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599038 | Not Scheduled | T2 EI COLGATE-SMARTVILLE #2 1/19 RPL ANC | 31512602 | COLGATE-SMARTVILLE #2 | 001/019 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.212295 | 39.3234 | ETL.6520 | 40754751 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599113 | Q2 | EI GARBERVILLE-LYTNVILL 36/001 REFRAME | 31514495 | GARBERVILLE-LAYTONVILLE | 036/001 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-08-11 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579177 | 39.8467 | ETL.8365 | 40906594 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599115 | Q2 | EI GARBERVIL-LYTNVIL 36/02 INST MRKS | 44476763 | GARBERVILLE-LAYTONVILLE | 036/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-11 | 2022-08-11 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.578653 | 39.848 | ETL.8365 | 40906595 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599155 | Q2 | T2 DI SALINAS-LAURELES 009/197 RPR GYWW | 44610150 | SALINAS-LAURELES | 009/197 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.712982 | 36.5842 | ETL.7930 | 40680282 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599240 | Q2 | EI GARBERVILLE-LYTNVILL 35/011 RPLC STRW | 31514633 | GARBERVILLE-LAYTONVILLE | 035/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.580673 | 39.843 | ETL.8365 | 40906591 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599246 | Not Scheduled | T3 EAGLE ROCK-FLTN-SLVRAD :4/23 RPR INSS |  | EAGLE ROCK-FULTON-SILVERADO | :004/023 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7627876 | 38.7429 | ETL.4392 | 40689040 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599300 | Feb | T3 EAGLE ROCK-FULTON-SILVERADO - 1_006/0 |  | EAGLE ROCK-FULTON-SILVERADO | 006/027 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7585323 | 38.6423 | ETL.4392 | 44387095 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599302 | Q2 | EI GARBERVILLE-LAYTONVILLE 36/5 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 036/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.575984 | 39.8523 | ETL.8365 | 40906597 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599318 | Feb | T3 EAGLE ROCK-FLTN-SILVERAD 3/0 RPR INNS |  | EAGLE ROCK-FULTON-SILVERADO | 003/016 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-02-11 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.8021504 | 38.8015 | ETL.4392 | 44387076 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599415 | Not Scheduled | T3 GEYSERS #9-LAKEVILLE :4/23 REPL INSS |  | GEYSERS #9-LAKEVILLE | :004/023 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7968525 | 38.7723 | ETL.4780 | 40676810 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599572 | Q2 | T2 DI BRDGVL-CTTNWD 55/408 RPR SHLS | 44477511 | BRIDGEVILLE-COTTONWOOD | 055/408 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.282368 | 40.3927 | ETL.1110 | 40594234 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119599906 | Not Scheduled | T2 EI COLGATE-SMARTVILL #2 7/089A RPLC S | 31512078 | COLGATE-SMARTVILLE #2 | 007/089A | 70Y | E | 2020_(1a) PSPS |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.28934 | 39.2528 | ETL.6520 | 40770754 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119599962 | Not Scheduled | T3 FULTON-PUEBLO 38/197 INST JUMP INSS | 31505500 | FULTON-PUEBLO | 038/197 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.68717 | 38.4965 | ETL.1600 | 40818390 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119600008 | Q2 | EI T3NT PITTSBURG-SAN MATO 12/048 RPR FO |  | PITTSBURG-SAN MATEO | 012/048 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2022-08-11 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.882802 | 37.8742 | ETL.5463 | 40644628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119600382 | Q2 | T2 DI SALINAS-LAURELES A014/304 RPR CNDW | 44391519 | SALINAS-LAURELES | A014/304 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.801246 | 36.57 | ETL.7930 | 40613882 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119600387 | Q2 | T2 DI SALINAS-LAURELES A16/351 RPR PL | 44391519 | SALINAS-LAURELES | A016/351 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.835785 | 36.5809 | ETL.7930 | 40812867 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119600388 | Q2 | T2 DI SALINAS-LAURELES A12/259 RPR STRW | 44294541 | SALINAS-LAURELES | A012/259 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.764106 | 36.5704 | ETL.7930 | 40754675 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119600610 | Not Scheduled | T2 DI SALINAS-LAURELES A016/345 RPL PL | 31519843 | SALINAS-LAURELES | A016/345 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.831132 | 36.5817 | ETL.7930 | 40594191 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | Caltrans (DSDD) | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119601109 | Q2 | T2 DI BRDGVL-CTTNWD 55/411 RPR INSS | 44477511 | BRIDGEVILLE-COTTONWOOD | 055/411 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.291371 | 40.3902 | ETL.1110 | 40786775 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119601181 | Q2 | T2 DI SALINAS-LAURELES 11/245 RPLC INSW | 31511430 | SALINAS-LAURELES | 011/245 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.751444 | 36.5698 | ETL.7930 | 44913430 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-30 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119601253 | Q2 | EI LS BANOS-MIDWAY #2 22/96 RPR STRT |  | LOS BANOS-MIDWAY #2 | 022/096 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2021-08-11 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to edits |  | WECC | South | WSIP | [6 empty] | '-120.788663 | 36.7889 | ETL.6010 | 40812148 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119601273 | Feb | T3 EI COLGATE-GRASS VALLEY 7/165 RPL POL | 31514628 | COLGATE-GRASS VALLEY | 007/165 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.094423 | 39.2802 | ETL.6490 | 40612747 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119601425 | Q2 | T2 DI SALINAS-LAURELES A13/278 RPR WDPKR | 44294541 | SALINAS-LAURELES | A013/278 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.780332 | 36.5673 | ETL.7930 | 40761089 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119601686 | Not Scheduled | EI T2 CLGT-SMRTV #2 3/38 RPL PL | 31514629 | COLGATE-SMARTVILLE #2 | 003/038 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.240385 | 39.3073 | ETL.6520 | 40669368 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119601773 | Not Scheduled | EI DRUM-SUMMIT #1 13/150 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/150 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2021-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.565692 | 39.3261 | ETL.1440 | 40671376 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119601776 | Not Scheduled | EI DRUM-SUMMIT #1 13/151 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/151 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2021-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.564488 | 39.3255 | ETL.1440 | 40654775 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119601779 | Not Scheduled | EI DRUM-SUMMIT #1 13/148 RPL ANCHW |  | DRUM-SUMMIT #1 | 013/148 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2021-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.568297 | 39.3281 | ETL.1440 | 40618820 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119601787 | Not Scheduled | EI DRUM-SUMMIT #1 13/148 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/148 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2021-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.568297 | 39.3281 | ETL.1440 | 40618820 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119602208 | Not Scheduled | EI ROUND MTN-COTTOND#3 55/497 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 055/497 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.224782 | 40.4477 | ETL.5650 | 40819339 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602606 | Not Scheduled | T2 EI DRUM-SUMMIT#2 27/327C RPL ANCW |  | DRUM-SUMMIT #2 | 027/327 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3318281 | 39.3128 | ETL.1450 | 44552314 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602651 | Q2 | EI COTTONWOOD #1 19/129 RPR STRT |  | COTTONWOOD #1 | 019/129 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-13 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.248858 | 40.1215 | ETL.6620 | 40912053 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602674 | Q2 | EI COTTONWOOD #1 19/129 RPR FOUND |  | COTTONWOOD #1 | 019/129 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-12 | 2022-08-12 |  |  | 2021-05-13 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.248858 | 40.1215 | ETL.6620 | 40912053 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602681 | Not Scheduled | EI T2 COLGATE-SMARTVILLE #2 3/036 RPL PL | 31514629 | COLGATE-SMARTVILLE #2 | 003/036 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.237627 | 39.3101 | ETL.6520 | 40602842 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602682 | Not Scheduled | EI T2 CLGTE-SMRTVIL #2 3/35 RPL PL | 31514629 | COLGATE-SMARTVILLE #2 | 003/035 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.237224 | 39.3106 | ETL.6520 | 40619296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602877 | Not Scheduled | T2 DI SALNAS-LAURELES A015/331 RPL PL | 31519843 | SALINAS-LAURELES | A015/331 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.823153 | 36.5758 | ETL.7930 | 40768291 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | Caltrans (DSDD) | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119602896 | Q2 | T2 DI BRDGVLLE-COTTONWD 53/396 RPR OPGW | 44398374 | BRIDGEVILLE-COTTONWOOD | 053/396 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.243279 | 40.4024 | ETL.1110 | 40604126 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119603150 | Q2 | T2 DI SALNAS-LAURELES A12/254 RPR GYWW | 44294541 | SALINAS-LAURELES | A012/254 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.75964 | 36.5701 | ETL.7930 | 40603140 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119603165 | Q2 | T2 DI SALINAS-LRLS A13/277 RPR STRW | 44294541 | SALINAS-LAURELES | A013/277 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.778843 | 36.5675 | ETL.7930 | 40666666 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119603512 | Not Scheduled | EI DRUM-SUMMIT #1 15/182C RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/182C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523612 | 39.3074 | ETL.1440 | 44162106 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119603623 | Not Scheduled | EI DRUM-SUMMIT #1 15/182B RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/182 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523633 | 39.3074 | ETL.1440 | 42572686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119603631 | Not Scheduled | EI DRUM-SUMMIT #1 15/182B INST MRKW | 44478431 | DRUM-SUMMIT #1 | 015/182 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523633 | 39.3074 | ETL.1440 | 42572686 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119603733 | Q4 | EI MIDDLE FORK-GOLD HILL 008/074R RPL ST | 31510070 | MIDDLE FORK-GOLD HILL | 008/074 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.73223 | 38.9931 | ETL.5140 | 44553542 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119603755 | Not Scheduled | EI DRUM-SUMMIT #1 15/182A INST MRKW | 44478431 | DRUM-SUMMIT #1 | 015/182A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523676 | 39.3074 | ETL.1440 | 40671380 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119603756 | Not Scheduled | EI DRUM-SUMMIT #1 15/182A RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/182A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523676 | 39.3074 | ETL.1440 | 40671380 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119603809 | Q2 | T2NT DI SALINAS-LRLS 10/214 INST MRKW | 44610150 | SALINAS-LAURELES | 010/214 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-11 | 2022-08-11 |  |  | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.726176 | 36.5785 | ETL.7930 | 40594167 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119603862 | Q4 | T3 EI MIDDLE FORK-GOLD HILL 13/114R RPL | 31510070 | MIDDLE FORK-GOLD HILL | 013/114 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2020-12-26 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.810129 | 38.9489 | ETL.5140 | 44553648 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119603898 | Q2 | T2 DI SALNAS-LAURELES 009/199 RPR SPLW | 44610150 | SALINAS-LAURELES | 009/199 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.714272 | 36.5832 | ETL.7930 | 40768985 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604532 | Not Scheduled | T2NT EI COLGTE-SMRTVL #2 2/27 RMV DEBRIS | 44478903 | COLGATE-SMARTVILLE #2 | 002/027 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-12 | 2022-08-12 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.225514 | 39.3171 | ETL.6520 | 40666771 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604533 | Not Scheduled | T2 EI COLGATE-SMARTVILL #2 2/27 RPL POLE | 31514629 | COLGATE-SMARTVILLE #2 | 002/027 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.225514 | 39.3171 | ETL.6520 | 40666771 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604808 | Q2 | EI LOS BANOS-MIDWAY #2 024/103 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 024/103 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.764055 | 36.7742 | ETL.6010 | 40651929 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119604810 | Q2 | T2 DI SALNAS-LAURELES 006/141 RPL HRDW | 44578873 | SALINAS-LAURELES | 006/141 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.686473 | 36.6181 | ETL.7930 | 40851430 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604866 | Q2 | EI GARBERVILLE-LAYTONVILLE 37/0 RMV DBR | 44311203 | GARBERVILLE-LAYTONVILLE | 037/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-12 | 2022-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570397 | 39.8565 | ETL.8365 | 40906600 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604870 | Q2 | EI GARBERVILLE-LAYTONVILLE 37/0 RPR STRW | 44449697 | GARBERVILLE-LAYTONVILLE | 037/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570397 | 39.8565 | ETL.8365 | 40906600 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604871 | Q2 | EI GARBERVILLE-LAYTONVILLE 36/006 REPULL | 44453326 | GARBERVILLE-LAYTONVILLE | 036/006 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.573907 | 39.8539 | ETL.8365 | 40906598 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119604873 | Q2 | EI GARBERVILLE-LAYTNVLLE 37/0 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 037/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570397 | 39.8565 | ETL.8365 | 40906600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605049 | Q3 | DI BRDGVLL-GRBRVLL 000/007 RMV PL BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 000/007 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-12 | 2021-08-12 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.791454 | 40.4753 | ETL.6220 | 40810318 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605080 | Q2 | EI GARBERVILLE-LAYTONVILLE 37/005 RPL GY | 44476763 | GARBERVILLE-LAYTONVILLE | 037/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.573711 | 39.8635 | ETL.8365 | 40906609 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605154 | Q2 | EI LS BANOS-MIDWAY #2 24/104 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 024/104 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.761051 | 36.7724 | ETL.6010 | 40753962 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119605308 | Q2 | T2 WV PHILO JCT-ELK 004/004 INST DAMW |  | PHILO JCT-ELK | 004/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.215722 | 39.0733 | ETL.7780 | 40769212 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605325 | Q4 | T2 WV MAPLE CREEK-HOOPA 0/1 INST DAMW | 44453147 | MAPLE CREEK-HOOPA | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.873813 | 40.7682 | ETL.7490 | 40602126 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605486 | Q3 | EI BEARDSLEY TAP 01/09 RPR STRW |  | BEARDSLEY TAP | 001/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-08-12 |  |  | 2021-09-04 | 2021-09-03 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.060243 | 38.1875 | ETL.1401 | 44390918 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605595 | Q3 | DI BRDGVL-GRBRVL 0/6 RPR STRW WDPK | 44299806 | BRIDGEVILLE-GARBERVILLE | 000/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.789077 | 40.4761 | ETL.6220 | 40810905 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605692 | Q2 | T2 DI SALINAS-LAURELES A16/344 RPR STRW | 44391519 | SALINAS-LAURELES | A016/344 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.830622 | 36.5817 | ETL.7930 | 40875044 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605706 | Not Scheduled | T2 EI CLGTE-SMRTVLLE #2 0/7 COTTER KEY | 44460816 | COLGATE-SMARTVILLE #2 | 000/007A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.193705 | 39.3291 | ETL.6520 | 40826819 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119605737 | Not Scheduled | EI GATES-MUSTANG S S #2 13/54 REPLUMB IN | 44509237 | ETL.2605.INSL.CERA | 013/054 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-119.920898 | 36.2307 | ETL.2605 | 40739028 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119605759 | Q3 | EI GATES-GREGG 13/054 RPR FOND | 44490873 | SPARE T-LINE RECORD | 013/054 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.920898 | 36.2307 | ETL.2604 | 40746632 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119606030 | Q2 | EI MI-WUK CURTIS 23/1 RPL POLE | 31516010 | ETL.1073.POLE.WDPS | 023/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.2691804 | 38.0053 | ETL.1073 | 44774785 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119606643 | Q2 | NT DI GATES-PANOCHE #1 29/139 RPR FOND | 44490730 | GATES-PANOCHE #1 | 029/139 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.431273 | 36.4842 | ETL.4720 | 40863303 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119606946 | Q2 | EI LS BANOS-GATES #1 18/078 RPR FOUND | 44490735 | LOS BANOS-GATES #1 | 018/078 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.843898 | 36.8299 | ETL.6000 | 40868367 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119606964 | Q2 | EI LS BANOS-GATES #1 19/83 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 019/083 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.829928 | 36.8158 | ETL.6000 | 40658382 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119606965 | Q2 | EI LOS BANOS-MIDWAY #2 025/108 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 025/108 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.746187 | 36.7634 | ETL.6010 | 40871233 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119607221 | Q2 | T2 EI MI-WUK CURTIS 23/6 RPL HRDW | 44623588 | ETL.1073.POLE.WDPS | 023/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.2765767 | 37.9984 | ETL.1073 | 44776427 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607679 | Q2 | EI GARBERVILL-LAYTONVILLE 37/2B RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 037/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5691165 | 39.859 | ETL.8365 | 44403646 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607688 | Q2 | EI GARBERVILL-LAYTONVILLE 37/2B RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 037/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5691165 | 39.859 | ETL.8365 | 44403644 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607689 | Q2 | EI GARBERVILL-LAYTONVILLE 37/2 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 037/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5691165 | 39.859 | ETL.8365 | 44403645 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607729 | Not Scheduled | T3 EI COLGATE-CHALLENGE 7/136 REPLUMB IN | 44439112 | COLGATE-CHALLENGE | 007/136 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.196123 | 39.4193 | ETL.6480 | 40598651 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607777 | Not Scheduled | T3 EI COLGATE-CHALLENGE 7/134 RPR SPLW | 44439112 | COLGATE-CHALLENGE | 007/134 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.195222 | 39.4169 | ETL.6480 | 40873623 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607803 | Not Scheduled | T3 EI COLGATE-CHALLENGE 7/136 REPL SPLW | 44439112 | COLGATE-CHALLENGE | 007/136 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.196123 | 39.4193 | ETL.6480 | 40598651 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607807 | Not Scheduled | T3 EI COLGATE-CHALLENGE 8/141 REPL SPLW | 44439112 | COLGATE-CHALLENGE | 008/141 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.197775 | 39.4237 | ETL.6480 | 40767151 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607918 | Not Scheduled | T2 EI COLGATE-SMARTVLLE #2 2/31 RMV DBRS | 44483495 | COLGATE-SMARTVILLE #2 | 002/031 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-12 | 2022-08-12 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.232378 | 39.3146 | ETL.6520 | 40828767 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119607955 | Not Scheduled | T2 EI COLGATE-SMARTVILLE #2 2/031 RPL PL | 31514629 | COLGATE-SMARTVILLE #2 | 002/031 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.232378 | 39.3146 | ETL.6520 | 40828767 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608409 | Q4 | EI MAPLE CREEK-HOOPA_015/007 RPR WDPK | 44192340 | MAPLE CREEK-HOOPA | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7001724 | 40.9165 | ETL.7490 | 44145859 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608474 | Q4 | EI MAPLE CREEK-HOOPA_015/007 RPR ANCW | 44482958 | MAPLE CREEK-HOOPA | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7001724 | 40.9165 | ETL.7490 | 44145859 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608656 | Q4 | EI MAPLE CREEK-HOOPA_015/007 RPR WDPK | 44192340 | MAPLE CREEK-HOOPA | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7001724 | 40.9165 | ETL.7490 | 44145857 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608756 | Q3 | DI BRIDGEVILLE-GARBERVILL 0/8 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.792921 | 40.4749 | ETL.6220 | 40862820 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608773 | Q2 | DI GATES-PANOCHE #1 29/137 MASTIC | 44490730 | GATES-PANOCHE #1 | 029/137 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.426463 | 36.4793 | ETL.4720 | 40818933 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119608796 | Q4 | T2 EI MAPLE CREEK-HOOPA 16/003 RPR GYWW | 44453324 | MAPLE CREEK-HOOPA | 016/003 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.69646 | 40.9203 | ETL.7490 | 44735741 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608808 | Not Scheduled | DI GATES-PANOCHE #1 29/137 RPR INSS | 44509129 | GATES-PANOCHE #1 | 029/137 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.427019 | 36.4797 | ETL.4720 | 40845557 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119608881 | Q4 | T3 EI MAPLE CREEK-HOOPA 10/12 INST JMPRW | 44394730 | MAPLE CREEK-HOOPA | 010/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7711294 | 40.8935 | ETL.7490 | 40713626 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608882 | Q4 | T3 EI MAPLE CREEK-HOOPA 10/012 RPR ANCHW | 31515409 | MAPLE CREEK-HOOPA | 010/012 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-08 | 2021-02-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.771116 | 40.8935 | ETL.7490 | 40662154 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608909 | Q2 | EI GARBERVILLE-LAYTONVILLE 55/3 RPR WDPK | 44449697 | GARBERVILLE-LAYTONVILLE | 055/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.667415 | 40.0844 | ETL.8365 | 43590410 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608923 | Not Scheduled | T2 EI DRUM-SUMMIT#2 26/319L RPL STRW |  | DRUM-SUMMIT #2 | 026/319 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3421871 | 39.3095 | ETL.1450 | 44558933 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608939 | Q2 | EI GARBERVILLE-LAYTONVILLE 55/4 RPR WDPK | 44449697 | GARBERVILLE-LAYTONVILLE | 055/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.669336 | 40.086 | ETL.8365 | 43590411 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608951 | Not Scheduled | T2 EI RUM-SUMMIT#2 27/321L RPLC STRW | 31521951 | DRUM-SUMMIT #2 | 027/321 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3397735 | 39.3104 | ETL.1450 | 44557781 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608952 | Not Scheduled | T2 EI DRUM-SUMMIT#2 27/321C RPLC STRW | 31521951 | DRUM-SUMMIT #2 | 027/321 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3397735 | 39.3104 | ETL.1450 | 44557780 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119608971 | Mar | T2 DI EAGLE ROCK-CORTINA :14/19 INS MRKW |  | EAGLE ROCK-CORTINA | :014/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-12 | 2022-08-12 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.609304 | 38.9365 | ETL.1470 | 41176322 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609020 | Q2 | EI GARBERVILLE-LAYTONVILL 55/5 RPL POLE | 31511613 | GARBERVILLE-LAYTONVILLE | 055/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.670963 | 40.0873 | ETL.8365 | 40912619 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609129 | Q4 | EI MAPLE CREEK-HOOPA 10/013 RPR GYWW | 44453147 | MAPLE CREEK-HOOPA | 010/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7708964 | 40.895 | ETL.7490 | 44769635 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609167 | Q2 | EI T3NT PITTSBURG-SAN MATEO 28/111 RPR F | 44623139 | PITTSBURG-SAN MATEO | 028/111 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-13 | 2022-08-13 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.025694 | 37.6847 | ETL.5463 | 40819144 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609510 | Q2 | DI KONOCTI-EAGLE ROCK 9/7 RPR GYWW | 44610613 | KONOCTI-EAGLE ROCK | 009/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-07 | 2021-05-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.741513 | 38.9294 | ETL.6861 | 40808798 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609599 | Q2 | T2 EI SALT SPRINGS-TGR CRK 8/71 RPR STRT |  | SALT SPRINGS-TIGER CREEK | 008/071 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-08-10 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.369556 | 38.4825 | ETL.3500 | 40580454 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609690 | Q2 | T2 SALT SPRINGS-TIGER CRK 9/73 RPR STRT | 44631415 | SALT SPRINGS-TIGER CREEK | 009/073 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.372962 | 38.4824 | ETL.3500 | 40643023 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609769 | Q2 | T2 DI LAKEVILLE #2 12/261 GRD WAS INSU |  | LAKEVILLE #2 | 012/261 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.700608 | 38.2919 | ETL.7340 | 40735297 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609825 | Q2 | T2 EI MI WUK CURTIS 24/2 RMV PL BUTT | 44623589 | ETL.1073.POLE.WDPS | 024/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-13 | 2022-08-13 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.2829779 | 37.9939 | ETL.1073 | 44774795 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119609895 | Q2 | T2 EI MI WUK CURTIS 24/2 RPR WDPKR | 44623590 | ETL.1073.POLE.WDPS | 024/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.2829779 | 37.9939 | ETL.1073 | 44774795 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119610176 | Feb | T3 EAGLE ROCK-FLTN-SLVRDO 4/24 REPL HRDS | 44650521 | EAGLE ROCK-FULTON-SILVERADO | 004/024 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-02-13 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.797524 | 38.7748 | ETL.4392 | 40756575 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119610242 | Q2 | IGNACIO-MARE ISLAND #2 24/166 REPL INSS | 31514217 | IGNACIO-MARE ISLAND #2 | 024/166 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-06-03 | 2021-06-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.177245 | 38.1333 | ETL.1840 | 40785535 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119610243 | Q3 | T3 EI DONNELLS-CURTIS 3/005 RPR STRW | 44623591 | DONNELLS-CURTIS | 003/005B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-02-13 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.037169 | 38.1949 | ETL.1400 | 40744827 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119610680 | Q2 | DI MUSTANG SW STA-GREGG 28/119 RPR FOND | 44490886 | GATES-GREGG | 028/119 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.890369 | 36.4235 | ETL.4700 | 40858227 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119611160 | Q2 | EI GARBERVILLE-LAYTONVILLE 38/9 RPR GYWW | 44453326 | GARBERVILLE-LAYTONVILLE | 038/009 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.582411 | 39.8808 | ETL.8365 | 40906622 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611162 | Q2 | EI GARBERVILLE-LAYTONVILLE 38/9 RMV ANCH | 44311203 | GARBERVILLE-LAYTONVILLE | 038/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-13 | 2022-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.582411 | 39.8808 | ETL.8365 | 40906622 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611217 | Q2 | EI T3NT FULTON-PUEBLO 4/204 RPR FOND |  | FULTON-PUEBLO | 040/204 | ICQ | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-13 | 2022-08-13 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.705787 | 38.4969 | ETL.1600 | 40762051 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611219 | Not Scheduled | T3 EI EAGLE ROCK-FULTON 40/205 REPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 040/205 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-02-13 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.708134 | 38.4969 | ETL.4392 | 40791360 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611256 | Q2 | EI T3NT PITTSBURG-SAN MATEO 23/092 INST | 44623139 | PITTSBURG-SAN MATEO | 023/092 | ICQ | F | 2020_(3) On high spread structure |  | 2020-08-13 | 2022-08-13 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.963067 | 37.7326 | ETL.5463 | 40805061 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611271 | Q2 | EI T3NT PITTSBURG-SAN MATEO 23/92 RPR FO | 44623139 | PITTSBURG-SAN MATEO | 023/092 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-13 | 2022-08-13 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.963067 | 37.7326 | ETL.5463 | 40805061 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611398 | Q2 | EI LOS BANOS-MIDWAY #2 27/116 BENT STL | 44490736 | LOS BANOS-MIDWAY #2 | 027/116 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.720047 | 36.7467 | ETL.6010 | 40812150 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119611437 | Not Scheduled | T2 TEMBLOR-SAN LUIS OBISPO 57/3 RPL INSS | 31514502 | TEMBLOR-SAN LUIS OBISPO | 057/314 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.6271753 | 35.2637 | ETL.3960 | 40780995 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611481 | Q2 | EI T3NT PITTSBURG-SAN MATEO 23/093 RPR F | 44623139 | PITTSBURG-SAN MATEO | 023/093 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-13 | 2022-08-13 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.964182 | 37.7313 | ETL.5463 | 40858022 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611591 | Q2 | T2 DI SALINAS-LAURELES A12/266 RPR SPLW | 44294541 | SALINAS-LAURELES | A012/266 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.770321 | 36.5706 | ETL.7930 | 40666658 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611848 | Feb | T2 EI COLGATE-GRASS VALLEY 0/1 REPL POLE | 31510989 | COLGATE-GRASS VALLEY | 000/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.18931 | 39.3314 | ETL.6490 | 40599624 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119611883 | Feb | T2 EI COLGATE-GRASS VALLEY 0/1 RPR ANCW | 44439113 | COLGATE-GRASS VALLEY | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.18931 | 39.3314 | ETL.6490 | 40599624 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119612058 | Not Scheduled | EI DRUM-SUMMIT #1 16/193L RPR GYWW | 44478430 | DRUM-SUMMIT #1 | 016/193 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5088438 | 39.314 | ETL.1440 | 44162405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119612133 | Not Scheduled | EI DRUM-SUMMIT #1 16/193C RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 016/193 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5088438 | 39.314 | ETL.1440 | 44162406 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119612143 | Not Scheduled | EI DRUM-SUMMIT #1 16/193R RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 016/193 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5088438 | 39.314 | ETL.1440 | 44162407 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119612479 | Q2 | DI GARBERVILLE-LYTNVL 50/4 RPL STRW | 31515658 | GARBERVILLE-LAYTONVILLE | 050/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.630048 | 40.0258 | ETL.8365 | 40912562 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119612623 | Not Scheduled | EI DIVIDE-CABRILLO #2 1/28 RPL INSW | 31515253 | DIVIDE-CABRILLO #2 | 001/028 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 | [9 empty] | South | WSIP | [6 empty] | '-120.4455176 | 34.805 | ETL.1370 | 40616237 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613122 | Not Scheduled | EI DRUM-SUMMIT #1 17/197A RPL POLE | 31521943 | DRUM-SUMMIT #1 | 017/197A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.502783 | 39.3137 | ETL.1440 | 40590111 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613145 | Not Scheduled | EI DRUM-SUMMIT #1 17/197B RPL STRW | 31521943 | DRUM-SUMMIT #1 | 017/197 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.502773 | 39.3136 | ETL.1440 | 42572700 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613180 | Not Scheduled | EI DRUM-SUMMIT #1 17/197C RPL POLE | 31521943 | DRUM-SUMMIT #1 | 017/197C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.502744 | 39.3136 | ETL.1440 | 42572701 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613386 | Q2 | EI GARBERVILLE-LAYTONVILLE 38/3 RMV BUTT | 44449697 | GARBERVILLE-LAYTONVILLE | 038/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.580916 | 39.8725 | ETL.8365 | 40906616 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613387 | Q2 | EI GARBERVILLE-LAYTONVILLE 38/5 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 038/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.581657 | 39.8751 | ETL.8365 | 44356187 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613391 | Q2 | EI GARBERVILLE-LYTNVLLE 038/000 RPL POL | 31512220 | GARBERVILLE-LAYTONVILLE | 038/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579475 | 39.8693 | ETL.8365 | 40906613 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613394 | Q2 | EI GARBERVILLE-LYTNVLLE 038/0 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 038/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-13 | 2022-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579475 | 39.8693 | ETL.8365 | 40906613 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613400 | Q2 | EI GARBERVILLE-LAYTONVILLE 38/3 RPL POLE | 31514633 | GARBERVILLE-LAYTONVILLE | 038/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.580916 | 39.8725 | ETL.8365 | 40906616 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613401 | Q2 | EI GARBERVILLE-LAYTONVILLE 37/8 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 037/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.578306 | 39.8681 | ETL.8365 | 40906612 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613445 | Not Scheduled | EI DRUM-SUMMIT #1 14/160 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/160 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.552163 | 39.3184 | ETL.1440 | 40579655 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613455 | Not Scheduled | EI DRUM-SUMMIT #2 14/163L RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/163 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5520749 | 39.3186 | ETL.1450 | 44159099 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613459 | Not Scheduled | EI DRUM-SUMMIT#2 14/162L INST MRKW | 44478436 | DRUM-SUMMIT #2 | 014/162 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2022-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5529819 | 39.3188 | ETL.1450 | 44561277 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613489 | Not Scheduled | EI DRUM-SUMMIT #1 13/158 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/158 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55486 | 39.3192 | ETL.1440 | 40607800 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613495 | Not Scheduled | EI DRUM-SUMMIT #2 14/163C RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/163 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5520749 | 39.3186 | ETL.1450 | 44159100 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613510 | Not Scheduled | EI DRUM-SUMMIT#2_014/162R INST MRKW | 44478436 | DRUM-SUMMIT #2 | 014/162 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2022-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5529819 | 39.3188 | ETL.1450 | 44561378 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613511 | Not Scheduled | EI DRUM-SUMMIT #1 014/159 INST MKRW | 44453260 | DRUM-SUMMIT #1 | 014/159 | DEA | F | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2022-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.553065 | 39.3187 | ETL.1440 | 40618777 | Marker (i.e. signs)-Wood | Missing | Install | UNSC ObjC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | DEA | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613512 | Not Scheduled | EI DRUM-SUMMIT #2 14/161C RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/161 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.5547704 | 39.3194 | ETL.1450 | 44159096 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613514 | Not Scheduled | EI DRUM-SUMMIT #2 14/161 RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/161 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.5547704 | 39.3194 | ETL.1450 | 44159095 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613518 | Not Scheduled | EI DRUM-SUMMIT #1 13/157 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/157 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.555563 | 39.3195 | ETL.1440 | 40870570 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613538 | Not Scheduled | EI DRUM-SUMMIT#20 13/154 INST MRKW | 44478436 | DRUM-SUMMIT #2 | 013/154 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2022-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.564528 | 39.3257 | ETL.1450 | 44561205 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613571 | Not Scheduled | EI DRUM-SUMMIT#2 13/154 INST MRKW | 44478436 | DRUM-SUMMIT #2 | 013/154 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2022-08-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.564528 | 39.3257 | ETL.1450 | 44561287 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613669 | Q2 | EI LOS BANOS-GATES #1 23/99 BENT STL | 44490735 | LOS BANOS-GATES #1 | 023/099 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2021-08-13 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.77802 | 36.7822 | ETL.6000 | 40867754 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119613936 | Q2 | EI GARBERVILLE-LAYTONVILLE 53/4 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 053/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.646186 | 40.0648 | ETL.8365 | 40912593 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119613992 | Not Scheduled | T3 EI COLGATE-CHALLENGE 9/169 RPR GYWW | 44448163 | COLGATE-CHALLENGE | 009/169 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.205635 | 39.4452 | ETL.6480 | 40757262 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615155 | Not Scheduled | T2 EI BRIDGEVILLE-CTWD 51/387 CAGE CLEAR |  | BRIDGEVILLE-COTTONWOOD | 051/387 | HNA | E | 2020_(3) On high spread structure |  | 2020-08-13 | 2021-08-13 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.220662 | 40.4139 | ETL.1110 | 40650422 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615156 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 51/385 MASTIC | 44634176 | BRIDGEVILLE-COTTONWOOD | 051/385 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-13 | 2022-08-13 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.215351 | 40.415 | ETL.1110 | 40592233 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615171 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 51/389 MASTIC | 44634178 | BRIDGEVILLE-COTTONWOOD | 051/389 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-13 | 2022-08-13 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.225746 | 40.4128 | ETL.1110 | 40756708 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615386 | Not Scheduled | HUMBOLDT-BRIDGEVILLE 88/001 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 088/001 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.811986 | 40.5032 | ETL.1810 | 44322237 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615388 | Not Scheduled | HUMBOLDT-BRIDGEVILLE 90/5 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 090/005 | 93Z | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.83306 | 40.5324 | ETL.1810 | 44322281 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615411 | Not Scheduled | HUMBOLDT-BRIDGEVILLE 94/4 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 094/004 | 93Z | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.854387 | 40.5926 | ETL.1810 | 44322341 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615414 | Not Scheduled | HUMBOLDT-BRIDGEVILLE 99/001 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 099/001 | 93Z | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.891011 | 40.6431 | ETL.1810 | 44322405 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615416 | Not Scheduled | HUMBOLDT-BRIDGEVILLE 99/007 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 099/007 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.901921 | 40.6479 | ETL.1810 | 44322425 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615431 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 108/005 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 108/005 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.982845 | 40.7519 | ETL.1810 | 44324317 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615441 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 109/008 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 109/008 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.003507 | 40.7586 | ETL.1810 | 44322622 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615443 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 110/003 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 110/003 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.013775 | 40.7607 | ETL.1810 | 44322634 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615444 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 110/004 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 110/004 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.01465 | 40.7608 | ETL.1810 | 44322637 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615448 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 110/005 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 110/005 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.017999 | 40.7608 | ETL.1810 | 44322640 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615454 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 110/006 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 110/006 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.021378 | 40.7609 | ETL.1810 | 44322643 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615458 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 112/001 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 112/001 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.047807 | 40.7611 | ETL.1810 | 44322671 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615461 | Not Scheduled | EI DRUM-SUMMIT #1 17/200L RPL POLE |  | DRUM-SUMMIT #1 | 017/200 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.498477 | 39.3142 | ETL.1440 | 45016516 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119615471 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 110/007 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 110/007 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.021991 | 40.7609 | ETL.1810 | 44322646 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615476 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 110/008 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 110/008 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.024353 | 40.7609 | ETL.1810 | 44322649 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615491 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 112/2 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 112/002 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.049067 | 40.7611 | ETL.1810 | 44322674 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615493 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 112/6 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 112/006 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.056485 | 40.7627 | ETL.1810 | 44322688 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615499 | Q2 | EI LOS BANOS-MIDWAY #2 29/124 REPL HRDS | 44490736 | LOS BANOS-MIDWAY #2 | 029/124 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.705982 | 36.7209 | ETL.6010 | 40762802 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119615503 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 113/0 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 113/000 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.062707 | 40.7658 | ETL.1810 | 44322700 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615506 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 113/002 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 113/002 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-05-31 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.065139 | 40.7677 | ETL.1810 | 44322708 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615514 | Q2 | EI LOS BANOS-MIDWAY #2 29/124 BENT STL | 44490736 | LOS BANOS-MIDWAY #2 | 029/124 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.705982 | 36.7209 | ETL.6010 | 40762802 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119615520 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 114/003 RPL CRSL | 31511685 | HUMBOLDT-BRIDGEVILLE | 114/003 | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-124.086082 | 40.7753 | ETL.1810 | 44322740 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615565 | Q3 | T3 EI BEARDSLEY TAP 0/2 RPR WDPKR |  | BEARDSLEY TAP | 000/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-09-04 | 2021-09-03 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.0741576 | 38.2023 | ETL.1401 | 44390887 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119615740 | Not Scheduled | T3 EI DRUM-SUMMIT#2 00/005 RPL ANCW |  | DRUM-SUMMIT #2 | 000/005 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-02-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.7618682 | 39.2549 | ETL.1450 | 44549915 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119616501 | Not Scheduled | T3 EI PITTSBURG-EASTSHORE 026/102 | 44609900 | PITTSBURG-EASTSHORE | 026/102 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-121.9975433 | 37.7052 | ETL.5462 | 41135633 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119616670 | Q2 | EI LOS BANOS-MIDWAY #2 30/129 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 030/129 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.696705 | 36.7039 | ETL.6010 | 40863645 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617108 | Q2 | EI GARBERVILLE-LAYTONVILLE 53/9A RPL INS | 31514495 | GARBERVILLE-LAYTONVILLE | 053/009A | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40922408 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617176 | Q2 | EI T3NT PITTSBURG-SAN MATEO 24/97 RPR FO |  | PITTSBURG-SAN MATEO | 024/097 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-14 | 2022-08-14 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.975955 | 37.7199 | ETL.5463 | 40681930 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617221 | Q2 | EI GARBERVILLE-LAYTONVILL 53/9B RPL INSW | 31514495 | GARBERVILLE-LAYTONVILLE | 053/009B | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650284 | 40.0706 | ETL.8365 | 40922409 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617242 | Q2 | EI GARBERVILLE-LAYTONVILLE 53/9C RPL INS | 31514495 | GARBERVILLE-LAYTONVILLE | 053/009C | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650266 | 40.0706 | ETL.8365 | 40922410 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617259 | Not Scheduled | EI DRUM-SUMMIT#2 17/207 RPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/207 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4950561 | 39.3148 | ETL.1450 | 44549913 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617277 | Not Scheduled | EI DRUM-SUMMIT#2 17/207 RPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/207 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4950561 | 39.3148 | ETL.1450 | 44549942 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617296 | Q2 | EI T3NT PITTSBURG-SAN MATEO 24/096 RPR F | 44623139 | PITTSBURG-SAN MATEO | 024/096 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-14 | 2022-08-14 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.970879 | 37.7238 | ETL.5463 | 40581163 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617311 | Not Scheduled | EI DRUM-SUMMIT#2 17/207 RPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/207 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4950561 | 39.3148 | ETL.1450 | 44550041 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617322 | Not Scheduled | EI DRUM-SUMMIT#2 17/205L RPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/205 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4977111 | 39.3144 | ETL.1450 | 44565771 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617496 | Q2 | T2 SALT SPRINGS-TGR CRK 4/38 RPR MEMBR | 44631415 | SALT SPRINGS-TIGER CREEK | 004/038 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.287662 | 38.4778 | ETL.3500 | 40856668 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617626 | Not Scheduled | T2 SALT SPRINGS-TIGER CRK 4/43 RPR MEMBR | 44631415 | SALT SPRINGS-TIGER CREEK | 004/043 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.298334 | 38.4779 | ETL.3500 | 40643017 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617646 | Not Scheduled | EI DRUM-SUMMIT #2 17/201A RPL STRW | 31521945 | DRUM-SUMMIT #2 | 017/201A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.502777 | 39.3138 | ETL.1450 | 40586206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617747 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 22/595 RPR SPLW | 44448161 | COLGATE-ALLEGHANY | 022/595 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.873147 | 39.4717 | ETL.6470 | 40731128 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617802 | Not Scheduled | EI DRUM-SUMMIT #2 17/201B RPL POLE | 31521945 | DRUM-SUMMIT #2 | 017/201B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.50277 | 39.3138 | ETL.1450 | 42572826 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617845 | Q2 | T2 SALT SPRINGS-TIGER CRK 10/82 RPR FOND | 44631415 | SALT SPRINGS-TIGER CREEK | 010/082 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.391625 | 38.4807 | ETL.3500 | 40643405 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617867 | Q2 | EI GARBERVILLE-LAYTONVILLE 47/2 RPL POLE | 31514633 | GARBERVILLE-LAYTONVILLE | 047/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.620542 | 39.9842 | ETL.8365 | 40912527 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617870 | Q2 | EI GARBERVILLE-LAYTONVILLE 47/3 RPL POLE | 31514633 | GARBERVILLE-LAYTONVILLE | 047/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.619712 | 39.9852 | ETL.8365 | 40912528 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617877 | Not Scheduled | EI DRUM-SUMMIT #2 17/201C RPL POLE | 31521945 | DRUM-SUMMIT #2 | 017/201C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.502779 | 39.3137 | ETL.1450 | 42572827 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119617984 | Not Scheduled | T2 EI DRUM-SUMMIT #2 24/289B INST MRKW | 44478436 | DRUM-SUMMIT #2 | 024/289B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2022-08-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380617 | 39.322 | ETL.1450 | 44766954 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617994 | Not Scheduled | T2 EI DRUM-SUMMIT #2 24/289C INST MRKW | 44478436 | DRUM-SUMMIT #2 | 024/289C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2022-08-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380671 | 39.3219 | ETL.1450 | 44766884 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119617996 | Not Scheduled | T2 EI DRUM-SUMMIT #2 24/289A INST MRKW | 44478436 | DRUM-SUMMIT #2 | 024/289A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2022-08-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380545 | 39.3221 | ETL.1450 | 44766885 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119618015 | Q2 | EI LOS BANOS-GATES #1 26/111 RPR FOND | 44490735 | LOS BANOS-GATES #1 | 026/111 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.73565 | 36.7565 | ETL.6000 | 40593662 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619075 | Not Scheduled | EI DRUM-SUMMIT #1 14/162B RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/162 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549341 | 39.3171 | ETL.1440 | 42572663 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619081 | Not Scheduled | EI DRUM-SUMMIT #1 14/162C RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/162C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549365 | 39.317 | ETL.1440 | 42572668 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619091 | Not Scheduled | EI DRUM-SUMMIT #1 14/162A RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/162A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549325 | 39.3171 | ETL.1440 | 40663002 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619108 | Not Scheduled | EI DRUM-SUMMIT #1 14/161 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/161 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.551085 | 39.3179 | ETL.1440 | 40668895 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619203 | Not Scheduled | EI DRUM-SUMMIT #1 13/156 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/156 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556968 | 39.3201 | ETL.1440 | 40866551 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619211 | Not Scheduled | EI DRUM-SUMMIT #1 13/155 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/155 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.558585 | 39.3213 | ETL.1440 | 40814110 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619236 | Not Scheduled | EI DRUM-SUMMIT#2 13/158 INST MRKW | 44478436 | DRUM-SUMMIT #2 | 013/158 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2022-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5584343 | 39.3214 | ETL.1450 | 44561343 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619239 | Not Scheduled | EI DRUM-SUMMIT #1 13/154 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/154 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.560202 | 39.3225 | ETL.1440 | 40820270 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619241 | Not Scheduled | EI DRUM-SUMMIT#2 13/158 INST MRKW | 44482692 | DRUM-SUMMIT #2 | 013/158 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2022-08-14 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5584343 | 39.3214 | ETL.1450 | 44561375 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119619308 | Q2 | EI MI-WUK CURTIS 25/9 RMV POLE BUTTS | 44623592 | ETL.1073.POLE.WDPS | 025/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-14 | 2022-08-14 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.3035343 | 37.9772 | ETL.1073 | 44774793 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619349 | Q4 | T2NT EI MAPLE CRK-HOOPA 16/7 RMV PL BUTT | 44593017 | MAPLE CREEK-HOOPA | 016/007 | ICW | F | 2020_(2) High fire spread TD |  | 2020-08-14 | 2022-08-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.68882 | 40.9267 | ETL.7490 | 40826047 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619455 | Q4 | T2 EI MAPLE CREEK-HOOPA 16/004 RPR GYWW | 44453324 | MAPLE CREEK-HOOPA | 016/004 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.693205 | 40.9217 | ETL.7490 | 44838213 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619457 | Q4 | EI MAPLE CREEK-HOOPA 16/004C RPR GYWW | 44453147 | MAPLE CREEK-HOOPA | 016/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.693205 | 40.9217 | ETL.7490 | 44838224 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619508 | Not Scheduled | T3 EI COLGATE-CHALLENGE 10/174 RPR GYWW | 44448163 | COLGATE-CHALLENGE | 010/174 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.207195 | 39.4494 | ETL.6480 | 40693469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619633 | Q2 | EI T3NT TIGER CREEK-ELECTRA 1/9 INST ACG | 31432683 | TIGER CREEK-ELECTRA | 001/009 | 93A | F | 2020_(3) On high spread structure |  | 2020-08-13 | 2022-08-13 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.510146 | 38.4458 | ETL.5780 | 40862690 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619660 | Q2 | T3 EI TIGER CREEK-ELECTRA 1/9 RPR STRT |  | TIGER CREEK-ELECTRA | 001/009 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.510146 | 38.4458 | ETL.5780 | 40862690 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119619661 | Q2 | T3 EI TIGER CREEK-ELECTRA 0/4 RPR STRT |  | TIGER CREEK-ELECTRA | 000/004 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.495177 | 38.4517 | ETL.5780 | 40651008 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12 | BLM | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119620304 | Not Scheduled | EI NEWARK-LAWRENCE LAB 14/87 REPLUMB | 44620195 | NEWARK-LAWRENCE LAB | 014/087 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | [9 empty] | Central | WSIP | [6 empty] | '-121.792401 | 37.6251 | ETL.3060 | 40851063 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119620322 | Not Scheduled | EI NEWARK-LAWRENCE LAB 014/090 REPL INSS | 31507589 | NEWARK-LAWRENCE LAB | 014/090 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 | [9 empty] | Central | WSIP | [6 empty] | '-121.78523 | 37.6289 | ETL.3060 | 40621730 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119620323 | Not Scheduled | EI NEWARK-LAWRENCE LAB 013/079 REPL INSS | 31507589 | NEWARK-LAWRENCE LAB | 013/079 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | [9 empty] | Central | WSIP | [6 empty] | '-121.811745 | 37.6138 | ETL.3060 | 40878597 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-13 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119620536 | Q4 | T3 EI DRUM-RIO OSO #1 0/1 RMV CLMB STP | 44448949 | DRUM-RIO OSO #1 | 000/001 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.769665 | 39.2571 | ETL.1420 | 40594929 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621606 | Mar | T3 DEER CREEK-DRUM 4/113 REFRAME | 31516593 | DEER CREEK-DRUM | 004/113 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.792966 | 39.2565 | ETL.6690 | 40767464 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621608 | Mar | T3 DEER CRK-DRUM 4/112 REFRAME | 31516593 | DEER CREEK-DRUM | 004/112 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.793723 | 39.2565 | ETL.6690 | 40664843 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621628 | Mar | T3 DEER CREEK-DRUM 4/111 REFRAME | 31516593 | DEER CREEK-DRUM | 004/111 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.794052 | 39.2565 | ETL.6690 | 40671648 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621805 | Q2 | EI GARBERVILLE-LAYTONVILLE 41/2 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 041/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-15 | 2021-08-15 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577108 | 39.9133 | ETL.8365 | 40906655 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621826 | Q2 | EI GARBERVILLE-LYTNVILE 40/13 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 040/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-15 | 2021-08-15 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577582 | 39.9104 | ETL.8365 | 40906652 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621835 | Mar | T3 EI DRUM-RIO OSO #1 0/4 RMV CLMB STP | 44448948 | DRUM-RIO OSO #1 | 000/004 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.77553 | 39.2569 | ETL.1420 | 40756296 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621836 | Mar | T3 EI DRUM-RIO OSO #1 1/15 RMV CLMB STP | 44448948 | DRUM-RIO OSO #1 | 001/015 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.79422 | 39.2563 | ETL.1420 | 40756199 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621837 | Mar | T3 EI DRUM-RIO OSO #1 00/02 RPL CRSMS |  | DRUM-RIO OSO #1 | 000/002 |  | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1420 | 44337044 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade |  | Mar |  |  | 2021-01-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621844 | Q4 | EI DRUM-RIO OSO NO. 1 0/3 RPR CROSSARM | 44453164 | DRUM-RIO OSO #1 | 000/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-08-15 |  |  | 2021-12-31 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.7724463 | 39.257 | ETL.1420 | 44337047 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621845 | Mar | T3 EI DRUM-RIO OSO #1 1/13 RMV CLMB STP | 44448948 | DRUM-RIO OSO #1 | 001/013 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-02-15 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791076 | 39.2564 | ETL.1420 | 40654181 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621911 | Q2 | EI GARBERVILLE-LAYTONVILLE 39/011 REPULL | 44476763 | GARBERVILLE-LAYTONVILLE | 039/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-08-15 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.580304 | 39.8937 | ETL.8365 | 40906637 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119621931 | Q2 | EI GARBERVILLE-LAYTONVILL 39/12 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 039/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-15 | 2021-08-15 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.580149 | 39.8948 | ETL.8365 | 40906638 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119622036 | Not Scheduled | T2 EI COLGATE-CHALLENGE 00/022 RMV DEBRI | 44482825 | COLGATE-CHALLENGE | 000/022 | ICW | E | 2020_(1a) PSPS |  | 2020-08-15 | 2021-08-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19013 | 39.3438 | ETL.6480 | 40598490 | Conductor-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119622040 | Not Scheduled | T2 EI COLGATE-CHALLENGE 0/019 RPR JUMPR | 44482825 | COLGATE-CHALLENGE | 000/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-15 | 2021-08-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19143 | 39.3421 | ETL.6480 | 40866889 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119623120 | Q4 | T2 EI MAPLE CREEK-HOOPA 8/1 JUMPR INSW | 44453147 | MAPLE CREEK-HOOPA | 008/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-16 | 2021-08-16 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.805891 | 40.8597 | ETL.7490 | 40602064 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119623139 | Q4 | T2 EI MAPLE CREEK-HOOPA 7/004 RPR GYWW | 44453147 | MAPLE CREEK-HOOPA | 007/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-16 | 2021-08-16 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.813368 | 40.8533 | ETL.7490 | 44735728 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119623203 | Q4 | T2 EI MAPLE CREEK-HOOPA 8/5 RMV DEBRIS | 44453324 | MAPLE CREEK-HOOPA | 008/005 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-16 | 2022-08-16 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.801362 | 40.8638 | ETL.7490 | 44707296 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119623263 | Q4 | T2 EI MAPLE CRK-HOOPA 8/5 RPR STRW | 44497905 | MAPLE CREEK-HOOPA | 008/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-16 | 2021-08-16 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.801362 | 40.8638 | ETL.7490 | 44707296 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119623587 | Q2 | T3 DI IGNACIO-BOLINAS #1 4/45 RPR SPLW | 44640733 | IGNACIO-BOLINAS #1 | 004/045 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.600447 | 38.0466 | ETL.7140 | 40668079 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624163 | Q3 | T2 DI BRDGVLL-GARBERVILLE 11/10 RPL HRDD | 44453320 | BRIDGEVILLE-GARBERVILLE | 011/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.718999 | 40.3464 | ETL.6220 | 44414891 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624403 | Q2 | EI GARBERVILLE-LAYVILLE 40/4 RMV ANCHOR | 44484408 | GARBERVILLE-LAYTONVILLE | 040/004 | ICW | E | 2020_(3) On high spread structure |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579198 | 39.9004 | ETL.8365 | 44241872 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624411 | Q2 | EI GARBERVILLE-LAYTONVILLE 40/4 RPR JUMP | 44453326 | GARBERVILLE-LAYTONVILLE | 040/004 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579198 | 39.9004 | ETL.8365 | 44241872 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624412 | Q2 | EI GARBERVILL-LAYTONVILLE 40/4 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 040/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579198 | 39.9004 | ETL.8365 | 44241872 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624474 | Q2 | EI GARBERVILLE-LAYTONVILLE 40/5 RPL DAMP | 44476763 | GARBERVILLE-LAYTONVILLE | 040/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579035 | 39.9017 | ETL.8365 | 40906645 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624741 | Not Scheduled | T3 DI MONTE RIO-FORT ROSS 21/1 RPR STRW |  | ETL.6979.POLE.WOOD | 021/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.112969 | 38.4793 | ETL.6979 | 40584641 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624746 | Q2 | T3 DI SLY CREEK TAP 002/025A RPR SPLW | 44639818 | SLY CREEK TAP | 002/025A | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.158969 | 39.5557 | ETL.4221 | 44921306 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624752 | Q2 | EI LOS BANOS-MIDWAY #2 31/130 RPR MEMBR | 44490736 | LOS BANOS-MIDWAY #2 | 031/130 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.69464 | 36.7001 | ETL.6010 | 40600301 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119624798 | Q2 | EI GARBERVIL-LAYTONVILLE 47/6 RPL GUY PL | 31514685 | GARBERVILLE-LAYTONVILLE | 047/006 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.616899 | 39.9932 | ETL.8365 | 40912534 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624799 | Q2 | EI GARBERVILLE-LAYTONVILLE 47/6 RMV BUTT | 44484408 | GARBERVILLE-LAYTONVILLE | 047/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-17 | 2022-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.616899 | 39.9932 | ETL.8365 | 40912534 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624937 | Not Scheduled | T2 EI DRUM-SUMMIT#2 20/244L RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/244 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4400984 | 39.3208 | ETL.1450 | 44559048 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624970 | Q2 | T2 LAKEVLE-SBRNTE#2 38/180 REPL INSS | 31526415 | LAKEVILLE-SOBRANTE #2 | 038/180 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-16 | 2021-08-16 |  |  | 2021-05-10 | 2021-05-10 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.2339028 | 38.0218 | ETL.4960 | 40635473 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624971 | Not Scheduled | T2 EI DRUM-SUMMIT#2 20/244R RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/244 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4400984 | 39.3208 | ETL.1450 | 44558983 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119624998 | Not Scheduled | T2 EI DRUM-SUMMIT#2 20/245L RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/245 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4388698 | 39.3218 | ETL.1450 | 44549971 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625083 | Not Scheduled | T2 EI DRUM-SUMMIT#2 20/245R RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/245 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4388698 | 39.3218 | ETL.1450 | 44549993 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625149 | Q2 | EI GARBERVILLE-LAYTONVILLE 40/7 RPL DAMP | 44453326 | GARBERVILLE-LAYTONVILLE | 040/007 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.578436 | 39.905 | ETL.8365 | 40906647 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625233 | Not Scheduled | T2 EI DRUM-SUMMIT #2 20/247A RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/247A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.436649 | 39.3236 | ETL.1450 | 40862036 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625247 | Not Scheduled | T2 EI DRUM-SUMMIT #2 20/247B RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/247B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.43662 | 39.3236 | ETL.1450 | 42572835 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625249 | Not Scheduled | EI DRUM-SUMMIT #1 23/280 RPL HRDD | 44482753 | DRUM-SUMMIT #1 | 023/280 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.3837997 | 39.3113 | ETL.1440 | 44162118 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119625308 | Not Scheduled | T2 EI DRUM-SUMMIT #2 20/247C RPL STRW | 31506920 | DRUM-SUMMIT #2 | 020/247C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.436594 | 39.3235 | ETL.1450 | 42572836 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625367 | Q2 | EI LOS BANOS-MIDWAY #2 31/132 BENT MEMBR | 44490736 | LOS BANOS-MIDWAY #2 | 031/132 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.69087 | 36.6932 | ETL.6010 | 40664773 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119625468 | Q2 | T2 DI TRINTY-MAPLE CREEK 42/10 RPR POLE | 44295371 | TRINITY-MAPLE CREEK | 042/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.67568 | 40.7305 | ETL.8170 | 40588771 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625592 | Q2 | T2 DI TRINTY-MAPLE CREEK 38/7 RPR STRW | 44295371 | TRINITY-MAPLE CREEK | 038/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.599857 | 40.7125 | ETL.8170 | 40808959 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625597 | Q2 | T2 DI KONOCTI MIDDLETOWN ;24/1 RPL STRW | 31513487 | KONOCTI-MIDDLETOWN | ;024/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.614959 | 38.9036 | ETL.6380 | 40586670 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625827 | Mar | HUMBOLDT-TRINITY 100/4R RPL POLE |  | HUMBOLDT-TRINITY | 100/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8719017 | 40.7681 | ETL.1820 | 44562979 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625850 | Mar | HUMBOLDT-TRINITY 100/4C RPL POLE |  | HUMBOLDT-TRINITY | 100/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.8718985 | 40.7681 | ETL.1820 | 44562977 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625914 | Q2 | T3NT DI IGNACO-BOLINAS #1 8/100 RMV BUTT | 44640733 | IGNACIO-BOLINAS #1 | 008/100 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-17 | 2022-08-17 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.656185 | 37.9976 | ETL.7140 | 40808615 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119625994 | Not Scheduled | T2NT EI DRUM-SUMMIT#2 10/117 INST MRKW | 44482692 | DRUM-SUMMIT #2 | 010/117 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2022-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6158861 | 39.3219 | ETL.1450 | 44553718 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626005 | Q2 | T3 EI EAGLE RCK-FLTN-SLVRDO 013/54 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 013/054 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-17 | 2022-08-17 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.706876 | 38.5714 | ETL.4392 | 41129356 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626028 | Not Scheduled | T2NT EI DRUM-SUMMIT#2 9/115 INST MRKW | 44482691 | DRUM-SUMMIT #2 | 009/115 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2022-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.618803 | 39.3214 | ETL.1450 | 44836800 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626166 | Not Scheduled | EI LOS BANOS-MIDWAY #2 31/134 RMV VEG |  | LOS BANOS-MIDWAY #2 | 031/134 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.687052 | 36.6862 | ETL.6010 | 40753966 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119626181 | Mar | T3NT DI LAURELES-OTTER-WD 13/12 INS MRKW |  | LAURELES-OTTER | 013/012 | ICW | F | 2020_(1a) PSPS |  | 2020-08-17 | 2022-08-17 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.867333 | 36.3864 | ETL.7380 | 40701577 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119626280 | Q4 | T2 EI MAPLE CREEK-HOOPA 7/005 JUMPER INS | 44482958 | MAPLE CREEK-HOOPA | 017/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.676618 | 40.9335 | ETL.7490 | 40752758 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626370 | Q2 | T3 EI EAGLE ROCK-FLTN-SLVRDO 13/55 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 013/055 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-17 | 2022-08-17 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.704956 | 38.5701 | ETL.4392 | 41129357 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626381 | Q2 | T3 DI IGNACIO-BOLINAS #1 2/31 RPR STRW | 44640733 | IGNACIO-BOLINAS #1 | 002/031 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-02-14 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.582173 | 38.0699 | ETL.7140 | 40770917 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626670 | Q4 | T2 EI MAPLE CREEK-HOOPA 16/8 RPR GROUND | 44453324 | MAPLE CREEK-HOOPA | 016/008 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.68807 | 40.9275 | ETL.7490 | 40877954 | Ground Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626671 | Q4 | T2 EI MAPLE CREEK-HOOPA 16/8 JUMPR INSW | 44482958 | MAPLE CREEK-HOOPA | 016/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.68807 | 40.9275 | ETL.7490 | 40877954 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626710 | Not Scheduled | T3 DI FRNCH MDWS-MDDL FRK 1/32 RPR STRW | 31511734 | FRENCH MEADOWS-MIDDLE FORK | 001/032 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.426097 | 39.0641 | ETL.6870 | 40593745 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626711 | Q2 | T3 DI IGNACIO-BOLINAS #1 1/29 RPR STRW | 44640733 | IGNACIO-BOLINAS #1 | 001/029 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.578748 | 38.0718 | ETL.7140 | 40657311 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626714 | Not Scheduled | T3NT DI FLTN-CALISTOGA :003/0 RMV DEBRIS | 44597303 | FULTON-CALISTOGA | :003/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-17 | 2022-08-17 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.595056 | 38.6326 | ETL.6880 | 40912430 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626718 | Not Scheduled | T3 DI FRNCH MDWS-MDDL FRK 4/91 RPR SPLW | 44448942 | FRENCH MEADOWS-MIDDLE FORK | 004/091 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.477756 | 39.0442 | ETL.6870 | 40798945 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626931 | Not Scheduled | T2 WV DRUM-GRAS VALY-WEMR 20/478 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | 020/478 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.985262 | 39.0468 | ETL.6760 | 40611270 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119626999 | Q2 | EI LOS BANOS-MIDWAY #2 32/136 INST BOLT | 44490736 | LOS BANOS-MIDWAY #2 | 032/136 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.683487 | 36.6797 | ETL.6010 | 40820168 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627013 | Q2 | T3 DI LAURELES-OTTER 15/2 RPR HRDD | 44610149 | LAURELES-OTTER | 015/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-04-02 | 2021-03-31 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.891199 | 36.3807 | ETL.7380 | 40701567 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627119 | Q2 | EI GARBERVILLE-LAYTONVILLE 48/0 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 048/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617141 | 39.9944 | ETL.8365 | 40912535 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627124 | Q2 | EI GARBERVILLE-LAYTONVILL 48/7 RPL STRW | 31515658 | GARBERVILLE-LAYTONVILLE | 048/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.619496 | 40.005 | ETL.8365 | 40912542 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627125 | Q2 | EI GARBERVILLE-LAYTONVILL 49/0 RPL POLE | 31515658 | GARBERVILLE-LAYTONVILLE | 049/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.620624 | 40.008 | ETL.8365 | 40912544 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627126 | Q2 | EI GARBERVILLE-LAYTONVILLE 48/8 RPL POLE | 31515658 | GARBERVILLE-LAYTONVILLE | 048/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.619909 | 40.0061 | ETL.8365 | 40912543 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627141 | Q2 | EI GARBERVILLE-LAYTONVILLE 49/2 RMV BUTT | 44484408 | GARBERVILLE-LAYTONVILLE | 049/002 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.621905 | 40.0115 | ETL.8365 | 40912546 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627197 | Not Scheduled | T3NT DI DRUM-SMMT #1 000/003B RMV DEBRIS | 44449509 | DRUM-SUMMIT #1 | 000/003B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2022-08-03 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763934 | 39.255 | ETL.1440 | 42572613 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627305 | Q2 | T3 EI EAGLE ROCK-FLTN-SLVRDO 12/50 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 012/050 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-17 | 2022-08-17 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.717659 | 38.581 | ETL.4392 | 41129352 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627312 | Q2 | T3 DI IGNACIO-BOLINAS #1 7/83 RPL HRDD | 44640733 | IGNACIO-BOLINAS #1 | 007/083 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.65343 | 38.0137 | ETL.7140 | 40808613 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627318 | Q2 | T3 DI LAURELES-OTTER 004/007 RPL STRW | 31521909 | LAURELES-OTTER | 004/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.740093 | 36.4296 | ETL.7380 | 40816763 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627562 | Not Scheduled | T3 EI PITTSBURG-EASTSHORE 26/104 RPL INS | 31529489 | PITTSBURG-SAN MATEO | 026/104 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | Central | WSIP | [6 empty] | '-122.005443 | 37.6979 | ETL.5463 | 40879223 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119627838 | Not Scheduled | EI DRUM-SUMMIT #2 14/167C RPR STRW | 44482685 | DRUM-SUMMIT #2 | 014/167C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545581 | 39.3164 | ETL.1450 | 44155592 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627859 | Not Scheduled | EI DRUM-SUMMIT #1 14/164A RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/164A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545647 | 39.3163 | ETL.1440 | 40744508 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627870 | Not Scheduled | EI DRUM-SUMMIT #2 14/167B RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/167B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.54553 | 39.3164 | ETL.1450 | 44155591 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627881 | Not Scheduled | EI DRUM-SUMMIT #2 14/167A RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/167A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545483 | 39.3164 | ETL.1450 | 44155590 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627885 | Not Scheduled | EI DRUM-SUMMIT #1 14/164C RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/164C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545759 | 39.3162 | ETL.1440 | 42572671 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627886 | Not Scheduled | EI DRUM-SUMMIT #1 14/164B RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/164B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545706 | 39.3163 | ETL.1440 | 42572669 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627901 | Not Scheduled | EI DRUM-SUMMIT#2 14/166L RPL STRW | 31521945 | DRUM-SUMMIT #2 | 014/166 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5474304 | 39.3168 | ETL.1450 | 44561432 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627910 | Not Scheduled | EI DRUM-SUMMIT#2 14/166R RPL STRW |  | DRUM-SUMMIT #2 | 014/166 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.54743 | 39.3168 | ETL.1450 | 44561379 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627911 | Not Scheduled | EI DRUM-SUMMIT #2 14/165C RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 014/165C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549303 | 39.3172 | ETL.1450 | 44155589 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119627916 | Q2 | T3 EI EAGLE ROCK-FLTN-SLVRDO 11/45 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 011/045 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.727002 | 38.595 | ETL.4392 | 41129347 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628013 | Not Scheduled | T3 DI MONTE RIO-FULTON 008/000 RPR GYWW |  | MONTE RIO-FULTON | 008/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.902401 | 38.4905 | ETL.7630 | 44178641 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628154 | Not Scheduled | T3NT DI DRUM-SMMT #1 000/003A RMV DEBRIS | 44449509 | DRUM-SUMMIT #1 | 000/003A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2022-08-03 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763911 | 39.255 | ETL.1440 | 40642863 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628179 | Q2 | EI LOS BANOS-MIDWAY #2 33/139 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 033/139 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2021-08-17 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.677688 | 36.6691 | ETL.6010 | 40867844 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119628425 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 3/63 RPR STRW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 003/063 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.448577 | 39.0468 | ETL.6870 | 40751812 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628428 | Not Scheduled | T3NT DRUM-SUMMIT #1 INST MRKW | 44449509 | DRUM-SUMMIT #1 | 000/003C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2022-08-03 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763902 | 39.2551 | ETL.1440 | 42572614 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628531 | Not Scheduled | T3 DI FRNCH MDW-MDL FRK 8/166 RPL STRW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 008/166 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.546022 | 39.0197 | ETL.6870 | 42574902 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628535 | Not Scheduled | T3 DI FRNCH MDW-MDL FRK 1/23 RPL STRW | 31511734 | FRENCH MEADOWS-MIDDLE FORK | 001/023 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.420752 | 39.069 | ETL.6870 | 40693745 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119628656 | Not Scheduled | T3 DI FRNCH MDW-MDL FRK 011/204 REFRAME | 31516599 | FRENCH MEADOWS-MIDDLE FORK | 011/204 | 93E | E | 2020_(1a) PSPS |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.582535 | 39.0116 | ETL.6870 | 40603359 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119629193 | Q2 | T3NT DI LAURLES-OTTER 013/013 RMV DEBRIS | 44610151 | LAURELES-OTTER | 013/013 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-17 | 2022-08-17 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.868232 | 36.3862 | ETL.7380 | 40668280 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629216 | Q2 | EI GARBERVILLE-LAYTONVILL 52/7C RPL POLE | 31511613 | GARBERVILLE-LAYTONVILLE | 052/007C | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639287 | 40.0584 | ETL.8365 | 44404873 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629282 | Q2 | EI GARBERVILLE-LAYTONVILLE 53/3 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 053/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.644745 | 40.0635 | ETL.8365 | 40912592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629368 | Q2 | EI GARBERVILL-LAYTONVILLE 52/7A RPL POLE | 31511613 | GARBERVILLE-LAYTONVILLE | 052/007A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639369 | 40.0584 | ETL.8365 | 44404872 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629374 | Q2 | EI GARBERVIL-LAYTONVILLE 52/7B RPL POLE | 31511613 | GARBERVILLE-LAYTONVILLE | 052/007B | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639329 | 40.0584 | ETL.8365 | 40912587 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629399 | Not Scheduled | T2NT EI DRUM-SUMMIT #1 9/112 INST MRKW | 44482862 | DRUM-SUMMIT #1 | 009/112 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2022-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6218216 | 39.3208 | ETL.1440 | 44765195 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629688 | Q2 | NT DI BRDGVLL-CTTNWD 41/332L INST MRKS | 44477511 | BRIDGEVILLE-COTTONWOOD | 041/332 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-20 | 2022-07-20 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-123.044968 | 40.388 | ETL.1110 | 44862873 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629715 | Not Scheduled | T3NT DI DRUM-SMMT #1 000/003C RMV BUTT | 44449509 | DRUM-SUMMIT #1 | 000/003C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-03 | 2022-08-03 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763902 | 39.2551 | ETL.1440 | 42572614 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119629810 | Not Scheduled | T3 DI FRNCH MDW-MDL FRK 7/130 RPR INSW | 44448942 | FRENCH MEADOWS-MIDDLE FORK | 007/130 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.51304 | 39.03 | ETL.6870 | 40639253 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119630051 | Not Scheduled | T3 DI MONTE RIO-FORT ROSS 22/3 RPR GYWW |  | ETL.6979.POLE.WOOD | 022/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-02-14 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.131795 | 38.4739 | ETL.6979 | 40648462 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119630192 | Q2 | T3 DI IGNACIO-BOLINAS #1 2/30 RPR SPLW | 44640733 | IGNACIO-BOLINAS #1 | 002/030 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.58017 | 38.071 | ETL.7140 | 44370065 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119630259 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 11/216 RPR SPLW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 011/216 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.594593 | 39.01 | ETL.6870 | 40693705 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119630479 | Q2 | EI LOS BANOS-MIDWAY #2 33/141 BENT MEMB | 44490736 | LOS BANOS-MIDWAY #2 | 033/141 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.673808 | 36.662 | ETL.6010 | 40592129 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119630673 | Q2 | EI LOS BANOS-MIDWAY #2 33/142 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 033/142 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.672058 | 36.6588 | ETL.6010 | 40664778 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119630690 | Not Scheduled | T3NT DI FRCH MDWS-MDL FRK 4/82 MRKW CNCL | 44448943 | FRENCH MEADOWS-MIDDLE FORK | 004/082 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-17 | 2022-08-17 | [6 empty] | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-120.466787 | 39.0446 | ETL.6870 | 40751842 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119630691 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 4/82 GYWW CNCL | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 004/082 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [6 empty] | CANCEL/CNCL | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.466787 | 39.0446 | ETL.6870 | 40751842 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119631066 | Q2 | EI LOS BANOS-MIDWAY #2 34/143 RPL HRDT | 44490736 | LOS BANOS-MIDWAY #2 | 034/143 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.670148 | 36.6557 | ETL.6010 | 40651933 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119631481 | Q2 | EI LOS BANOS-MIDWAY #2 034/146 RPR STRT |  | LOS BANOS-MIDWAY #2 | 034/146 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to edits |  | WECC | South | WSIP | [6 empty] | '-120.663211 | 36.647 | ETL.6010 | 40822691 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119631624 | Mar | T2 DI EAGLE ROCK-CORTINA :17/7 RPR GYWW | 44563383 | EAGLE ROCK-CORTINA | :017/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.611082 | 38.9727 | ETL.1470 | 41176371 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119631693 | Not Scheduled | T2 EI DRUM-SUMMIT#2 22/261L RPL STRW | 31521951 | DRUM-SUMMIT #2 | 022/261 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4159251 | 39.3284 | ETL.1450 | 44558976 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119631869 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 9/174 RPL STRW | 31511734 | FRENCH MEADOWS-MIDDLE FORK | 009/174 | 70Y | E | 2020_(1a) PSPS |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.55298 | 39.0168 | ETL.6870 | 40809614 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119632036 | Not Scheduled | T3 DI FRCH MDWS-MDDL FRK 5/97 RPL CRSW | 31511733 | FRENCH MEADOWS-MIDDLE FORK | 005/097 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.48356 | 39.0427 | ETL.6870 | 40649987 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632039 | Q2 | T3 DI IGNACIO-BOLINAS #1 7/79 RPL POLE | 31511689 | IGNACIO-BOLINAS #1 | 007/079 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.649713 | 38.0151 | ETL.7140 | 40668101 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632106 | Q2 | EI LOS BANOS-MIDWAY #2 035/147 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 035/147 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.660518 | 36.644 | ETL.6010 | 40811493 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119632154 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 10/185 RPR STRW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 010/185 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.563763 | 39.0151 | ETL.6870 | 40603356 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632166 | Q2 | EI GARBERVILLE-LAYTONVILLE 53/8 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 053/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-18 | 2022-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650421 | 40.0695 | ETL.8365 | 40912597 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632171 | Q2 | EI GARBERVILLE-LAYTONVILL 53/8 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 053/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650421 | 40.0695 | ETL.8365 | 40912597 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632176 | Not Scheduled | T2 EI DRUM-SUMMIT #2 9/106 INST MRKW | 44482690 | DRUM-SUMMIT #2 | 009/106 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2022-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6306908 | 39.3215 | ETL.1450 | 44899058 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632205 | Not Scheduled | EI DRUM-SUMMIT#2 19/231C REPL POLE | 31506920 | DRUM-SUMMIT #2 | 019/231 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4591308 | 39.3192 | ETL.1450 | 44557689 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119632232 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 10/201 RPR STRW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 010/201 | ICW | E | 2020_(1a) PSPS |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.579533 | 39.0119 | ETL.6870 | 40824483 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119632241 | Not Scheduled | EI DRUM-SUMMIT#2 19/231L REPL POLE | 31506920 | DRUM-SUMMIT #2 | 019/231 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4591308 | 39.3192 | ETL.1450 | 44557577 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119632242 | Not Scheduled | EI DRUM-SUMMIT#2 19/231R REPL POLE | 31506920 | DRUM-SUMMIT #2 | 019/231 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.4591308 | 39.3192 | ETL.1450 | 44557493 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119632253 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 9/181 RPL STRW | 31511734 | FRENCH MEADOWS-MIDDLE FORK | 009/181 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.560786 | 39.0163 | ETL.6870 | 40767433 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632391 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 6/112 RPL STRW | 31511734 | FRENCH MEADOWS-MIDDLE FORK | 006/112 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.497492 | 39.0362 | ETL.6870 | 40598759 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632394 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 10/191 RPR GYWW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 010/191 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.568677 | 39.0133 | ETL.6870 | 40824463 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632665 | Q2 | EI LOS BANOS-MIDWAY #2 35/149 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 035/149 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.654745 | 36.6375 | ETL.6010 | 40863647 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119632697 | Q2 | EI GARBERVILLE-LAYTONVILLE 54/0 RPR ANCH | 44453316 | GARBERVILLE-LAYTONVILLE | 054/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650596 | 40.071 | ETL.8365 | 40912602 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632733 | Q2 | EI GARBERVILLE-LAYTONVILLE 54/0 RPR WPKR | 44449697 | GARBERVILLE-LAYTONVILLE | 054/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650596 | 40.071 | ETL.8365 | 40912602 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632811 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 11/205 RPR SPLW | 44448942 | FRENCH MEADOWS-MIDDLE FORK | 011/205 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.583379 | 39.0114 | ETL.6870 | 40610566 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632813 | Not Scheduled | T3 DI FRCH MDWS-MDL FRK 10/87 RPR STRW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 010/187 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.565223 | 39.0144 | ETL.6870 | 40693713 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119632838 | Q2 | T2 DI LAURELES-OTTER 002/011 RPR STRW | 44587870 | LAURELES-OTTER | 002/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71587 | 36.4514 | ETL.7380 | 40591168 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119633029 | Q2 | T2NT DI LAURELES-OTTER 1/5 RMV BUTT | 44587870 | LAURELES-OTTER | 001/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-18 | 2022-08-18 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.713386 | 36.4645 | ETL.7380 | 40751592 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119633108 | Q2 | T2 DI LAURELES-OTTER 000/008 RMV BUTT | 44587870 | LAURELES-OTTER | 000/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-18 | 2022-08-18 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.722437 | 36.4759 | ETL.7380 | 40861940 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119633123 | Q2 | T2 DI IGNACIO-BOLINAS #1 1/21 RPR STRW | 44640733 | IGNACIO-BOLINAS #1 | 001/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.567518 | 38.0743 | ETL.7140 | 40770890 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119633293 | Not Scheduled | T2NT DI DRUM-SUMT #2 22/269 INST MRKW | 44449917 | DRUM-SUMMIT #2 | 022/269 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2022-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.400495 | 39.3289 | ETL.1450 | 44559030 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119633576 | Q2 | EI GARBERVILLE-LAYTONVILLE 54/2 RPR POLE | 44449697 | GARBERVILLE-LAYTONVILLE | 054/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.653405 | 40.0752 | ETL.8365 | 40912604 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119633600 | Q2 | EI GARBERVILLE-LAYTONVILLE 54/2 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 054/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.653405 | 40.0752 | ETL.8365 | 40912604 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119634008 | Not Scheduled | EI DRUM-SUMMIT #1 14/167A RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/167A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.543687 | 39.3132 | ETL.1440 | 40866553 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634010 | Not Scheduled | EI DRUM-SUMMIT #1 14/167C INST MRKW | 44482863 | DRUM-SUMMIT #1 | 014/167C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2022-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.543762 | 39.3131 | ETL.1440 | 42572675 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634013 | Not Scheduled | EI DRUM-SUMMIT #1 14/167B INST MRKW | 44482863 | DRUM-SUMMIT #1 | 014/167B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2022-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.543724 | 39.3132 | ETL.1440 | 42572674 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634031 | Not Scheduled | EI DRUM-SUMMIT #1 14/166C RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/166C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545232 | 39.3143 | ETL.1440 | 42572673 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634034 | Not Scheduled | EI DRUM-SUMMIT #1 14/166B RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/166B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545168 | 39.3143 | ETL.1440 | 42572672 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634038 | Not Scheduled | EI DRUM-SUMMIT #1 13/152 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 013/152 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.563585 | 39.325 | ETL.1440 | 40762647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634043 | Not Scheduled | EI DRUM-SUMMIT #1 14/166A RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 014/166A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545122 | 39.3144 | ETL.1440 | 40819193 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119634139 | Q2 | EI GARBERVILLE-LAYTONVILLE 49/6C RPL STR | 31506024 | GARBERVILLE-LAYTONVILLE | 049/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.623517 | 40.0158 | ETL.8365 | 44403657 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119634147 | Q2 | EI GARBERVILLE-LAYTONVILL 49/8 RPL PL | 31515658 | GARBERVILLE-LAYTONVILLE | 049/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.62544 | 40.0182 | ETL.8365 | 40912555 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119634153 | Q2 | EI GARBERVILLE-LAYTONVILLE 49/6R RPL STR | 31506024 | GARBERVILLE-LAYTONVILLE | 049/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.623517 | 40.0158 | ETL.8365 | 44403658 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635513 | Q2 | T2NT DI SBT-STD OL SW S #1 9/53 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 009/053 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2022-08-18 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.260494 | 37.9964 | ETL.3800 | 40644455 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635561 | Not Scheduled | T2 EI DRUM-SUMMIT #1 22/260 RPL STRW | 31453474 | DRUM-SUMMIT #1 | 022/260 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.41562 | 39.3123 | ETL.1440 | 40590120 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635624 | Not Scheduled | T2 DI DRUM-SUMMIT #2 17/212 RPL STRW | 31521949 | DRUM-SUMMIT #2 | 017/212 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.488388 | 39.3162 | ETL.1450 | 44550018 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635626 | Not Scheduled | T2 DI DRUM-SUMMIT #2 17/212 RPL STRW | 31521949 | DRUM-SUMMIT #2 | 017/212 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.488388 | 39.3162 | ETL.1450 | 44549944 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635878 | Q2 | T2 DI IGNACIO-BOLINAS#1 7/72 RPLC STRW | 31511689 | IGNACIO-BOLINAS #1 | 007/072 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.640188 | 38.016 | ETL.7140 | 40809042 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635887 | Q2 | EI GARBERVILLE-LAYTONVILL 41/5 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 041/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.576994 | 39.9184 | ETL.8365 | 40906658 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635892 | Q2 | T2 EI SLT SPRINGS-TGR CRK 11/09 RPR FOUD | 44631415 | SALT SPRINGS-TIGER CREEK | 011/091 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.413491 | 38.4788 | ETL.3500 | 40579800 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119635961 | Q2 | EI GARBERVILLE-LAYTONVILLE 41/6 RPR STRW | 44453326 | GARBERVILLE-LAYTONVILLE | 041/006 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577113 | 39.9197 | ETL.8365 | 40906659 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636066 | Not Scheduled | T3 DI FRCH MDW-MDL FRK 5/95 RPR GYWW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 005/095 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.481855 | 39.0435 | ETL.6870 | 40586038 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636067 | Not Scheduled | T3 DI FRCH MDW-MDL FRK 004/080 RPR GYWW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 004/080 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.46472 | 39.0447 | ETL.6870 | 40664841 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636068 | Not Scheduled | T3 DI FRCH MDW-MDL FRK 004/080 RPL HRDD | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 004/080 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-02-17 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.46472 | 39.0447 | ETL.6870 | 40664841 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636103 | Q2 | T3 SLT SPRNGS-TGR CRK 15/11 RPR HRDWR |  | SALT SPRINGS-TIGER CREEK | 015/119 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.479381 | 38.4529 | ETL.3500 | 40856720 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636105 | Q2 | T3 SLT SPRNGS-TGR CRK 15/12 RPR TWR MMBR |  | SALT SPRINGS-TIGER CREEK | 015/120 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.480713 | 38.4528 | ETL.3500 | 40579984 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636107 | Q2 | T3 SLT SPRNGS-TGR CRK 16/124 |  | SALT SPRINGS-TIGER CREEK | 016/124 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.486638 | 38.4498 | ETL.3500 | 40744676 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 17 | BLM | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636120 | Q2 | T3 SLT SPRNGS-TGR CRK 15/118 RPR HRDWR |  | SALT SPRINGS-TIGER CREEK | 015/118 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.477709 | 38.4532 | ETL.3500 | 40856680 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636122 | Q2 | T3 SALT SPRINGS-TIGER CRK 15/12 RPR FOND | 44631415 | SALT SPRINGS-TIGER CREEK | 015/120 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.480713 | 38.4528 | ETL.3500 | 40579984 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636255 | Not Scheduled | T2 DI COLGATE-SMRTVL#2 0/9B RPR GYWW | 44448400 | COLGATE-SMARTVILLE #2 | 000/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.199155 | 39.3292 | ETL.6520 | 42562716 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636283 | Not Scheduled | T2 DI COLGATE-SMRTVL#2 0/9B RPLC INSW | 31511688 | COLGATE-SMARTVILLE #2 | 000/009 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.199155 | 39.3292 | ETL.6520 | 42562730 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636363 | Q2 | EI LOS BANOS-MIDWAY #2 36/154 BENT MEMB | 44490736 | LOS BANOS-MIDWAY #2 | 036/154 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.641747 | 36.623 | ETL.6010 | 40753970 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119636365 | Mar | EI T2NT CORTIN-MNDCIN #1 59/287 RPR FOND |  | CORTINA-MENDOCINO #1 | 059/287 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2022-08-19 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636739 | Q2 | EI T3NT EGLE RCK-FLTN-SLVRD :13/52 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | :013/052 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-19 | 2022-08-19 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.712515 | 38.576 | ETL.4392 | 41129354 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636820 | Not Scheduled | EI DRUM-SUMMIT #2 15/178A INST MRKW | 44482688 | DRUM-SUMMIT #2 | 015/178A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2022-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535378 | 39.3083 | ETL.1450 | 44270077 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119636911 | Q2 | T2 DI SBNT-STD OL SS #1 3/16 BENT STEEL | 44624392 | SOBRANTE-STANDARD OIL SW STA #2 | 003/016 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.20415 | 37.9406 | ETL.3800 | 40804919 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636942 | Q2 | DI IGNACIO-BOLINAS #1 6/69 RPLC CRSW | 31514815 | IGNACIO-BOLINAS #1 | 006/069 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-03 | 2021-04-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.638587 | 38.0193 | ETL.7140 | 40648877 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636944 | Q2 | DI IGNACIO-BOLINAS #1 6/69 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 006/069 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-03 | 2021-04-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.638587 | 38.0193 | ETL.7140 | 40648877 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119636949 | Mar | T3NT DI MDDL FRK-GLD HILL 7/65 RPR FOND | 44449603 | MIDDLE FORK-GOLD HILL | 007/065 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-07 | 2022-08-07 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.717937 | 39.0039 | ETL.5140 | 40761204 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637053 | Q2 | EI LOS BANOS-MIDWAY #2 37/156 BENT MEMB | 44490736 | LOS BANOS-MIDWAY #2 | 037/156 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.636067 | 36.6167 | ETL.6010 | 40817165 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119637099 | Q2 | T3 EI PITTSBURG-SAN RAMON 9/39 RPR STRT |  | PITTSBURG-SAN RAMON | 009/039 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-02-19 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-121.882806 | 37.906 | ETL.5490 | 40857920 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637202 | Q2 | EI GARBERVILLE-LAYTONVILLE 43/7 RMV DEBR | 44311203 | GARBERVILLE-LAYTONVILLE | 043/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-19 | 2022-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.583112 | 39.9499 | ETL.8365 | 40906680 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637218 | Q2 | EI GARBERVILLE-LAYTONVILL 43/7 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 043/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.583112 | 39.9499 | ETL.8365 | 40906680 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637338 | Not Scheduled | T3 DI FRCH MDW-MDL FRK 007/144 RPR STRW | 44448940 | FRENCH MEADOWS-MIDDLE FORK | 007/144 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.526407 | 39.0271 | ETL.6870 | 40767437 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637339 | Q2 | T2 DI IGNACIO-BOLINAS #1 5/61 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 005/061 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.623632 | 38.0284 | ETL.7140 | 40648876 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637377 | Q2 | EI GARBERVILLE-LAYTONVILL 44/0 REPL POLE | 31514633 | GARBERVILLE-LAYTONVILLE | 044/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.587002 | 39.9523 | ETL.8365 | 40906684 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637560 | Mar | EI T2NT CORTINA-MNDCN #1 58/284 RPR FOND |  | CORTINA-MENDOCINO #1 | 058/284 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2022-08-19 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.147742 | 39.2368 | ETL.1330 | 40762067 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637562 | Q2 | EI GARBERVILLE-LAYTONVILLE 44/1 RPL STRW | 31515741 | GARBERVILLE-LAYTONVILLE | 044/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.588324 | 39.9532 | ETL.8365 | 40906685 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637604 | Not Scheduled | T2 DI DRUM-SUMMIT #2 25/303 REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/303 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.368884 | 39.3105 | ETL.1450 | 44552352 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119637714 | Not Scheduled | T2 EI DRUM-SUMMIT #2 8/101 RPL STRW | 31498154 | DRUM-SUMMIT #2 | 008/101 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.638589 | 39.3217 | ETL.1450 | 44553580 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637724 | Q3 | T2 BRIDGEVILLE-CTTNWD 73/5 RPLC CRSL |  | BRIDGEVILLE-COTTONWOOD | 073/531 |  | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.568275 | 40.4815 | ETL.1110 | 44513676 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  | 2020-10-29 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637738 | Q3 | T2 BRIDGEVILLE-COTTONWOOD 82/5L RPL CRSL |  | BRIDGEVILLE-COTTONWOOD | 082/575 |  | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.708091 | 40.478 | ETL.1110 | 44425587 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  | 2020-12-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637748 | Q3 | T2 BRIDGEVILLE-CTTNWD 72/518 RPLC CRSS |  | BRIDGEVILLE-COTTONWOOD | 072/518 |  | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.538038 | 40.4685 | ETL.1110 | 44425583 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  | 2020-10-29 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637759 | Q3 | T2 BRIDGEVILLE-CTTNWD 83/582L RPL XARMS |  | BRIDGEVILLE-COTTONWOOD | 083/582 |  | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.72642 | 40.4833 | ETL.1110 | 44425593 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  | 2020-12-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637764 | Not Scheduled | T2NT DI DRUM-SMIT #2 26/320 RMV DEBRIS | 44449917 | DRUM-SUMMIT #2 | 026/320 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2022-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.340893 | 39.3099 | ETL.1450 | 44553574 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637772 | Q3 | T2 BRIDGEVILLE-CTTNWD 82/578 RPL XARMS |  | BRIDGEVILLE-COTTONWOOD | 082/578 |  | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.716419 | 40.4804 | ETL.1110 | 44425589 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  | 2020-12-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637774 | Q3 | T2 BRIDGEVILLE CTTNWD 86/604 RPL XARMS |  | BRIDGEVILLE-COTTONWOOD | 086/604 |  | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.778976 | 40.4822 | ETL.1110 | 44425596 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  | 2020-12-16 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637805 | Mar | T3 EI PITTSBURG-SAN RAMON - 230 kV_010/0 | 44609901 | PITTSBURG-SAN RAMON | 010/040 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-121.880954 | 37.8996 | ETL.5490 | 40607996 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637857 | Mar | T2 EI EAGLE ROCK-CORTINA 14/67 RPL INSU | 43730688 | EAGLE ROCK-CORTINA | 014/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-03-06 | 2021-03-01 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-122.4513873 | 39.0308 | ETL.1470 | 40847660 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637858 | Feb | T2 EI CORTINA-MENDOCINO#1 14/67 RPL INSU | 31518808 | CORTINA-MENDOCINO #1 | 014/067 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-02-18 | 2021-02-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.4513873 | 39.0308 | ETL.1330 | 40832986 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637860 | Not Scheduled | T2 DI DRUM-SUMMIT #2 022/266 RPL HRDS | 44482685 | DRUM-SUMMIT #2 | 022/266 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.406155 | 39.3287 | ETL.1450 | 44553754 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637862 | Not Scheduled | T2 DI DRUM-SUMMIT #2 22/266 RPR STRW | 44482685 | DRUM-SUMMIT #2 | 022/266 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.406155 | 39.3287 | ETL.1450 | 44553710 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637864 | Not Scheduled | T2 DI DRUM-SUMMIT #2 22/266 RPR STRW | 44482685 | DRUM-SUMMIT #2 | 022/266 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.406155 | 39.3287 | ETL.1450 | 44553754 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637867 | Not Scheduled | T2 DI DRUM-SUMMIT #2 019/228 RPR STRW | 44482685 | DRUM-SUMMIT #2 | 019/228 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.463999 | 39.3193 | ETL.1450 | 44557655 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637869 | Not Scheduled | T2 DI DRUM-SUMMIT #2 012/145R REPL POLE |  | DRUM-SUMMIT #2 | 012/145 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.573569 | 39.3322 | ETL.1450 | 44561221 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637900 | Not Scheduled | T2 EI DRUM-SUMMIT #2 8/100 RPL STRW | 44482685 | DRUM-SUMMIT #2 | 008/100 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6402364 | 39.3209 | ETL.1450 | 44553719 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119637946 | Mar | T3 EI DRUM-RIO OSO #2 6/69A RPL INSS | 31528394 | DRUM-RIO OSO #2 | 006/069A | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.863432 | 39.2054 | ETL.1430 | 40913100 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638219 | Q2 | EI GARBERVILLE-LAYTONVILL 42/5A RPR GYWW | 44453326 | GARBERVILLE-LAYTONVILLE | 042/005A | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.578553 | 39.9328 | ETL.8365 | 43250090 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638276 | Q2 | EI GARBERVILLE-LYTNVLL 41/10 RPL COND | 31527023 | GARBERVILLE-LAYTONVILLE | 041/010 | 93C | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577758 | 39.9255 | ETL.8365 | 40906663 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638279 | Q2 | EI GARBERVILLE-LAYTONVILLE 42/4 RPR STRW | 44453326 | GARBERVILLE-LAYTONVILLE | 042/004 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.578396 | 39.9313 | ETL.8365 | 40906668 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638292 | Q2 | EI GARBERVILLE-LAYTNVLL 41/10 RPL DAMPER | 44453326 | GARBERVILLE-LAYTONVILLE | 041/010 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577758 | 39.9255 | ETL.8365 | 40906663 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638340 | Q2 | EI GARBERVILLE-LAYTONVILL 44/11 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 044/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.598542 | 39.9589 | ETL.8365 | 40912496 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638374 | Q4 | T3 EI MAPLE CREEK-HOOPA 19/001 REFRAME | 44394730 | MAPLE CREEK-HOOPA | 019/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.656427 | 40.948 | ETL.7490 | 40586855 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638378 | Q2 | EI GARBERVILLE-LAYTONVILLE 44/10 RPL INS | 31513498 | GARBERVILLE-LAYTONVILLE | 044/010 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5969427 | 39.958 | ETL.8365 | 40922304 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638379 | Q2 | EI GARBERVILLE-LAYTONVILLE 44/10 RMV BUT | 44311203 | GARBERVILLE-LAYTONVILLE | 044/010 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-19 | 2022-08-19 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.596929 | 39.958 | ETL.8365 | 40912495 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638469 | Mar | T2 EI CORTINA-MENDCNO #1 15/75 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 015/075 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.477715 | 39.0194 | ETL.1330 | 40750569 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638499 | Not Scheduled | T2 DI DRUM-SUMMIT#2 22/270L REPL POLE |  | DRUM-SUMMIT #2 | 022/270 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.399088 | 39.3289 | ETL.1450 | 44553672 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119638562 | Q3 | EI T3NT MAPLE CREEK-HOOPA 21/8 RMV VEG | 44226794 | MAPLE CREEK-HOOPA | 021/008 | CHS | F | 2020_(3) On high spread structure |  | 2020-08-19 | 2022-08-19 |  |  | 2021-08-31 | 2121-08-01 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.642108 | 40.9684 | ETL.7490 | 40877919 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638585 | Not Scheduled | T3 EI MAPLE CREEK-HOOPA 21/8 REGRADE | 44453147 | MAPLE CREEK-HOOPA | 021/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.642108 | 40.9684 | ETL.7490 | 40877919 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638680 | Not Scheduled | T2 DI DRUM-SUMMIT#2 22/270R REPL POLE |  | DRUM-SUMMIT #2 | 022/270 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.399088 | 39.3289 | ETL.1450 | 44553747 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119638780 | Q4 | T3 EI MAPLE CREEK-HOOPA 25/4 REFRAME | 31510992 | MAPLE CREEK-HOOPA | 025/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-25 | 2021-01-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.64689 | 41.0159 | ETL.7490 | 40771317 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119638834 | Q4 | MAPLE CREEK-HOOPA 19/000L RPL POLE | 31437835 | MAPLE CREEK-HOOPA | 019/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.184972 | 38.4988 | ETL.7490 | 44145866 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy idoc |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639004 | Not Scheduled | EI DRUM-SUMMIT#2 15/181R RPL STRW | 31521945 | DRUM-SUMMIT #2 | 015/181 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.529653 | 39.3073 | ETL.1450 | 44561289 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639007 | Not Scheduled | EI DRUM-SUMMIT#2 15/182R RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/182 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5280897 | 39.3071 | ETL.1450 | 44561345 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639033 | Q2 | EI LOS BANOS-MIDWAY #2 38/161 BENT MEMB | 44490736 | LOS BANOS-MIDWAY #2 | 038/161 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.621938 | 36.6009 | ETL.6010 | 40587746 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639035 | Not Scheduled | EI DRUM-SUMMIT#2 15/182C RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/182 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5280897 | 39.3071 | ETL.1450 | 44561380 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639040 | Not Scheduled | EI DRUM-SUMMIT#2 15/181C RPL STRW | 31521945 | DRUM-SUMMIT #2 | 015/181 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.529653 | 39.3073 | ETL.1450 | 44561381 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639041 | Not Scheduled | EI DRUM-SUMMIT#2 15/181L RPL STRW | 31521945 | DRUM-SUMMIT #2 | 015/181 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.529653 | 39.3073 | ETL.1450 | 44561290 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639044 | Not Scheduled | EI DRUM-SUMMIT#2_015/182L RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/182 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5280897 | 39.3071 | ETL.1450 | 44561433 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639050 | Not Scheduled | EI DRUM-SUMMIT #2 15/184B INST MRKW | 44449917 | DRUM-SUMMIT #2 | 015/184B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2022-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525626 | 39.307 | ETL.1450 | 44155597 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639051 | Not Scheduled | EI DRUM-SUMMIT #2 15/184C RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/184C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525615 | 39.307 | ETL.1450 | 44155598 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639274 | Q2 | T2 BRIDGEVILLE-CTTNWD 58/425A RPR FOND | 44634440 | BRIDGEVILLE-COTTONWOOD | 058/425A | ICQ | E | 2020_(3) On high spread structure |  | 2020-07-20 | 2021-07-20 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.337168 | 40.3784 | ETL.1110 | 40676686 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639566 | Not Scheduled | EI DRUM-SUMMIT #1 14/168C INST GYWW | 44476654 | DRUM-SUMMIT #1 | 014/168C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.541669 | 39.3128 | ETL.1440 | 42572677 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639569 | Not Scheduled | EI DRUM-SUMMIT #1 15/170A RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/170A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538595 | 39.3114 | ETL.1440 | 40603737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639572 | Not Scheduled | EI DRUM-SUMMIT #1 14/168B INST GYWW | 44476654 | DRUM-SUMMIT #1 | 014/168B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.541641 | 39.3129 | ETL.1440 | 42572676 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639574 | Not Scheduled | EI DRUM-SUMMIT #1 14/168A INST GYWW | 44476654 | DRUM-SUMMIT #1 | 014/168A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.541617 | 39.3129 | ETL.1440 | 40865993 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639575 | Not Scheduled | EI DRUM-SUMMIT #1 15/173 RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/173 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.537335 | 39.3097 | ETL.1440 | 40653604 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639577 | Not Scheduled | EI DRUM-SUMMIT #1 15/170C RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/170C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538684 | 39.3114 | ETL.1440 | 42572680 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639578 | Not Scheduled | EI DRUM-SUMMIT #1 15/170B RPR GYWW | 44476654 | DRUM-SUMMIT #1 | 015/170B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538637 | 39.3114 | ETL.1440 | 42572678 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639581 | Not Scheduled | EI DRUM-SUMMIT #1 15/172 INST GYWW | 44476654 | DRUM-SUMMIT #1 | 015/172 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.537816 | 39.3103 | ETL.1440 | 40702400 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639656 | Not Scheduled | T2 HUMBOLDT-BRIDGEVILLE 113/3A RPL X-ARM | 31511685 | HUMBOLDT-BRIDGEVILLE | 113/003A | 93Z | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 | [7 empty] | TR2 |  | North Coast | WSIP | [8 empty] | ETL.1810 | 44322715 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639778 | Mar | T3 EI DRUM-RIO OSO #2 10/100 RPL INSS | 31528394 | DRUM-RIO OSO #2 | 010/100 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.9190415 | 39.1756 | ETL.1430 | 40638284 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639803 | Q2 | EI T3NT FULTON-PUEBLO 036/184 INST ACG | 31529483 | FULTON-PUEBLO | 036/184 | 93A | F | 2020_(3) On high spread structure |  | 2020-08-19 | 2022-08-19 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.647169 | 38.4971 | ETL.1600 | 40750537 | GO95 / Anti Climb | Ground / Clearance | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639822 | Not Scheduled | T3 EI DRM-RIO OSO #2 10/100 RMV VEG |  | DRUM-RIO OSO #2 | 010/100 | HNA | E | 2020_(3) On high spread structure |  | 2020-08-19 | 2021-02-19 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.919028 | 39.1756 | ETL.1430 | 40608843 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639823 | Mar | EI T3NT DRUM-RIO OSO #2 - 10/100 INST MR | 44449034 | DRUM-RIO OSO #2 | 010/100 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-19 | 2022-08-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.919028 | 39.1756 | ETL.1430 | 40608843 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639825 | Q2 | EI T3NT FULTON-PUEBLO 36/183 INST ACG | 31529483 | FULTON-PUEBLO | 036/183 | 93A | F | 2020_(3) On high spread structure |  | 2020-08-19 | 2022-08-19 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.644933 | 38.4972 | ETL.1600 | 40645131 | GO95 / Anti Climb | Ground / Clearance | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639830 | Q2 | EI T3NT FULTON-PUEBL 36/184 INST FOND | 44306536 | FULTON-PUEBLO | 036/184 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-19 | 2022-08-19 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.647169 | 38.4971 | ETL.1600 | 40750537 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119639893 | Not Scheduled | EI DRUM-SUMMIT #1 15/181A RPL STRW | 31521943 | DRUM-SUMMIT #1 | 015/181A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525436 | 39.3069 | ETL.1440 | 40590108 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639895 | Not Scheduled | EI DRUM-SUMMIT #1 15/181B RPL STRW | 31521943 | DRUM-SUMMIT #1 | 015/181 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525415 | 39.3069 | ETL.1440 | 42572684 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119639942 | Not Scheduled | EI DRUM-SUMMIT #1 15/181C RPL STRW | 31521943 | DRUM-SUMMIT #1 | 015/181C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525388 | 39.3068 | ETL.1440 | 42572685 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640054 | Q2 | EI GARBERVILLE-LAYTONVILL 54/8 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 054/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.662996 | 40.0816 | ETL.8365 | 44694239 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119640209 | Not Scheduled | EI DRUM-SUMMIT#2 15/175L HIGH SIGN | 44482692 | DRUM-SUMMIT #2 | 015/175 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2022-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5376236 | 39.3104 | ETL.1450 | 44558939 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640234 | Q2 | EI GARBERVILLE-LAYTNVLE 54/4 REPL POLE | 31512220 | GARBERVILLE-LAYTONVILLE | 054/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.656322 | 40.0795 | ETL.8365 | 40912606 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119640246 | Q2 | EI GARBERVILLE-LAYTONVILL 54/3 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 054/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.655835 | 40.0787 | ETL.8365 | 44241869 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119640253 | Not Scheduled | EI DRUM-SUMMIT#2 15/177C RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/177 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535967 | 39.3088 | ETL.1450 | 44549863 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640255 | Not Scheduled | EI DRUM-SUMMIT#2 15/177L RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/177 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535967 | 39.3088 | ETL.1450 | 44549908 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640260 | Not Scheduled | EI DRUM-SUMMIT#2 15/177R RPR GYWW | 44476655 | DRUM-SUMMIT #2 | 015/177 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535967 | 39.3088 | ETL.1450 | 44549937 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640269 | Not Scheduled | EI DRUM-SUMMIT#2_015/175R HIGH SIGN | 44482692 | DRUM-SUMMIT #2 | 015/175 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2022-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5376236 | 39.3104 | ETL.1450 | 44559015 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640272 | Not Scheduled | EI DRUM-SUMMIT#2 14/174L HIGH SIGN | 44482692 | DRUM-SUMMIT #2 | 014/174 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2022-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5380618 | 39.311 | ETL.1450 | 44559041 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640291 | Not Scheduled | EI DRUM-SUMMIT#2 14/174R HIGH SIGN | 44482692 | DRUM-SUMMIT #2 | 014/174 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2022-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5380618 | 39.311 | ETL.1450 | 44559065 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119640878 | Mar | EI T2NT CORTINA-MENDCN #1 57/282 RPR FON |  | CORTINA-MENDOCINO #1 | 057/282 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2022-08-19 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.140592 | 39.236 | ETL.1330 | 40657099 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119640879 | Mar | EI T2NT CORTNA-MNDCINO #1 57/280 RPR FON |  | CORTINA-MENDOCINO #1 | 057/280 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2022-08-19 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.131303 | 39.2336 | ETL.1330 | 40587924 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119641082 | Not Scheduled | T2 DRUM-SUMMIT #1 8/94 RPR WDPKR | 44645317 | DRUM-SUMMIT #1 | 008/094 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.652874 | 39.3135 | ETL.1440 | 44768895 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119641326 | Not Scheduled | T3 EI SBRNT-GRZZLY-CLRMNT #1 4/0 RMV VEG | 44627172 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/038E | CHS | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-20 | 2021-02-20 | [7 empty] | TR3 | <15D | Central | WSIP | [6 empty] | '-122.18839 | 37.8565 | ETL.3740 | 44188755 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119641366 | Q2 | LOS BANOS-MIDWAY #2 036/151 RPR STRT |  | LOS BANOS-MIDWAY #2 | 036/151 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.648588 | 36.6307 | ETL.6010 | 40587745 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119642130 | Q2 | EI LOS BANOS-MIDWAY #2 40/166 BENT MEMB | 44490736 | LOS BANOS-MIDWAY #2 | 040/166 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.60783 | 36.588 | ETL.6010 | 40820169 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119642134 | Not Scheduled | T2 EI DRUM-SUMMIT #1 20/240 RPL STRW | 31453474 | DRUM-SUMMIT #1 | 020/240 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.439073 | 39.3201 | ETL.1440 | 40814118 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119642135 | Q2 | EI T3NT FULTON-PUEBLO 37/186 RPR FOND |  | FULTON-PUEBLO | 037/186 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.651963 | 38.4971 | ETL.1600 | 40805564 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119642136 | Not Scheduled | T3 EI FULTON-PUEBLO 37/186 RPL INSUL | 31505500 | FULTON-PUEBLO | 037/186 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-02-20 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.6519763 | 38.4971 | ETL.1600 | 40831847 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119642376 | Q2 | EI LOS BANOS-MIDWAY #2 040/167 RPR STRS |  | LOS BANOS-MIDWAY #2 | 040/167 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.604693 | 36.5852 | ETL.6010 | 40811497 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119643015 | Q2 | EI LOS BANOS-GATES #1 036/152 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 036/152 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.647955 | 36.6293 | ETL.6000 | 40679639 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119643293 | Q2 | T3 DI IGNACIO-BLNS #1 8/92 RPL POLE | 31511689 | IGNACIO-BOLINAS #1 | 008/092 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.654972 | 38.0083 | ETL.7140 | 40835672 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119643549 | Q2 | EI MI WUK CURTIS 26/1 RPR WDPKR | 44623593 | ETL.1073.POLE.WDPS | 026/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.3086156 | 37.9757 | ETL.1073 | 44771121 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119643735 | Q4 | T3 EI MAPLE CREEK-HPA 17/6 INST JMPS SPP | 44394730 | MAPLE CREEK-HOOPA | 017/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-02-20 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.675507 | 40.9346 | ETL.7490 | 40827965 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119643741 | Q4 | T3NT EI MAPLE CREEK-HOOPA 17/6 RMV DBRS | 44593017 | MAPLE CREEK-HOOPA | 017/006 | ICW | F | 2020_(2) High fire spread TD |  | 2020-08-20 | 2022-08-20 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.675507 | 40.9346 | ETL.7490 | 40827965 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119643924 | Mar | T3 EI PITTSBURG-TASSAJARA 13/52 RPR INSU | 44609902 | PITTSBURG-TASSAJARA | 013/052 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-02-20 |  |  | 2021-03-31 | 2021-03-31 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-121.8868374 | 37.864 | ETL.5470 | 40705455 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119643926 | Q3 | EI LOS BANOS-MIDWAY #2 121/497 RMV VEGN |  | LOS BANOS-MIDWAY #2 | 121/497 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-08-15 | 2021-08-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.69062 | 35.6931 | ETL.6010 | 40817795 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119644017 | Q2 | EI MI WUK CURTIS 26/4 RPR WDPKR | 44623595 | ETL.1073.POLE.WDPS | 026/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.315742 | 37.9746 | ETL.1073 | 44515773 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644021 | Q2 | EI MI WUK CURTIS 26/4 RPR WDPKR |  | ETL.1073.POLE.WDPS | 026/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.315742 | 37.9746 | ETL.1073 | 44515772 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644022 | Q2 | EI MI WUK CURTIS 26/4 RPR WDPKR |  | ETL.1073.POLE.WDPS | 026/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.315742 | 37.9746 | ETL.1073 | 44515774 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644097 | Not Scheduled | T2 EI COLGATE-CHALLENGE A0/021 RPR GYWW | 44461284 | COLGATE-CHALLENGE | A000/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.194778 | 39.3399 | ETL.6480 | 42549797 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644138 | Q2 | EI T3NT EAGLE RK-FLTN-SLVRD 13/56 RPR FO |  | EAGLE ROCK-FULTON-SILVERADO | 013/056 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2022-08-20 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.701611 | 38.5678 | ETL.4392 | 41129358 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644253 | Q2 | EI GARBERVILLE-LAYTNVLLE 46/000 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 046/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.618465 | 39.9681 | ETL.8365 | 40912510 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644254 | Q2 | EI GARBERVILLE-LYTNVLLE 46/000 RPR SPLW | 44476763 | GARBERVILLE-LAYTONVILLE | 046/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.618465 | 39.9681 | ETL.8365 | 40912510 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644258 | Q2 | EI GARBERVILLE-LAYTONVILL 45/6R RPL GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6135369 | 39.9661 | ETL.8365 | 44403650 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644261 | Q2 | EI GARBERVILLE-LYTNVLLE 46/000 RPLC INSW | 31505611 | GARBERVILLE-LAYTONVILLE | 046/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.618479 | 39.9681 | ETL.8365 | 40922319 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644262 | Q2 | EI GARBERVILLE-LAYTONVILL 45/6L RPL GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6135369 | 39.9661 | ETL.8365 | 44403648 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644263 | Q2 | EI GARBERVILLE-LAYTONVILLE 46/1 RPL STRW | 31514965 | GARBERVILLE-LAYTONVILLE | 046/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.619044 | 39.9688 | ETL.8365 | 40912511 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644265 | Q2 | EI GARBERVILLE-LAYTONVILL 45/6C RPL GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6135369 | 39.9661 | ETL.8365 | 44403649 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644267 | Q2 | EI GARBERVILLE-LAYTONVILLE 45/8 RMV DEBR | 44311203 | GARBERVILLE-LAYTONVILLE | 045/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617512 | 39.967 | ETL.8365 | 40912509 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644268 | Q2 | EI GARBERVILLE-LAYTONVILLE 45/7 REPL POL | 31514965 | GARBERVILLE-LAYTONVILLE | 045/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.615797 | 39.9666 | ETL.8365 | 40912508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644270 | Q2 | EI GARBERVILLE-LYTNVLLE 46/000 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 046/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.618465 | 39.9681 | ETL.8365 | 40912510 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644288 | Q2 | EI LOS BANOS-GATES #1 037/156 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 037/156 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.636479 | 36.6164 | ETL.6000 | 40817031 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119644336 | Q2 | EI GARBERVILLE-LAYTONVILL 45/0 REPL POLE | 31514686 | GARBERVILLE-LAYTONVILLE | 045/000 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.602321 | 39.9609 | ETL.8365 | 40912498 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644337 | Q2 | EI GARBERVILLE-LAYTONVILL 45/0 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 045/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.602321 | 39.9609 | ETL.8365 | 40912498 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644486 | Q2 | EI GARBERVILLE-LAYTONVILL 45/3 RPL POLE | 31514965 | GARBERVILLE-LAYTONVILLE | 045/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.607076 | 39.9634 | ETL.8365 | 40912501 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644554 | Q3 | T2 DI BRDGVL-CTTNWD 65/473 RPR OPGW | 44398374 | BRIDGEVILLE-COTTONWOOD | 065/473 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-08-20 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.451547 | 40.4121 | ETL.1110 | 40770888 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644668 | Not Scheduled | T2 DI DRUM-SUMMIT #1 8/102 INST DAMPER | 44449506 | DRUM-SUMMIT #1 | 008/102 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.638423 | 39.3173 | ETL.1440 | 40865989 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119644951 | Q2 | EI LOS BANOS-MIDWAY #2 41/174 RPR FOND | 44490736 | LOS BANOS-MIDWAY #2 | 041/174 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.583058 | 36.5697 | ETL.6010 | 40753972 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119645060 | Mar | T2 EI CORTINA-MENDCNO #1 40/194 RPR FOND |  | CORTINA-MENDOCINO #1 | 040/194 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.871784 | 39.1407 | ETL.1330 | 40750608 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645068 | Q4 | T3 EI MAPLE CREEK-HOOPA 14/001 RPR CRSAR | 44394730 | MAPLE CREEK-HOOPA | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-02-20 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.727342 | 40.9049 | ETL.7490 | 40586851 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645158 | Q2 | EI LOS BANOS-MIDWAY #2 042/175 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 042/175 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.579649 | 36.5676 | ETL.6010 | 40764985 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119645189 | Q3 | CARIBOU-PLMS JCT SW ;10/06 RPR SWITCH |  | CARIBOU-PLUMAS JCT | ;010/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-08-20 |  |  | 2021-08-20 | 2021-08-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.91621 | 39.9348 | ETL.6290 | 40840970 | Switch-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645628 | Not Scheduled | T3NT EI DRUM-SUMMIT #1 4/58 INST MRKW | 44476843 | DRUM-SUMMIT #1 | 004/058 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2022-08-20 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.7036413 | 39.2929 | ETL.1440 | 44162389 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645770 | Q2 | EI GARBERVILLE-LAYTONVILLE 51/3 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 051/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.640271 | 40.0368 | ETL.8365 | 40912572 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645772 | Q2 | EI GARBERVILLE-LAYTONVILLE 51/10 RPL STR | 31514965 | GARBERVILLE-LAYTONVILLE | 051/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.640631 | 40.0452 | ETL.8365 | 40912579 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645776 | Q2 | EI GARBERVILLE-LAYTONVILLE 51/8 RPL STRW | 31514965 | GARBERVILLE-LAYTONVILLE | 051/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.640954 | 40.0432 | ETL.8365 | 40912577 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645777 | Q2 | EI GARBERVILLE-LAYTONVILL 50/9 RPL POLE | 31515658 | GARBERVILLE-LAYTONVILLE | 050/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.638192 | 40.0319 | ETL.8365 | 40912567 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645780 | Q2 | EI GARBERVILLE-LAYTONVILLE 51/9A RPR WDP | 44449697 | GARBERVILLE-LAYTONVILLE | 051/009A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.640674 | 40.0449 | ETL.8365 | 42600438 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645782 | Q2 | EI GARBERVILLE-LAYTONVILLE 50/2 RPL STRW | 31515658 | GARBERVILLE-LAYTONVILLE | 050/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6282 | 40.0237 | ETL.8365 | 40912560 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645785 | Q2 | EI GARBERVILLE-LAYTONVILLE 50/7 RPL STRW | 31514965 | GARBERVILLE-LAYTONVILLE | 050/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.634204 | 40.029 | ETL.8365 | 40912565 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645790 | Q2 | EI GARBERVILLE-LAYTONVILLE 50/3 RPR WPKR | 44449697 | GARBERVILLE-LAYTONVILLE | 050/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.628784 | 40.0248 | ETL.8365 | 40912561 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645791 | Q2 | EI GARBERVILLE-LAYTONVILL 51/1 RPL POLE | 31515658 | GARBERVILLE-LAYTONVILLE | 051/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639448 | 40.0345 | ETL.8365 | 40912570 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645801 | Q2 | EI GARBERVILLE-LAYTONVILL 51/7 RPL POLE | 31515658 | GARBERVILLE-LAYTONVILLE | 051/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-19 | 2021-08-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.64116 | 40.0416 | ETL.8365 | 40912576 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645939 | Q2 | EI GARBERVILLE-LYTNVLL 45/005 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 045/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.611006 | 39.9655 | ETL.8365 | 40912503 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119645972 | Q2 | EI GARBERVILLE-LYTNVLL 45/005 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 045/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.611006 | 39.9655 | ETL.8365 | 40912503 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119647390 | Q2 | EI LOS BANOS-MIDWAY #2 042/178 RPR STRS |  | LOS BANOS-MIDWAY #2 | 042/178 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-21 | 2021-08-21 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.570655 | 36.5622 | ETL.6010 | 40863974 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119647607 | Q2 | EI LOS BANOS-MIDWAY #2 042/179 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 042/179 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-21 | 2021-08-21 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.568508 | 36.5609 | ETL.6010 | 40863653 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119647738 | Q2 | DI SNTH LN-HLF MN BY ?/7 RPR SPLW | 44308003 | SNEATH LANE-HALF MOON BAY | ?000/007 | GCD | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-18 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.492761 | 37.5925 | ETL.7212 | 40815494 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC ObjC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | GCD | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119647739 | Not Scheduled | DI SNTH LN-HLF MN BY ?/7 RMV BUTT | 44620192 | SNEATH LANE-HALF MOON BAY | ?000/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-20 | 2022-08-20 | [9 empty] | Central | WSIP | [6 empty] | '-122.492761 | 37.5925 | ETL.7212 | 40815494 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119647858 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 7/62 RPR GYWW |  | ATASCADERO-CAYUCOS | 007/062 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-19 | 2021-02-19 | [7 empty] | TR3 | <15D | South | WSIP | [6 empty] | '-120.792829 | 35.4567 | ETL.8480 | 40679170 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119647922 | Q2 | T2 DI PITTSBURG-EASTSHORE 3/17 RPL HRDT |  | PITTSBURG-EASTSHORE | 003/017 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.909324 | 37.9927 | ETL.5462 | 40804935 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648016 | Q2 | EI IGNACIO-BOLINAS #2 15/170 REPULL GUY | 44640735 | IGNACIO-BOLINAS #2 | 015/170 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-08-21 |  |  | 2021-04-14 | 2021-04-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.7373611 | 38.0533 | ETL.7180 | 44924647 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648114 | Not Scheduled | T3 EI EAGLE ROCK-FULTON-SLV 37/186 RPL I | 31522190 | EAGLE ROCK-FULTON-SILVERADO | 037/186 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-02-20 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.6519763 | 38.4971 | ETL.4392 | 40831849 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648490 | Mar | T3 EI PARKWAY-MORAGA 18/104 RPL INSLS | 31526488 | PARKWAY-MORAGA | 018/104 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.2122897 | 37.8934 | ETL.5930 | 40890773 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648671 | Q2 | T2 DI SBRNT-STNDRD OIL#1 5/30 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 005/030 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.210498 | 37.9714 | ETL.3800 | 40590866 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648672 | Q2 | T2 DI SBRNT-STNDRD OIL#1 5/30 RPR STRT |  | SOBRANTE-STANDARD OIL SW STA #2 | 005/030 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.210498 | 37.9714 | ETL.3800 | 40590866 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648676 | Q2 | T2 DI SBRNT-STNDRD OIL #1 3/17 RPR STRT | 44624392 | SOBRANTE-STANDARD OIL SW STA #2 | 003/017 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.204559 | 37.9425 | ETL.3800 | 40804893 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648725 | Feb | STNILS-MLNS SW ST-MNT 28/176 INST DAMPER |  | STANISLAUS-MELONES SS-MANTECA #1+ | 028/176 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-08-21 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.791739 | 37.9166 | ETL.3830 | 40744442 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-27 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648861 | Q2 | T2 DI HAT CRK #1-WSTWD 40/779 BOND HRD |  | HAT CREEK #1-WESTWOOD | 040/779 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.031144 | 40.5102 | ETL.7030 | 44311024 | Ground Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648863 | Q2 | T2 DI SBRNT-STNDRD OIL#1 6/38 RPLC INSS |  | SOBRANTE-STANDARD OIL SW STA #2 | 006/038 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-04 | 2021-05-04 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.223615 | 37.9881 | ETL.3800 | 40898593 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119648864 | Q2 | T2 DI SBRNT-STNDRD OIL#1 4/26 RPR STRT | 44624392 | SOBRANTE-STANDARD OIL SW STA #2 | 004/026 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.204115 | 37.9635 | ETL.3800 | 40822975 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649009 | Not Scheduled | T3 EI DRUM-RIO OSO #1 - 2/28 RPR TWR | 44449904 | DRUM-RIO OSO #1 | 002/028 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.815542 | 39.2456 | ETL.1420 | 40866005 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649040 | Mar | T3 EI DRUM-RIO OSO #1 2/28 RPR FOND | 44449904 | DRUM-RIO OSO #1 | 002/028 | ICQ | E | 2020_(3) On high spread structure |  | 2020-08-21 | 2021-02-21 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.815542 | 39.2456 | ETL.1420 | 40866005 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649070 | Q3 | T2 DI BRDGVL-CTTNWD 60/436 RPR OPGW | 44398374 | BRIDGEVILLE-COTTONWOOD | 060/436 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-08-20 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.365887 | 40.3738 | ETL.1110 | 40676694 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649093 | Q2 | EI LOS BANOS-GATES #1 040/168 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 040/168 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-21 | 2021-08-21 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.602614 | 36.5827 | ETL.6000 | 40868376 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119649112 | Q2 | EI GARBERVILLE-LAYTONVILLE 46/2 RMV DEBR | 44311203 | GARBERVILLE-LAYTONVILLE | 046/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-21 | 2022-08-21 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.620364 | 39.9704 | ETL.8365 | 40912512 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649200 | Q2 | EI GARBERVILLE-LAYTONVILLE 46/6 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 046/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-21 | 2021-08-21 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6234 | 39.9743 | ETL.8365 | 40912516 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649201 | Q2 | EI GARBERVILLE-LAYTONVILLE 46/6 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 046/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-21 | 2022-08-21 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6234 | 39.9743 | ETL.8365 | 40912516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649239 | Not Scheduled | T2 DI CLGTE-SMARTVILLE #2 8/100 REGRADE | 44452456 | COLGATE-SMARTVILLE #2 | 008/100 | ICW | E | 2020_(1a) PSPS |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295814 | 39.2389 | ETL.6520 | 40594280 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119649280 | Q2 | EI GARBERVILLE-LAYTONVILLE 47/1 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 047/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-21 | 2022-08-21 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.622801 | 39.9815 | ETL.8365 | 40912526 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649282 | Q2 | EI GARBERVILLE-LAYTONVILL 47/1 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 047/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-21 | 2021-08-21 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.622801 | 39.9815 | ETL.8365 | 40912526 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649283 | Q2 | EI GARBERVILLE-LAYTONVILLE 47/1 RPR FOND | 44449697 | GARBERVILLE-LAYTONVILLE | 047/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-21 | 2021-08-21 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.622801 | 39.9815 | ETL.8365 | 40912526 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649310 | Not Scheduled | T2 WV DRUM-SUMMIT #1 22/268 RPL DAMPER | 44482753 | DRUM-SUMMIT #1 | 022/268 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-21 | 2021-08-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.40423 | 39.3105 | ETL.1440 | 40864940 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649325 | Q2 | T3 EI MISRI FLAT-GLD HL #1 17/153 RPL IS | 31504275 | MISSOURI FLAT-GOLD HILL #1 | 017/153 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-21 | 2021-02-21 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.8731486 | 38.6687 | ETL.2660 | 40680502 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649340 | Q2 | T3 EI MISSOURI FLAT-GLD HLL #1 15/1 RMV | 44453050 | MISSOURI FLAT-GOLD HILL #1 | 015/137 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-21 | 2021-02-21 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.846522 | 38.6862 | ETL.2660 | 40818739 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649355 | Not Scheduled | T2 WV COLGT-SMRTVL #2 009/108 INST DAMW | 44482827 | COLGATE-SMARTVILLE #2 | 009/108 | ICW | E | 2020_(1a) PSPS |  | 2020-08-21 | 2021-08-21 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.29549 | 39.2338 | ETL.6520 | 40828236 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119649511 | Not Scheduled | EI T3NT MSR FLT-GD HL #1 017/152 INST CL | 31512555 | MISSOURI FLAT-GOLD HILL #1 | 017/152 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-21 | 2022-08-21 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.870283 | 38.6698 | ETL.2660 | 40660285 | GO95 / Anti Climb | Ground / Clearance | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649545 | Q2 | T2NT SBRT-STDRD OL SW ST #1 7/41 RPR FON |  | SOBRANTE-STANDARD OIL SW STA #2 | 007/041 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.229278 | 37.9949 | ETL.3800 | 40594295 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649622 | Not Scheduled | T3 EI DRUM-RIO OSO #1 3/35 RPR TWR | 44449904 | DRUM-RIO OSO #1 | 003/035 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.82221 | 39.2392 | ETL.1420 | 40756203 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649733 | Q4 | T3 EI MAPLE CREEK-HOOPA 14/002 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 014/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.726315 | 40.9045 | ETL.7490 | 44735738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649856 | Q4 | T3 EI MAPLE CREEK-HOOPA 13/010 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 013/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.728742 | 40.9053 | ETL.7490 | 44885536 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119649921 | Q2 | EI LOS BANOS-MIDWAY #2 044/186 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 044/186 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-21 | 2021-08-21 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.54291 | 36.5447 | ETL.6010 | 40812152 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119650065 | Q4 | T3 EI MAPLE CREEK-HOOPA 13/7 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 013/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.733576 | 40.9061 | ETL.7490 | 40826044 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119650066 | Q4 | T3 EI MAPLE CREEK-HOOPA 13/7 REFRAME | 31510992 | MAPLE CREEK-HOOPA | 013/007 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.733576 | 40.9061 | ETL.7490 | 40826044 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119650090 | Q4 | EI T3NT MAPLE CREEK-HOOPA 13/7 RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 013/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-21 | 2022-08-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.733576 | 40.9061 | ETL.7490 | 40826044 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119650411 | Q4 | T3 EI MAPLE CREEK-HOOPA 13/6 RPR GYWW | 44394730 | MAPLE CREEK-HOOPA | 013/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-21 | 2021-02-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.735012 | 40.9058 | ETL.7490 | 44735737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119652842 | Not Scheduled | EI T3NT GEYSERS #17-FULTON 0/1 REPAINT | 44585957 | GEYSERS #17-FULTON | 000/001 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-21 | 2022-08-21 | 2021-01-18 | 2021-01-21 | [5 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.781153 | 38.8241 | ETL.4770 | 40587523 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119652843 | Q2 | EI T3NT GEYSERS #17-FULTON 0/1 RPR FOND | 44637021 | GEYSERS #17-FULTON | 000/001 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-21 | 2022-08-21 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.781153 | 38.8241 | ETL.4770 | 40587523 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119652851 | Q2 | EI T3NT GEYSERS #17-FULTON 0/01 INST ACG |  | GEYSERS #17-FULTON | 000/001 | 93A | F | 2020_(3) On high spread structure |  | 2020-08-21 | 2022-08-21 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.781153 | 38.8241 | ETL.4770 | 40587523 | GO95 / Anti Climb | Clearance | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119653597 | Not Scheduled | T3 FRENCH MEADOWS-MIDDLE FORK 0/4 RPL PO | 31512077 | FRENCH MEADOWS-MIDDLE FORK | 000/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-01-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.40918 | 39.0775 | ETL.6870 | 40767468 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119654030 | Not Scheduled | T3 FRENCH MEADOWS-MIDDLE FORK 9/170 RPL | 31512077 | FRENCH MEADOWS-MIDDLE FORK | 009/170 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-01-20 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.549678 | 39.0178 | ETL.6870 | 40664828 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119654219 | Not Scheduled | T3 EI FULTON-PUEBLO 31/152 RMV VEG |  | FULTON-PUEBLO | 031/152 | HNA | E | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-02-21 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.5503 | 38.4856 | ETL.1600 | 40656848 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119654402 | Q4 | T3 EI MAPLE CREEK-HOOPA 15/001 REFRAME | 31510992 | MAPLE CREEK-HOOPA | 015/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.708747 | 40.9091 | ETL.7490 | 40586852 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119655745 | Not Scheduled | T2 COLGATE-SMARTVILLE #2 0/5 RPL POLE | 31515572 | COLGATE-SMARTVILLE #2 | 000/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2021-06-18 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.191655 | 39.3294 | ETL.6520 | 40771345 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119656641 | Q2 | T3 EI IGNACIO-BOLINAS #2 3/039 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 003/039 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-21 | 2021-02-21 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.591755 | 38.0807 | ETL.7180 | 40770936 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119657731 | Q2 | EI GARBERVILLE-LAYTONVILL 39/6 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 039/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-08-22 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.581298 | 39.8876 | ETL.8365 | 40906632 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119657790 | Feb | T3 EI DRUM-RIO OSO #1 3/039 RPL INSLS | 31505600 | DRUM-RIO OSO #1 | 003/039 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-02-22 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8261538 | 39.2352 | ETL.1420 | 40888167 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119658235 | Feb | EI DRUM-RIO OSO #1 10/109A RPL POLE | 31518677 | DRUM-RIO OSO #1 | 010/109A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-08-22 |  |  | 2021-02-23 | 2021-02-10 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.9398701 | 39.1676 | ETL.1420 | 44415624 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119658264 | Feb | EI DRUM-RIO OSO #1 10/109A RPL POLE | 31518677 | DRUM-RIO OSO #1 | 010/109A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-08-22 |  |  | 2021-02-23 | 2021-02-10 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.9398701 | 39.1676 | ETL.1420 | 44415625 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119659126 | Q2 | EI T3NT FULTON-PUEBLO 2/159 RPR FOND | 44306536 | FULTON-PUEBLO | 032/159 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-22 | 2022-08-22 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.567663 | 38.4894 | ETL.1600 | 40872724 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119659129 | Q2 | T3 EI FULTON-PUEBLO 32/156 RPR FOND | 44306536 | FULTON-PUEBLO | 032/156 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-02-22 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.560724 | 38.4879 | ETL.1600 | 40808845 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119659140 | Q2 | T3 EI FULTON-PUEBLO 32/155 RPR FOND | 44306536 | FULTON-PUEBLO | 032/155 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-02-22 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.558278 | 38.4873 | ETL.1600 | 40750501 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119659274 | Not Scheduled | T2 EI SALT SPRNGS-TGR CRK 4/044 RPR STRS | 44631415 | SALT SPRINGS-TIGER CREEK | 004/044 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-23 | 2021-08-23 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.303406 | 38.4779 | ETL.3500 | 40744666 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119659285 | Not Scheduled | T2 EI SALT SPRIGS-TGR CRK 5/046 RPR STRT | 44631415 | SALT SPRINGS-TIGER CREEK | 005/046 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-23 | 2021-08-23 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.306095 | 38.4779 | ETL.3500 | 40804243 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119660148 | Feb | T3 EI DRUM-RIO OSO #1 4/052 REFRAME | 44449911 | DRUM-RIO OSO #1 | 004/052 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-23 | 2021-02-23 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.83886 | 39.2229 | ETL.1420 | 40683420 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119660866 | Q2 | EI GARBERVILLE-LAYTONVILL 39/0 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 039/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-22 | 2021-08-22 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.582184 | 39.8821 | ETL.8365 | 40906626 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119661060 | Q2 | DI SALINAS-LAURELES A016/343 RPR SPLW | 44391519 | SALINAS-LAURELES | A016/343 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | [5 empty] | South | WSIP | [6 empty] | '-121.82995 | 36.5816 | ETL.7930 | 40864619 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119661390 | Not Scheduled | EI LOS BANOS-MIDWAY #2 47/199 INST ZENA | 44507666 | LOS BANOS-MIDWAY #2 | 047/199 | ICB | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.50504 | 36.5177 | ETL.6010 | 40867852 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119661912 | Q2 | EI LOS BANOS-MIDWAY #2 45/188 BENT STEEL | 44507667 | LOS BANOS-MIDWAY #2 | 045/188 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.536008 | 36.54 | ETL.6010 | 40863976 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119661949 | Q2 | EI LS BNS-MIDWY #2 - 48/201 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 048/201 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.498212 | 36.5121 | ETL.6010 | 40587751 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119662407 | Q2 | T2 EI HAT CRK #1-WESTWOOD 9/173 RPL STRW | 31514964 | HAT CREEK #1-WESTWOOD | 009/173 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.407968 | 40.8662 | ETL.7030 | 40592062 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662475 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 8/170 REFRM | 31514229 | HAT CREEK #1-WESTWOOD | 008/170 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-06-25 | 2021-05-03 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.4093265 | 40.8681 | ETL.7030 | 40800754 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662481 | Q2 | T2 EI HAT CRK #1-WESTWD 9/172 RPL STRW | 31514964 | HAT CREEK #1-WESTWOOD | 009/172 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.408378 | 40.8668 | ETL.7030 | 40616844 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662484 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 8/171 REFRM | 31512257 | HAT CREEK #1-WESTWOOD | 008/171 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.408878 | 40.8675 | ETL.7030 | 40827587 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662521 | Q2 | T2 EI HAT CREEK #1-WTWD 41/791 REFRAME | 31514136 | HAT CREEK #1-WESTWOOD | 041/791 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-24 | 2021-08-24 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.027277 | 40.5015 | ETL.7030 | 40827621 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662522 | Q2 | T2 EI HAT CRK #1-WESTWD 8/169 RPL STRW | 31514964 | HAT CREEK #1-WESTWOOD | 008/169 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.409808 | 40.8687 | ETL.7030 | 40759141 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662563 | Q2 | T2 EI HAT CREEK #1-WESTWD 41/792 RPL POL | 31514137 | HAT CREEK #1-WESTWOOD | 041/792 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-24 | 2021-08-24 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.026985 | 40.5007 | ETL.7030 | 40809585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119662692 | Q2 | T3 EI FULTON-PUEBLO 28/137 RPR FOND | 44306536 | FULTON-PUEBLO | 028/137 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-02-24 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.499874 | 38.4944 | ETL.1600 | 40818546 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119663194 | Q2 | EI LOS BANOS-MIDWAY #2 45/190 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 045/190 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.529588 | 36.5358 | ETL.6010 | 40600326 | Guy Wire-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119663428 | Not Scheduled | T3NT DI MSSR FLT-GLD HL#1 17/150 RMV VEG |  | MISSOURI FLAT-GOLD HILL #1 | 017/150 | HNA | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-20 | 2022-08-20 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.864608 | 38.6718 | ETL.2660 | 40590100 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119663631 | Q2 | EI LS BANOS-MIDWAY #2 48/205 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 048/205 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.48831 | 36.5031 | ETL.6010 | 40753904 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119663738 | Q2 | T2 EI TRINITY-MAPLE CREEK 43/011 RPL STR | 31514143 | TRINITY-MAPLE CREEK | 043/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.69079 | 40.7403 | ETL.8170 | 40602088 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119663803 | Q2 | T3 EI MISRI FLT-GLD HL #1 18/156 RPL INS | 31504275 | MISSOURI FLAT-GOLD HILL #1 | 018/156 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-02-24 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.8838319 | 38.6662 | ETL.2660 | 40837036 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119663957 | Q2 | EI LOS BANOS-MIDWAY #2 49/206 BENT STEEL | 44507667 | LOS BANOS-MIDWAY #2 | 049/206 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.484632 | 36.4998 | ETL.6010 | 40812155 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119664153 | Not Scheduled | T3 CARIBOU-PALERMO 37/298 RPR CONDS |  | CARIBOU-PALERMO | :037/298 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-24 | 2021-02-24 | [7 empty] | TR3 | <15D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.485645 | 39.6868 | ETL.3190 | 40913193 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119664240 | Q2 | T3 EI FULTON-PUEBLO 29/139 RPR FOND | 44306536 | FULTON-PUEBLO | 029/139 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-02-24 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.505612 | 38.495 | ETL.1600 | 40863101 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119664328 | Q2 | EI LOS BANOS-MIDWAY #2 49/207 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 049/207 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.481304 | 36.4968 | ETL.6010 | 40811503 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119664335 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 7/89C RPL STRW | 31512078 | COLGATE-SMARTVILLE #2 | 007/089C | 70Y | E | 2020_(1a) PSPS |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.289378 | 39.2528 | ETL.6520 | 42562756 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119664516 | Q2 | DI SALINAS-LAURELES A17/376 RPR GYWW | 44391519 | SALINAS-LAURELES | A017/376 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | [5 empty] | South | WSIP | [6 empty] | '-121.856719 | 36.5835 | ETL.7930 | 40864621 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119665033 | Q3 | EI VACA-VCVL-JSN-N TWR 03/26 RMV VEGN |  | VACA-VACAVILLE-JAMESON-NTH TWR | 003/026 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-24 | 2021-08-24 |  |  | 2021-08-24 | 2021-07-20 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.981896 | 38.4049 | ETL.4100 | 40813732 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119665066 | Q2 | EI LOS BANOS-MIDWAY #2 46/196 RPL MEMBER | 44507667 | LOS BANOS-MIDWAY #2 | 046/196 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.512667 | 36.5232 | ETL.6010 | 40812154 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119665161 | Q2 | EI LOS BANOS-MIDWAY #2 50/210 RPR STRT | 44589059 | LOS BANOS-MIDWAY #2 | 050/210 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.472076 | 36.4886 | ETL.6010 | 40592930 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119665871 | Q2 | T2NT DI SBRT-STD OL SW S#1 7/44 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 007/044 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.233541 | 38.0003 | ETL.3800 | 40764274 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119666328 | Q4 | T3 EI MAPLE CREEK-HOOPA 14/4 RPR GYWW | 44453147 | MAPLE CREEK-HOOPA | 014/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.722601 | 40.9073 | ETL.7490 | 40752763 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119666362 | Q4 | T3 EI MAPLE CRK-HPA 14/4 INST JMP SPT IN | 44453147 | MAPLE CREEK-HOOPA | 014/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.722601 | 40.9073 | ETL.7490 | 40752763 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119666435 | Q2 | T2 DI SOBRNTE-STD OL S#1 7/42 RPR STRT |  | SOBRANTE-STANDARD OIL SW STA #2 | 007/042 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2021-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.230683 | 37.9967 | ETL.3800 | 40681223 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119666466 | Q2 | DI SALINAS-LAURELES 5/125 RPR SPLW | 44578873 | SALINAS-LAURELES | 005/125 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-21 | 2021-08-21 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | [5 empty] | South | WSIP | [6 empty] | '-121.688353 | 36.6256 | ETL.7930 | 40754654 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119666706 | Q4 | T3 EI MAPLE CREEK-HOOPA 23/6 INST JMP SP | 44453324 | MAPLE CREEK-HOOPA | 023/006 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.643741 | 40.9933 | ETL.7490 | 40828009 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119666937 | Not Scheduled | T2NT DI COLGATE-SMTVL #2 10/117 RMV BUTT | 44453373 | COLGATE-SMARTVILLE #2 | 010/117 | ICW | F | 2020_(1a) PSPS |  | 2020-08-20 | 2022-08-20 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.300744 | 39.2241 | ETL.6520 | 40618357 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119667416 | Mar | T2 VACA-VACAVILLE-JMSN-NTH 4/0 RPR FOND | 44501992 | VACA-VACAVILLE-JAMESON-NTH TWR | 004/033 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP |  |  |  | REJECT: Foreman submit wrong photos. Submission was intended for notification 120256575. |  |  | '-121.990481 | 38.396 | ETL.4100 | 40662930 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  | Reject |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119667565 | Q3 | T3NT DI DNNLLS-MI-WUK 006/008 RMV PL BUT | 44623597 | DONNELLS-CURTIS | 006/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-24 | 2022-08-24 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.086492 | 38.1702 | ETL.1400 | 44765230 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119667624 | Q3 | T3 DI DONNELLS-MI-WUK 006/008 RPR SPLW | 44623598 | DONNELLS-CURTIS | 006/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-02-24 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.086492 | 38.1702 | ETL.1400 | 44765231 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119667658 | Not Scheduled | T2 DI DRUM-SUMMIT #2 25/305L REPL POLE |  | DRUM-SUMMIT #2 | 025/305 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.366028 | 39.3102 | ETL.1450 | 44558954 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119667739 | Not Scheduled | DI DRUM-SUMMIT #2 025/305 RPL HRDD | 44449908 | DRUM-SUMMIT #2 | 025/305 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.366028 | 39.3102 | ETL.1450 | 44558954 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119667813 | Not Scheduled | T3 EI MSSR FLT-GLD HLL #1 19/1 RPR FOND | 44449646 | MISSOURI FLAT-GOLD HILL #1 | 019/160 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.900523 | 38.6629 | ETL.2660 | 40604663 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119667991 | Not Scheduled | T3 EI PARKWAY-MORAGA 19/106 RPR ACSS RD | 44627179 | PARKWAY-MORAGA | 019/106 | CHS | E | 2020_(3) On high spread structure |  | 2020-08-25 | 2021-02-25 | [7 empty] | TR3 | <15D | Central | WSIP | [6 empty] | '-122.216243 | 37.8861 | ETL.5930 | 40592029 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119668340 | Not Scheduled | EI T2 COLGATE-SMARTVILL #2 7/089B RPL PL | 31512078 | COLGATE-SMARTVILLE #2 | 007/089 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.289359 | 39.2528 | ETL.6520 | 42562755 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119668657 | Q2 | T3 EI SLY CREEK TAP 1/8 RPL SPLW | 44639815 | SLY CREEK TAP | 001/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.134066 | 39.5709 | ETL.4221 | 40885380 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119668720 | Q2 | EI LOS BANOS-GATES #1 047/200 RMV DEBRIS |  | LOS BANOS-GATES #1 | 047/200 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.502114 | 36.5145 | ETL.6000 | 40603209 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119668978 | Not Scheduled | VACA-VACAVIL-JMSN-NTH 6/050 RPR FOND | 44484178 | VACA-VACAVILLE-JAMESON-NTH TWR | 006/050 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.012517 | 38.3628 | ETL.4100 | 40589116 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119669006 | Q3 | VACA-VACAVIL-JMSN-NTH 6/050 RMV VEG |  | VACA-VACAVILLE-JAMESON-NTH TWR | 006/050 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2021-08-25 |  |  | 2021-08-24 | 2021-07-20 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.012517 | 38.3628 | ETL.4100 | 40589116 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119669761 | Q2 | EI GARBERVILLE-LAYTONVILLE 33/1 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 033/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.556241 | 39.8132 | ETL.8365 | 40600475 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119669786 | Q3 | T2 DI BRDGEVLLE-COTTNWD 68/490 RPR WDPK | 44404493 | BRIDGEVILLE-COTTONWOOD | 068/490 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.477823 | 40.4396 | ETL.1110 | 44423213 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119670069 | Q2 | EI GARBERVILLE-LAYTONVLL 34/0 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 034/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.565259 | 39.8247 | ETL.8365 | 40587735 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119670176 | Q2 | EI GARBERVILLE-LAYTONVILLE 34/1 RPL STRW | 31515741 | GARBERVILLE-LAYTONVILLE | 034/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.566189 | 39.8252 | ETL.8365 | 40584848 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119670275 | Q2 | EI GARBERVILLE-LAYTONVILLE 34/4 RPR JUMP | 44476763 | GARBERVILLE-LAYTONVILLE | 034/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570625 | 39.8278 | ETL.8365 | 40761558 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119670446 | Q2 | T2 DI BRDGVILLE-CTTONWD 15/139 RPL XARM |  | BRIDGEVILLE-COTTONWOOD | 015/139 |  | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.555091 | 40.3883 | ETL.1110 | 40686739 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade |  | Q2 |  |  | 2020-12-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119670481 | Q2 | EI LOS BANOS-GATES #1 45/191 RPR GYWT |  | LOS BANOS-GATES #1 | 045/191 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.52568 | 36.5326 | ETL.6000 | 40593675 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119671998 | Mar | T2 EI CORTINA-MNDCNO #1 35/170 RPR STRT |  | CORTINA-MENDOCINO #1 | 035/170 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.796553 | 39.1051 | ETL.1330 | 40587897 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119672310 | Q4 | T3 DI DRUM-RIO OSO #1 0/3 RPR SPLW | 44453164 | DRUM-RIO OSO #1 | 000/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [8 empty] | ETL.1420 | 44337048 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119672961 | Not Scheduled | T2 DI PHILO JCT-ELK 025/004 RPR SPLW | 44610684 | PHILO JCT-ELK | 025/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.53269 | 39.0835 | ETL.7780 | 40769176 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119673497 | Q2 | EI LOS BANOS-GATES #1 50/209 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 050/209 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.4757 | 36.4912 | ETL.6000 | 40872601 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119674591 | Mar | T2NT EI CORTNA-MNDCNO #1 48/236 RPR FOND |  | CORTINA-MENDOCINO #1 | 048/236 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2022-08-26 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.981973 | 39.2032 | ETL.1330 | 40808939 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675149 | Q2 | EI LOS BANOS-GATES #1 50/212 BENT STEEL | 44490735 | LOS BANOS-GATES #1 | 050/212 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.466135 | 36.4826 | ETL.6000 | 40676079 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119675191 | Not Scheduled | GATES-PANOCHE #1 25/119 RMV DEBRIS | 44507620 | GATES-PANOCHE #1 | 025/119 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-23 | 2022-07-23 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.38455 | 36.4348 | ETL.4720 | 40863298 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119675224 | Q2 | EI LOS BANOS-GATES #1 52/219 RPL RPTS | 44571722 | LOS BANOS-GATES #1 | 052/219 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-15 | 2021-02-16 |  |  | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.448409 | 36.4646 | ETL.6000 | 40866818 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 593 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119675370 | Not Scheduled | T2 EI VACA-VCVL-JMN-N TWR 10/74 RPR FOND | 44461632 | VACA-VACAVILLE-JAMESON-NTH TWR | 010/074 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.046852 | 38.3164 | ETL.4100 | 40752810 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675372 | Not Scheduled | T3 EI MONTE RIO-FORT ROSS 19/4 RPL SPLW |  | ETL.6979.POLE.WOOD | 019/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.086718 | 38.4826 | ETL.6979 | 40770580 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675373 | Not Scheduled | T3 EI MONTE RIO-FORT ROSS 20/0A RPL POLE | 31437439 | ETL.6979.POLE.WOOD | 020/000A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.09475 | 38.4843 | ETL.6979 | 40575977 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675374 | Not Scheduled | T3 EI MONTE RIO-FORT ROSS 19/6 SOIL |  | ETL.6979.POLE.NWOD | 019/006 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.088836 | 38.483 | ETL.6979 | 44917321 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675431 | Not Scheduled | T2 EI VAC-VCVL-JMN-NT TWR 10/76 RPL FOND | 44501992 | VACA-VACAVILLE-JAMESON-NTH TWR | 010/076 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.049924 | 38.3114 | ETL.4100 | 40812936 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675767 | Q2 | EI LOS BANOS-GATES #1 52/220 RPR FOND | 44490735 | LOS BANOS-GATES #1 | 052/220 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.44715 | 36.4633 | ETL.6000 | 40598410 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119675958 | Q2 | T3 EI WEIMAR #1 - 60 kV_006/086 RPL STRW | 31511049 | WEIMAR #1 | 006/086 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-02-26 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.892168 | 39.0189 | ETL.7560 | 40869854 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119675968 | Q2 | EI LOS BANOS-GATES #1 53/224A RPR GYWS |  | LOS BANOS-GATES #1 | 053/224A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.435958 | 36.4511 | ETL.6000 | 40576724 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y -22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119676367 | Mar | EI NEWARK-JARVIS #1 010/065 RMV BIRDHSE |  | NEWARK-JARVIS #1 | 010/065 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-26 | 2022-08-26 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.964475 | 37.5888 | ETL.3020 | 40745980 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119676380 | Mar | EI NEWARK-JARVIS #1 011/069 RPR FOND |  | NEWARK-JARVIS #1 | 011/069 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-03-20 | 2021-03-15 | [5 empty] | Central | WSIP | [6 empty] | '-121.975661 | 37.5924 | ETL.3020 | 40871964 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119676391 | Mar | EI NEWARK-JARVIS #1 011/066 RMV BRDHSE |  | NEWARK-JARVIS #1 | 011/066 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-26 | 2022-08-26 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.967706 | 37.5895 | ETL.3020 | 40804743 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119676398 | Not Scheduled | T2 EI SALT SPGS-TGR CRK 06/54 BENT MEMB | 44631415 | SALT SPRINGS-TIGER CREEK | 006/054 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.326099 | 38.477 | ETL.3500 | 40744667 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119676494 | Q2 | T2 EI SALT SPRINGS-TGR CRK 8/71 RPR FOND | 44631415 | SALT SPRINGS-TIGER CREEK | 008/071 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.369556 | 38.4825 | ETL.3500 | 40580454 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119676496 | Q2 | T3 EI WEIMAR #1 9/134 RPL POLE | 31517852 | WEIMAR #1 | 009/134 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.83859 | 39.0205 | ETL.7560 | 40913141 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119676497 | Q2 | T3 EI WEIMAR #1 9/135 REFRAME | 31506503 | WEIMAR #1 | 009/135 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.83755 | 39.0204 | ETL.7560 | 40913140 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677273 | Mar | EI POTTER VALLEY-WILLITS 7/1 RPR INSW | 44610689 | POTTER VALLEY-WILLITS | 007/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.2426689 | 39.3819 | ETL.7820 | 44149280 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677276 | Q2 | T2 EI IGNACIO-BOLINAS #2 11/134 RRP GYWS | 44640735 | IGNACIO-BOLINAS #2 | 011/134 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.68944 | 38.0932 | ETL.7180 | 44916325 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677278 | Q2 | T2 EI IGNACIO-BOLINAS #2 11/138 RPL ANCH | 31512611 | IGNACIO-BOLINAS #2 | 011/138 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-24 | 2021-08-24 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.692276 | 38.0904 | ETL.7180 | 40751195 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677281 | Mar | T3 EI POTTER VALLEY-WILLITS 10/7 RPL POL | 31512496 | POTTER VALLEY-WILLITS | 010/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 |  |  | 2021-03-11 | 2021-03-08 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.300017 | 39.3856 | ETL.7820 | 40824417 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-29 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677560 | Mar | T2 EI CORTINA-MNDCNO #1 56/277 RPR FOND |  | CORTINA-MENDOCINO #1 | 056/277 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.12171 | 39.2311 | ETL.1330 | 40808541 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677568 | Mar | T2 EI CORTINA-MNDCNO #1 59/289 MASTIC |  | CORTINA-MENDOCINO #1 | 059/289 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2022-08-26 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.174529 | 39.2398 | ETL.1330 | 40860995 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677569 | Mar | T2 EI CORTINA-MNDCNO #1 56/279 RPR FOND |  | CORTINA-MENDOCINO #1 | 056/279 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.12869 | 39.2329 | ETL.1330 | 40870095 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677823 | Q2 | T2 DI BRDGVL-CTTNWD 24/215 RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 024/215 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.733192 | 40.3714 | ETL.1110 | 44424490 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677825 | Q2 | T2 DI BRDGVL-CTTNWD 24/215 REPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 024/215 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.733192 | 40.3714 | ETL.1110 | 44424491 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677908 | Q3 | T2 DI BRIDGEVILLE-COTTON 63/455 RPR OPGW | 44431445 | BRIDGEVILLE-COTTONWOOD | 063/455 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.414395 | 40.3894 | ETL.1110 | 40586447 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677937 | Q2 | T2 DI SOBRANTE-STD OIL#1 6/36 RPLC INSS |  | SOBRANTE-STANDARD OIL SW STA #2 | 006/036 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-05-04 | 2021-05-04 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.219804 | 37.9834 | ETL.3800 | 40848555 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677943 | Q2 | T2 DI PHILO JCT-ELK 6/0 RPL INSW | 31514497 | PHILO JCT-ELK | 006/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.237276 | 39.0602 | ETL.7780 | 40640252 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677963 | Q2 | T2 DI SOBRANTE-STD OIL#1 6/36N RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 006/036 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2022-08-26 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.220317 | 37.9835 | ETL.3800 | 40819977 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677971 | Q2 | T2 DI SOBRNT-STN OIL SW #1 1/12 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 001/012 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.207758 | 37.9305 | ETL.3800 | 40646594 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119677978 | Q2 | T2 DI BRIDGEVILL-COTTON 48/369 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 048/369 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.162329 | 40.4135 | ETL.1110 | 40683976 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678312 | Q4 | T3 DI MDDL FRK-GLD HLL 13/108 RPL POLE | 31516281 | MIDDLE FORK-GOLD HILL | 013/108 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.803694 | 38.9551 | ETL.5140 | 44553723 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678318 | Q4 | T3 DI MDDL FRK-GLD HLL 13/108 RPL POLE | 31516281 | MIDDLE FORK-GOLD HILL | 013/108 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.803694 | 38.9551 | ETL.5140 | 44553722 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678380 | Q2 | T2 DI PHILO JCT-ELK 3/0 RPL PL | 31515022 | PHILO JCT-ELK | 003/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.20586 | 39.0954 | ETL.7780 | 40614240 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678427 | Q2 | T3 EI WEIMAR #1 8/127 REFRAME | 31512498 | WEIMAR #1 | 008/127 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.84635 | 39.0201 | ETL.7560 | 40598730 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678565 | Q3 | T3 DONNELLS-MI-WUK 9/4 RPR STRW | 31513657 | DONNELLS-CURTIS | 009/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.112242 | 38.1452 | ETL.1400 | 40744843 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678640 | Q2 | EI LOS BANOS-GATES #1 55/232 BENT MEMB | 44490735 | LOS BANOS-GATES #1 | 055/232 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.419838 | 36.4332 | ETL.6000 | 40680413 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119678800 | Q2 | EI LOS BANOS-MIDWAY #2 51/217 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 051/217 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.454981 | 36.4719 | ETL.6010 | 40811505 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119678814 | Q2 | T2 DI BRIDGEVILLE-COTTON 19/174 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 019/174 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.622992 | 40.3792 | ETL.1110 | 44423382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678879 | Q3 | T3NT EI DONNELLS-CURTIS 09/05 RMV BUTT | 44623620 | DONNELLS-CURTIS | 009/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-27 | 2022-08-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.1125073 | 38.1447 | ETL.1400 | 44774095 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678894 | Q2 | T2 DI BRIDGEVILLE-COTTON 21/186 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 021/186 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.661707 | 40.3765 | ETL.1110 | 44515777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119678909 | Feb | T3 EI DRUM-RIO OSO #1 7/79 RPR SPLS | 44453044 | DRUM-RIO OSO #1 | 007/079 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-02-27 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8765625 | 39.1934 | ETL.1420 | 40888171 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679026 | Mar | T3DI MONTA VIST-COYOTE SW 13/70 RPR SHLD | 31519995 | MONTA VISTA-COYOTE SW STA | 013/070 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-02-26 |  |  | 2021-03-03 | 2021-03-03 |  |  | Check FDA | TR3 | SCHD | South | WSIP | [6 empty] | '-121.962108 | 37.1932 | ETL.5090 | 40582103 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679116 | Mar | T3 EI DRUM-RIO OSO #1 7/82 RPL ANCHS |  | DRUM-RIO OSO #1 | 007/082 |  | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.879056 | 39.1915 | ETL.1420 | 40670134 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade |  | Mar |  |  | 2021-01-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679194 | Not Scheduled | T3 DI CARIBOU-TABLE MTN 38/280 MASTIC |  | CARIBOU-TABLE MTN | 038/280 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-24 | 2022-08-24 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.483791 | 39.7696 | ETL.4440 | 40604591 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679263 | Q2 | EI LOS BANOS-MIDWAY #2 52/218 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 052/218 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.451609 | 36.4685 | ETL.6010 | 40863980 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119679360 | Not Scheduled | T3 DI DRUM-SUMMIT #1 0/4 RMV PL BUTT | 44453260 | DRUM-SUMMIT #1 | 000/004 | DEA | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763455 | 39.255 | ETL.1440 | 44764262 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC ObjC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | DEA | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679369 | Not Scheduled | T3 DI DRUM-SUMMIT #1 0/4 RPL INSW | 31521959 | DRUM-SUMMIT #1 | 000/004 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-02-25 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763471 | 39.255 | ETL.1440 | 40786933 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679442 | Q2 | T2 T3 DI BRDGVILL-CTTNWD 24/209 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 024/209 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.717554 | 40.3725 | ETL.1110 | 44423391 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679460 | Q2 | T2 T3 DI BRDGVILL-CTTNWD 24/209 RPR WDPK | 44404807 | BRIDGEVILLE-COTTONWOOD | 024/209 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.717554 | 40.3725 | ETL.1110 | 44423391 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679461 | Q2 | T2 DI BRIDGEVILLE-COTTN 35/281 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 035/281 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.923219 | 40.3684 | ETL.1110 | 44423329 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679592 | Q2 | EI LOS BANOS-MIDWAY #2 52/220 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 052/220 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.446702 | 36.4635 | ETL.6010 | 40592933 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119679614 | Q2 | EI LOS BANOS-GATES #1 56/239 BENT MEMB | 44490735 | LOS BANOS-GATES #1 | 056/239 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.402562 | 36.4141 | ETL.6000 | 40866822 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119679698 | Q2 | EI LOS BANOS-GATES #1 057/240 RPR STRS | 44509125 | LOS BANOS-GATES #1 | 056/240 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.39947 | 36.4107 | ETL.6000 | 40605323 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119679699 | Q2 | EI LOS BANOS-GATES #1 57/240 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 056/240 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.39947 | 36.4107 | ETL.6000 | 40605323 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119679808 | Not Scheduled | T3 DI FULTON-HOPLAND 20/3 RPL POLE | 31512495 | FULTON-HOPLAND | 020/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.9035 | 38.7399 | ETL.6890 | 40667690 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119679891 | Q2 | T2 DI BRDGVL-CTTNWD 22/200 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 022/200 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.696021 | 40.374 | ETL.1110 | 44515786 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119680009 | Q2 | T2 DI BRDGVL-CTTNWD 29/250 RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 029/250 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.826345 | 40.3648 | ETL.1110 | 44561187 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119680039 | Q2 | T2 DI BRDGVLL-COTTNWD 36/293 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 036/293 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.957508 | 40.367 | ETL.1110 | 44424083 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119680052 | Q2 | T2 DI BRDGVLL-COTTNWD 36/293 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 036/293 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.957508 | 40.367 | ETL.1110 | 44424082 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119680254 | Q2 | EI LOS BANOS-MIDWAY #2 52/221 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 052/221 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.445276 | 36.462 | ETL.6010 | 40597461 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119680466 | Q2 | EI LOS BANOS-MIDWAY #2 52/222 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 052/222 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.442574 | 36.459 | ETL.6010 | 40664804 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119680514 | Not Scheduled | T3NT MONTE RIO-FORT ROSS 17/002 RPR ROAD | 44651223 | ETL.6979.POLE.WDPS | 017/002 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-27 | 2022-08-27 |  |  |  | 2022-04-01 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.054452 | 38.4784 | ETL.6979 | 44232821 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119680593 | Q2 | EI LOS BANOS-MIDWAY #2 53/223 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 053/223 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.440353 | 36.4565 | ETL.6010 | 40662871 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119680595 | Q2 | EI LOS BANOS-MIDWAY #2 53/223 RPR FOUND | 44490736 | LOS BANOS-MIDWAY #2 | 053/223 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.440353 | 36.4565 | ETL.6010 | 40662871 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119680692 | Q2 | EI LOS BANOS-GATES #1 058/246 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 058/246 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.383196 | 36.3934 | ETL.6000 | 40815950 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119680784 | Q2 | T2NT DI SBRNT-STAN OIL S#1 5/33 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 005/033 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-20 | 2022-08-20 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.215459 | 37.9775 | ETL.3800 | 40650623 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119680834 | Not Scheduled | T3 MONTE RIO-FORT ROSS 17/2 RPR SPLCW |  | ETL.6979.INSL.NCER | 017/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-02-27 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.0544522 | 38.4784 | ETL.6979 | 44232831 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681486 | Q2 | T3 DI SNTH LN-HLF MN BY ?4/2 RPL POLE | 31513802 | SNEATH LANE-HALF MOON BAY | ?004/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.473858 | 37.5509 | ETL.7212 | 44264950 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681488 | Q2 | T3 DI SNEATH LN-HLF MN BY ?4/2L RPL POLE | 31513802 | SNEATH LANE-HALF MOON BAY | ?004/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.473858 | 37.5509 | ETL.7212 | 44264952 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681527 | Q2 | EI LOS BANOS-MIDWAY #2 53/224 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 053/224 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.43774 | 36.4536 | ETL.6010 | 40753978 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119681529 | Not Scheduled | EI LOS BANOS-MIDWAY #2 53/224 PAINT STRT | 44490737 | LOS BANOS-MIDWAY #2 | 053/224 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2022-08-27 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.43774 | 36.4536 | ETL.6010 | 40753978 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119681559 | Q2 | EI LOS BANOS-GATES #1 058/247 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 058/247 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.380548 | 36.3908 | ETL.6000 | 40815044 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119681589 | Q2 | T3 WEIMAR #1 5/80 RPR GYWW | 44453242 | WEIMAR #1 | 005/080 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-02-27 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.899512 | 39.0191 | ETL.7560 | 44923840 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681630 | Mar | T2 DI KONOCTI MIDDLETOWN 13/007 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 013/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.586643 | 38.77 | ETL.6380 | 40810249 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681724 | Not Scheduled | EI LOS BANOS-MIDWAY #2 53/226 PAINT STRT | 44490737 | LOS BANOS-MIDWAY #2 | 053/226 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2022-08-27 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.434125 | 36.4497 | ETL.6010 | 40817173 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119681725 | Q2 | EI LOS BANOS-MIDWAY #2 53/226 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 053/226 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.434125 | 36.4497 | ETL.6010 | 40817173 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119681792 | Feb | T2 DI PHILO JCT-ELK 036/001 RPR GYWW | 44610684 | PHILO JCT-ELK | 036/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.700527 | 39.1405 | ETL.7780 | 40600299 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681828 | Mar | T2 EI CORTINA-MNDCNO #1 53/264 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 053/264 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-08-27 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.077963 | 39.217 | ETL.1330 | 40765734 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681884 | Q2 | DI HMBLDT-BRIDGEVILLE 108/1 RPL INSW | 31515021 | HUMBOLDT-BRIDGEVILLE | 108/001 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.973705 | 40.7487 | ETL.1810 | 40616447 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119681965 | Q2 | T2 DI BRDGVLLE-CTTNWD 053/399 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 053/399 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.252069 | 40.3967 | ETL.1110 | 42603492 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682047 | Q2 | T2 DI BRDGVL-CTTNWD 28/237 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 028/237 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.7946 | 40.367 | ETL.1110 | 44561125 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682066 | Q2 | EI LOS BANOS-GATES #1 059/250 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 059/250 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.371625 | 36.3828 | ETL.6000 | 40605325 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119682115 | Q2 | T2NT DI SNT-STD OIL SW S#1 1/13 RPR FOND | 44624392 | SOBRANTE-STANDARD OIL SW STA #2 | 001/013 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-25 | 2022-08-25 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.206239 | 37.9322 | ETL.3800 | 40644451 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682126 | Q2 | EI LOS BANOS-MIDWAY #2 54/228 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 054/228 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.429775 | 36.4449 | ETL.6010 | 40863981 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119682133 | Q2 | T2 DI BRDGVL-CTTNWD 24/211 RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 024/211 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.721722 | 40.3722 | ETL.1110 | 44423860 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682139 | Q2 | T2 DI BRDGVL-CTTNWD 24/211 RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 024/211 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.721722 | 40.3722 | ETL.1110 | 44423861 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682186 | Q2 | T2 DI PHILO JCT-ELK 009/008 RPR STRW | 44610684 | PHILO JCT-ELK | 009/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.289445 | 39.0274 | ETL.7780 | 40871798 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682220 | Q2 | T3 EI WEIMAR #1 9/149 INST JMPRW | 44453242 | WEIMAR #1 | 009/149 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.8275997 | 39.0182 | ETL.7560 | 40731300 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682228 | Feb | T2 DI PHILO JCT-ELK 036/004 RPR INSW | 44610684 | PHILO JCT-ELK | 036/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.705379 | 39.1388 | ETL.7780 | 40800731 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682251 | Q4 | T3T DI MIDDLE FORK-GOLD HLL 0/4 RMV STEP | 44452455 | MIDDLE FORK-GOLD HILL | 000/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.598018 | 39.0204 | ETL.5140 | 44416130 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682253 | Q2 | T2 DI BRIDGEVLLE-CTTNWD 34/276 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 034/276 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.909368 | 40.3668 | ETL.1110 | 44423285 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682268 | Q2 | T2 DI TRINITY-MAPLE CREEK 50/8 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 050/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.812309 | 40.7617 | ETL.8170 | 44752428 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682333 | Feb | T2 DI PHILO JCT-ELK 036/004 RPR GYWW | 44610684 | PHILO JCT-ELK | 036/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.705723 | 39.1382 | ETL.7780 | 40769166 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682340 | Q2 | T2 DI TRINITY-MAPLE CREEK 50/8 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 050/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.812309 | 40.7617 | ETL.8170 | 44752429 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682342 | Q2 | T2 DI TRINITY-MAPLE CREEK 50/8 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 050/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.812309 | 40.7617 | ETL.8170 | 44752436 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682343 | Q2 | T2 DI TRINITY-MAPLE CREEK 50/8 RPR INSW | 44484765 | TRINITY-MAPLE CREEK | 050/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.812309 | 40.7617 | ETL.8170 | 40884791 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682380 | Q4 | T3 EI DRUM-RIO OSO #1 8/88 RPR INSULS | 44453044 | DRUM-RIO OSO #1 | 008/088 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.8890749 | 39.1876 | ETL.1420 | 44337143 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682394 | Q2 | EI LOS BANOS-MIDWAY #2 54/229 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 054/229 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.426981 | 36.4418 | ETL.6010 | 40869310 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119682405 | Q2 | EI LOS BANOS-MIDWAY #2 54/230 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 054/230 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.424793 | 36.4394 | ETL.6010 | 40600329 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119682616 | Q2 | T2 DI BRIDGEVILLE-COTTNWD 10/92 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 010/092 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.454437 | 40.389 | ETL.1110 | 40636959 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682779 | Q2 | T2 DI BRIDGEVILLE-CTTNWD 28/236 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 028/236 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.791976 | 40.3672 | ETL.1110 | 40638338 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682815 | Q2 | T2 SALT SPRINGS-TGR CRK 06/56 BENT MEMB | 44631415 | SALT SPRINGS-TIGER CREEK | 006/056 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.329249 | 38.4767 | ETL.3500 | 40822479 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682836 | Q2 | T2 SALT SPRINGS-TGR CRK 06/57 BENT MEMB | 44631415 | SALT SPRINGS-TIGER CREEK | 006/057 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.330562 | 38.4766 | ETL.3500 | 40820781 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682879 | Q2 | T2T DI BRIDGEVLLE-CTTNWD 8/79R RPR INSW | 44404807 | BRIDGEVILLE-COTTONWOOD | 008/079 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.42671 | 40.3891 | ETL.1110 | 40788539 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682891 | Q2 | T2 DI BRIDGEVLL-CTTNWD 8/79L RPR XBRACE | 44404807 | BRIDGEVILLE-COTTONWOOD | 008/079 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.42671 | 40.3891 | ETL.1110 | 44424021 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682893 | Q2 | T2 DI BRIDGEVILLE-CTTNWD 8/79L RPR WPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 008/079 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.42671 | 40.3891 | ETL.1110 | 44424021 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119682909 | Q2 | EI LOS BANOS-GATES #1 060/255 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 060/255 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.355786 | 36.3688 | ETL.6000 | 40762441 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119682922 | Q2 | EI LOS BANOS-GATES #1 060/255 RPL HRDT | 44490735 | LOS BANOS-GATES #1 | 060/255 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.355786 | 36.3688 | ETL.6000 | 40762441 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119683010 | Not Scheduled | T2 VACA-VACAVILLE-JMSN 11/82 BENT MEMBR | 44452913 | VACA-VACAVILLE-JAMESON-NTH TWR | 011/082 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.058752 | 38.2971 | ETL.4100 | 40650935 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119684352 | Not Scheduled | T2 DI COLGATE-SMRTVILL #2 8/90C CANCEL | 44466987 | COLGATE-SMARTVILLE #2 | 008/090C | ICW | E | 2020_(1a) PSPS |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.290838 | 39.2497 | ETL.6520 | 42562758 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119685160 | Not Scheduled | T3 DI DRUM-SUMMIT #1 0/5 INST MRKS | 44453047 | DRUM-SUMMIT #1 | 000/005 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.762619 | 39.2549 | ETL.1440 | 44337852 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119685163 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 7/87 RMV DEBRIS | 44487749 | DRUM-SUMMIT #2 | 007/087 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.660716 | 39.3117 | ETL.1450 | 44552565 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685166 | Not Scheduled | T3 DI DRUM-SUMMIT #1 0/2 RMV PL BUTT | 44453360 | DRUM-SUMMIT #1 | 000/002 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162080 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119685402 | Q2 | T2 DI BRDGVL-CTTNWD 11/104 RMV PL BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/104 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.478934 | 40.389 | ETL.1110 | 44423877 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685406 | Not Scheduled | T3 FRENCH MEADOWS-MIDDLE FORK 3/73 STUB | 44453006 | FRENCH MEADOWS-MIDDLE FORK | 003/073 | GAR | E | 2020_(2) High fire spread TD |  | 2020-07-14 | 2021-01-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.458412 | 39.045 | ETL.6870 | 40767454 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685460 | Not Scheduled | T3 FRENCH MEADOWS-MIDDLE FRK 5/110 STUB | 44453006 | FRENCH MEADOWS-MIDDLE FORK | 005/110 | GAR | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-01-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.495563 | 39.0372 | ETL.6870 | 40824471 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685466 | Not Scheduled | T3 FRENCH MEADOWS-MIDDLE FRK 6/128 STUB | 44453006 | FRENCH MEADOWS-MIDDLE FORK | 006/128 | GAR | E | 2020_(2) High fire spread TD |  | 2020-07-16 | 2021-01-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.51126 | 39.0308 | ETL.6870 | 40826821 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685485 | Q2 | EI LOS BANOS-MIDWAY #2 55/232 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 055/232 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.419466 | 36.4335 | ETL.6010 | 40664808 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119685609 | Q2 | T3 DI SNTH LN-HLF MN BY ?2/0 INST HRDW | 44621668 | SNEATH LANE-HALF MOON BAY | ?002/000 | ICW | E | 2020_(3) On high spread structure |  | 2020-08-25 | 2021-02-25 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.500651 | 37.5729 | ETL.7212 | 44810096 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685793 | Q2 | T2 DI BRDGVL-CTTNWD 45/353C RMV NEST | 44398374 | BRIDGEVILLE-COTTONWOOD | 045/353C | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.108201 | 40.3967 | ETL.1110 | 42603429 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685795 | Not Scheduled | T2 DI BRDGVL-CTTNWD 45/353C RPR FOND |  | BRIDGEVILLE-COTTONWOOD | 045/353C | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.108201 | 40.3967 | ETL.1110 | 42603429 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685808 | Q2 | EI LOS BANOS-MIDWAY #2 55/235 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 055/235 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.412794 | 36.4261 | ETL.6010 | 40753908 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119685827 | Q2 | T2 DI BRIDGEVILLE-COTTNWD 4/39 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 004/039 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.34564 | 40.3908 | ETL.1110 | 44423907 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685854 | Q2 | T2 DI BRIDGEVILLE-CTTNWD 4/39 RMV PL BUT | 44404807 | BRIDGEVILLE-COTTONWOOD | 004/039 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.34564 | 40.3908 | ETL.1110 | 44423907 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119685922 | Not Scheduled | T2 DI DRUM-SUMMIT #1 25/298 RPR WDPKR |  | DRUM-SUMMIT #1 | 025/298 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.356938 | 39.3094 | ETL.1440 | 44762529 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119685924 | Q2 | T2 DI BRDGVL-CTTNWD 48/370 RPLC INSS | 31512268 | BRIDGEVILLE-COTTONWOOD | 048/370 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.163835 | 40.4141 | ETL.1110 | 40686782 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119686000 | Q2 | EI LOS BANOS-MIDWAY #2 55/234 BENT STL | 44490736 | LOS BANOS-MIDWAY #2 | 055/234 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.415306 | 36.4289 | ETL.6010 | 40759253 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119686001 | Q2 | EI LOS BANOS-MIDWAY #2 55/234 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 055/234 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.415306 | 36.4289 | ETL.6010 | 40759253 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119686798 | Q2 | EI LOS BANOS-MIDWAY #2 56/239 INST HRDT | 44490736 | LOS BANOS-MIDWAY #2 | 056/239 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.402158 | 36.4144 | ETL.6010 | 40863659 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119686888 | Q2 | T3 EI WEIMAR #1 10/157 REPLUMB INSU | 44453242 | WEIMAR #1 | 010/157 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.813796 | 39.0139 | ETL.7560 | 40759968 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119686934 | Q2 | T3 EI WEIMAR #1 10/157 RMV DEBRIS | 44453443 | WEIMAR #1 | 010/157 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-28 | 2022-08-28 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.813796 | 39.0139 | ETL.7560 | 40759968 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687014 | Q2 | T2 DI BRIDGVLLE-CTTNWD 21/187 RPL INSS | 31512268 | BRIDGEVILLE-COTTONWOOD | 021/187 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.667093 | 40.376 | ETL.1110 | 40610992 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687017 | Q2 | T2 EI ELK-GUALALA 44/003 RPL STRW | 31515080 | ELK-GUALALA | 044/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.681472 | 39.0345 | ETL.8410 | 40660601 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687152 | Q2 | EI LOS BANOS-MIDWAY #2 57/240 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 057/240 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.399141 | 36.4111 | ETL.6010 | 40592936 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119687171 | Q2 | T2 DI BRIDGVLLE-CTTNWD 023/202 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 023/202 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.701304 | 40.3737 | ETL.1110 | 44515790 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687177 | Feb | T2NT DI CLGT-GRSS VLLY 00/03B RMV DEBRIS | 44477156 | COLGATE-GRASS VALLEY | 000/003B | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.188488 | 39.3294 | ETL.6490 | 44190861 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687220 | Q2 | T2NT DI BRDGVL-CTTNWD 48/371 RPR FOND | 44634173 | BRIDGEVILLE-COTTONWOOD | 048/371 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-27 | 2022-08-27 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.166569 | 40.4151 | ETL.1110 | 40761789 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687225 | Q2 | T2 DI BRDGVL-CTTNWD 5/46 RPR SHLW | 44404807 | BRIDGEVILLE-COTTONWOOD | 005/046 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.359665 | 40.3909 | ETL.1110 | 44899403 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687461 | Q2 | EI LOS BANOS-MIDWAY #2 57/241 BENT STL |  | LOS BANOS-MIDWAY #2 | 057/241 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.396286 | 36.4079 | ETL.6010 | 40594799 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119687943 | Q2 | T2NT DI SBNT-STD OL SW S#1 5/32 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 005/032 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2022-08-26 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.213711 | 37.9753 | ETL.3800 | 40681869 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119687948 | Q2 | T2 DI SBNT-STD OIL SW ST#1 5/32 RPL INSS |  | SOBRANTE-STANDARD OIL SW STA #2 | 005/032 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-05-04 | 2021-05-04 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.213241 | 37.9753 | ETL.3800 | 40724769 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688011 | Q2 | T2 DI EXCHEQUER-YOSEMITE 1/11 BENT STL | 44490739 | EXCHEQUER-YOSEMITE | 001/011 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.246406 | 37.5757 | ETL.8650 | 40582615 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688015 | Not Scheduled | T2 DI EXCHEQUER-YOSEMITE 1/11 PNT STRS | 44507635 | EXCHEQUER-YOSEMITE | 001/011 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.246406 | 37.5757 | ETL.8650 | 40582615 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688100 | Q2 | T3 EI WEIMAR #1 11/167 RPR WDPKR | 44453242 | WEIMAR #1 | 011/167 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.797492 | 39.0126 | ETL.7560 | 40677911 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688192 | Feb | EI LYTNVIL-CVL 07/08 INST MRKW |  | LAYTONVILLE-COVELO | 007/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-28 | 2022-08-28 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.347337 | 39.7136 | ETL.7390 | 40876447 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688197 | Feb | EI LYTNVILLE-COVELO 7/10 RPL PL | 31515081 | LAYTONVILLE-COVELO | 007/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 |  |  | 2021-02-24 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.345713 | 39.7154 | ETL.7390 | 40614484 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688228 | Q2 | EI LOS BANOS-GATES #1 62/260 BENT MEMB | 44490735 | LOS BANOS-GATES #1 | 062/260 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.339597 | 36.354 | ETL.6000 | 40598404 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119688334 | Q2 | T2 DI BRIDGEVILLE-COTTON 22/194 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 022/194 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.682713 | 40.375 | ETL.1110 | 40721721 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688337 | Not Scheduled | T2 DI DRUM-SUMMIT #1 19/223 REMV DEBRIS | 44487748 | DRUM-SUMMIT #1 | 019/223 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.464007 | 39.3191 | ETL.1440 | 40756919 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688339 | Not Scheduled | T2 DI DRUM-SUMMIT #1 19/223 RPL ANCW | 44487747 | DRUM-SUMMIT #1 | 019/223 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.464007 | 39.3191 | ETL.1440 | 44768922 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119688353 | Q2 | EI LOS BANOS-MIDWAY #2 58/247 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 058/247 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.38016 | 36.391 | ETL.6010 | 40818984 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119688440 | Not Scheduled | T2 DI DRUM-SUMMIT #1 19/223 RPR WKPKR | 44645317 | DRUM-SUMMIT #1 | 019/223 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.464007 | 39.3191 | ETL.1440 | 44768922 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119689562 | Q3 | EI BRIDGEVILLE-CTTNWD 82/575 INS MRKS | 44477511 | BRIDGEVILLE-COTTONWOOD | 082/575 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7080914 | 40.478 | ETL.1110 | 44425587 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119691404 | Feb | EI LAYTONVILLE-COVELO 8/011 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 008/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.331813 | 39.7257 | ETL.7390 | 40600467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | ReleasedSpecial-Cond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119692689 | Mar | T3T DI POE-RIO OSO 19/129 RPL HRDS |  | POE-RIO OSO | 019/129 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.481635 | 39.716 | ETL.5540 | 40866272 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119692812 | Not Scheduled | T3T DI CARIBOU-TABLE MTN 39/287 BENT STL |  | CARIBOU-TABLE MTN | 039/287 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-121.490053 | 39.7582 | ETL.4440 | 40821420 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119692817 | Mar | T3 DI DEER CREEK-DRUM 3/94 RPL INSW | 31512744 | DEER CREEK-DRUM | 003/094 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.804343 | 39.2602 | ETL.6690 | 40888969 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119692960 | Q3 | EI MIDWAY-WHIRLWIND 16/070 RMV VEG |  | MIDWAY-WHIRLWIND | 016/070 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 |  |  | 2021-08-15 | 2021-08-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.20128 | 35.3226 | ETL.6030 | 40608307 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119693004 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 9/111 RMV DEBRIS | 44454187 | DRUM-SUMMIT #1 | 009/111 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624006 | 39.3204 | ETL.1440 | 44837645 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693005 | Not Scheduled | T2 DI DRUM-SUMMIT #1 9/111 RPR SPLW | 44454186 | DRUM-SUMMIT #1 | 009/111 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624006 | 39.3204 | ETL.1440 | 44837656 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693008 | Not Scheduled | T2 DI DRUM-SUMMIT #1 9/111 RPR GYWW | 44454186 | DRUM-SUMMIT #1 | 009/111 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624006 | 39.3204 | ETL.1440 | 44837656 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693009 | Not Scheduled | T2 DI DRUM-SUMMIT #1 9/111 RPR GYWW | 44454186 | DRUM-SUMMIT #1 | 009/111 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624006 | 39.3204 | ETL.1440 | 44837677 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693200 | Not Scheduled | T2 DI DRUM-SUMMIT #1 9/111 RPR GYWW | 44454186 | DRUM-SUMMIT #1 | 009/111 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624006 | 39.3204 | ETL.1440 | 44837645 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693554 | Feb | EI RIO DL JCT-BRDGVIL 40/1 RPL PL | 31514233 | RIO DELL JCT-BRIDGEVILLE | 040/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.791488 | 40.4754 | ETL.7850 | 40584735 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-12-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693559 | Feb | EI RIO DL JCT-BRIDGEVILLE 40/2 RPL PL | 31514233 | RIO DELL JCT-BRIDGEVILLE | 040/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.789129 | 40.4762 | ETL.7850 | 40656598 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693562 | Q2 | EI LOS BANOS-MIDWAY #2 58/248 RPL SHACKL |  | LOS BANOS-MIDWAY #2 | 058/248 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.377239 | 36.3884 | ETL.6010 | 40863983 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119693794 | Mar | T3 EI GEYSERS #3-CLOVRDL 07/89 RPR POLE | 44580896 | GEYSERS #3-CLOVERDALE | 007/089 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-02-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.945138 | 38.8015 | ETL.1650 | 40594056 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693863 | Not Scheduled | T2T DI SPAULDING-SUMMIT 09/328 RPR WDPKR | 44487980 | SPAULDING-SUMMIT | 009/328 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.484427 | 39.3166 | ETL.8060 | 40770663 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693914 | Q4 | EI T2 KESWICK-TRINITY 23/357A RPL HRDW |  | KESWICK-TRINITY | 023/357A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.805684 | 40.7124 | ETL.7270 | 40906082 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119693935 | Q2 | EI LOS BANOS-GATES #1 063/266 BENT MEMB | 44490735 | LOS BANOS-GATES #1 | 063/266 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.322037 | 36.3379 | ETL.6000 | 40815944 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119693978 | Q2 | EI LOS BANOS-MIDWAY #2 59/252 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 059/252 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.365132 | 36.3779 | ETL.6010 | 40664816 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119694014 | Not Scheduled | T2 DRUM-GRASS VALLEY-WMR 19/441 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 019/441 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.979873 | 39.0671 | ETL.6760 | 40822680 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694015 | Not Scheduled | DRUM-GRASS VALLEY-WEIMAR 16/380 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 016/380 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.959835 | 39.1006 | ETL.6760 | 40874743 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694016 | Not Scheduled | T3 DRUM-GRASS VLLY-WMR B18/403 REFRAME | 31512745 | DRUM-GRASS VALLEY-WEIMAR | B018/403 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-28 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-120.971813 | 39.142 | ETL.6760 | 40767288 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694017 | Not Scheduled | T2 DRUM-GRASS VALLEY-WMR 20/471 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 020/471 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.9844 | 39.0502 | ETL.6760 | 40664687 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694018 | Not Scheduled | T2 DRUM-GRASS VALLEY-WMR 19/443 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 019/443 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.980252 | 39.066 | ETL.6760 | 40873725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694020 | Not Scheduled | T2 DRUM-GRASS VALLEY-WMR 17/402 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 017/402 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.966393 | 39.0869 | ETL.6760 | 40867764 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694021 | Not Scheduled | T2 DRUM-GRASS VALLEY-WMR 17/390 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 017/390 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962883 | 39.0943 | ETL.6760 | 40824315 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694043 | Not Scheduled | T3 EI GEYSERS #3-CLVRDLE 08/92 RMV VEGN |  | GEYSERS #3-CLOVERDALE | 008/092 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-08-31 | 2021-02-28 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.948579 | 38.8009 | ETL.1650 | 40594505 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694269 | Mar | T3 DI DEER CREEK-DRUM 0/8 RPR SPLW | 44461482 | DEER CREEK-DRUM | 000/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.843535 | 39.2943 | ETL.6690 | 40874924 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694329 | Mar | T3 EI GEYSERS #3-CLVRDL 07/84 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 007/084 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-02-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.939793 | 38.8033 | ETL.1650 | 40819430 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694492 | Q2 | EI LOS BANOS-MIDWAY #2 60/254 INST HRDT | 44490736 | LOS BANOS-MIDWAY #2 | 060/254 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.359009 | 36.3724 | ETL.6010 | 40753982 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119694518 | Q4 | T2 DI KESWICK-TRINITY 26/430 RMV PL BUT |  | KESWICK-TRINITY | 026/430 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.857414 | 40.6962 | ETL.7270 | 40906486 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694519 | Q4 | T2 DI KESWICK-TRINITY 26/430 REFRAME | 31515030 | KESWICK-TRINITY | 026/430 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.857414 | 40.6962 | ETL.7270 | 40906486 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694575 | Q2 | EI LOS BANOS-MIDWAY #2 59/249 BENT STEEL |  | LOS BANOS-MIDWAY #2 | 059/249 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.374307 | 36.3857 | ETL.6010 | 40863661 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119694711 | Q4 | T2 DI KESWICK-TRINITY 26/439 RMV DEBRI |  | KESWICK-TRINITY | 026/439 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.862775 | 40.6956 | ETL.7270 | 40906099 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694714 | Q4 | T2 DI KSWICK-TRINITY 17/231 RMV PL BUT |  | KESWICK-TRINITY | 017/231 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.703544 | 40.7223 | ETL.7270 | 40752207 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694715 | Q4 | T2 DI KESWCK-TRINTY 17/231 RPR GND WIRE |  | KESWICK-TRINITY | 017/231 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.703544 | 40.7223 | ETL.7270 | 40752207 | Ground Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694721 | Mar | T3NT DI DEER CREEK-DRUM 2/56 RMV PL BUTT | 44461397 | DEER CREEK-DRUM | 002/056 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.829855 | 39.2645 | ETL.6690 | 40873862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119694723 | Mar | T3 DI DEER CREEK-DRUM 2/56 RPLC INSW | 31512744 | DEER CREEK-DRUM | 002/056 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.829882 | 39.2645 | ETL.6690 | 40898270 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695018 | Q2 | EI GARBERVILLE-LYTNVL 59/05 RPR GYWW | 44453316 | GARBERVILLE-LAYTONVILLE | 059/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.731759 | 40.1102 | ETL.8365 | 40912672 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695028 | Q2 | EI GRBRVILLE-LYTNVLLE 59/005 RPR JMPRW | 44476763 | GARBERVILLE-LAYTONVILLE | 059/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.731759 | 40.1102 | ETL.8365 | 40912672 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695150 | Not Scheduled | T3 GEYSERS #3-CLOVERDALE 08/098 RMV VEGN |  | GEYSERS #3-CLOVERDALE | 008/098 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-08-31 | 2021-02-28 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.956213 | 38.7974 | ETL.1650 | 40818244 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695151 | Mar | T3 GEYSERS #3-CLOVRDLE 08/98 RPL POLE | 31512743 | GEYSERS #3-CLOVERDALE | 008/098 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-02-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.956213 | 38.7974 | ETL.1650 | 40818244 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695214 | Q2 | EI LOS BANOS-MIDWAY #2 61/257 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 061/257 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.349281 | 36.3635 | ETL.6010 | 40811511 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119695280 | Feb | T3 DI KILARC-CEDAR CREEK 6/145 RPR SPLW | 44406464 | KILARC-CEDAR CREEK | 006/145 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.985358 | 40.7124 | ETL.7290 | 44645363 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695383 | Q3 | T2 DI CARIBOU-WSTWD A15/305 RPR SPLS |  | CARIBOU-WESTWOOD | A015/305 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.087724 | 40.269 | ETL.6300 | 44815090 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695385 | Not Scheduled | T2 DI BRDGVL-CTTNWD 64/462 INTS HRDT | 44623123 | BRIDGEVILLE-COTTONWOOD | 064/462 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.425461 | 40.3957 | ETL.1110 | 40634782 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695487 | Not Scheduled | T2 EI DIABLO-MESA 6/030 RPR INSS |  | DIABLO-MESA | 006/030 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.7624369 | 35.3206 | ETL.4620 | 44330006 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695539 | Q2 | EI LOS BANOS-MIDWAY #2 61/258 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 061/258 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.345734 | 36.3602 | ETL.6010 | 40868534 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119695805 | Mar | T3 EI GEYSERS #3-CLOVRDLE 07/78A RPR POL | 44580896 | GEYSERS #3-CLOVERDALE | 007/078A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-02-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.932887 | 38.8071 | ETL.1650 | 44298416 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119695973 | Not Scheduled | T3 EI GEYSERS #3-CLVRDL 07/84 RMV VEGN |  | GEYSERS #3-CLOVERDALE | 007/081 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-08-31 | 2021-02-28 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.936216 | 38.8051 | ETL.1650 | 40669104 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696028 | Q2 | EI LOS BANOS-MIDWAY #2 62/261 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 062/261 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.336459 | 36.3517 | ETL.6010 | 40595069 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119696371 | Q3 | T2T DI CARIBOU-WESTWOOD 9/183 RMV STRW |  | CARIBOU-WESTWOOD | 009/183 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2022-08-29 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.072228 | 40.1965 | ETL.6300 | 40826509 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696373 | Q3 | T2T DI CARIBOU-WESTWOOD 9/183 RPL INSW | 31513339 | CARIBOU-WESTWOOD | 009/183 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.072228 | 40.1965 | ETL.6300 | 40855113 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696392 | Q2 | EI LOS BANOS-MIDWAY #2 62/260 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 062/260 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.339328 | 36.3543 | ETL.6010 | 40608676 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119696485 | Q2 | T3 DI WEIMAR #1 12/174 RPL POLE | 31517853 | WEIMAR #1 | 012/174 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [8 empty] | ETL.7560 | 44414809 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696486 | Q2 | T2 DI KONOCTI-MIDDLETOWN 18/1 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 018/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.577748 | 38.8256 | ETL.6380 | 40600731 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696502 | Not Scheduled | T2 DI SLO-CAYUCOS 14/134 RPR WDPKR |  | SAN LUIS OBISPO-CAYUCOS | 014/134 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.79957 | 35.3486 | ETL.9090 | 40813825 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696539 | Q2 | EI LOS BANOS-MIDWAY #2 62/262 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 062/262 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.333089 | 36.3486 | ETL.6010 | 40689574 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119696646 | Q4 | T2 DI KESWICK-TRINITY 25/401 RPL HRDW |  | KESWICK-TRINITY | 025/401 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.840397 | 40.7037 | ETL.7270 | 40909447 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696648 | Not Scheduled | T2T DI CAYUCOS-CAMBRIA 14/95 RPL STRW | 31517522 | CAYUCOS-CAMBRIA | 014/095 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.055692 | 35.5708 | ETL.8560 | 40576922 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-12-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696667 | Q2 | EI LOS BANOS-MIDWAY #2 63/265 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 063/265 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.325445 | 36.3416 | ETL.6010 | 40753912 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119696712 | Q2 | T3T DI KONOCTI-EAGLE ROCK 3/8 RPR GYWW | 44565795 | KONOCTI-EAGLE ROCK | 003/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-05-06 | 2021-05-05 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.788178 | 38.8664 | ETL.6861 | 44141957 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119696758 | Q2 | EI LOS BANOS-MIDWAY #2 63/264 RPR GYWW | 44509080 | LOS BANOS-MIDWAY #2 | 063/264 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.328035 | 36.344 | ETL.6010 | 40762424 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119697044 | Q2 | EI LOS BANOS-GATES #1 070/295 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 070/295 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.238265 | 36.2672 | ETL.6000 | 40757859 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119697611 | Q2 | T2 FULTON-PUEBLO 38/196 RPL HRDT |  | FULTON-PUEBLO | 038/196 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.681041 | 38.4963 | ETL.1600 | 40835398 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119697661 | Not Scheduled | T2 EAGL RK FLTN-SL 38/196 INST JUMS INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 038/196 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.681281 | 38.4966 | ETL.4392 | 40835401 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119697663 | Q2 | T2 EAGLE RK FLTN-SL 38/196 RPL HRDT | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 038/196 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.681281 | 38.4966 | ETL.4392 | 40835401 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 92 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119697761 | Q3 | T2 DI BRDGVL-CTTNWD 63/461A RPLC DAMS | 44398374 | BRIDGEVILLE-COTTONWOOD | 063/461A | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.424074 | 40.3948 | ETL.1110 | 40819318 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698022 | Q2 | EI LOS BANOS-GATES #1 071/298 RPR STRT | 44490735 | LOS BANOS-GATES #1 | 071/298 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.22784 | 36.2596 | ETL.6000 | 40870068 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119698293 | Q2 | EI LOS BANOS-GATES #1 52/218 INST HRDT | 44490735 | LOS BANOS-GATES #1 | 052/218 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.452042 | 36.4683 | ETL.6000 | 40867456 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119698296 | Q2 | EI LOS BANOS-GATES #1 46/193 RPR TURNBCK |  | LOS BANOS-GATES #1 | 046/193 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.520744 | 36.5284 | ETL.6000 | 40658359 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119698308 | Mar | T3 DI DEER CREEK-DRUM 005/131 RRP SPLW | 44461482 | DEER CREEK-DRUM | 005/131 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.780435 | 39.2591 | ETL.6690 | 42568599 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698313 | Q2 | EI LOS BANOS-GATES #1 44/187 RPR FOUND | 44490735 | LOS BANOS-GATES #1 | 044/187 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.540818 | 36.5426 | ETL.6000 | 40816041 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119698314 | Q2 | EI LOS BANOS-GATES #1 43/182 RMV DEBRIS |  | LOS BANOS-GATES #1 | 043/182 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2022-08-24 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Recommend delinking prior to editing |  | WECC | South | WSIP | [6 empty] | '-120.558023 | 36.5541 | ETL.6000 | 40679555 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119698315 | Q2 | EI LOS BANOS-GATES #1 45/189 RPR STRT | 44509124 | LOS BANOS-GATES #1 | 045/189 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-15 | 2021-02-16 |  |  | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-120.533898 | 36.5381 | ETL.6000 | 40867763 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119698427 | Not Scheduled | T2 DI SPAULDING-SUMMIT 12/419 REFRAME | 31514886 | SPAULDING-SUMMIT | 012/419 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.438164 | 39.322 | ETL.8060 | 40602257 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698791 | Not Scheduled | T2 EI VC-VCVIL-JAMSN-NRTH 7/54 RPR STRT | 44487353 | VACA-VACAVILLE-JAMESON-NTH TWR | 007/054 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-01 | 2021-09-01 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.018808 | 38.3555 | ETL.4100 | 40755557 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698794 | Feb | EI LAYTONVILLE-COVELO 11/8 RPR WDPKR |  | LAYTONVILLE-COVELO | 011/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 |  |  | 2021-02-24 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.285811 | 39.7432 | ETL.7390 | 40878663 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698955 | Q3 | T2 DI CARIBOU-WESTWOOD 000/010 RPL CRSW | 31512791 | CARIBOU-WESTWOOD | 000/010 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.146383 | 40.0893 | ETL.6300 | 40875462 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released 10/14 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-09 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698962 | Q3 | T2 DI CARIBOU #2 11/19 REFRAME | 31521961 | CARIBOU #2 | 011/019 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.165363 | 40.0229 | ETL.6280 | 44465287 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698964 | Q3 | T2NT DI CARIBOU #2 11/19 RMV DEBRIS |  | CARIBOU #2 | 011/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.165363 | 40.0229 | ETL.6280 | 44465287 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119698986 | Q2 | T2 DI BRDGVL-CTTNWD 20/181 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 020/181 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.64667 | 40.3775 | ETL.1110 | 44423236 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699024 | Mar | T2 EI FULTON-HOPLAND 10/7 RPL HRDW | 44579280 | FULTON-HOPLAND | 010/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-01 | 2021-09-01 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.847007 | 38.6211 | ETL.6890 | 40808468 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699093 | Q4 | T2 DI KESWICK-TRINITY 22/349 RPR GYWW |  | KESWICK-TRINITY | 022/349 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.803248 | 40.7161 | ETL.7270 | 40909533 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699097 | Q4 | T2NT DI KESWICK-TRINITY 22/349 INST MRKW |  | KESWICK-TRINITY | 022/349 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.803248 | 40.7161 | ETL.7270 | 40909533 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699107 | Mar | T2NT DI KNCTI-MIDLTWN 015/000 RMV DEB | 44610651 | KONOCTI-MIDDLETOWN | 015/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.574752 | 38.7821 | ETL.6380 | 44370573 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699120 | Q4 | T2 DI KESWICK-TRINITY 22/349 RMV PL BUT |  | KESWICK-TRINITY | 022/349 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2021-02-28 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.803248 | 40.7161 | ETL.7270 | 40909533 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699221 | Q4 | T2 DI KESWICK-TRINITY 28/484 RPR SPLW |  | KESWICK-TRINITY | 028/484 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.896223 | 40.709 | ETL.7270 | 40908541 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699267 | Mar | T2 DI KONOCTI-MIDDLETOWN 015/00 RPL DAM | 44610651 | KONOCTI-MIDDLETOWN | 015/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.574752 | 38.7821 | ETL.6380 | 44370573 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699307 | Q2 | EI LOS BANOS-GATES #1 72/305 RPR TURNBCK |  | LOS BANOS-GATES #1 | 072/305 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.207311 | 36.2428 | ETL.6000 | 40760520 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119699564 | Q3 | T2 DI CARIBOU #2 019/505 RPR SPLW |  | CARIBOU #2 | 019/505 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.029745 | 40.0189 | ETL.6280 | 44259025 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699583 | Q3 | T2NT DI CARIBOU #2 019/505 RMV DEBRIS |  | CARIBOU #2 | 019/505 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.029745 | 40.0189 | ETL.6280 | 44259025 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119699629 | Q2 | EI LOS BANOS-MIDWAY #2 66/277 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 066/277 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.288827 | 36.3081 | ETL.6010 | 40816189 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119699752 | Mar | T2 DI EAGLE RCK-CRTN :14/4 RMV IDL ANCH | 31516133 | EAGLE ROCK-CORTINA | :014/004 | 93J | F | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2022-08-31 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.607913 | 38.9259 | ETL.1470 | 41176307 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Capital | 673 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700374 | Mar | T3 DI DRUM-RIO OSO #2 6/64 RPR STRS | 44461299 | DRUM-RIO OSO #2 | 006/064 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.857225 | 39.2121 | ETL.1430 | 40746448 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700394 | Q2 | T3 DI SNTH LN-HLF MN BY ?4/0 RPR INSW | 44621671 | SNEATH LANE-HALF MOON BAY | ?004/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.477872 | 37.5522 | ETL.7212 | 44913910 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700397 | Not Scheduled | T2 DI CRESTA-RIO OSO 30/245 RPR FOND |  | CRESTA-RIO OSO | 030/245 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.535431 | 39.5396 | ETL.4590 | 41083066 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700458 | Q2 | T2 DI CRESTA-RIO OSO 30/245 RPLC INSS | 31500129 | CRESTA-RIO OSO | 030/245 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.535431 | 39.5396 | ETL.4590 | 41083067 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700470 | Mar | T3 WV DEER CREEK-DRUM 03/081 REFRAME | 31487260 | DEER CREEK-DRUM | 003/081 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-03-01 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.812124 | 39.2623 | ETL.6690 | 40824502 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700774 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/349 RMV DEBRIS | 44487982 | SPAULDING-SUMMIT | 010/349 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.474031 | 39.3178 | ETL.8060 | 40702016 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700826 | Mar | T3 DI DEER CREEK-DRUM 1/28 RPR STRW | 44461482 | DEER CREEK-DRUM | 001/028 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.83789 | 39.2824 | ETL.6690 | 40824513 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119700978 | Q2 | EI LOS BANOS-GATES #1 74/312 BENT MEMB | 44490735 | LOS BANOS-GATES #1 | 074/312 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.191583 | 36.2228 | ETL.6000 | 40673623 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119701025 | Not Scheduled | T2 DI SPAULDING-SUMMIT 013/451 RPL PL | 31514885 | SPAULDING-SUMMIT | 013/451 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.413416 | 39.3282 | ETL.8060 | 40862176 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701351 | Not Scheduled | T2NT DI SPAULDING-SMMT 11/406 RMV DEBRIS | 44478911 | SPAULDING-SUMMIT | 011/406 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.444875 | 39.3184 | ETL.8060 | 40862170 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701354 | Not Scheduled | T2 DI DRUM-SUMMIT #1 25/296 RPL PL |  | DRUM-SUMMIT #1 | 025/296 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2021-08-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.360197 | 39.3097 | ETL.1440 | 44762506 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701468 | Not Scheduled | T2 DI SPAULDING-SUMMIT 14/460 REFRAME | 31514886 | SPAULDING-SUMMIT | 014/460 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.407046 | 39.3285 | ETL.8060 | 40802797 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701550 | Q2 | EI LOS BANOS-MIDWAY #2 67/283 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 067/283 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.273737 | 36.2943 | ETL.6010 | 40651952 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119701647 | Not Scheduled | T2 DI SPAULDING-SUMMIT 13/439 RPL PL | 31514885 | SPAULDING-SUMMIT | 013/439 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.42262 | 39.3275 | ETL.8060 | 40862174 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701772 | Q2 | T2 DI PHILO JCT-ELK 12/6 RPLC STRW | 31515022 | PHILO JCT-ELK | 012/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-08-27 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.341752 | 39.0239 | ETL.7780 | 40826097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701857 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/372 CANCEL | 44483533 | SPAULDING-SUMMIT | 011/372 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.460245 | 39.3189 | ETL.8060 | 40761663 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701986 | Not Scheduled | DI ARCO-CHOLAME 019/182 RMV PL BUTT |  | ARCO-CHOLAME | 019/182 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-28 | 2022-08-28 | [9 empty] | South | WSIP | [6 empty] | '-120.214257 | 35.7097 | ETL.8440 | 40588606 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119701989 | Not Scheduled | DI ARCO-CHOLAME 019/182 RPR INSW |  | ARCO-CHOLAME | 019/182 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-08-28 | [9 empty] | South | WSIP | [6 empty] | '-120.214257 | 35.7097 | ETL.8440 | 40613676 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702081 | Not Scheduled | T3 DI FULTON-HOPLAND 20/0 INST HRDW | 44579280 | FULTON-HOPLAND | 020/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-27 | 2021-02-27 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.895057 | 38.7373 | ETL.6890 | 40616494 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702102 | Not Scheduled | T3 DI FULTON-HOPLAND 20/0 RPR STRW | 44579280 | FULTON-HOPLAND | 020/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-02-27 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.895057 | 38.7373 | ETL.6890 | 40616494 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702105 | Q2 | T2 DI BRDGVL-CTTNWD 3/33 RMV DEBRIS | 44404807 | BRIDGEVILLE-COTTONWOOD | 003/033 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.332351 | 40.3907 | ETL.1110 | 44168669 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702107 | Q2 | T2 DI BRDGVL-CTTNWD 3/33 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 003/033 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.332351 | 40.3907 | ETL.1110 | 44168668 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702146 | Not Scheduled | EI LAYTONVILLE-COVELO 2/2 RPR GYWS | 44610674 | LAYTONVILLE-COVELO | 002/002 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.438455 | 39.6943 | ETL.7390 | 44837898 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702150 | Q2 | EI LOS BANOS-MIDWAY #2 68/286 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 068/286 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.265814 | 36.288 | ETL.6010 | 40812166 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119702283 | Q2 | T2 DI PHILO JCT-ELK 17/6 RMV PL BUTT | 44610684 | PHILO JCT-ELK | 017/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4208 | 39.0564 | ETL.7780 | 40820707 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702284 | Q2 | T2 DI PHILO JCT-ELK 17/6 RPR STRW | 44610684 | PHILO JCT-ELK | 017/006 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2022-08-25 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4208 | 39.0564 | ETL.7780 | 40820707 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702287 | Q3 | T2 DI BRDGVL-CTTNWD 67/483 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 067/483 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.468599 | 40.4279 | ETL.1110 | 40592245 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702362 | Q2 | T3NT DI DRUM-SPAULDING 5/125 RMV DBRIS | 44461622 | DRUM-SPAULDING | 005/125 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.70303 | 39.2963 | ETL.6770 | 40650020 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702363 | Q2 | T3 DI DRUM-SPAULDING 5/125 RPL STRW | 31529084 | DRUM-SPAULDING | 005/125 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.70303 | 39.2963 | ETL.6770 | 40650020 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119702366 | Feb | T3 DI KILARC-CEDAR CREEK 1/38 RPR INSW | 44406464 | KILARC-CEDAR CREEK | 001/038 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.7290 | 44159614 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119703457 | Q2 | EI GARBERVILLE-LAYTONVILLE 41/2 REFRAME | 31512796 | GARBERVILLE-LAYTONVILLE | 041/002 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-15 | 2021-08-15 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577108 | 39.9133 | ETL.8365 | 40906655 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119703458 | Q2 | EI GARBERVILLE-LAYTONVILLE 41/2 RPL SPLC | 44453316 | GARBERVILLE-LAYTONVILLE | 041/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-15 | 2021-08-15 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577108 | 39.9133 | ETL.8365 | 40906655 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119703537 | Q2 | T2 EI IGNACIO-BOLINAS #1 0/9 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 000/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-01 | 2021-09-01 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.55124 | 38.0744 | ETL.7140 | 40825695 | Guy Stub-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119703538 | Q2 | T2 EI IGNACIO-BOLINAS #1 14/148 RPL STRW | 31514917 | IGNACIO-BOLINAS #1 | 014/148 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.70569 | 37.9412 | ETL.7140 | 40742416 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119703544 | Q2 | T2 EI IGNACIO-BOLINAS #1 14/149 RPL STRW | 31514918 | IGNACIO-BOLINAS #1 | 014/149 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.706232 | 37.9409 | ETL.7140 | 40742645 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119703755 | Not Scheduled | DI SPAULDING-SUMMIT 8/302 RPR GYWW | 44461262 | SPAULDING-SUMMIT | 008/302 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-29 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.497176 | 39.3142 | ETL.8060 | 40825445 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119703756 | Not Scheduled | DI SPAULDING-SUMMIT 8/302 RMV BUTT | 44461263 | SPAULDING-SUMMIT | 008/302 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.497176 | 39.3142 | ETL.8060 | 40825445 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119704042 | Not Scheduled | T3 DI CRESTA-RIO OSO 17/140 RMV HRDT |  | CRESTA-RIO OSO | 017/140 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-121.48005 | 39.7241 | ETL.4590 | 40910156 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119704044 | Feb | T3 DI COLGATE-GRASS VLLY 5/128 RPL STRW | 31518651 | COLGATE-GRASS VALLEY | 005/128 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.109515 | 39.3045 | ETL.6490 | 40655414 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119704181 | Q2 | EI LOS BANOS-MIDWAY #2 69/290 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 069/290 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.253183 | 36.2787 | ETL.6010 | 40600332 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119704201 | Q2 | T2 SALT SPRINGS-TIGER CRK 12/09 RPR STRT | 44631415 | SALT SPRINGS-TIGER CREEK | 012/095 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.430594 | 38.4771 | ETL.3500 | 40744662 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119704267 | Q2 | LOS BANOS-MIDWAY #2 69/289 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 069/289 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.256388 | 36.2811 | ETL.6010 | 40870402 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119704391 | Q2 | T2 SLT SPRNGS-TIGR CRK 13/10 RPR STRT | 44631415 | SALT SPRINGS-TIGER CREEK | 013/100 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.449188 | 38.4727 | ETL.3500 | 40579977 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119704780 | Q2 | EI LOS BANOS-MIDWAY #2 69/293 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 069/293 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.244395 | 36.2723 | ETL.6010 | 40651954 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119704954 | Q2 | LOS BANOS-MIDWAY #2 70/294 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 070/294 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.240874 | 36.2697 | ETL.6010 | 40759256 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119705055 | Q2 | T2 DI FORT ROSS-GUALALA 033/009 RPR STRW |  | GUALALA-MONTE RIO | 033/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.286196 | 38.5737 | ETL.6980 | 40876104 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119705086 | Not Scheduled | T2 DI CARIBOU-PALERMO 0/2 RPL INSS |  | CARIBOU-PALERMO | 000/002 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.521449 | 39.4545 | ETL.3190 | 40689941 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119705227 | Q2 | LOS BANOS-MIDWAY #2 70/296 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 070/296 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.234471 | 36.265 | ETL.6010 | 40817177 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119705300 | Q2 | T2 DI FORT ROSS-GULALA 33/9 WASH INS |  | GUALALA-MONTE RIO | 033/009 | ICD | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.286083 | 38.574 | ETL.6980 | 40900563 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119705669 | Q3 | T2 DI CARIBOU #2 17/20 RPR GYWW |  | CARIBOU #2 | 017/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.066152 | 40.0232 | ETL.6280 | 40614836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706039 | Q3 | T2 DI CARIBOU #2 :4/15 RPR HRDW |  | CARIBOU #2 | ;004/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.947902 | 39.9708 | ETL.6280 | 40768852 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706095 | Q3 | T2 DI CARIBOU #2 :4/15 RMV PL BUTT |  | CARIBOU #2 | ;004/015 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.947902 | 39.9708 | ETL.6280 | 40768852 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706175 | Q2 | LOS BANS-MIDWAY #2 71/299 RPL TURNBUCKLE | 44509081 | LOS BANOS-MIDWAY #2 | 071/299 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.224424 | 36.2576 | ETL.6010 | 40863670 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119706191 | Q2 | LOS BANOS-MIDWAY #2 71/299 RPR STRT | 44509080 | LOS BANOS-MIDWAY #2 | 071/299 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.224424 | 36.2576 | ETL.6010 | 40863670 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119706441 | Q3 | T2 DI CARIBOU-PLMAS JCT 9/6 RPR JUMPER |  | CARIBOU-PLUMAS JCT | 009/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.029577 | 40.0008 | ETL.6290 | 40810056 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706461 | Mar | T3 DI DEER CREEK-DRUM 3/93 RPLC CRSW | 31513191 | DEER CREEK-DRUM | 003/093 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-28 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.804768 | 39.2608 | ETL.6690 | 40866660 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706694 | Q3 | T2 DI CARIBOU-PLUMAS JCT 6/16 RPR POLE |  | CARIBOU-PLUMAS JCT | 006/016 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.062863 | 40.0186 | ETL.6290 | 40816708 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706855 | Q2 | T2 DI BRIDGEVILLE-CTNWD 19/175 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 019/175 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.626492 | 40.3789 | ETL.1110 | 40621358 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706858 | Q3 | T2 DI CARIBOU-WESTWOOD 0/9 RPR REFRAME | 31514919 | CARIBOU-WESTWOOD | 000/009 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.146413 | 40.0888 | ETL.6300 | 40876678 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706859 | Q2 | T2 DI BRIDGEVILL-CWD 39/317L RMV PL BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 039/317 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-26 | 2022-08-26 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-123.012212 | 40.3804 | ETL.1110 | 44425578 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119706944 | Q2 | T3NT DI VOLTA-DESCHUTES 0/16 RMV BUTT |  | VOLTA-DESCHUTES | 000/016 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2022-08-28 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.879192 | 40.4629 | ETL.8290 | 40759234 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-23 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707099 | Q3 | T2NT DI CARIBOU #2 12/19 REMV DEBRIS |  | CARIBOU #2 | 012/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.147652 | 40.0252 | ETL.6280 | 40875406 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707212 | Not Scheduled | EI LS BNS-MDWY #2 47/200 INST ZENA GARD | 31526469 | LOS BANOS-MIDWAY #2 | 047/200 | 93R | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.501644 | 36.515 | ETL.6010 | 40608673 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119707228 | Q3 | T2 DI CARIBOU #2 12/19 RPR GYWW |  | CARIBOU #2 | 012/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.147652 | 40.0252 | ETL.6280 | 40875406 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707240 | Not Scheduled | LOS BANOS-MIDWAY #2 49/207 ZENA GUARD | 31526469 | LOS BANOS-MIDWAY #2 | 049/207 | 93R | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.481304 | 36.4968 | ETL.6010 | 40811503 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119707243 | Not Scheduled | LOS BANS-MIDWY #2 50/211 INST ZENA GUARD | 31526469 | LOS BANOS-MIDWAY #2 | 050/211 | 93R | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.469284 | 36.4861 | ETL.6010 | 40587752 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119707318 | Q3 | T2 DI CARIBOU-PLUMAS JCT 09/01 RPL HRDW | 44408852 | CARIBOU-PLUMAS JCT | 009/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.034862 | 40.0014 | ETL.6290 | 40591663 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707424 | Not Scheduled | T3 DI CRESTA-RIO OSO 16/137 RPR STRT |  | CRESTA-RIO OSO | 016/137 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 | [7 empty] | TR3 | <15D | North Valley | WSIP | [6 empty] | '-121.479098 | 39.7299 | ETL.4590 | 40910153 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707469 | Q3 | EI LOS BANOS-MIDWAY #2 73/307 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 073/307 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-08-15 | 2021-07-02 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.201926 | 36.2372 | ETL.6010 | 40811517 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119707702 | Mar | T3 DI DEER CREEK-DRUM 4/112 RMV BUTT | 44461482 | DEER CREEK-DRUM | 004/112 | ICW | E | 2020_(3) On high spread structure |  | 2020-08-29 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.793723 | 39.2565 | ETL.6690 | 40664843 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707707 | Feb | T3 DI KILARC-CEDAR CREEK 10/240 RPL INSW | 31514887 | KILARC-CEDAR CREEK | 010/240 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.962838 | 40.7622 | ETL.7290 | 40900515 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-02 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707718 | Not Scheduled | T2 DI SPAULDNG-SUMMIT 10/367 RMV PL BUTT | 44487982 | SPAULDING-SUMMIT | 010/367 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.462888 | 39.3189 | ETL.8060 | 44349552 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707829 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/371 RPL POLE | 31514885 | SPAULDING-SUMMIT | 011/371 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.46079 | 39.3189 | ETL.8060 | 40668704 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707947 | Feb | T3 DI KILARC-CEDAR CRK 11/248 RPL INSW | 31530140 | KILARC-CEDAR CREEK | 011/248 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.958837 | 40.7669 | ETL.7290 | 40849794 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707969 | Q3 | T2 DI CARIBOU #2 19/503 RMV PL BUTT |  | CARIBOU #2 | 019/503 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.030827 | 40.0181 | ETL.6280 | 44259023 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119707971 | Q2 | EI LOS BANOS-GATES #1 80/338 ADJUST TURN |  | LOS BANOS-GATES #1 | 080/338 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.130005 | 36.148 | ETL.6000 | 40867440 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708016 | Feb | T3NT DI KILARC-CEDAR CRK 6/138 RMV BUTT | 44406464 | KILARC-CEDAR CREEK | 006/138 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2022-08-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.98035 | 40.7109 | ETL.7290 | 40617662 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708030 | Q3 | T2 DI CARIBOU #2 19/503 RPR INSW |  | CARIBOU #2 | 019/503 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.030827 | 40.0181 | ETL.6280 | 44259023 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708033 | Q3 | T2 DI CARIBOU-WESTWOOD 16/344 RPR STRW |  | CARIBOU-WESTWOOD | 016/344 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.069295 | 40.2905 | ETL.6300 | 44191122 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708038 | Mar | T3 DI PARKWAY-MORAGA 19/107 RPL INSS | 31526488 | PARKWAY-MORAGA | 019/107 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-28 |  |  | 2021-03-16 | 2021-03-16 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.213666 | 37.8823 | ETL.5930 | 44723514 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708044 | Q2 | EI LOS BANOS-MIDWAY #2 74/313 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 074/313 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.188573 | 36.2198 | ETL.6010 | 40662872 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708046 | Q2 | EI LOS BANOS-GATES #1 80/339 ADJUST TURN |  | LOS BANOS-GATES #1 | 080/338A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.129484 | 36.1454 | ETL.6000 | 40576536 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708064 | Not Scheduled | T2 DI SPLDNG-SMIT 14/174 INST ANTI SPLIT | 44487980 | SPAULDING-SUMMIT | 014/474 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.39517 | 39.3288 | ETL.8060 | 40862178 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708101 | Q2 | EI LOS BANOS-MIDWAY #2 74/313 RPR FOUND | 44490736 | LOS BANOS-MIDWAY #2 | 074/313 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.188573 | 36.2198 | ETL.6010 | 40662872 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708132 | Not Scheduled | DI SPAULDING-SUMMIT 005/183 RPR WDPKR | 44487980 | SPAULDING-SUMMIT | 005/183 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55988 | 39.3062 | ETL.8060 | 40751847 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708135 | Not Scheduled | DI SPAULDING-SUMMIT 005/183 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/183 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55988 | 39.3062 | ETL.8060 | 40751847 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708166 | Q3 | T2 DI CARIBOU-WESTWOOD 2/49 RPR GYWW |  | CARIBOU-WESTWOOD | 002/049 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.126345 | 40.1114 | ETL.6300 | 40861869 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708246 | Not Scheduled | DI SPAULDING-SUMMIT 006/220 RPL HRDD | 44487980 | SPAULDING-SUMMIT | 006/220 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.54419 | 39.3072 | ETL.8060 | 40586087 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708255 | Not Scheduled | DI SPAULDING-SUMMIT 6/215 RPL POLE |  | SPAULDING-SUMMIT | 006/215 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.546593 | 39.3066 | ETL.8060 | 40819459 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708258 | Not Scheduled | DI SPAULDING-SUMMIT 5/186 RPR WDPKR | 44487980 | SPAULDING-SUMMIT | 005/186 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.558582 | 39.306 | ETL.8060 | 40826235 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119708347 | Q4 | T2 DI MAPLE CREEK-HOOPA 17/4 RPLC SPLW | 44453147 | MAPLE CREEK-HOOPA | 017/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.677695 | 40.9333 | ETL.7490 | 44963389 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708435 | Q3 | DI CARIBOU-PLUMAS JCT ;8/28 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | ;008/028 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-01 | 2021-09-01 |  |  | 2021-08-20 | 2021-08-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.934618 | 39.941 | ETL.6290 | 44168156 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708574 | Not Scheduled | T2 DI SPAULDING-SUMMIT 012/426 RPL POLE |  | SPAULDING-SUMMIT | 012/426 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.43338 | 39.3245 | ETL.8060 | 40862172 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708633 | Q4 | T2 DI MAPLE CREEK-HOOPA 003/001 RPR GYWW | 44453147 | MAPLE CREEK-HOOPA | 003/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-02 | 2021-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.833985 | 40.7956 | ETL.7490 | 40586842 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119708634 | Q4 | T2 DI MAPLE CREEK-HOOPA 003/001 RPL SPLW | 44453147 | MAPLE CREEK-HOOPA | 003/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-02 | 2021-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.833985 | 40.7956 | ETL.7490 | 44942299 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709020 | Q3 | T2 DI CARIBOU #2 19/507 RPR INSW |  | CARIBOU #2 | 019/507 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.02882 | 40.0199 | ETL.6280 | 44259787 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709024 | Not Scheduled | T2 DI SPAULDING-SUMMIT 9/332 RMV PL BUTT | 44487982 | SPAULDING-SUMMIT | 009/332 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.482722 | 39.3169 | ETL.8060 | 44349541 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709396 | Q2 | T2 DI IGNACIO-BOLINS#1 7/75 GRD WSH INSU | 44640984 | IGNACIO-BOLINAS #1 | 007/075 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-09-01 | 2021-09-01 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.644995 | 38.0156 | ETL.7140 | 40900755 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709469 | Q3 | T2 DI BRIDGEVILL-COTTON 64/466 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 064/466 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.439682 | 40.4048 | ETL.1110 | 40764797 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709550 | Q3 | T2 DI CARIBOU-WESTW 5/97 RPR GYWW |  | CARIBOU-WESTWOOD | 005/097 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.114968 | 40.1463 | ETL.6300 | 40698896 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709592 | Q3 | T2 DI CARIBOU #2 14/03 REFRAME | 31515447 | CARIBOU #2 | 014/003 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.128208 | 40.0284 | ETL.6280 | 40666854 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709621 | Mar | T3NT DI DUTCH FLAT #2 0/1 RPR FOND | 44476841 | DUTCH FLAT #2 TAP | 000/001 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-29 | 2022-08-29 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.83495 | 39.2185 | ETL.1421 | 40581248 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709649 | Q3 | T2 DI CARIBOU-WESTWOOD 10/210 RPR GYWW |  | CARIBOU-WESTWOOD | 010/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.066532 | 40.213 | ETL.6300 | 44190980 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709744 | Q3 | T2NT DI CARIBOU #2 ;5/11 RMV PL BUTT |  | CARIBOU #2 | ;005/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2022-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.952778 | 39.9582 | ETL.6280 | 40585976 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709792 | Q3 | T2 DI CARIBOU #2 ;5/11 RPR INBWW |  | CARIBOU #2 | ;005/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.952778 | 39.9582 | ETL.6280 | 40585976 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709830 | Q2 | T3 DI VOLTA-DESCHUTES 4/98 RPR STRW |  | VOLTA-DESCHUTES | 004/098 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.948933 | 40.4802 | ETL.8290 | 40590554 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-23 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709836 | Feb | T3 DI KILARC-CEDAR CREEK 11/254 RPR STRW | 44406464 | KILARC-CEDAR CREEK | 011/254 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-02-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.955722 | 40.7707 | ETL.7290 | 40664566 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709847 | Mar | T3NT DI POE-RIO OSO 19/128 INST MRKS |  | POE-RIO OSO | 019/128 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-29 | 2022-08-29 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.481084 | 39.7199 | ETL.5540 | 40866865 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709849 | Not Scheduled | T3NT DI POE-RIO OSO 19/128 RPR FOND |  | POE-RIO OSO | 019/128 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2022-08-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.481084 | 39.7199 | ETL.5540 | 40866865 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709897 | Q3 | T2 DI CARIBOU-WESTWOOD 9/187 RPR GYWW |  | CARIBOU-WESTWOOD | 009/187 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.07103 | 40.199 | ETL.6300 | 44191058 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119709922 | Not Scheduled | DI SPAULDING-SUMMIT 5/188 INS MRKW | 44487982 | SPAULDING-SUMMIT | 005/188 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.557594 | 39.3057 | ETL.8060 | 40876683 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119709928 | Not Scheduled | DI SPAULDING-SUMMIT 5/188 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/188 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.557594 | 39.3057 | ETL.8060 | 40876683 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119710078 | Feb | T3 DI KILARC-CEDAR CREEK 1/31 RPR SPLW | 44406464 | KILARC-CEDAR CREEK | 001/031 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.895903 | 40.686 | ETL.7290 | 44159601 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119710251 | Q4 | T2 DI KESWICK-TRINITY 20/296 RMV PL BUTT |  | KESWICK-TRINITY | 020/296 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.75846 | 40.716 | ETL.7270 | 44649263 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119710293 | Not Scheduled | DI SPAULDING-SUMMIT 7/245 RPR GYWW | 44477440 | SPAULDING-SUMMIT | 007/245 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.529654 | 39.307 | ETL.8060 | 40668670 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119710347 | Q3 | T2 DI CARIBOU #2 19/511 RPR INSW |  | CARIBOU #2 | 019/511 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.027752 | 40.0219 | ETL.6280 | 44259031 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119710772 | Not Scheduled | T2NT DI BRIDGEVILLE-CNWD 61/445 RPR FOND | 44623123 | BRIDGEVILLE-COTTONWOOD | 061/445 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-29 | 2022-08-29 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.390345 | 40.3806 | ETL.1110 | 40762548 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119710774 | Q3 | T2 DI BRIDGEVILLE-CNWD 61/445 RPR OPGW | 44398374 | BRIDGEVILLE-COTTONWOOD | 061/445 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.390345 | 40.3806 | ETL.1110 | 40762548 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119711130 | Q2 | T3 DI DRUM-SPAULDING 3/87 RPL STRW | 31529084 | DRUM-SPAULDING | 003/087 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.720842 | 39.2822 | ETL.6770 | 40589989 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119711257 | Not Scheduled | DI SPAULDING-SUMMIT 9/307 RPR WDPKR | 44487980 | SPAULDING-SUMMIT | 009/307 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.494544 | 39.3145 | ETL.8060 | 40751861 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119711404 | Feb | EI LAYTONVILLE-COVELO 10/009 RPR STRW | 44610673 | LAYTONVILLE-COVELO | 010/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-03 | 2021-09-03 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.298031 | 39.7337 | ETL.7390 | 40860899 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119711456 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/379 RPL POLE |  | SPAULDING-SUMMIT | 011/379 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.457016 | 39.3185 | ETL.8060 | 40602254 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119711602 | Q2 | T2 DI IGNACIO-BOLINAS#2 9/120 RPR STRW | 44640732 | IGNACIO-BOLINAS #2 | 009/120 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.680527 | 38.1099 | ETL.7180 | 40617163 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119712229 | Not Scheduled | DI SPAULDING-SUMMIT 6/237 REMV BUTT | 44487981 | SPAULDING-SUMMIT | 006/237 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.533865 | 39.3077 | ETL.8060 | 40650044 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712251 | Not Scheduled | LOS BANOS-MIDWAY #2 89/373 INST ZENA | 44509079 | LOS BANOS-MIDWAY #2 | 089/373 | ICB | E | 2020_(1b) Lines with special commitments |  | 2020-09-03 | 2021-09-03 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.039045 | 36.0503 | ETL.6010 | 40662873 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712358 | Q4 | T2 DI KESWICK-TRINITY 026/425 RPL STRW | 31515029 | KESWICK-TRINITY | 026/425 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.854745 | 40.6988 | ETL.7270 | 40906094 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119712439 | Not Scheduled | DI SPAULDING-SUMMIT 7/251 INS MRKW | 44487982 | SPAULDING-SUMMIT | 007/251 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525893 | 39.3067 | ETL.8060 | 44349510 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712621 | Not Scheduled | DI SPAULDING-SUMMIT 7/251 RMV PL BUTT | 44487982 | SPAULDING-SUMMIT | 007/251 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525893 | 39.3067 | ETL.8060 | 44349510 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712624 | Not Scheduled | DI SPAULDING-SUMMIT 6/222 RMV DEBRIS | 44487981 | SPAULDING-SUMMIT | 006/222 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.543169 | 39.3075 | ETL.8060 | 40650043 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712629 | Q2 | T3 DI FULTON-CALISTOGA ;002/006 RPR STRT |  | FULTON-CALISTOGA | ;002/006 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-01 | 2021-03-01 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.705787 | 38.4967 | ETL.6880 | 44650012 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119712788 | Not Scheduled | DI SPAULDING-SUMMIT 005/190 RPR GYWW | 44477440 | SPAULDING-SUMMIT | 005/190 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556817 | 39.3055 | ETL.8060 | 40594094 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712812 | Q2 | EI LOS BANOS-MIDWAY #2 79/331 RPR GYWS | 44509081 | LOS BANOS-MIDWAY #2 | 079/331 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-03 | 2021-09-03 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.145531 | 36.167 | ETL.6010 | 40597463 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712888 | Q2 | T2 DI FORT RS-GUALALA 33/3 GRD WSH INSU |  | GUALALA-MONTE RIO | 033/003 | ICD | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.278288 | 38.5724 | ETL.6980 | 40692237 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119712950 | Not Scheduled | DI SPAULDING-SUMMIT 005/190 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/190 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556817 | 39.3055 | ETL.8060 | 40594094 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119712969 | Mar | EI GEYSERS #3-CLOVERDALE 9/107 RPL POLE | 31515454 | GEYSERS #3-CLOVERDALE | 009/107 | 70Y | E | 2020_(1a) PSPS |  | 2020-09-03 | 2021-09-03 |  |  | 2021-03-27 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.9686431 | 38.7988 | ETL.1650 | 44298332 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119713016 | Q2 | LOS BANOS-MIDWAY #2 79/332 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 079/332 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-03 | 2021-09-03 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.142933 | 36.1639 | ETL.6010 | 40664834 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119713123 | Not Scheduled | T2NT WV DRUM-SUMMIT #2 11/137A INST MRKW | 44487703 | DRUM-SUMMIT #2 | 011/137A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-09-03 | 2022-09-03 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.587827 | 39.3334 | ETL.1450 | 40876971 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119713184 | Not Scheduled | T2 DI SPAULDING-SUMMIT 14/462 REFRAME | 31514886 | SPAULDING-SUMMIT | 014/462 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.405567 | 39.3285 | ETL.8060 | 40836973 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119713248 | Q3 | T2NT DI CARIBOU-PLUMAS JCT 8/6 RMV BUTT | 44408852 | CARIBOU-PLUMAS JCT | 008/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-31 | 2022-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.048235 | 40.0053 | ETL.6290 | 40816720 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119713346 | Q2 | GATES-PANOCHE #1 1/008 RPR FOND | 44490730 | GATES-PANOCHE #1 | 001/008 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-03 | 2021-09-03 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.137272 | 36.1579 | ETL.4720 | 40863626 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119713416 | Q4 | T2 DI KESWICK-TRINITY 26/443 RPR GYWW |  | KESWICK-TRINITY | 026/443 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.866818 | 40.6972 | ETL.7270 | 40906103 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119713417 | Q4 | T2 DI KESWICK-TRINITY 26/443 RMV PL BUTT |  | KESWICK-TRINITY | 026/443 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.866818 | 40.6972 | ETL.7270 | 40906103 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119713497 | Q3 | T2DI CARIBOU-PLUMAS JCT 5/12 RPL CRSW | 31511087 | CARIBOU-PLUMAS JCT | 005/012 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.068396 | 40.0333 | ETL.6290 | 40659861 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119713569 | Q2 | EI VACA-VACA-JAMESON-NTH 24/165 RPR FOND | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 024/165 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-04 | 2021-09-04 |  |  | 2021-06-04 | 2021-06-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.176381 | 38.1345 | ETL.4100 | 40644302 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714380 | Q4 | T2 DI KESWICK-TRINITY 22/330 REMV PL BUT |  | KESWICK-TRINITY | 022/330 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.788271 | 40.7195 | ETL.7270 | 40906069 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714381 | Q4 | T2 DI KESWICK-TRINITY 22/330 RPL INSW | 31515028 | KESWICK-TRINITY | 022/330 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.788271 | 40.7195 | ETL.7270 | 40915738 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714416 | Q3 | T2 DI CARIBOU-PLUMAS JCT 7/0 RPL HRDW | 44408852 | CARIBOU-PLUMAS JCT | 007/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.064315 | 40.0166 | ETL.6290 | 40599506 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714417 | Q3 | T2 DI CARIBOU-PLUMAS JCT 7/0 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 007/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.064315 | 40.0166 | ETL.6290 | 40599506 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714438 | Q4 | T3 DI MAPLE CREEK-HOOPA 012/003 RPR WDPK | 44192340 | MAPLE CREEK-HOOPA | 012/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-03-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.759972 | 40.906 | ETL.7490 | 40668477 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714609 | Not Scheduled | T3NT DI PTER VLEY-WILLIT 8/7 INST MRKW |  | POTTER VALLEY-WILLITS | 008/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-02 | 2022-09-02 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-123.268437 | 39.3721 | ETL.7820 | 40808408 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-29 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714649 | Q2 | EI LOS BANOS-MIDWAY #2 80/336 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 080/336 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.132484 | 36.1517 | ETL.6010 | 40812170 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119714668 | Not Scheduled | T3 DI POTTER VALLEY-WILLIT 8/7 RPL INSW | 31514057 | POTTER VALLEY-WILLITS | 008/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-03-02 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.268437 | 39.3721 | ETL.7820 | 40832863 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714691 | Q4 | T3 DI MAPLE CREEK-HOOPA 014/006 RPL STRW | 31513821 | MAPLE CREEK-HOOPA | 014/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-02 | 2021-03-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.71896 | 40.9084 | ETL.7490 | 40827999 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714774 | Q3 | T2 DI CARBOU-PLUMAS JCT 11/0 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 011/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.005893 | 39.9857 | ETL.6290 | 40599532 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714775 | Q3 | T2 DI CARIBOU-WESTWOOD 011/219 RPR HRDD |  | CARIBOU-WESTWOOD | 011/219 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.070762 | 40.2183 | ETL.6300 | 40876705 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119714776 | Q3 | T2 DI CARIBOU-WESTWOOD 11/219 RPR GYWW |  | CARIBOU-WESTWOOD | 011/219 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.070762 | 40.2183 | ETL.6300 | 40876705 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119715020 | Feb | EI LAYTONVILLE-COVELO 10/007 RPR POLE | 44610673 | LAYTONVILLE-COVELO | 010/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.301214 | 39.733 | ETL.7390 | 40824451 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119715275 | Not Scheduled | T3NT DI MSR FLT-GLD HL#1 18/157 RPR FOND | 44477054 | MISSOURI FLAT-GOLD HILL #1 | 018/157 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-02 | 2022-09-02 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.889248 | 38.6651 | ETL.2660 | 40809722 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119715485 | Q3 | T2 DI BRDGVLLE-GARBRVLL 21/9 RPL INSW | 31514126 | BRIDGEVILLE-GARBERVILLE | 021/009 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.767828 | 40.2606 | ETL.6220 | 40899734 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119715923 | Mar | T3 DI POTTER VLY-WILLITS 7/8 REFRAME | 31528872 | POTTER VALLEY-WILLITS | 007/008 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-03-02 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.247846 | 39.3786 | ETL.7820 | 40884221 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716110 | Q2 | T2 DI TRINITY-MPLE CRK 49/14 RMV PL BUTT | 44470706 | TRINITY-MAPLE CREEK | 049/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-02 | 2022-09-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.801086 | 40.7564 | ETL.8170 | 40751121 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716111 | Q2 | T2 DI TRINITY-MAPLE CRK 49/14 RPR HRDW | 44484765 | TRINITY-MAPLE CREEK | 049/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.801086 | 40.7564 | ETL.8170 | 40751121 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716113 | Q2 | T2 DI TRINITY-MAPLE CRK 49/14 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 049/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.801086 | 40.7564 | ETL.8170 | 40751121 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716255 | Q3 | T2 DI BRDGVLLE-GRBERVLLE 22/03 REPL POLE | 31514123 | BRIDGEVILLE-GARBERVILLE | 022/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.751942 | 40.2159 | ETL.6220 | 40650770 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716259 | Q4 | T2 DI MAPLE CREEK-HOOPA 017/001 INS HRDW | 44482958 | MAPLE CREEK-HOOPA | 017/001 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-02 | 2021-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.686753 | 40.9303 | ETL.7490 | 40602070 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716430 | Q3 | T2 DI BRIDGVLLE-GRBRVLE 22/03 RMV PL BUT | 44476761 | BRIDGEVILLE-GARBERVILLE | 022/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-02 | 2022-09-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.751942 | 40.2159 | ETL.6220 | 40650770 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716433 | Q4 | T2NT DI MAPLE CREEK-HOOP 17/1 RMV DEBRIS | 44461912 | MAPLE CREEK-HOOPA | 017/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-02 | 2022-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.686753 | 40.9303 | ETL.7490 | 40602070 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716525 | Q3 | T2 DI BRDGVLL-GRBRVLL 021/000 RMV PL BUT | 44476761 | BRIDGEVILLE-GARBERVILLE | 021/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-02 | 2022-09-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.760588 | 40.2322 | ETL.6220 | 40591113 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716796 | Q4 | T3 DI MAPLE CREEK-HOOPA 18/0 RPLC INSW | 31514052 | MAPLE CREEK-HOOPA | 018/000 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-03-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.672728 | 40.9371 | ETL.7490 | 40641460 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716896 | Not Scheduled | T3 DI POTTER VLY-WLTS 8/8 RPR GYWW | 44610689 | POTTER VALLEY-WILLITS | 008/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-03-02 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.272275 | 39.3728 | ETL.7820 | 40876422 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716962 | Q4 | DI MAPLE CREEK-HOOPA 4/10 RPL STRW | 31516371 | MAPLE CREEK-HOOPA | 004/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-03 | 2021-09-03 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.828218 | 40.8194 | ETL.7490 | 40617945 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119716969 | Not Scheduled | T2 DI DRUM-SUMMIT #2 21/258L CANCEL | 44487756 | DRUM-SUMMIT #2 | 021/258 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2021-08-31 | [6 empty] | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.419166 | 39.3281 | ETL.1450 | 44553753 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119717021 | Not Scheduled | DI SPAULDING-SUMMIT 5/169 RPR STRW | 44487980 | SPAULDING-SUMMIT | 005/169 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.566613 | 39.3058 | ETL.8060 | 40618283 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119717208 | Q4 | T2 DI MAPLE CREEK-HOOPA 5/11 RPL STRW | 31516371 | MAPLE CREEK-HOOPA | 005/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.822658 | 40.8348 | ETL.7490 | 40602062 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119717673 | Q2 | EI LAKEVILLE-IGNACIO #1 4/025 RPR FOND |  | LAKEVILLE-IGNACIO #1 | IG004/025 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 |  |  | 2021-05-28 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.541029 | 38.0815 | ETL.4940 | 40760311 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119717686 | Not Scheduled | EI LAKEVILLE-IGNACIO #1 4/025 REPAINT | 43761676 | LAKEVILLE-IGNACIO #1 | IG004/025 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-04 | 2022-09-04 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.541029 | 38.0815 | ETL.4940 | 40760311 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119717877 | Q3 | T2DI BRIDGEVILLE-COTTON 65/469 RPR SHLDS | 44477511 | BRIDGEVILLE-COTTONWOOD | 065/469 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-03 | 2021-09-03 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.445307 | 40.4076 | ETL.1110 | 44424633 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119717910 | Q2 | T2 DI TRINITY-MAPLE CREEK 49/12 RPL INSW | 31514141 | TRINITY-MAPLE CREEK | 049/012 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.798059 | 40.7563 | ETL.8170 | 40711453 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718164 | Q2 | EI LOS BANOS-MIDWAY #2 83/349 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 083/349 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.102555 | 36.1165 | ETL.6010 | 40869003 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119718535 | Q2 | EI GARBERVILLE-LAYTONVILLE 53/5 REPL POL | 31512796 | GARBERVILLE-LAYTONVILLE | 053/005 | 93E | E | 2020_(3) On high spread structure |  | 2020-09-04 | 2021-09-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.647364 | 40.0652 | ETL.8365 | 40912594 | Anchor-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718596 | Mar | T2 NN CORTNA-MENDCIN #1 26/128 INST HRDT |  | CORTINA-MENDOCINO #1 | 026/128 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.671615 | 39.0295 | ETL.1330 | 40861866 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718598 | Not Scheduled | T2 NN MENDOCINO-REDBUD 026/128 RPL INSS | 31530110 | MENDOCINO-REDBUD | 026/128 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.672523 | 39.0296 | ETL.2410 | 40885241 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718607 | Q2 | EI LOS BANOS-MIDWAY #2 83/351 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 083/351 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.097413 | 36.1105 | ETL.6010 | 40587764 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119718608 | Not Scheduled | EI LOS BANOS-MIDWAY #2 83/351 RPR SHLS | 44507430 | LOS BANOS-MIDWAY #2 | 083/351 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.097413 | 36.1105 | ETL.6010 | 40587764 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119718612 | Q2 | EI LOS BANOS-MIDWAY #2 83/351 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 083/351 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.097413 | 36.1105 | ETL.6010 | 40587764 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119718828 | Feb | EI LAYTONVILLE-COVELO 10/1 RPR GYWS |  | LAYTONVILLE-COVELO | 010/001 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-04 | 2021-09-04 |  |  | 2021-02-24 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.309999 | 39.7323 | ETL.7390 | 44931504 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718829 | Q2 | EI LAYTONVILLE-COVELO 010/002 RPLC STRW | 31515457 | LAYTONVILLE-COVELO | 010/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-04 | 2021-09-04 |  |  | 2021-06-11 | 2021-06-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.308156 | 39.7324 | ETL.7390 | 40698255 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718844 | Feb | EI LAYTONVILLE-COVELO 10/4 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 010/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.305552 | 39.7326 | ETL.7390 | 40769314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718845 | Feb | EI LAYTONVILLE-CVLO 10/5 INST GMKR | 44610673 | LAYTONVILLE-COVELO | 010/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-04 | 2022-09-04 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.304341 | 39.7327 | ETL.7390 | 40750438 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718846 | Feb | EI LAYTONVILLE-CVLO 10/5 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 010/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.304341 | 39.7327 | ETL.7390 | 40750438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718885 | Feb | DI STNSLS-MLNS SW ST-MTC 19/122 RPR SPLS | 44566006 | STANISLAUS-MELONES SS-MANTECA #1+ | 019/122 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-27 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.659151 | 37.9746 | ETL.3830 | 40579574 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718911 | Before Feb | T3 NN GYSRS#12-FLTN :4/22 RPL INSS | 31505663 | GEYSERS #12-FULTON | :004/022 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-01-29 | 2021-01-25 | 2021-01-28 | 2021-01-28 | 2021-01-25 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76181 | 38.7447 | ETL.4750 | 40714795 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718925 | Mar | T3 NN MORAGA-OAKLAND #2 000/003 RPR SPLS | 44621942 | MORAGA-OAKLAND #2 | 000/003 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.168362 | 37.8478 | ETL.2730 | 40694419 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718950 | Not Scheduled | T3NTDI CARIBOU-TBLE MTN 38/285 RPR FOND |  | CARIBOU-TABLE MTN | 038/285 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.488569 | 39.7607 | ETL.4440 | 40758291 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718952 | Not Scheduled | T3NT DI CARIBU-TBL MTN 39/293 RPR FOND |  | CARIBOU-TABLE MTN | 039/293 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.496349 | 39.7471 | ETL.4440 | 40649137 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119718954 | Not Scheduled | T3 DI CRESTA-RIO OSO 14/112 INST STEP |  | CRESTA-RIO OSO | 014/112 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-03-04 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.460985 | 39.7661 | ETL.4590 | 40910134 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719052 | Q2 | T2 DI BRIDGEVLLE-CTTNWD 5/48 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 005/048 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-03 | 2021-09-03 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.363936 | 40.3906 | ETL.1110 | 44423888 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719149 | Q2 | T2 BRIDGEVILLE-COTTON 5/52 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 005/052 | ICW | E | 2020_(1a) PSPS |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.371799 | 40.3901 | ETL.1110 | 44424398 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119719177 | Q2 | DI IGNACIO-BOLINAS #2 22/255 RPR SPLW | 44640732 | IGNACIO-BOLINAS #2 | 022/255 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.738614 | 37.9859 | ETL.7180 | 40779566 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719180 | Q2 | T2 BRIDGEVILLE-COTTON 5/52 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 005/052 | ICW | E | 2020_(1a) PSPS |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.371799 | 40.3901 | ETL.1110 | 44424397 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119719181 | Q2 | T2 BRIDGEVILLE-COTTON 5/52 RPL X-BRACE |  | BRIDGEVILLE-COTTONWOOD | 005/052 | 93E | E | 2020_(1a) PSPS |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.371799 | 40.3901 | ETL.1110 | 44424397 | Crossarm-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-30 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119719186 | Q2 | BRIDGEVILLE-COTTONWOOD 9/85 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/085 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-03 | 2021-09-03 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.439796 | 40.3891 | ETL.1110 | 44423891 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719225 | Q2 | T2 NN LAURELES-OTTER 1/12 RPR GYWW | 44587870 | LAURELES-OTTER | 001/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.708722 | 36.4589 | ETL.7380 | 40659513 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719229 | Not Scheduled | T3 NN DRUM-SUMMIT #2 0/6C INST DAMW | 44470921 | DRUM-SUMMIT #2 | 000/006C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.760505 | 39.2549 | ETL.1450 | 44868810 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719268 | Q2 | BRIDGEVILLE-COTTONWD 029/245R RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 029/245 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-03 | 2021-09-03 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.815161 | 40.3656 | ETL.1110 | 44561141 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719360 | Not Scheduled | T3NT CRIBU-TABLE MTN 37/273 RPR FOUND |  | CARIBOU-TABLE MTN | 037/273 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2022-09-04 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.47708 | 39.7832 | ETL.4440 | 40663299 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719379 | Q2 | T2 NN BRDGVL-CTTNWD 46/357 RPLC INSS | 31512268 | BRIDGEVILLE-COTTONWOOD | 046/357 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.12576 | 40.3999 | ETL.1110 | 40712930 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719541 | Q2 | DI TRINITY-MAPLE CREEK 0/7 RPR SWIW | 44453151 | TRINITY-MAPLE CREEK | 000/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-12 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.93845 | 40.7228 | ETL.8170 | 40906226 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719686 | Q2 | T2 NN FORT RS-GUALALA 57/11 GRD WSH INSU |  | GUALALA-MONTE RIO | 057/011 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.514771 | 38.7738 | ETL.6980 | 40608960 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719881 | Mar | T3 NN MORAGA-OAKLAND ""J"" 3/23 RPR SPLS | 44621941 | MORAGA-OAKLAND "J" | 003/023 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 |  |  | 2021-03-31 | 2021-03-31 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.136402 | 37.8124 | ETL.2760 | 40676708 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719935 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 5/145 RPR SPLCW | 44470852 | COLGATE-ALLEGHANY | 005/145 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.094601 | 39.3359 | ETL.6470 | 40824242 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719936 | Not Scheduled | T3NT NN CLGTE-ALLEGHNY 5/145 RMV PL BUTT | 44470935 | COLGATE-ALLEGHANY | 005/145 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2022-02-05 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.094601 | 39.3359 | ETL.6470 | 40824242 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719938 | Not Scheduled | T2 NN SPAULDING-SMT 17/559 INST MRKW | 44487982 | SPAULDING-SUMMIT | 017/559 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.353534 | 39.3086 | ETL.8060 | 40658645 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119719980 | Mar | T3 NN TIGER CRK-VLLY SPRGS 2/17 RPL HRDS |  | TIGER CREEK-VALLEY SPRINGS | 002/017 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 |  |  | 2021-03-09 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.528254 | 38.4391 | ETL.5790 | 40870622 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720137 | Mar | T2 DI COLEMAN-RED BLUFF 3/62 RPL STRW | 31513407 | COLEMAN-RED BLUFF | 003/062 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-03 | 2021-09-03 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.121775 | 40.3525 | ETL.6440 | 41144114 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-10-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720140 | Mar | T3 NN DRM-GRS VLY-WMAR 11/263 RPR SPLCW | 44470858 | DRUM-GRASS VALLEY-WEIMAR | 011/263 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.896785 | 39.1511 | ETL.6760 | 40685677 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720142 | Mar | T3NT NN DRM-GRS VL-WMR 11/263 RMV PL BUT | 44470941 | DRUM-GRASS VALLEY-WEIMAR | 011/263 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.896785 | 39.1511 | ETL.6760 | 40656067 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720143 | Feb | T3 NN KILARC-CEDAR CREEK 4/110 RPL STRW | 31513481 | KILARC-CEDAR CREEK | 004/110 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.958895 | 40.7045 | ETL.7290 | 40825972 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720186 | Q3 | T2 DI CARIBOU-PLUMAS JCT 4/2 INST DAMW | 44408852 | CARIBOU-PLUMAS JCT | 004/002 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-03 | 2021-09-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.09144 | 40.0486 | ETL.6290 | 40675189 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720288 | Q3 | T2 NN CARBU-PLUMS JCT ;009/011 RPR SPLCW | 44408852 | CARIBOU-PLUMAS JCT | ;009/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.930668 | 39.9369 | ETL.6290 | 44168163 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720301 | Q2 | T3NT NN EAGLE ROCK-REDBUD :3/20 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :003/020 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-22 | 2022-06-22 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.766159 | 38.8637 | ETL.1480 | 40604564 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720328 | Q3 | DI HAAS-MC CALL 027/139 RPR FOND | 44490955 | HAAS-MCCALL | 027/139 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-22 | 2022-06-22 |  |  | 2021-08-15 | 2021-07-02 | [5 empty] | South | WSIP | [6 empty] | '-119.43276 | 36.7587 | ETL.4850 | 40858150 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720329 | Mar | T3 NN POTTER VALLEY-WILLITS 4/5 RPR GRWW | 44610689 | POTTER VALLEY-WILLITS | 004/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.204817 | 39.3719 | ETL.7820 | 40768596 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720380 | Mar | T3NT NN PTER VALEY-WILLITS 4/5 INS MRKW |  | POTTER VALLEY-WILLITS | 004/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.204817 | 39.3719 | ETL.7820 | 40768596 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720381 | Mar | DI ATASCADERO-CAYUCOS 2/20 RPR GYWW |  | ATASCADERO-CAYUCOS | 002/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-22 | 2021-06-22 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319791 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720392 | Q2 | EI OLEUM-G #1 007/049 RPR FOND |  | OLEUM-G #1 | 007/049 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-05 | 2021-09-05 |  |  | 2021-04-02 | 2021-03-29 | [5 empty] | Central | WSIP | [6 empty] | '-122.267964 | 37.958 | ETL.3150 | 40869893 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720414 | Q2 | T3 DI SLT SPRNGS-TGR CRK 16/124 RPL INSS | 31526474 | SALT SPRINGS-TIGER CREEK | 016/124 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.486697 | 38.4497 | ETL.3500 | 40772691 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 17 | BLM | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720712 | Not Scheduled | T3 NN CARIBOU-PALERMO :037/303 RPL INSS |  | CARIBOU-PALERMO | :037/303 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.490301 | 39.6782 | ETL.3190 | 41082472 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720720 | Mar | T3 NN MORG-SAN LEANDR #1 3/25 BENT STEEL | 44303861 | MORAGA-SAN LEANDRO #1 | 003/025 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.134013 | 37.8074 | ETL.2770 | 40764480 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720721 | Not Scheduled | T3 NN TIGER CREEK-ELECTRA 4/33 RPL INSS | 31526473 | TIGER CREEK-ELECTRA | 004/033 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.560224 | 38.4303 | ETL.5780 | 40683719 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720722 | Mar | T3 NN TIGER CREEK-ELECTRA 4/33 RMV STEP |  | TIGER CREEK-ELECTRA | 004/033 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 |  |  | 2021-03-09 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.560128 | 38.4299 | ETL.5780 | 40654405 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720727 | Q2 | T3NT NN FULTON-PUEBLO 19/89 MASTIC | 44306536 | FULTON-PUEBLO | 019/089 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-27 | 2022-07-27 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.340086 | 38.5016 | ETL.1600 | 40858402 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720754 | Not Scheduled | T2 DI CARIBOU-PALERMO 011/095 RPR GYWS |  | CARIBOU-PALERMO | 011/095 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.518138 | 39.6146 | ETL.3190 | 40755509 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720764 | Not Scheduled | T3 NN SALMON CREEK TAP 000/006 RPR GYWW |  | SALMON CREEK TAP | 000/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.121548 | 38.4696 | ETL.6981 | 40821297 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720766 | Q2 | T3NT NN EL RCK-FLTN-SLVRD 11/49 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 011/049 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-27 | 2022-07-27 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.7184 | 38.5836 | ETL.4392 | 41129351 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720822 | Q2 | T3NT NN GRN VLY-PAL SWT 11/103 RMV BUTT | 44487364 | GREEN VALLEY-PAUL SWEET | 011/103 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-27 | 2022-07-27 |  |  | 2021-06-08 | 2021-06-07 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.918551 | 37.0102 | ETL.1730 | 40876809 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 19 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720826 | Not Scheduled | T2 NN CARIBOU-PALERMO :003/023 RPL INSS |  | CARIBOU-PALERMO | :003/023 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-08 | 2021-07-27 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40920006 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720835 | Mar | T3 NN CORTNA-MENDOCNO #1 20/95 RMV STEP | 44238817 | CORTINA-MENDOCINO #1 | 020/095 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.556036 | 39.0036 | ETL.1330 | 40764805 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720845 | Mar | T3 NN GEYSERS #3-CLOVERDALE 5/65 RPL PL | 31513327 | GEYSERS #3-CLOVERDALE | 005/065 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.910828 | 38.8159 | ETL.1650 | 40826581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720848 | Mar | T2 NN CORTINA-MENDCNO #1 58/284 RPR STRT |  | CORTINA-MENDOCINO #1 | 058/284 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.147742 | 39.2368 | ETL.1330 | 40762067 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720857 | Q2 | T3 NN SBRNT-GRZZY-CLMT #1 4/38D RPR FOND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/038D | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.187064 | 37.8555 | ETL.3740 | 44188760 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720865 | Mar | T3 NN GEYSERS #3-CLVRDAL 10/116 RPR GYWW |  | GEYSERS #3-CLOVERDALE | 010/116 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.981734 | 38.8008 | ETL.1650 | 40584963 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720866 | Mar | T3 NN GEYSERS #3-CLVRDL 9/106A RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 009/106A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-01-28 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.965816 | 38.7961 | ETL.1650 | 44298418 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720870 | Feb | T3 NN CORTNA-MENDOCNO #1 19/91A RPR GYWW | 44563301 | CORTINA-MENDOCINO #1 | 019/091A | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-02-18 | 2021-02-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.542931 | 39.0039 | ETL.1330 | 44645378 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720871 | Q2 | T3 NN WST PNT-VLLY SPRNGS 5/60 RPR STRW |  | WEST POINT-VALLEY SPRINGS | 005/060 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-01-28 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.626494 | 38.3949 | ETL.8350 | 40643817 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119720873 | Q2 | T2 NN WOODLEAF-PALERM 016/163 RPR JUMPER |  | WOODLEAF-PALERMO | 016/163 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.473545 | 39.4761 | ETL.4220 | 44838023 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721010 | Mar | T3 NN DRM-GRSS VLLY-WMR 4/117 RPR SPLW | 44470858 | DRUM-GRASS VALLEY-WEIMAR | 004/117 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.808509 | 39.2151 | ETL.6760 | 40598581 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721018 | Feb | T2 NN COLGATE-GRASS VALLEY 1/27 RPR SPLW | 44470854 | COLGATE-GRASS VALLEY | 001/027 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.170292 | 39.3249 | ETL.6490 | 40760670 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721114 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 24/660 RPR SPLW | 44470852 | COLGATE-ALLEGHANY | 024/660 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.846811 | 39.4686 | ETL.6470 | 40874834 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721155 | Feb | T3 NN BOTTLE RCK TAP D.W.R. 0/3 RPR FOND | 44611370 | BOTTLE ROCK TAP D.W.R. | 000/003 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-01-27 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.77372 | 38.8325 | ETL.4771 | 40650466 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721157 | Not Scheduled | T2 NN MENDOCINO-REDBUD 058/286 RPLC INSS | 31530110 | MENDOCINO-REDBUD | 058/286 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.160898 | 39.2412 | ETL.2410 | 40835539 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721158 | Mar | T2 NN CORTINA-MENDO #1 058/286 RPL HRDT |  | CORTINA-MENDOCINO #1 | 058/286 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.160942 | 39.2413 | ETL.1330 | 40808947 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721230 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 15/408 RPR IBWW | 44470852 | COLGATE-ALLEGHANY | 015/408 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.993171 | 39.4456 | ETL.6470 | 40898089 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721232 | Not Scheduled | T3 NN FULTON-PUEBLO 040/204 RPL INSS | 31505500 | FULTON-PUEBLO | 040/204 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.705202 | 38.4966 | ETL.1600 | 40792680 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721233 | Q2 | DI ELK-GUALALA 040/000 RPL BOND | 44610591 | ELK-GUALALA | 040/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-04 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.695795 | 39.0884 | ETL.8410 | 44743355 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721292 | Q2 | T3 NN TASSAJARA-NEWARK 8/40 RPL INSS | 31529881 | TASSAJARA-NEWARK | 008/040 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-05-20 | 2021-05-19 |  | Work calls for different Structure number |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.995803 | 37.7067 | ETL.5920 | 40774648 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721326 | Mar | T2 NN CORTINA-MNDOCNO #1 20/99 RPL HRDT | 44238817 | CORTINA-MENDOCINO #1 | 020/099 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-07-29 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.576803 | 39.0052 | ETL.1330 | 40870081 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721327 | Mar | T2 NN CORTINA-MNDOCNO #1 20/99 MASTIC | 44238817 | CORTINA-MENDOCINO #1 | 020/099 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-29 | 2022-07-29 |  |  | 2021-03-19 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.576803 | 39.0052 | ETL.1330 | 40870081 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721329 | Q2 | T3 NN SNTH LE-HF MN BY ?009/002 RPR GYWW | 44621945 | SNEATH LANE-HALF MOON BAY | ?009/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.4242 | 37.5054 | ETL.7212 | 40674743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 32 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721381 | Not Scheduled | DI SN LUIS OBIPO-CAYUCOS 12/110 RPR GYWW |  | SAN LUIS OBISPO-CAYUCOS | 012/110 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-01 | 2021-05-01 | [8 empty] | <90D | South | WSIP | [6 empty] | '-120.761571 | 35.3206 | ETL.9090 | 44565360 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721386 | Mar | T3 NN PARKWAY-MORAGA 19/106 RPL INSS | 31526488 | PARKWAY-MORAGA | 019/106 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.216111 | 37.8863 | ETL.5930 | 40617637 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721390 | Mar | T3 DI CARIBOU-TABLE MTN 43/314 INST DAMS |  | CARIBOU-TABLE MTN | 043/314 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-02-26 |  |  | 2021-03-11 | 2021-03-11 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.507434 | 39.7029 | ETL.4440 | 40762735 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721395 | Q4 | DI KESWICK-TRINITY 13/167 RPR CNDS |  | KESWICK-TRINITY | 013/167 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-02 | 2021-09-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.646024 | 40.6976 | ETL.7270 | 44649569 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721403 | Q2 | T2 NN ELK-GUALALA 065/007 REFRAME | 31506142 | ELK-GUALALA | 065/007 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.527479 | 38.7948 | ETL.8410 | 40825508 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721432 | Mar | T2 NN COLEMAN-RED BLUFF 006/117 RPL STRW | 31513407 | COLEMAN-RED BLUFF | 006/117 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-07-30 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.128435 | 40.308 | ETL.6440 | 41144150 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-11-23 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721434 | Not Scheduled | T3 NN BTTLE RCK TAP D.W.R. 0/1 RPR STRT |  | BOTTLE ROCK TAP D.W.R. | 000/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.770626 | 38.8335 | ETL.4771 | 40586476 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721443 | Q3 | T3 NN DONNELLS-MI-WUK 12/8 RPR GYWW | 44623625 | DONNELLS-CURTIS | 012/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.143302 | 38.1048 | ETL.1400 | 44986665 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721444 | Q3 | T3NT NN DONNELLS-MI-WUK 12/8 RMV BUTT | 44623626 | DONNELLS-CURTIS | 012/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-28 | 2022-07-28 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.143302 | 38.1048 | ETL.1400 | 44986665 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721458 | Mar | T3 NN GYSRS-CLVRDL 9/108 RPL STRW | 31513327 | GEYSERS #3-CLOVERDALE | 009/108 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.970229 | 38.8003 | ETL.1650 | 40648819 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721500 | Before Feb | T3 NN GEYSERS #12-FUL 3/018 RPL INSS | 31505663 | GEYSERS #12-FULTON | 003/018 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 | 2021-01-25 | 2021-01-28 | 2021-01-28 | 2021-01-25 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76184 | 38.7624 | ETL.4750 | 40680350 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721510 | Mar | T3NT NN CRTINA-MENDOCINO #1 19/91 MASTIC | 44238817 | CORTINA-MENDOCINO #1 | 019/091 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-29 | 2022-01-29 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.54292 | 39.0037 | ETL.1330 | 40584915 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721512 | Mar | T3 NN CRTINA-MENDOCN #1 19/91 BENT STEEL | 44238817 | CORTINA-MENDOCINO #1 | 019/091 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.54292 | 39.0037 | ETL.1330 | 40584915 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721514 | Q2 | T3 NN KONOCTI-EAGLE ROCK 7/4 RPR STRW | 44610613 | KONOCTI-EAGLE ROCK | 007/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-05-07 | 2021-05-07 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.766988 | 38.9087 | ETL.6861 | 40750921 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721554 | Not Scheduled | T2 DI WOODLEAF-PALERMO 006/057 CANCEL | 31513416 | WOODLEAF-PALERMO | 006/057 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.31709 | 39.539 | ETL.4220 | 44923876 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721559 | Mar | T3 NN MORAGA-SN LEADR #1 4/33 BENT STEEL | 44303861 | MORAGA-SAN LEANDRO #1 | 004/033 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-01-29 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.127977 | 37.7936 | ETL.2770 | 40644209 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721590 | Q2 | T2 NN FORT RSS-GUALALA 34/3 WASH INSW |  | GUALALA-MONTE RIO | 034/003 | ICD | E | 2020_(2) High fire spread TD |  | 2020-07-29 | 2021-07-29 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.290991 | 38.579 | ETL.6980 | 40699242 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721616 | Mar | DI SBRNT-GRZZLY-CLRMNT #2 A3/17 RPR INSS | 44620191 | SOBRANTE-GRIZLY-CLARMNT #2+ | A003/017 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | Central | WSIP | [6 empty] | '-122.242557 | 37.8758 | ETL.3750 | 40829907 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721617 | Q2 | DI MORRO BAY-TEMPLETON 14/58 RPL HRDT | 44490871 | MORRO BAY-TEMPLETON | 014/058 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 |  |  | 2021-04-15 | 2021-04-01 | [5 empty] | South | WSIP | [6 empty] | '-120.7045 | 35.5284 | ETL.5933 | 40863301 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721690 | Q3 | DI GATES-MUSTANG SW STA #1 8/35 BENT STL | 44490873 | SPARE T-LINE RECORD | 008/035 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-31 | 2021-07-31 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.996272 | 36.1944 | ETL.2604 | 40761657 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119721696 | Not Scheduled | T3 NN PIT #1-COTTONWD 30/252 BENT STL |  | PIT #1-COTTONWOOD | 030/252 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-01-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.969717 | 40.7542 | ETL.5390 | 40677365 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721730 | Q2 | T3NT NN FULTON-LAKEVILLE 35/150 RPR FOND | 44636937 | FULTON-LAKEVILLE | 035/150 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-29 | 2022-07-29 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592317 | 38.368 | ETL.4950 | 40812169 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721783 | Q3 | T3 NN BEARDSLEY TAP 000/003 RPL INSW | 31513593 | BEARDSLEY TAP | 000/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-09-04 | 2021-09-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.072756 | 38.2019 | ETL.1401 | 40670212 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721801 | Not Scheduled | T3 NN ATSCDRO CYUCOS 5/46 REFRAME | 31513592 | ATASCADERO-CAYUCOS | 005/046 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.759628 | 35.4628 | ETL.8480 | 40660691 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119721919 | Mar | T3 NN SAN RAMON-MORAGA 014/065 RPL INSS | 31526414 | SAN RAMON-MORAGA | 014/065 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-03-19 | 2021-03-19 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.088967 | 37.774 | ETL.5660 | 40691033 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722479 | Not Scheduled | T2 NN COLEMAN-RED BLUFF 7/127 CANCEL |  | COLEMAN-RED BLUFF | 007/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2021-07-31 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.130752 | 40.2999 | ETL.6440 | 44927786 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722502 | Q4 | T3 NN DRUM-RIO OSO #1 9/91 RPLC INSS | 31505600 | DRUM-RIO OSO #1 | 009/091 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-31 | 2021-01-31 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1420 | 44337145 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722503 | Q4 | DI DRUM-RIO OSO #1 9/91 RMV DEBRIS | 44470665 | DRUM-RIO OSO #1 | 009/091 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-31 | 2022-07-31 |  |  | 2021-12-31 | 2021-04-01 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1420 | 44337062 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722521 | Q4 | T3 NN MDDL FRK-GLD HLL 13/106C RPL DAMS | 44470924 | MIDDLE FORK-GOLD HILL | 013/106C | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.794694 | 38.9608 | ETL.5140 | 40820689 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722523 | Q2 | T2 NN ELK-GUALALA 065/002 RPL STRW | 31513488 | ELK-GUALALA | 065/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-08-04 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.530769 | 38.7997 | ETL.8410 | 40684567 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722529 | Mar | T3NT NN DRM-GRS VLLY WMR 2/54 RMV PL BUT | 44476904 | DRUM-GRASS VALLEY-WEIMAR | 002/054 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-04 | 2022-08-04 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.775766 | 39.2364 | ETL.6760 | 40611206 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722531 | Q2 | DI SN LS OBISPO-OCEANO 16/80 RMV BUTT |  | SAN LUIS OBISPO-OCEANO | 016/080 | ICW | E | 2020_(3) On high spread structure |  | 2020-08-03 | 2021-08-03 | 2021-03-08 | 2021-03-11 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.523056 | 35.0979 | ETL.3530 | 40809745 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722533 | Not Scheduled | T3 NN FULTON-CALISTOGA 6/0 RPL POLE | 31513779 | FULTON-CALISTOGA | 006/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.505916 | 38.5661 | ETL.6880 | 40588911 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722534 | Q2 | T3 NN GRN VLY-PL SWT 10/100 RPL DAMPERS | 44497630 | GREEN VALLEY-PAUL SWEET | 010/100 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-06-08 | 2021-06-07 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.910484 | 37.0066 | ETL.1730 | 42567573 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 19 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722536 | Q2 | T3NT NN GRN VLY-PL SWT 10/100 RMV PL BUT | 44497630 | GREEN VALLEY-PAUL SWEET | 010/100 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-03 | 2022-08-03 |  |  | 2021-06-08 | 2021-06-07 |  |  |  | TR3 |  | South | WSIP | [8 empty] | ETL.1730 | 44413420 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 21 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722537 | Not Scheduled | T2 NN SN LS OBISPO-CYCS 13/126 RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 013/126 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-03 | 2021-08-03 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.788071 | 35.3401 | ETL.9090 | 40602381 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722558 | Mar | DI ATASCADERO-CAYUCOS 2/20 RPR GYWW |  | ATASCADERO-CAYUCOS | 002/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-07 | 2021-09-07 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319792 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722559 | Mar | DI ATASCADERO-CAYUCOS 2/20 RPR GYWW |  | ATASCADERO-CAYUCOS | 002/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-07 | 2021-09-07 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319793 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722588 | Mar | T2 NN COLEMAN-RD BLFF 003/055 RPL HRDD |  | COLEMAN-RED BLUFF | 003/055 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-08-04 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.121777 | 40.3584 | ETL.6440 | 44191459 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722589 | Mar | T2 NN COLEMAN-RD BLFF 003/055 RMV BUTT |  | COLEMAN-RED BLUFF | 003/055 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-04 | 2022-08-04 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.121777 | 40.3584 | ETL.6440 | 44191459 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722674 | Q2 | T2 NN ELK-GUALALA 53/3 REPL STEP | 44610596 | ELK-GUALALA | 053/003 | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2022-08-26 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.67801 | 38.9113 | ETL.8410 | 40667865 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722677 | Q2 | T3 NN FULTON-PUEBLO 29/139 RPR BENT STL | 44306536 | FULTON-PUEBLO | 029/139 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.506514 | 38.4951 | ETL.1600 | 40885434 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722781 | Q2 | T3 NN SBRNT-GRZLY-CLRMNT#2 6/43 BENT STL | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/043 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-02-03 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.209237 | 37.851 | ETL.3750 | 40857800 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722788 | Q2 | T2 NN ELK-GUALALA 55/3 RPR GYWW | 44610591 | ELK-GUALALA | 055/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-03 | 2021-08-03 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.643987 | 38.9051 | ETL.8410 | 40667884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722789 | Not Scheduled | DI BRIDGEVILLE-COTTONWOOD 0/11 INST STEP |  | BRIDGEVILLE-COTTONWOOD | 000/011 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.284625 | 40.3993 | ETL.1110 | 40592755 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722801 | Q2 | T3 NN WEIMAR #1 8/120 RPR INSW | 44476737 | WEIMAR #1 | 008/120 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.854273 | 39.0194 | ETL.7560 | 40630457 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722809 | Q2 | T3 NN IGNACIO-BLNS#1 10/113B RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 010/113 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66228 | 37.9712 | ETL.7140 | 40668093 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722864 | Mar | T3 NN GEYSERS #3-CLVRDL 5/61 RPR PL | 44580896 | GEYSERS #3-CLOVERDALE | 005/061 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.904363 | 38.8155 | ETL.1650 | 44512126 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722866 | Q2 | T3 NN LAURELES-OTTER 6/1 RPLC INSW | 31514039 | LAURELES-OTTER | 006/001 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-06 | 2021-02-06 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.756044 | 36.4213 | ETL.7380 | 44562172 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722868 | Q2 | T3 NN IGNACIO-BOLINAS #1 13/144 RPR STRW | 44640733 | IGNACIO-BOLINAS #1 | 013/144 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.701127 | 37.9424 | ETL.7140 | 40809056 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722872 | Not Scheduled | T3 NN COLGATE-ALLEGHNY 8/217 RPR PL | 44470852 | COLGATE-ALLEGHANY | 008/217 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.056468 | 39.3601 | ETL.6470 | 40824250 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722910 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 5/139 REFRAME | 31513480 | COLGATE-ALLEGHANY | 005/139 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.098282 | 39.3339 | ETL.6470 | 40602495 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722912 | Not Scheduled | T3 NN MDL FRK-GLD HL 31/228 RPR FOND | 44470927 | MIDDLE FORK-GOLD HILL | 031/228 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.980484 | 38.7568 | ETL.5140 | 44690709 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722932 | Not Scheduled | T3NT NN DRUM-SUMMIT #1 6/72 RMV DEBRIS | 44470667 | DRUM-SUMMIT #1 | 006/072 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-06 | 2022-08-06 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.685722 | 39.3042 | ETL.1440 | 40590098 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722934 | Mar | T2 NN KILARC-DESCHUTES 19/405 RPR ANCW | 31510881 | KILARC-DESCHUTES | 019/405 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.180084 | 40.5638 | ETL.7300 | 40770407 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722935 | Mar | T2 NN KILARC-DESCHUTES 19/405 REFRAME | 31510881 | KILARC-DESCHUTES | 019/405 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-08-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.180084 | 40.5638 | ETL.7300 | 40770407 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722951 | Not Scheduled | T3 NN CRESTA-RIO OSO 20/159 RPR FOND |  | CRESTA-RIO OSO | 020/159 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-06 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.486135 | 39.6867 | ETL.4590 | 40910171 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722954 | Q2 | T3 NN METCALF-GRN VLY 20/148 REFRAME | 31513719 | METCALF-GREEN VALLEY | 020/148 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-27 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.72007 | 36.9927 | ETL.2540 | 44551409 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722958 | Q2 | T3 NN VOLTA-DESCHUTES 3/73 REFRAME |  | VOLTA-DESCHUTES | 003/073 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.927898 | 40.4749 | ETL.8290 | 40825122 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-23 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722959 | Q2 | DI SNTH LN-HLF MN BY ?10/8 RPL STRW | 31513802 | SNEATH LANE-HALF MOON BAY | ?010/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [8 empty] | ETL.7212 | 44384414 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722966 | Mar | T3 NN MORGA-SAN LEANDRO #3 6/46 BENT STL |  | MORAGA-SAN LEANDRO #3 | 006/046 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-04 | 2021-02-04 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.114652 | 37.7613 | ETL.2790 | 40804670 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119722991 | Feb | T2 NN COLGATE-GRS VLY 10/235 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 010/235 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-08-07 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079725 | 39.2348 | ETL.6490 | 40768374 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723020 | Mar | T3 NN DRUM-HIGGINS 7/73 RPLC INSS | 31506971 | DRUM-HIGGINS | 007/073 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-02-11 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.86153 | 39.1863 | ETL.4393 | 40678248 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723028 | Not Scheduled | DI DRUM-SUMMIT #1 0/12 RMV DEBRIS | 44476843 | DRUM-SUMMIT #1 | 000/012 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2022-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.749944 | 39.2536 | ETL.1440 | 44338099 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119723029 | Not Scheduled | DI DRUM-SUMMIT #1 0/12 INST MRKW | 44476843 | DRUM-SUMMIT #1 | 000/012 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2022-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.749944 | 39.2536 | ETL.1440 | 44338100 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119723039 | Not Scheduled | T2NT DI CARIBOU-PALERMO :3/22 INS MRKS |  | CARIBOU-PALERMO | :003/022 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-28 | 2022-07-28 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40910266 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723041 | Not Scheduled | T3 DI CLGTE-ALLGHANY 021/569 RPL PL | 31513410 | COLGATE-ALLEGHANY | 021/569 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8904 | 39.4674 | ETL.6470 | 40658316 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723045 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 004/126 RPR INSW | 44470852 | COLGATE-ALLEGHANY | 004/126 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-02-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.104695 | 39.3303 | ETL.6470 | 44918019 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723051 | Not Scheduled | DI DRUM-SUMMIT #2 4/53L CANCEL | 44477051 | DRUM-SUMMIT #2 | 004/053 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-11 | 2022-08-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.705703 | 39.2908 | ETL.1450 | 44549891 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119723059 | Q3 | T2 NN CARIBOU-PLUMAS JCT 1/8B RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 001/008B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-08-11 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.121552 | 40.0766 | ETL.6290 | 42721898 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723071 | Q4 | T2NT NN KESWICK-TRINTY 29/494 RPL HRDS |  | KESWICK-TRINITY | 029/494 | ICW | F | 2020_(2) High fire spread TD |  | 2020-08-11 | 2022-08-11 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.906308 | 40.7112 | ETL.7270 | 44164736 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723074 | Q2 | T3 NN WEIMAR #1 6/92 RPR JUMPRW | 44476737 | WEIMAR #1 | 006/092 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-02-11 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.884519 | 39.0188 | ETL.7560 | 44842008 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723085 | Not Scheduled | T3 NN MIDDLEFORK #1 009/131 RPR GYWW | 44470923 | MIDDLE FORK #1 | 009/131 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-02-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.742392 | 39.0065 | ETL.8405 | 40755573 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723087 | Not Scheduled | T3 NN MIDDLEFORK #1 000/003 REFRAME | 31513482 | MIDDLE FORK #1 | 000/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-02-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597278 | 39.0228 | ETL.8405 | 40664811 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723104 | Q2 | T3 NN GEYSERS #12-FUL 10/046 RPR STRT |  | GEYSERS #12-FULTON | 010/046 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2021-02-10 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761503 | 38.7052 | ETL.4750 | 40814640 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723109 | Feb | T2 NN JOLON TAP 15/210 RPR INSW | 44578863 | JOLON TAP | 015/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.171271 | 36.0231 | ETL.7321 | 44212751 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723120 | Feb | T3 NN DRUM-HIGGINS 11/108 RPL STRW | 31522721 | DRUM-HIGGINS | 011/108 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.918022 | 39.1758 | ETL.4393 | 44172301 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723140 | Feb | T2 NN JOLON TAP 15/210 RPR GYWW | 44575318 | JOLON TAP | 015/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.171271 | 36.0231 | ETL.7321 | 44212737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723147 | Q4 | T2 NN MAPLE CREEK-HOOPA 8/3C RPR STRW | 44461912 | MAPLE CREEK-HOOPA | 008/003C | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-10 | 2022-08-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.80311 | 40.8638 | ETL.7490 | 44735712 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723174 | Q2 | T3 NN LAURELES-OTTER 013/009 RPL PL | 31516075 | LAURELES-OTTER | 013/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-02-04 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.86538 | 36.3871 | ETL.7380 | 40876413 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723179 | Q3 | T3 NN DONNELLS-MI-WUK 8/2 RPR GYWW | 44623627 | DONNELLS-CURTIS | 008/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-02-05 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.104351 | 38.1602 | ETL.1400 | 40656086 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723191 | Q2 | T2 NN BRIDGEVILLE-CTNWD 12/112 RPR SHLW | 44404807 | BRIDGEVILLE-COTTONWOOD | 012/112 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.496241 | 40.3913 | ETL.1110 | 40617830 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723192 | Not Scheduled | T3 NN MORRO BAY-TEMPLETON 11/44 RPR SHLW |  | MORRO BAY-GATES #2 | 011/044 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-03 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.735786 | 35.4912 | ETL.5280 | 44775827 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723202 | Not Scheduled | T2 DI SPAULDING-SUMMT 18/580 RMV PL STUB | 44470932 | SPAULDING-SUMMIT | 018/580 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.343285 | 39.3089 | ETL.8060 | 40826229 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723300 | Mar | T2 NN KILARC-DESCHUTES 000/016 REFRAME | 31510881 | KILARC-DESCHUTES | 000/016 | 93E | E | 2020_(2) High fire spread TD |  | 2020-08-11 | 2021-08-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.874796 | 40.6675 | ETL.7300 | 40816207 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723357 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 4/124 RPR WDPKR | 44470852 | COLGATE-ALLEGHANY | 004/124 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.105697 | 39.3297 | ETL.6470 | 44398580 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723401 | Not Scheduled | T3 NN FULTON-PUEBLO 037/191A RPL INSS | 31505500 | FULTON-PUEBLO | 037/191A | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.667641 | 38.497 | ETL.1600 | 40576009 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723404 | Not Scheduled | T3 NN FULTON-PUEBLO 41/211 RPL INSS | 31505500 | FULTON-PUEBLO | 041/211 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.72589 | 38.4965 | ETL.1600 | 40609144 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723406 | Q2 | T2 NN TRINITY-MAPLE CREEK 8/8 RPR INSW | 44453151 | TRINITY-MAPLE CREEK | 008/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 40916038 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723444 | Mar | T3 NN POE-RIO OSO 19/131 RPL INSS | 31454862 | POE-RIO OSO | 019/131 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-02-07 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483203 | 39.7085 | ETL.5540 | 40615879 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723446 | Not Scheduled | T2 NN VLY SPGS-MRTL #1 9/3 RPL POLE | 31514492 | VALLEY SPRINGS-MARTELL #1 | 009/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.77156 | 38.3188 | ETL.8240 | 40653541 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723483 | Q2 | T3 NN DRM-SPLDING 001/041 RPL POLE | 31529084 | DRUM-SPAULDING | 001/041 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-07 | 2021-02-07 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.742135 | 39.2591 | ETL.6770 | 40770252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723484 | Q2 | T3 NN DRM-SPLDING 001/041 RMV PL BUTT | 44470666 | DRUM-SPAULDING | 001/041 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-07 | 2022-08-07 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.742135 | 39.2591 | ETL.6770 | 40770252 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723735 | Feb | T3 NN DESABLA-CENTERVILLE 5/68 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 005/068 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.654434 | 39.7938 | ETL.6720 | 44324218 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723743 | Q2 | T2 NN ELK-GUALALA 53/8 RPLC INSW | 31506140 | ELK-GUALALA | 053/008 | 93I | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-08-04 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.669302 | 38.9077 | ETL.8410 | 44387654 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723937 | Q2 | T3 NN WEIMAR #1 5/67C RPR GYWW | 44476737 | WEIMAR #1 | 005/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.915675 | 39.0193 | ETL.7560 | 44923837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119723956 | Q2 | EI LOS BANOS-MIDWAY #2 84/354 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 084/354 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.089673 | 36.1014 | ETL.6010 | 40762426 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119723957 | Q2 | EI LOS BANOS-MIDWAY #2 84/354 RPR ANCS | 44507430 | LOS BANOS-MIDWAY #2 | 084/354 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.089673 | 36.1014 | ETL.6010 | 40762426 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119723964 | Q2 | EI LOS BANOS-MIDWAY #2 84/352 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 084/352 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.094809 | 36.1074 | ETL.6010 | 40664838 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119723990 | Feb | T2 NN COLGATE-GRASS VLLY 12/296 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 012/296 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-08-05 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.072508 | 39.208 | ETL.6490 | 40874476 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119724095 | Q2 | EI LOS BANOS-MIDWAY #2 84/353 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 084/353 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.092359 | 36.1046 | ETL.6010 | 40651959 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119724168 | Not Scheduled | T3 COLGATE-ALLEGHANY 16/447 RPL POLE | 31514049 | COLGATE-ALLEGHANY | 016/447 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.966831 | 39.4486 | ETL.6470 | 40874708 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119724170 | Not Scheduled | T3 COLGATE-ALLEGHANY 9/262 RPL POLE | 31514049 | COLGATE-ALLEGHANY | 009/262 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-06 | 2021-03-06 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.037237 | 39.3772 | ETL.6470 | 40767334 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119724175 | Not Scheduled | T3 COLGATE-ALLEGHANY 16/444 RPL POLE | 31514049 | COLGATE-ALLEGHANY | 016/444 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-06 | 2021-03-06 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.968691 | 39.4483 | ETL.6470 | 40760445 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119724202 | Q2 | T3 NN DRUM-HIGGINS 003/042A RMV STEPS | 44470859 | DRUM-HIGGINS | 003/042A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-05 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817539 | 39.2191 | ETL.4393 | 44313912 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119724206 | Mar | T2 NN KILARC-DESCHUTES 9/195 RMV BUTT | 44406470 | KILARC-DESCHUTES | 009/195 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-05 | 2021-08-05 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.996602 | 40.5865 | ETL.7300 | 40617788 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119724331 | Q2 | EI LOS BANOS-MIDWAY #2 85/356 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 085/356 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.084162 | 36.0949 | ETL.6010 | 40812172 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119724688 | Q2 | EI LOS BANOS-MIDWAY #2 85/359 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 085/359 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.076571 | 36.086 | ETL.6010 | 40863676 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119724722 | Q2 | EI LOS BANOS-MIDWAY #2 85/359 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 085/359 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.076571 | 36.086 | ETL.6010 | 40863676 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119725138 | Not Scheduled | T2 EI VACA-VACAVILE-JMSN 98/63 RPL TOWER | 31528997 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/063 | 70S | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-09-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.032541 | 38.3394 | ETL.4100 | 40765438 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119725209 | Q2 | EI LOS BANOS-MIDWAY #2 86/361 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 086/361 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.071124 | 36.0796 | ETL.6010 | 40587766 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119725552 | Not Scheduled | DI DRUM-SUMMIT #2 11/138 RPR GYWW | 44477258 | DRUM-SUMMIT #2 | 011/138 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565766 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119725555 | Not Scheduled | DI DRUM-SUMMIT #2 11/138 RPR GYWW | 44477258 | DRUM-SUMMIT #2 | 011/138 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565795 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119725557 | Not Scheduled | DI DRUM-SUMMIT #2 11/138 RPR GYWW | 44477258 | DRUM-SUMMIT #2 | 011/138 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2021-08-12 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565756 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119725876 | Q2 | EI LOS BANOS-MIDWAY #2 86/363 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 086/363 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.065659 | 36.0732 | ETL.6010 | 40651962 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119725977 | Q2 | DI TRINITY-MAPLE CREEK 26/8 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 026/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-08-12 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8170 | 44420635 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119726023 | Q2 | DI TRINITY-MAPLE CREEK 26/8 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 026/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-08-12 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8170 | 44420637 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119726369 | Q3 | T2 NN CARIBOU-WESTWOOD 4/89 RPL DAMW |  | CARIBOU-WESTWOOD | 004/089 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.118283 | 40.1402 | ETL.6300 | 44191083 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119726435 | Q2 | LOS BANOS-MIDWAY #2 81/342 INST HRDT | 44507430 | LOS BANOS-MIDWAY #2 | 081/342 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.11988 | 36.1343 | ETL.6010 | 40680421 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119726436 | Not Scheduled | T2 NN SAN LUS OBSPO-CAYUCS 7/48 RPR CNDW |  | SAN LUIS OBISPO-CAYUCOS | 007/048 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.675618 | 35.316 | ETL.9090 | 40588961 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119726728 | Q2 | EI LOS BANOS-MIDWAY #2 88/368 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 088/368 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.053697 | 36.061 | ETL.6010 | 40870072 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119726786 | Not Scheduled | T3 NN COLGATE-ALLEGHANY 010/270 RPR STRW | 44473097 | COLGATE-ALLEGHANY | 010/270 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.035301 | 39.3819 | ETL.6470 | 40766596 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119726877 | Q2 | EI LOS BANOS-MIDWAY #2 88/369 RPR FOND | 44490736 | LOS BANOS-MIDWAY #2 | 088/369 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.051019 | 36.0588 | ETL.6010 | 40863678 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119727048 | Q2 | EI LOS BANOS-MIDWAY #2 88/371 RMV NEST | 44507430 | LOS BANOS-MIDWAY #2 | 088/371 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.045542 | 36.0546 | ETL.6010 | 40587767 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119727174 | Q2 | EI VC-VCVLL-JAMSON-NORTH 23/164 RPR FOND | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/164 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-09-08 |  |  | 2021-06-04 | 2021-06-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.174094 | 38.138 | ETL.4100 | 40683355 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727211 | Q2 | T2 NN TRINITY-MAPLE CREEK 44/3L RPR GYWW | 44470716 | TRINITY-MAPLE CREEK | 044/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-08-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.697538 | 40.7451 | ETL.8170 | 44565345 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727213 | Q2 | T3 NN TRINITY-MAPLE CREEK 44/3C RPR GYWW | 44470716 | TRINITY-MAPLE CREEK | 044/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-02-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.697538 | 40.7451 | ETL.8170 | 44565358 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727216 | Q2 | T3 NN TRINITY-MAPLE CREEK 44/3R RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 044/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-02-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.697538 | 40.7451 | ETL.8170 | 44565606 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727256 | Q2 | EI VACA-VACA-JAMESON-NTH 24/165 RPR STRT | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 024/165 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-04 | 2021-09-04 |  |  | 2021-06-04 | 2021-06-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.176381 | 38.1345 | ETL.4100 | 40644302 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727283 | Not Scheduled | EI VC-VCVLL-JAMN-NRTH 23/164 RPL HRDT | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/164 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-09-08 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.174094 | 38.138 | ETL.4100 | 40683355 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727301 | Not Scheduled | EI VC-VCVL-JMSN-NORTH 23/164 RPL HNGR PL | 44611131 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/164 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-09-08 | 2021-03-16 | 2021-03-16 | [7 empty] | North Coast | WSIP | [6 empty] | '-122.174107 | 38.138 | ETL.4100 | 40725777 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727713 | Mar | T3 DI MORAGA-OAKLAND #3 002/022 RPL INSS |  | MORAGA-OAKLAND #3 | 002/022 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-03-04 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.202856 | 37.8257 | ETL.2740 | 40704848 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-09-21 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727743 | Q2 | T2 DI SLNS-LRLS-LRLS 8/191 BOND GYWW | 44610150 | SALINAS-LAURELES | 008/191 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.710973 | 36.5883 | ETL.7930 | 40824185 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727917 | Not Scheduled | T3 DI CLGTE-AALLGHNY 009/245 REFRAM PL | 31513497 | COLGATE-ALLEGHANY | 009/245 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.041755 | 39.3697 | ETL.6470 | 40823275 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119727919 | Not Scheduled | DI COLGATE-ALLEGHANY 012/335 RMV PL BUT | 44470935 | COLGATE-ALLEGHANY | 012/335 | ICW | F | 2020_(1a) PSPS |  | 2020-09-08 | 2022-09-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.014813 | 39.415 | ETL.6470 | 40664618 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119728064 | Not Scheduled | T2 DI CLGTE-SMRTVILE#2 2/26 RMV PL BUTT | 44470855 | COLGATE-SMARTVILLE #2 | 002/026 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-08 | 2021-09-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.223185 | 39.3183 | ETL.6520 | 40594294 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119728073 | Not Scheduled | EI VC-VCVLL-JMSN-NRTH 23/162 PRT STRT | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/162 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.170041 | 38.144 | ETL.4100 | 40581672 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119728087 | Not Scheduled | EI VC-VCVLL-JMSN-NORTH 23/162 RPR FOND | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/162 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.170041 | 38.144 | ETL.4100 | 40581672 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119728091 | Mar | T3NT DI DRM-GSS VLY-WMR 1/33 RMV PL BUT | 44470941 | DRUM-GRASS VALLEY-WEIMAR | 001/033 | ICW | F | 2020_(1a) PSPS |  | 2020-09-08 | 2022-09-08 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.764562 | 39.2461 | ETL.6760 | 40598576 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119728093 | Not Scheduled | EI VC-VCVLL-JMSN-NRTH TO 23/161 RPR STRT | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/161 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.169169 | 38.1453 | ETL.4100 | 40864976 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119728101 | Not Scheduled | EI VC-VCVLL-JMSN-NORTH 23/161 RPR FOND | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 023/161 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.169169 | 38.1453 | ETL.4100 | 40864976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119728567 | Q2 | T2 DI BRDGVLLE-COTTONWD 11/105 RPR SHLW | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/105 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.481271 | 40.389 | ETL.1110 | 44423994 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119728577 | Q2 | EI LOS BANOS-MIDWAY #2 90/377 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 090/377 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.023203 | 36.0404 | ETL.6010 | 40811527 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119728617 | Q2 | EI LOS BANOS-MIDWAY #2 91/380 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 091/380 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.01166 | 36.0331 | ETL.6010 | 40592957 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119728681 | Q2 | T2 DI TRINITY-MAPLE CREEK 48/12 RPL POLE | 31512092 | TRINITY-MAPLE CREEK | 048/012 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.773466 | 40.7535 | ETL.8170 | 40701802 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119729004 | Q2 | LOS BANOS-MIDWAY #2 91/383 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 091/383 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.000439 | 36.0261 | ETL.6010 | 40659986 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729054 | Q2 | LOS BANOS-MIDWAY #2 91/383 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 091/383 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.000439 | 36.0261 | ETL.6010 | 40659986 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729057 | Q2 | EI LOS BANOS-MIDWAY #2 92/384 INST HRDT | 44507430 | LOS BANOS-MIDWAY #2 | 092/384 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.99672 | 36.0238 | ETL.6010 | 40753998 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729103 | Q2 | EI LOS BANOS-MIDWAY #2 92/384 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 092/384 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.99672 | 36.0238 | ETL.6010 | 40753998 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729187 | Q2 | EI LOS BANOS-MIDWAY #2 92/386 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 092/386 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.990026 | 36.0196 | ETL.6010 | 40812176 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729203 | Q2 | EI LOS BANOS-MIDWAY #2 92/385 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 092/385 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.993246 | 36.0216 | ETL.6010 | 40765260 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729373 | Q2 | EI LOS BANOS-MIDWAY #2 93/388 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 093/388 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.983152 | 36.015 | ETL.6010 | 40864000 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729374 | Q2 | EI LOS BANOS-MIDWAY #2 93/388 INST HRDT | 44507430 | LOS BANOS-MIDWAY #2 | 093/388 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.983152 | 36.015 | ETL.6010 | 40864000 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729418 | Q2 | EI LOS BANOS-MIDWAY #2 93/389 RPR SHLS | 44507430 | LOS BANOS-MIDWAY #2 | 093/389 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.980089 | 36.0127 | ETL.6010 | 40869314 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729423 | Q2 | EI LOS BANOS-MIDWAY #2 93/389 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 093/389 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.980089 | 36.0127 | ETL.6010 | 40869314 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119729493 | Q2 | LOS BANOS-MIDWAY #2 93/391 BENT STEEL | 44507430 | LOS BANOS-MIDWAY #2 | 093/391 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.973622 | 36.0079 | ETL.6010 | 40587769 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119730046 | Q2 | EI LOS BANOS-MIDWAY #2 94/394 RPR GYWS | 44507430 | LOS BANOS-MIDWAY #2 | 094/394 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.963761 | 36.0019 | ETL.6010 | 40765379 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119730075 | Q2 | EI LOS BANOS-MIDWAY #2 94/395 RPR FOND | 44490736 | LOS BANOS-MIDWAY #2 | 094/395 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.960399 | 35.9996 | ETL.6010 | 40753929 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119730379 | Q2 | LOS BANOS-MIDWAY #2 95/399 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 095/399 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.950164 | 35.9891 | ETL.6010 | 40863682 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119730701 | Q3 | T2 WV CARIBOU #2 9/6 REFRAME | 31426007 | CARIBOU #2 | 009/006 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-09-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.203507 | 40.0136 | ETL.6280 | 40826361 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119730704 | Q2 | EI LOS BANOS-MIDWAY #2 96/402 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 096/402 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.941879 | 35.9796 | ETL.6010 | 40664851 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119730948 | Q2 | EI LOS BANOS-MIDWAY #2 96/403 BENT STEEL | 44507430 | LOS BANOS-MIDWAY #2 | 096/403 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.939247 | 35.9765 | ETL.6010 | 40651963 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119730991 | Q2 | EI LOS BANOS-MIDWAY #2 96/403 RPR GYWS | 44507430 | LOS BANOS-MIDWAY #2 | 096/403 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.939247 | 35.9765 | ETL.6010 | 40651963 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119731039 | Q2 | EI LOS BANOS-MIDWAY #2 97/406 RPR FOND | 44490736 | LOS BANOS-MIDWAY #2 | 097/406 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.931351 | 35.9675 | ETL.6010 | 40812181 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119731043 | Q2 | EI LOS BANOS-MIDWAY #2 97/406 RPR GYWS | 44507430 | LOS BANOS-MIDWAY #2 | 097/406 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.931351 | 35.9675 | ETL.6010 | 40812181 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119731313 | Q2 | EI LOS BANOS-MIDWAY #2 98/411 REGRADE | 44490736 | LOS BANOS-MIDWAY #2 | 098/411 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.918474 | 35.9544 | ETL.6010 | 40587770 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119731343 | Q2 | EI LOS BANOS-MIDWAY #2 98/411 RPR GYWS | 44507430 | LOS BANOS-MIDWAY #2 | 098/411 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.918474 | 35.9544 | ETL.6010 | 40587770 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119731344 | Q2 | EI LOS BANOS-MIDWAY #2 98/411 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 098/411 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.918474 | 35.9544 | ETL.6010 | 40587770 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119740657 | Not Scheduled | EI VC-VCVL-JMSN-NRTH 23/160 RPL INSS |  | VACA-VACAVILLE-JAMESON-NTH TWR | 023/160 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-10 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.1685332 | 38.1463 | ETL.4100 | 40889601 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119740851 | Q2 | EI LOS BANOS-MIDWAY #2 99/413 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 099/413 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.914516 | 35.9491 | ETL.6010 | 40651965 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119740911 | Not Scheduled | T3 DI COLGATE-CHALLNGE 10/178 RPR CNDW | 44473098 | COLGATE-CHALLENGE | 010/178 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.208542 | 39.453 | ETL.6480 | 40824364 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119741639 | Q2 | EI DIABLO-GATES #1 64/265 RPR GYWS |  | DIABLO-GATES #1 | 064/265 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-06-05 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  |  | South | WSIP | [6 empty] | '-120.219834 | 35.9493 | ETL.5960 | 40746856 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119741792 | Q2 | EI LOS BANOS-MIDWAY #2 101/423 INST HRDT | 44490736 | LOS BANOS-MIDWAY #2 | 101/423 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.888724 | 35.9208 | ETL.6010 | 40658739 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119741795 | Q2 | EI DIABLO-GATES #1 64/264 RPR GYWS |  | DIABLO-GATES #1 | 064/264 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-06-05 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  |  | South | WSIP | [6 empty] | '-120.223948 | 35.9459 | ETL.5960 | 40746867 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742112 | Q2 | EI LOS BANOS-MIDWAY #2 101/424 BENT STEE | 44507430 | LOS BANOS-MIDWAY #2 | 101/424 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.885846 | 35.9177 | ETL.6010 | 40754002 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119742217 | Q4 | T3 MIDDLE FORK-GOLD HILL 0/6R RPL POLE | 31454603 | MIDDLE FORK-GOLD HILL | 000/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-08-08 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.598509 | 39.018 | ETL.5140 | 44552437 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742262 | Not Scheduled | T3 MIDDLE FORK-GOLD HILL 0/7R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 000/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-08-08 | 2020-02-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.598701 | 39.017 | ETL.5140 | 44076538 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742269 | Not Scheduled | T3 MIDDLE FORK-GOLD HILL 1/16R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 001/016 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-07-29 | 2020-01-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.606065 | 39.0035 | ETL.5140 | 44951517 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742314 | Q2 | T3 EI EDRD-MSSRI FLT #2 1/11 RPL INSS | 31462723 | ELDORADO-MISSOURI FLAT #2 | 001/011 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-04-01 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638268 | 38.7814 | ETL.1540 | 40618949 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742490 | Q2 | EI DIABLO-GATES #1 64/262 BENT STEEL | 44490734 | DIABLO-GATES #1 | 064/262 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-06-05 | 2021-06-01 | [5 empty] | South | WSIP | [6 empty] | '-120.231341 | 35.9419 | ETL.5960 | 40688638 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742516 | Not Scheduled | DIVIDE-CABRILLO #1 11/136 RPL CONN |  | DIVIDE-CABRILLO #1 | 011/136 | ICM | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 | [9 empty] | South | WSIP | [6 empty] | '-120.45284 | 34.6732 | ETL.1380 | 42574031 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | GDP | Maintenance | Expense | 534 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742642 | Not Scheduled | T3 EI MIDDLE FORK-GLD HILL 3/30L CANCEL | 31421211 | MIDDLE FORK-GOLD HILL | 003/030 | 70Y | E | 2020_(2) High fire spread TD |  | 2018-12-15 | 2019-06-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.636658 | 38.997 | ETL.5140 | 44951515 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742646 | Not Scheduled | T3 EI MIDDLE FORK-GLD HILL 3/30R CANCEL | 31421211 | MIDDLE FORK-GOLD HILL | 003/030 | 70Y | E | 2020_(2) High fire spread TD |  | 2018-12-15 | 2019-06-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.636658 | 38.997 | ETL.5140 | 44951514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742649 | Not Scheduled | T3 MIDDLE FORK-GOLD HILL 3/31R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 003/031 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-08-08 | 2020-02-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.637747 | 38.9965 | ETL.5140 | 44076544 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742712 | Q2 | T2 NN TRINITY-MAPLE CREEK 1/12 RPR STRW | 44295371 | TRINITY-MAPLE CREEK | 001/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-22 | 2021-07-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.958905 | 40.7291 | ETL.8170 | 40906255 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742905 | Q4 | T3 EI MIDDLE FRK-GLD HLL 012/102R RPL PL | 31421211 | MIDDLE FORK-GOLD HILL | 012/102 | 70Y | E | 2020_(2) High fire spread TD |  | 2018-12-26 | 2019-06-26 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.789387 | 38.9637 | ETL.5140 | 44553581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742946 | Q2 | T2 DI IGNACIO-BOLINS#1 0/14 RPL INSW | 31514525 | IGNACIO-BOLINAS #1 | 000/014 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-11 | 2021-07-11 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.557288 | 38.075 | ETL.7140 | 40629566 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742964 | Not Scheduled | T3 EI MIDDLE FRK-GLD HLL 012/104R CANCEL | 31421211 | MIDDLE FORK-GOLD HILL | 012/104 | 70Y | E | 2020_(2) High fire spread TD |  | 2018-12-26 | 2019-06-26 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791779 | 38.9623 | ETL.5140 | 44553608 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119742986 | Q2 | EI LOS BANOS-MIDWAY #2 103/429 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 103/429 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.871872 | 35.903 | ETL.6010 | 40863686 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119743202 | Feb | T2 DI COLGATE-GRS VLY 10/242 RMV BUTT | 44477156 | COLGATE-GRASS VALLEY | 010/242 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-10 | 2022-09-10 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079255 | 39.2316 | ETL.6490 | 40593248 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743208 | Q2 | EI LOS BANOS-MIDWAY #2 99/415 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 099/415 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.910552 | 35.9438 | ETL.6010 | 40760843 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119743251 | Q2 | DI T2 TRINITY-MAPLE CREEK 51/10 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 051/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420683 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743252 | Q2 | T2 NN TRINITY-MAPLE CRK 51/10 RPLC INSW | 31514141 | TRINITY-MAPLE CREEK | 051/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.835351 | 40.7669 | ETL.8170 | 40641471 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743253 | Q2 | T2 FULTON-PUEBLO 11/053 RPR STRT |  | FULTON-PUEBLO | 011/053 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.190927 | 38.51 | ETL.1600 | 40650792 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743257 | Q2 | T2 NN TRINITY-MPLE CRK 51/10 RMV DEBRIS | 44470706 | TRINITY-MAPLE CREEK | 051/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-10 | 2022-09-10 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420683 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743259 | Q2 | T2 NN TRINITY-MAPLE CRK 51/10 RPLC DAMW | 44484765 | TRINITY-MAPLE CREEK | 051/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.835351 | 40.7669 | ETL.8170 | 40641471 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743270 | Not Scheduled | T3 EI MDDL FRK-GLD HLL 19/157R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 019/157 | 70Y | E | 2020_(2) High fire spread TD |  | 2018-12-22 | 2019-06-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.877174 | 38.8893 | ETL.5140 | 44557591 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743273 | Q2 | EI LOS BANOS-MIDWAY #2 103/431 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 103/431 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.866001 | 35.8968 | ETL.6010 | 40587773 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119743464 | Not Scheduled | T2 MIDDLE FORK-GLD HILL 22/178R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 022/178 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-08-07 | 2020-08-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.906157 | 38.857 | ETL.5140 | 44557717 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743466 | Not Scheduled | T2 EI MDLE FRK-GLD HILL 024/188R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 024/188 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.9223 | 38.8411 | ETL.5140 | 44552509 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743523 | Not Scheduled | T2 MIDDLE FORK-GOLD HILL 25/200R CANCEL | 31461248 | MIDDLE FORK-GOLD HILL | 025/200 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-08 | 2020-07-08 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.93596 | 38.8189 | ETL.5140 | 44558362 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743586 | Not Scheduled | T3 EI MIDDLE FORK-GLD H 31/227R CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 031/227 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-06-21 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.979962 | 38.7584 | ETL.5140 | 44565772 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743588 | Not Scheduled | T3 EI MIDDLE FORK-GLD H 31/227C CANCEL | 31454603 | MIDDLE FORK-GOLD HILL | 031/227 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2018-12-21 | 2019-06-21 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.979962 | 38.7584 | ETL.5140 | 44565824 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743640 | Not Scheduled | T3 DI MDDL FRK-GLD HILL 32/234L CANCEL | 31421211 | MIDDLE FORK-GOLD HILL | 032/234 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-01-28 | 2019-07-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.986991 | 38.7439 | ETL.5140 | 44558199 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119743743 | Q2 | EI LOS BANOS-MIDWAY #2 105/437 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 105/437 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.848334 | 35.8781 | ETL.6010 | 40818987 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119743759 | Q2 | EI LOS BANOS-MIDWAY #2 104/436 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 104/436 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.851418 | 35.8814 | ETL.6010 | 40812187 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119743766 | Not Scheduled | T2 TEMBLOR-SAN LUIS OBISPO 35/2 RPL INSS |  | TEMBLOR-SAN LUIS OBISPO | 035/206 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.313548 | 35.3703 | ETL.3960 | 40829438 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119749839 | Q2 | DI WOODLEAF-PALERMO 1/17 RPR STRW |  | WOODLEAF-PALERMO | 001/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-17 | 2021-08-17 |  |  | 2021-04-15 | 2021-04-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.230087 | 39.5584 | ETL.4220 | 44561233 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119750271 | Q2 | DI SLY CREEK TAP 2/22 RPR WDPKR | 44639817 | SLY CREEK TAP | 002/022 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-15 | 2021-04-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.155959 | 39.5587 | ETL.4221 | 44356487 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119750324 | Q4 | T2 NN KESWICK-TRINITY 11/137 RPR STRW |  | KESWICK-TRINITY | 011/137 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.634584 | 40.6766 | ETL.7270 | 40591296 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119750328 | Q2 | EI LOS BANOS-MIDWAY #2 105/438 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 105/438 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.845712 | 35.8754 | ETL.6010 | 40864004 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119750384 | Q3 | EI DONNELLS-MI-WUK 5/3 RPR STRW | 44623628 | DONNELLS-CURTIS | 005/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-12 | 2021-08-12 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.058472 | 38.1801 | ETL.1400 | 44770773 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119750587 | Not Scheduled | I FULTON-HOPLAND 26/8 RPL PL | 31513820 | FULTON-HOPLAND | 026/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-25 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.989765 | 38.806 | ETL.6890 | 40874649 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119750724 | Q3 | EI MIDWAY-WHIRLWIND 23/098 RMV VEG |  | MIDWAY-WHIRLWIND | 023/098 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-09-15 | 2021-09-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.116371 | 35.2434 | ETL.6030 | 40860515 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  | 2020-11-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119750753 | Q3 | EI MIDWAY-WHIRLWIND 24/099 RMV VEG |  | MIDWAY-WHIRLWIND | 024/099 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-09-11 | 2021-09-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.113343 | 35.2405 | ETL.6030 | 40860443 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  | 2020-11-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119750798 | Q2 | T2 EXCHEQUER-INDIAN FLAT 2/13 BENT STEEL | 44490739 | EXCHEQUER-YOSEMITE | 002/013 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-03 | 2021-09-03 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.239428 | 37.5757 | ETL.8650 | 40660801 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119751050 | Q2 | DI CASTRO VLY-NWRK-TWR 1/9 RPR INSS | 31504845 | CASTRO VALLEY-NEWARK | 001/009 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 |  |  | 2021-05-18 | 2021-05-17 | [5 empty] | Central | WSIP | [6 empty] | 122.0424 | 37.6915 | ETL.4450 | 40633217 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119751121 | Q2 | DI HUMBOLDT-BRIDGEVILLE 95/02L RPR SHLW | 44356653 | HUMBOLDT-BRIDGEVILLE | 095/002 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322351 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119751165 | Q3 | T2 BRIDGEVILLE-CTTNWD 80/566L RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 080/566 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.676419 | 40.4747 | ETL.1110 | 44423251 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119751328 | Q2 | T3 NN IGNACIO-BOLINAS #1 11/117 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 011/117 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-11 | 2021-02-11 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.666956 | 37.9657 | ETL.7140 | 44942606 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752014 | Q2 | EI LOS BANOS-MIDWAY #2 108/448 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 108/448 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.816417 | 35.8444 | ETL.6010 | 40870074 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119752165 | Q4 | T3 NN KESWICK-TRINITY 001/025 RPR STRW |  | KESWICK-TRINITY | 001/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.47659 | 40.6186 | ETL.7270 | 40674320 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752283 | Q2 | T2 NN TRINITY-MAPLE CRK 23/003 RPLC STRW | 31514142 | TRINITY-MAPLE CREEK | 023/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.325068 | 40.7052 | ETL.8170 | 40659741 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752285 | Q2 | T3 NN DRUM-SPAULDING 04/104 RPL POLE | 31529084 | DRUM-SPAULDING | 004/104 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.708394 | 39.2868 | ETL.6770 | 40751833 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752318 | Mar | T3 NN PITTSBURG-SAN RAMON 10/40 RPL INSS | 31529490 | PITTSBURG-SAN RAMON | 010/040 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-26 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-121.880807 | 37.9 | ETL.5490 | 40637912 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752344 | Q4 | T3 NN KESWICK-TRINITY 001/025 RPR INSW |  | KESWICK-TRINITY | 001/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.47659 | 40.6186 | ETL.7270 | 40720532 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752482 | Q4 | T3NT NN KESWICK-TRINITY 1/025 RMV PL BUT |  | KESWICK-TRINITY | 001/025 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-13 | 2022-08-13 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.47659 | 40.6186 | ETL.7270 | 40674320 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752633 | Q2 | T2 NN FORT ROSS-GUALALA 29/7 RPR STRW |  | GUALALA-MONTE RIO | 029/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.228204 | 38.5443 | ETL.6980 | 44942621 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752712 | Q3 | T2 NN CARIBOU-WESTWOOD 004/077B RPR GYWW |  | CARIBOU-WESTWOOD | 004/077 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-08-12 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.123968 | 40.1329 | ETL.6300 | 42624216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119752880 | Q2 | T2 NN HAT CRK#1 WSTWD 41/794 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 041/794 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-14 | 2022-08-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.026413 | 40.4992 | ETL.7030 | 40876209 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753079 | Q3 | DI BRDGEVLLE-GRBRVLLE 023/002 RPLC SPLC | 44453320 | BRIDGEVILLE-GARBERVILLE | 023/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-08-28 | 2021-08-23 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.738093 | 40.2128 | ETL.6220 | 44848207 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753107 | Q2 | T3 NN CRESTA RIO OSO 16/135 RMV STEP |  | CRESTA-RIO OSO | 016/135 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-12 | 2021-02-12 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.478901 | 39.7311 | ETL.4590 | 40906786 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753120 | Feb | T2 NN TRINITY-MAPLE CRK 3/6 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 003/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-08-05 | 2021-02-22 | 2021-02-27 | 2021-02-26 | 2021-02-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.988451 | 40.7317 | ETL.8170 | 40906286 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753192 | Q2 | EI LOS BANOS-MIDWAY #2 109/452 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 109/452 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.804476 | 35.8317 | ETL.6010 | 40664868 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119753235 | Q3 | T2 NN BRDGVLLE-CTTNWD 074/534 RPR OPGW | 44398374 | BRIDGEVILLE-COTTONWOOD | 074/534 | ICS | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.576832 | 40.4856 | ETL.1110 | 40676730 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753238 | Feb | DI LAYTONVILLE-COVELO 008/000 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 008/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.34412 | 39.7169 | ETL.7390 | 44202128 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753379 | Q3 | T2 EI CARIBOU #2 :7/10A RPR STRW |  | CARIBOU #2 | :007/010A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.955635 | 39.9578 | ETL.6280 | 40576411 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753381 | Q3 | T2 NN CARIBOU-PLMS JCT 003/007 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 003/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-08-13 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.101411 | 40.0544 | ETL.6290 | 40809562 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753400 | Q2 | EI LOS BANOS-MIDWAY #2 110/455 RPR GYWS | 44507430 | LOS BANOS-MIDWAY #2 | 110/455 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.795882 | 35.822 | ETL.6010 | 40764995 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119753426 | Q2 | EI DIABLO-GATES #1 61/250 RPR GYWS |  | DIABLO-GATES #1 | 061/250 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-06-05 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  |  | South | WSIP | [6 empty] | '-120.273135 | 35.916 | ETL.5960 | 40582836 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753427 | Not Scheduled | T2 NN SLO-CAYUCOS 14/134 RPR WDPKR |  | SAN LUIS OBISPO-CAYUCOS | 014/133 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.798229 | 35.3477 | ETL.9090 | 40814660 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753445 | Q2 | EI DIABLO-GATES #1 62/254 BENT STEEL | 44490734 | DIABLO-GATES #1 | 062/254 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-06-05 | 2021-06-01 | [5 empty] | South | WSIP | [6 empty] | '-120.261243 | 35.9256 | ETL.5960 | 40746865 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753447 | Q2 | EI DIABLO-GATES #1 061/252 RPR GYWS |  | DIABLO-GATES #1 | 061/252 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-06-05 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  |  | South | WSIP | [6 empty] | '-120.266716 | 35.9217 | ETL.5960 | 40648226 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753549 | Not Scheduled | T2 NN DRUM-SUMMIT #2 10/122C RPL INSW | 31522060 | DRUM-SUMMIT #2 | 010/122C | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-08-14 | 2021-08-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.609517 | 39.3246 | ETL.1450 | 42573087 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753680 | Q2 | T2 NN EAGLE ROCK-REDBUD 25/119 RPL INSS | 31528734 | EAGLE ROCK-REDBUD | 025/119 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-07-29 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.644992 | 39.0272 | ETL.1480 | 40893654 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753765 | Q2 | EI LOS BANOS-MIDWAY #2 110/457 RPR GYWS | 44509081 | LOS BANOS-MIDWAY #2 | 110/457 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.790218 | 35.8156 | ETL.6010 | 40811538 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119753766 | Not Scheduled | T3 CARIBOU-PALERMO 32/263 INS DAMPS |  | CARIBOU-PALERMO | :032/263 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-11 | 2021-03-11 | [7 empty] | TR3 | <30D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Damper-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119753768 | Q2 | EI LOS BANOS-MIDWAY #2 110/456 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 110/456 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.793029 | 35.8188 | ETL.6010 | 40812191 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119753863 | Q4 | T2 NN KESWICK-TRINITY 013/068C RPR STRW |  | KESWICK-TRINITY | 013/168C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-14 | 2021-08-14 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.649632 | 40.6994 | ETL.7270 | 42621503 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754037 | Q2 | T2 NN W. PNT-VLY SPRNGS 10/119 RMV BUTT | 44595508 | WEST POINT-VALLEY SPRINGS | 010/119 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.667732 | 38.3334 | ETL.8350 | 40643843 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y -36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754065 | Q2 | T2 EI TRINITY MAPLE CREKK 021/000R RPL I | 31511867 | TRINITY-MAPLE CREEK | 021/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.279026 | 40.7159 | ETL.8170 | 44771076 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754067 | Q2 | T2 EI TRINITY MAPLE CREKK 021/000C RPL I | 31511867 | TRINITY-MAPLE CREEK | 021/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-16 | 2021-07-16 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.279026 | 40.7159 | ETL.8170 | 44771077 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754076 | Mar | T2 EI KILARC-DESCHUTES 12/270 RPR STRW | 44406470 | KILARC-DESCHUTES | 012/270 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2021-08-13 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.049662 | 40.5641 | ETL.7300 | 40877880 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754132 | Q2 | T2 NN W. PNT-VLY SPRNGS 10/119 RPR IBWW | 44631100 | WEST POINT-VALLEY SPRINGS | 010/119 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-31 | 2021-08-31 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.667732 | 38.3334 | ETL.8350 | 40643843 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754174 | Not Scheduled | EI T3NT DRUM-SUMMIT #2 2/30B INST MRKW | 44477050 | DRUM-SUMMIT #2 | 002/030B | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2022-09-11 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.733857 | 39.2732 | ETL.1450 | 44928869 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754343 | Q2 | EI SOB-GRIZZLY-CLARE #2 2/23 RPL HRDT |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/023 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-05-08 | 2021-05-03 | [5 empty] | Central | WSIP | [6 empty] | '-122.183663 | 37.8769 | ETL.3750 | 40872284 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754567 | Q2 | T2 NN BRIDGEVILLE-CTTWD 42/338C RPL FOND | 44634171 | BRIDGEVILLE-COTTONWOOD | 042/338C | ICQ | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.056809 | 40.3902 | ETL.1110 | 42603423 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754625 | Q2 | T2 DI SALINAS-LAURELES 12/271 RPR SPLW | 44478560 | SALINAS-LAURELES | 012/271 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR2 |  | South | WSIP | [5 empty] | Downgrade to E priority; crew verified 1 of 2 dampers present | '-121.752427 | 36.555 | ETL.7930 | 40697468 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 403 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754694 | Q2 | T3 DI CRESTA-RIO OSO 13/107 RPR HRDT |  | CRESTA-RIO OSO | 013/107 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-03-04 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.454387 | 39.7751 | ETL.4590 | 44237866 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754707 | Q3 | T2 NN CARIBOU-PLUMAS JCT 12/0 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 012/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.99068 | 39.9781 | ETL.6290 | 40614949 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754722 | Q3 | T2 CARIBOU-PLUMAS JCT 11/010 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 011/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.996217 | 39.9813 | ETL.6290 | 40614947 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754755 | Q3 | T2NT NN CARIBOU-WWD 3/69B RMV BUTT |  | CARIBOU-WESTWOOD | 003/069 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-17 | 2022-08-17 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127723 | 40.1275 | ETL.6300 | 42624198 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754758 | Q3 | T2 NN CARIBOU-WWD 3/69B RPR GYWW |  | CARIBOU-WESTWOOD | 003/069 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127723 | 40.1275 | ETL.6300 | 42624198 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754787 | Not Scheduled | T3 NN FULTON-HOPLAND :26/9 REFRAME | 31509679 | FULTON-HOPLAND | :026/009 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-02-17 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.985997 | 38.7971 | ETL.6890 | 40875976 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119754813 | Q2 | T2 DI BRDGVL-CTTNWD 5/51 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 005/051 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.369616 | 40.3903 | ETL.1110 | 40788535 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119755538 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 23/620 REFRAME | 31513480 | COLGATE-ALLEGHANY | 023/620 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.857824 | 39.4769 | ETL.6470 | 40598567 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119755587 | Mar | T3 NN MNDCNO-WILTS-FRT BRG 9/3 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 009/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | SCHD | North Coast | WSIP | [8 empty] | ETL.7550 | 44211121 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119755621 | Mar | T3 NN MNDCNO-WILTS-FRT BRG 9/3 PRR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 009/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | SCHD | North Coast | WSIP | [8 empty] | ETL.7550 | 44211122 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119755625 | Mar | T3 NN MNDCNO-WILTS-FRT BRG 9/3 CANCEL | 44610682 | MENDOCINO-WILLITS-FORT BRAGG | 009/003 | ICI | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.302919 | 39.3369 | ETL.7550 | 40577995 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119756043 | Q3 | T2 NN BRIDGVLL-CTTNWD 070/508R RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 070/508 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.51343 | 40.4639 | ETL.1110 | 44510546 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-10-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119756199 | Not Scheduled | T3 DI DRUM-SUMMIT #1 5/069 RPL HRDS | 44472733 | DRUM-SUMMIT #1 | 005/069 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.691155 | 39.3012 | ETL.1440 | 44338145 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-18 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119756340 | Q2 | DI HUMBOLDT-BRDGVLLE 92/2 RPR ADSS | 44356653 | HUMBOLDT-BRIDGEVILLE | 092/002 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.841218 | 40.5574 | ETL.1810 | 44395979 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119756345 | Mar | T3NT NN KNCTI-MIDLTWN 14/1 RMV DEBRIS | 44610651 | KONOCTI-MIDDLETOWN | 014/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-18 | 2022-08-18 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.584737 | 38.7744 | ETL.6380 | 44370570 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119756346 | Q2 | T2 NN ELK-GUALALA 055/005 RPR STRW | 44610591 | ELK-GUALALA | 055/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.641567 | 38.9041 | ETL.8410 | 40762833 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119756410 | Not Scheduled | DI DIVIDE-CABRILO #2 9/111 RPR POLE |  | DIVIDE-CABRILLO #2 | 009/111 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 | [9 empty] | South | WSIP | [6 empty] | '-120.436439 | 34.6955 | ETL.1370 | 40770978 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119757296 | Q2 | T2 DI FORT ROSS-GUALALA 31/7 RPLC HRDW |  | GUALALA-MONTE RIO | 031/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-01 | 2021-09-01 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.261296 | 38.5548 | ETL.6980 | 40808286 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758308 | Q2 | DIABLO-GATES #1 63/257 RPR GYWS |  | DIABLO-GATES #1 | 063/257 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-06-05 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  |  | South | WSIP | [6 empty] | '-120.247506 | 35.9331 | ETL.5960 | 40805565 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758334 | Q2 | EI DIABLO-GATES #1 61/253 RPR GYWS |  | DIABLO-GATES #1 | 061/253 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-06-05 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  |  | South | WSIP | [6 empty] | '-120.263949 | 35.9241 | ETL.5960 | 40645165 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758384 | Q3 | DI DONNELLS-MI-WUK 5/6 RPL STRW | 31516006 | DONNELLS-CURTIS | 005/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.062343 | 38.1787 | ETL.1400 | 44770802 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758385 | Q3 | DI DONNELLS-MI-WUK 5/6 RPL STRW | 31516006 | DONNELLS-CURTIS | 005/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.062343 | 38.1787 | ETL.1400 | 44770803 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758513 | Mar | T2NT DI KILRC-DSCHTS 21/451 INST MRKW | 44406470 | KILARC-DESCHUTES | 021/451 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-11 | 2022-09-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.220084 | 40.5643 | ETL.7300 | 41190225 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758518 | Mar | T2 DI KILARC-DESCHUTES A25/537 RPLC POLE | 31514127 | KILARC-DESCHUTES | A025/537 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.291353 | 40.5711 | ETL.7300 | 41118630 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758653 | Q2 | T2 DI SALINAS-LAURELES 15/309 RPR STRW | 44610150 | SALINAS-LAURELES | 015/309 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-12 | 2021-09-12 | 2021-05-25 | 2021-05-28 | 2021-05-28 | 2021-05-21 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.739012 | 36.5112 | ETL.7930 | 40751586 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758880 | Q3 | T3 NN DONNELLS-MI-WUK 16/4 RPR GYWW | 44623631 | DONNELLS-CURTIS | 016/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.189279 | 38.0725 | ETL.1400 | 40764834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758881 | Q3 | T3 NN DONNELLS-MI-WUK 16/6 RPR GYWW | 44623632 | DONNELLS-CURTIS | 016/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.194179 | 38.069 | ETL.1400 | 44418040 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119758884 | Q2 | T2 DI TRINITY-MAPLE CREEK 50/0 RPL BOND | 44484765 | TRINITY-MAPLE CREEK | 050/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.802393 | 40.7563 | ETL.8170 | 40617855 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119759204 | Mar | T3 DI POTTER VALLEY-WILLITS 7/6 RPR POLE | 44610689 | POTTER VALLEY-WILLITS | 007/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-03-02 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.252917 | 39.3779 | ETL.7820 | 44637596 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119760134 | Q2 | EI LOS BANOS-MIDWAY #2 112/466 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 112/466 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-14 | 2021-09-14 |  |  | 2021-06-14 | 2021-06-01 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.766983 | 35.7877 | ETL.6010 | 40812203 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119760252 | Q2 | T3 DI SBRNT-GRZZLY-CNT #1 5/50 RPR STRT |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/050 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-03-04 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.219517 | 37.8478 | ETL.3740 | 40752436 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119760338 | Mar | T2 EI DIABLO-GATES #1 58/239A BENT STEEL | 44490734 | DIABLO-GATES #1 | 058/239A | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.300477 | 35.8934 | ETL.5960 | 41130203 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119760415 | Feb | T3 DI MORAGA-OAKLAND #1 003/023 RPR STRT |  | MORAGA-OAKLAND #1 | 003/023 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-03-04 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.205243 | 37.8214 | ETL.2720 | 40644194 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119760470 | Q2 | T2 DI SALINAS-LAURELES 008/178 RPR GYWW | 44610150 | SALINAS-LAURELES | 008/178 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2021-09-04 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.703981 | 36.5938 | ETL.7930 | 40768987 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119760642 | Not Scheduled | T3NT DI DRM-GRS VLY-WMR B16/382 RMV BUTT | 44476901 | DRUM-GRASS VALLEY-WEIMAR | B016/382 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.963612 | 39.1301 | ETL.6760 | 40664754 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119760649 | Not Scheduled | T3 DI DRM-GRS VLY-WMR B16/382 RPR FOUND | 44473812 | DRUM-GRASS VALLEY-WEIMAR | B016/382 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.963612 | 39.1301 | ETL.6760 | 40664754 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119762347 | Q4 | T3 DI MAPLE CREEK-HOOPA 23/6 REPL INSS | 31519985 | MAPLE CREEK-HOOPA | 023/006 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.643741 | 40.9933 | ETL.7490 | 40855877 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-11-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119762512 | Q2 | T2 DI BRDGEVLLE-COTTNWD 3/36 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 003/036 | ICW | E | 2020_(1a) PSPS |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.338646 | 40.3907 | ETL.1110 | 44424529 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119762518 | Q2 | T2 DI BRDGEVLLE-COTTNWD 3/36 RPR SHLW | 44404807 | BRIDGEVILLE-COTTONWOOD | 003/036 | ICW | E | 2020_(1a) PSPS |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.338646 | 40.3907 | ETL.1110 | 44424529 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119762967 | Q2 | EI LOS BANOS-MIDWAY #2 93/390 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 093/390 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.976908 | 36.0103 | ETL.6010 | 40605022 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119762972 | Q2 | EI LOS BANOS-MIDWAY #2 94/394A INST MRKS | 44509081 | LOS BANOS-MIDWAY #2 | 094/394A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2022-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.961538 | 36.0004 | ETL.6010 | 44644355 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119762973 | Q2 | EI LOS BANOS-MIDWAY #2 92/387 RPR FOND | 44490736 | LOS BANOS-MIDWAY #2 | 092/387 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.986368 | 36.0173 | ETL.6010 | 40811529 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119762974 | Q2 | EI LOS BANOS-MIDWAY #2 96/400 BENT STEEL | 44490736 | LOS BANOS-MIDWAY #2 | 096/400 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.947432 | 35.986 | ETL.6010 | 40605025 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119763075 | Q2 | T3 NN DRUM-HIGGINS 3/42B RMV POLE BUTT | 44473089 | DRUM-HIGGINS | 003/042B | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-08 | 2021-03-08 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.81757 | 39.2191 | ETL.4393 | 44313913 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119763268 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 10/283 RPR INSW | 44473097 | COLGATE-ALLEGHANY | 010/283 | ICW | E | 2020_(1a) PSPS |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.032777 | 39.3882 | ETL.6470 | 40900541 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119763304 | Not Scheduled | T2 DI VLLY SPRNGS-MRTL #1 3/15 RPL STRW | 31514492 | VALLEY SPRINGS-MARTELL #1 | 003/015 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-12 | 2021-09-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.774111 | 38.2531 | ETL.8240 | 40746424 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119763349 | Q2 | T3 MI-WUK-CURTIS 19/004L RPL POLE | 31505692 | ETL.1073.POLE.WDPS | 019/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-03-14 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.232759 | 38.0482 | ETL.1073 | 44777810 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-02 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119763621 | Q2 | T2 DI BRIDGEVILLE-COTNWD 9/86R RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/086 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.441963 | 40.3891 | ETL.1110 | 44423428 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119763860 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 9/107 RMV DBRS | 44487748 | DRUM-SUMMIT #1 | 009/107 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.630509 | 39.3182 | ETL.1440 | 44768889 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119763865 | Q2 | T2 DI HT CRK #1-WESTWD 53/1026 RPR STRW |  | HAT CREEK #1-WESTWOOD | 053/1026 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.005335 | 40.3298 | ETL.7030 | 40701325 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764307 | Q3 | T2 DI BRDGEVLLE-GRBERVLLE 12/12 RPL INSW | 31514126 | BRIDGEVILLE-GARBERVILLE | 012/012 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-09-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.727966 | 40.3644 | ETL.6220 | 40713468 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764309 | Q3 | T2NT DI BRDGVLL-GRBRVL 12/12 RMV PL BUT | 44476761 | BRIDGEVILLE-GARBERVILLE | 012/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-14 | 2022-09-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.723737 | 40.333 | ETL.6220 | 40661851 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764406 | Not Scheduled | T3 DI DRM-GRS VLY-WMR B22/496 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | B022/496 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.013586 | 39.1932 | ETL.6760 | 40598614 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764482 | Not Scheduled | T3NT DI DRM-GS VLY-WR B22/496 RMV PL BUT | 44476904 | DRUM-GRASS VALLEY-WEIMAR | B022/496 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.013586 | 39.1932 | ETL.6760 | 40598614 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764487 | Q2 | T2 DI HAT CRK #1-WSTWD 40/778 RPL INSW | 31514229 | HAT CREEK #1-WESTWOOD | 040/778 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.031487 | 40.511 | ETL.7030 | 44685343 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764636 | Q2 | DONNELS-CURTIS 19/004R RPL POLE | 31505692 | ETL.1073.POLE.WDPS | 019/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-09-15 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.232759 | 38.0482 | ETL.1073 | 44777811 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-02 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119764708 | Not Scheduled | T3NT DI CLGTE-ALGHNY 12/337 RMV PL BUTT | 44477153 | COLGATE-ALLEGHANY | 012/337 | ICW | F | 2020_(1a) PSPS |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.013742 | 39.4158 | ETL.6470 | 40766608 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119764709 | Not Scheduled | T3NT DI CLGTE-ALLEGHANY 12/337 INS MRKW | 44477153 | COLGATE-ALLEGHANY | 012/337 | ICW | F | 2020_(1a) PSPS |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.013742 | 39.4158 | ETL.6470 | 40766608 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119765361 | Not Scheduled | T3NT DI CLGT-CHALLENGE 11/200 RMV DEBRIS | 44476900 | COLGATE-CHALLENGE | 011/200 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.214578 | 39.4694 | ETL.6480 | 40597563 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765367 | Q2 | EI LOS BANOS-MIDWAY #2 117/485 BENT STEE | 44490736 | LOS BANOS-MIDWAY #2 | 117/485 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-15 | 2021-09-15 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.721538 | 35.7273 | ETL.6010 | 40764997 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119765440 | Not Scheduled | T3 DI COLGATE-CHALLENGE 11/200 RMV STEP | 44473098 | COLGATE-CHALLENGE | 011/200 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.214578 | 39.4694 | ETL.6480 | 40597563 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765503 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 12/336 RPR STRW | 44473097 | COLGATE-ALLEGHANY | 012/336 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.01443 | 39.4152 | ETL.6470 | 40760719 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765509 | Not Scheduled | T3NT DI COLGTE-ALGHNY 12/336 RMV PL BUT | 44477153 | COLGATE-ALLEGHANY | 012/336 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.01443 | 39.4152 | ETL.6470 | 40760719 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765583 | Mar | T3 DI DRM-GRS VLY-WMR 6/151 RPR GYWW | 44473816 | DRUM-GRASS VALLEY-WEIMAR | 006/151 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.830847 | 39.2073 | ETL.6760 | 40766654 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765593 | Q2 | T2NT EI IGNCIO-BLINAS #2 15/177 INS MRKS | 44640735 | IGNACIO-BOLINAS #2 | 015/177 | ICS | F | 2020_(3) On high spread structure |  | 2020-09-15 | 2022-09-15 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.744164 | 38.0473 | ETL.7180 | 44963442 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765616 | Not Scheduled | T3NT DI CLGTE-CHALLENGE 4/95 RMV DEBRIS | 44476900 | COLGATE-CHALLENGE | 004/095 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.160378 | 39.3906 | ETL.6480 | 40766537 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765892 | Q4 | T3 EI GYSRS #3-CLVRDLE 0/1 SLIDE AREA |  | GEYSERS #3-CLOVERDALE | 000/001 | 921 | F | 2020_(3) On high spread structure |  | 2020-09-03 | 2022-03-03 |  |  | 2021-12-31 | 2021-12-31 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.814888 | 38.8052 | ETL.1650 | 40585258 | Emergency-Wood | Other | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 500 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | 92 | Q4 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119765917 | Q3 | T2 NN BRIDGEVLL-CTTNWD 70/508L RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 070/508 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-08-17 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.51343 | 40.4639 | ETL.1110 | 44510608 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-10-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766118 | Q2 | T2 DI BRIDGEVILLE-COTTON 3/36 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 003/036 | 93I | E | 2020_(1a) PSPS |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.338646 | 40.3907 | ETL.1110 | 40893714 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119766179 | Not Scheduled | EI LOS BANOS-MIDWAY #2 119/489 CANCEL |  | LOS BANOS-MIDWAY #2 | 119/489 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-15 | 2021-09-15 | [6 empty] | CANCEL/CNCL |  | WECC | South | WSIP | [6 empty] | '-119.712234 | 35.7157 | ETL.6010 | 40863696 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119766238 | Not Scheduled | T3 DI DRM-GRSS VLLY-WMR B17/398 RPR STRW | 44476731 | DRUM-GRASS VALLEY-WEIMAR | B017/398 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.971048 | 39.1389 | ETL.6760 | 40873733 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766275 | Mar | DI CARIBOU-PLUMAS JCT 17/26 RPLC POLE | 31513876 | CARIBOU-PLUMAS JCT | 017/026 | 70Y | B | 2020_(0) A and B Tags |  | 2020-09-15 | 2020-12-15 |  |  | 2021-03-25 | 2021-03-24 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance would take out neighboring utility, PSREC (Plumas Sierra Rural Elect. Cooperative). Late due to PSREC's switching constraints. 12/13 - Shut down by CalTrans due to weather. | '-120.901297 | 39.9355 | ETL.6290 | 40816730 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-09-25 | Released-Standard | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 119766437 | Not Scheduled | T2 DI COLGTE-SMRTVLLE #2 0/10 RPR GYWW | 44477355 | COLGATE-SMARTVILLE #2 | 000/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.201068 | 39.3285 | ETL.6520 | 40619284 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766472 | Not Scheduled | EI VC-VCVILLE-JMSN-NORTH RPL HRDT | 44466667 | VACA-VACAVILLE-JAMESON-NTH TWR | 024/167 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-02 | 2021-09-02 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.178206 | 38.1318 | ETL.4100 | 40745990 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766474 | Q2 | DI BRIDGEVILLE-COTTONWOOD 4/45 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 004/045 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.357696 | 40.3909 | ETL.1110 | 44424526 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766526 | Not Scheduled | T3 DI DRM-GRS VLY-WMR B21/480 RPL POLE | 31514059 | DRUM-GRASS VALLEY-WEIMAR | B021/480 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.004332 | 39.1865 | ETL.6760 | 40756951 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766532 | Q2 | DI BRIDGEVILLE-COTTONWOOD 4/45 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 004/045 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.357696 | 40.3909 | ETL.1110 | 44424527 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766611 | Q2 | T2 DI BRIDGEVILLE-COTTON 4/45 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 004/045 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.357696 | 40.3909 | ETL.1110 | 40893553 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766821 | Q2 | T3 NN SLY CREEK TAP 1/10C RPR POLE | 44639814 | SLY CREEK TAP | 001/010C | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.137886 | 39.5698 | ETL.4221 | 42564535 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766823 | Mar | T3 DI DRM-GRS VLY-WMR 6/165 RMV PL BUTT | 44476731 | DRUM-GRASS VALLEY-WEIMAR | 006/165 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-08 | 2021-03-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.838304 | 39.2003 | ETL.6760 | 40865387 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119766824 | Not Scheduled | T3 DI DRM GRS VLY-WMR B24/545 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | B024/545 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.050197 | 39.1983 | ETL.6760 | 40693406 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767104 | Feb | T3 DI COLGATE-GRS VLY 6/164 RPLC INSW | 31514058 | COLGATE-GRASS VALLEY | 006/164 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-03-08 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.09467 | 39.2808 | ETL.6490 | 40843303 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767105 | Q2 | T2 DI TRINITY-MAPLE CRK 48/9 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 048/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.771785 | 40.7529 | ETL.8170 | 40876580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767313 | Q2 | T2 DI BRIDGEVLLE-CTTNWD 9/84L RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/084 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.437703 | 40.3891 | ETL.1110 | 44423220 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767483 | Mar | T3 DI DRUM-GRASS VLLY-WMR 5/143 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | 005/143 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.824634 | 39.2097 | ETL.6760 | 40589531 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767541 | Mar | T3NT DI DRM-GRS VLY-WMR 5/143 RMV PL BUT | 44476904 | DRUM-GRASS VALLEY-WEIMAR | 005/143 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.824634 | 39.2097 | ETL.6760 | 40589531 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767703 | Q4 | T2 DI MAPLE CREEK-HOOPA 017/002 INS MRKW | 44482958 | MAPLE CREEK-HOOPA | 017/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.684449 | 40.9305 | ETL.7490 | 44813785 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767705 | Q4 | T2 DI MAPLE CREEK-HOOPA 017/002 RPR GYWW | 44482958 | MAPLE CREEK-HOOPA | 017/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-09-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.684449 | 40.9305 | ETL.7490 | 44813786 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767720 | Not Scheduled | T3 NN COLGATE-CHALLENGE 5/108 RPR INSW | 44473098 | COLGATE-CHALLENGE | 005/108 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-13 | 2021-02-13 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.173513 | 39.3989 | ETL.6480 | 40889189 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767873 | Q2 | T2 DI BRIDGVLLE-CTTNWD 11/102L RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 011/102 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423204 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119767954 | Q2 | T2 NN FRT RS-GUAL-GUAL 36/4 GRN WSH INSU |  | GUALALA-MONTE RIO | 036/004 | ICD | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.297417 | 38.6043 | ETL.6980 | 40779139 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119768201 | Q3 | DI BRIDGEVILLE-CTTNWD 79/560 RPR OPGW | 44431445 | BRIDGEVILLE-COTTONWOOD | 079/560 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.654244 | 40.4793 | ETL.1110 | 44340561 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119768427 | Not Scheduled | T2 EI DRUM-SUMMIT#2 11/128 RPR INSW | 44487702 | DRUM-SUMMIT #2 | 011/128 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-14 | 2021-09-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.600921 | 39.3281 | ETL.1450 | 40641836 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119768670 | Not Scheduled | NN FULTON-PUEBLO 27/127 RPL INSS | 31505500 | FULTON-PUEBLO | 027/127 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-09-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.469202 | 38.4942 | ETL.1600 | 44388725 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119768780 | Q2 | T2 DI TRINITY-MAPLE CREEK 48/8 RPL PL | 31515628 | TRINITY-MAPLE CREEK | 048/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.771266 | 40.7528 | ETL.8170 | 40877935 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119768885 | Q2 | T3 DI SLY CREEK TAP 002/020A RPR GYWW | 44639816 | SLY CREEK TAP | 002/020A | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.15405 | 39.5603 | ETL.4221 | 44565813 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769000 | Mar | T3 DI DRM-GRSS VLY-WMR 000/005 RPL HRDD | 44476731 | DRUM-GRASS VALLEY-WEIMAR | 000/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.763369 | 39.2565 | ETL.6760 | 40756134 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769061 | Mar | T3NT DI DRM-GRSS VLY-WMR 0/5 RMV PL BUTT | 44476904 | DRUM-GRASS VALLEY-WEIMAR | 000/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.763369 | 39.2565 | ETL.6760 | 40756134 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769195 | Not Scheduled | T2 NN SPAULDING-SUMMIT 18/573 INS MRKW | 44488856 | SPAULDING-SUMMIT | 018/573 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2022-09-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.346886 | 39.3082 | ETL.8060 | 40590047 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769197 | Not Scheduled | T2 NN SPAULDING-SUMMIT 18/573 RMV BUTT | 44488856 | SPAULDING-SUMMIT | 018/573 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2022-09-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.346886 | 39.3082 | ETL.8060 | 40590047 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769214 | Not Scheduled | T2 NN SPAULDING-SUMMIT 18/579 RMV BUTT | 44488856 | SPAULDING-SUMMIT | 018/579 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2022-09-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.343701 | 39.3088 | ETL.8060 | 40828175 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769272 | Not Scheduled | T3NT DI VLTA-DSCHUTES 3/82 CANCEL |  | VOLTA-DESCHUTES | 003/082 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-09 | 2022-09-09 | [6 empty] | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-121.935543 | 40.4768 | ETL.8290 | 40827013 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-23 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769273 | Q2 | T3 DI VOLTA-DESCHUTES 003/082 REFRAME | 31514130 | VOLTA-DESCHUTES | 003/082 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-03-09 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.935543 | 40.4768 | ETL.8290 | 40827013 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769274 | Q2 | T3 NN WOODLEAF-PALRMO 03/31A RPR GYWS |  | WOODLEAF-PALERMO | 003/031A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.261138 | 39.5561 | ETL.4220 | 44923809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769277 | Q2 | T3 NN WOODLEAF-PALRMO 03/31B RPR GYWS |  | WOODLEAF-PALERMO | 003/031B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.261171 | 39.5561 | ETL.4220 | 44923828 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769300 | Q2 | T3 NN WOODLEAF-PALRMO 03/31C RPR GYWS |  | WOODLEAF-PALERMO | 003/031C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-17 | 2021-02-17 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.261196 | 39.5562 | ETL.4220 | 44923808 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769303 | Q2 | DI BRIDGEVILLE CTTNWD 16/151 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 016/151 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-13 | 2021-07-13 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44232668 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769306 | Not Scheduled | DI LAYTONVILLE-COVELO 010/0L RPL POLE | 44610673 | LAYTONVILLE-COVELO | 010/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-14 | 2021-08-14 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.311951 | 39.7321 | ETL.7390 | 44412041 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769307 | Not Scheduled | T2 NN DRUM-SUMMIT #1 25/297 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/297 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.358696 | 39.3096 | ETL.1440 | 44762500 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769361 | Mar | T3 DRUM-GRASS VALY-WEIMAR 5/134 RMV BUTT | 44476731 | DRUM-GRASS VALLEY-WEIMAR | 005/134 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-20 | 2021-01-20 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.818654 | 39.2119 | ETL.6760 | 40693432 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769364 | Q2 | T2 DI TRINITY-MAPLE CREEK 10/13 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 010/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.104485 | 40.7671 | ETL.8170 | 43950782 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769391 | Q3 | T2 DI BRIDGEVLLE-GARBERVLLE 0/2 RPL INSW | 31514126 | BRIDGEVILLE-GARBERVILLE | 000/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.6220 | 40713440 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2021-01-25 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769397 | Q2 | T2 NN BRDGVLL-CTTNWOOD 046/356 RPR OPGW | 44625172 | BRIDGEVILLE-COTTONWOOD | 046/356 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-15 | 2021-07-15 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.124083 | 40.3995 | ETL.1110 | 40595080 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769410 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/466 RPR WDPK | 44478883 | COLGATE-ALLEGHANY | 017/466 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2020-12-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.954775 | 39.4499 | ETL.6470 | 40874206 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769661 | Not Scheduled | T2 EI DIABLO-GATES #1 51/207A RPR GYWS |  | DIABLO-GATES #1 | 051/207A | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-09-15 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.386906 | 35.8131 | ETL.5960 | 40576869 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769753 | Q2 | DI SNTH LN-HLF MN BY ?10/8 RPL STRW | 31513802 | SNEATH LANE-HALF MOON BAY | ?010/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2021-08-07 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [8 empty] | ETL.7212 | 44384413 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769760 | Not Scheduled | DI CARIBOU-PALERMO 001/013 RPL INSS |  | CARIBOU-PALERMO | 001/013 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 | [9 empty] | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540501 | 39.4699 | ETL.3190 | 40685930 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119769762 | Q2 | T2 DI TRINITY-MAPLE CRK 46/10 REPL INSW | 31514141 | TRINITY-MAPLE CREEK | 046/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-09-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.740517 | 40.7482 | ETL.8170 | 40629996 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770058 | Q2 | EI LOS BANOS-MIDWAY #2 118/486 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 118/486 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-15 | 2021-09-15 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.719322 | 35.7241 | ETL.6010 | 40812193 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119770089 | Q4 | T2 DI KESWICK-TRINITY 15/183C RPR GYWW |  | KESWICK-TRINITY | 015/183C | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.670176 | 40.7103 | ETL.7270 | 42621520 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770092 | Q2 | EI LOS BANOS-MIDWAY #2 119/488 BENT STEE | 44490868 | LOS BANOS-MIDWAY #2 | 119/488 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-15 | 2021-09-15 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.714568 | 35.7182 | ETL.6010 | 40870076 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119770140 | Mar | T2 NN COLEMAN-RED BLUFF A12/210 RPR GYWW |  | COLEMAN-RED BLUFF | A012/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.175187 | 40.2332 | ETL.6440 | 40826842 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770141 | Mar | T2NT NN COLEMAN-RED BLF A12/210 RMV DBRS |  | COLEMAN-RED BLUFF | A012/210 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-25 | 2022-08-25 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.175187 | 40.2332 | ETL.6440 | 40826842 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770176 | Not Scheduled | DI DIVIDE-CABRILLO #2 2/42 RPL IBWW |  | DIVIDE-CABRILLO #2 | 002/042 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 | [9 empty] | South | WSIP | [6 empty] | '-120.441095 | 34.7837 | ETL.1370 | 41138353 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770228 | Q2 | T3 NN MENDOCINO-WILLITS 9/4B RPL PL | 31514050 | MENDOCINO-WILLITS | 009/004B | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-02-26 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.303121 | 39.3367 | ETL.7540 | 40740741 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770303 | Q2 | T2 DI TRINITY-MAPLE CREEK 41/5B RPR WDPK | 44295371 | TRINITY-MAPLE CREEK | 041/005B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-18 | 2021-08-18 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.65012 | 40.7252 | ETL.8170 | 44271128 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770308 | Q4 | T3 NN MDDL FRK-GLD HLL 13/106B RPL INSS | 31514338 | MIDDLE FORK-GOLD HILL | 013/106B | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.794663 | 38.9607 | ETL.5140 | 42631472 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770352 | Not Scheduled | T2 NN DIVIDE-CABRILLO #2 10/134 RPL INSW | 31515253 | DIVIDE-CABRILLO #2 | 010/134 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.43826 | 34.6763 | ETL.1370 | 44646342 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119770755 | Not Scheduled | T2 DIABLO-GATES #1 51/207 ADJST TRNBCKL |  | DIABLO-GATES #1 | 051/207 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.387588 | 35.8124 | ETL.5960 | 40811471 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771123 | Feb | T3 NN ROCK CREEK-POE 016/114 RPL INSS | 31500380 | ROCK CREEK-POE | 016/114 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-18 | 2021-02-18 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.48298 | 39.7089 | ETL.5630 | 40788487 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771224 | Mar | T2 DIABLO-GATES #1 50/203 BENT STEEL | 44571499 | DIABLO-GATES #1 | 050/203 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.398344 | 35.8041 | ETL.5960 | 40650979 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771240 | Not Scheduled | T2 DIABLO-GATES #1 50/203 ADJUST TRNBCKL |  | DIABLO-GATES #1 | 050/203 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.398344 | 35.8041 | ETL.5960 | 40650979 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771353 | Mar | WV CRZY HORS CYN-HLLSTR 34/221 RPL INSS | 31438929 | HOLLISTER TAP | 034/221 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-09-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | [5 empty] | South | WSIP | [6 empty] | '-121.590847 | 36.8109 | ETL.2153 | 41157793 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771484 | Q3 | T3 NN DONNELLS-MI-WUK 13/3 RPR INSW | 44623634 | DONNELLS-CURTIS | 013/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-02-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.145315 | 38.0965 | ETL.1400 | 40670191 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771624 | Mar | T3 EI DEER CREEK-DRUM 1/023 RPL PL | 31514128 | DEER CREEK-DRUM | 001/023 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-03-16 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.839196 | 39.2856 | ETL.6690 | 40590222 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771719 | Not Scheduled | T3 NN PTER VLEY-WILLITS 8/4 RPR GYWW | 44610689 | POTTER VALLEY-WILLITS | 008/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-20 | 2021-02-20 | [7 empty] | TR3 | <15D | North Coast | WSIP | [6 empty] | '-123.26424 | 39.3724 | ETL.7820 | 40750475 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119771859 | Q3 | EI MIDWAY-WHIRLWIND 29/120 RMV VEG |  | MIDWAY-WHIRLWIND | 029/120 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-09-16 | 2021-09-16 |  |  | 2021-09-15 | 2021-09-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.050738 | 35.1821 | ETL.6030 | 40586501 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119772601 | Q4 | T2 NN KESWICK-TRINITY 13/168B RPR GYWW |  | KESWICK-TRINITY | 013/168B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-22 | 2021-08-22 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.649632 | 40.6994 | ETL.7270 | 42621502 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773049 | Feb | EI STANISLAUS-MANTECA #2 26/154 ARMOR RO | 44566010 | STANISLAUS-MANTECA #2 | 026/154 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-02-26 | 2021-02-26 | [5 empty] | Central | WSIP | [6 empty] | '-120.753705 | 37.9278 | ETL.3820 | 40750272 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773390 | Not Scheduled | T3NT DI DM-GS VLY-WMR B20/455 RMV PL BUT | 44476904 | DRUM-GRASS VALLEY-WEIMAR | B020/455 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995295 | 39.1722 | ETL.6760 | 40756947 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773521 | Mar | T3 DI DEER CREEK-DRUM 01/31 RPL STRW | 31514128 | DEER CREEK-DRUM | 001/031 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.837214 | 39.2806 | ETL.6690 | 40873872 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773523 | Mar | T3NT DI DEER CREEK-DRUM 01/31 RMV PL BUT | 44477159 | DEER CREEK-DRUM | 001/031 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-09 | 2022-09-09 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.837214 | 39.2806 | ETL.6690 | 40873872 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773781 | Not Scheduled | NN MORRO BAY-TEMPLETON 13/57 RPL INSS | 31527044 | MORRO BAY-TEMPLETON | 013/057 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-09-09 | [9 empty] | South | WSIP | [6 empty] | '-120.706128 | 35.5266 | ETL.5933 | 40845485 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773782 | Not Scheduled | NN MORRO BAY-CALIF. FLTS 13/57 RPL INSS | 31527044 | MORRO BAY-GATES #2 | 013/057 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-09-09 | [9 empty] | South | WSIP | [6 empty] | '-120.706128 | 35.5266 | ETL.5280 | 40845487 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119773948 | Q2 | DI BRIDGEVLLE-COTTONWOOD 33/270 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 033/270 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.894027 | 40.3658 | ETL.1110 | 44423863 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119774640 | Q2 | T2 DI TRINITY-MAPLE CREK 49/5 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 049/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.788484 | 40.7573 | ETL.8170 | 40770500 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119774643 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 32/274 RPR FOND |  | PIT #1-COTTONWOOD | 032/274 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-03-09 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.990853 | 40.7289 | ETL.5390 | 40744747 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119774706 | Feb | EI STN MEL SS-RVRBNK JCT 27/158 RPL INSS | 31519276 | STAN MEL SW STA-RVERBNK JCT SW STA | 027/158 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-09-16 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.7667489 | 37.9239 | ETL.3840 | 40878891 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119774770 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 10/282 RPL INSW | 31513497 | COLGATE-ALLEGHANY | 010/282 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-03-16 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.033011 | 39.3878 | ETL.6470 | 40850519 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119774773 | Q4 | T3 NN MDDL FRK-GLD HLL 8/72 RPL INSS | 31514338 | MIDDLE FORK-GOLD HILL | 008/072 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-03-16 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.72929 | 38.9964 | ETL.5140 | 40724265 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775091 | Feb | EI LAYTONVILLE-COVELO 14/001 RMV DBR | 44610673 | LAYTONVILLE-COVELO | 014/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-16 | 2022-09-16 |  |  | 2021-02-25 | 2021-02-25 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.2655409 | 39.7694 | ETL.7390 | 44412047 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775107 | Feb | EI LAYTONVILLE-COVELO 14/001 INS MRKW |  | LAYTONVILLE-COVELO | 014/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-16 | 2022-09-16 |  |  | 2021-02-25 | 2021-02-25 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.2655409 | 39.7694 | ETL.7390 | 44412046 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775119 | Feb | EI LAYTONVILLE-COVELO 14/001 INS GMKW |  | LAYTONVILLE-COVELO | 014/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-16 | 2022-09-16 |  |  | 2021-02-25 | 2021-02-25 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.2655409 | 39.7694 | ETL.7390 | 44412047 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775137 | Feb | EI LAYTONVILLE-COVELO 14/001 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-02-25 | 2021-02-25 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.2655409 | 39.7694 | ETL.7390 | 44412047 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775139 | Feb | EI LAYTONVILLE-COVELO 13/003 RPL STRW | 31515457 | LAYTONVILLE-COVELO | 013/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.267813 | 39.7564 | ETL.7390 | 40666670 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775274 | Not Scheduled | T3 DI DRM-GRS VLY-WMR B23/512 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | B023/512 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.023616 | 39.1985 | ETL.6760 | 40786208 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775421 | Not Scheduled | T3 DI DRM GRS VLY-WMR B21/479 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | B021/479 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-03-08 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.00401 | 39.1858 | ETL.6760 | 40798804 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775423 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 33/277 RPR FOND |  | PIT #1-COTTONWOOD | 033/277 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-03-09 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.994162 | 40.7249 | ETL.5390 | 40816470 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775553 | Q2 | T2 NN WEIMAR #1 001/029 RPL INSW | 31515629 | WEIMAR #1 | 001/029 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.967965 | 39.029 | ETL.7560 | 40923013 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775555 | Q2 | T2 DI WEIMAR #1 001/029 RPR GYWW | 44477415 | WEIMAR #1 | 001/029 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.967999 | 39.029 | ETL.7560 | 40913168 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775634 | Q2 | T3 DI UKH-HPLND-CLVRDLE 10/7 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 010/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-03-09 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.988195 | 38.802 | ETL.4050 | 40804072 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775638 | Q2 | T2 NN BRDGVLL-CTTNWD 42/338B RPR OPGW | 44625172 | BRIDGEVILLE-COTTONWOOD | 042/338B | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.056815 | 40.3901 | ETL.1110 | 42603422 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775772 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 3/35 RMV PL BUTT | 44482827 | COLGATE-SMARTVILLE #2 | 003/035 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-08 | 2021-09-08 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.237224 | 39.3106 | ETL.6520 | 40619296 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775775 | Q4 | T2 DI KESWICK-TRINITY 14/177 RPR GYWW |  | KESWICK-TRINITY | 014/177 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.663504 | 40.7034 | ETL.7270 | 40825945 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775853 | Q2 | T2 NN SALINAS-LURELES 16/317C RPR WDPKR | 44640866 | SALINAS-LAURELES | 016/317C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.743517 | 36.5021 | ETL.7930 | 42564788 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775857 | Not Scheduled | T2 NN SN LUIS OBSP-CYCS 14/131 RPR INSW |  | SAN LUIS OBISPO-CAYUCOS | 014/131 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-09 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.793588 | 35.3442 | ETL.9090 | 44655774 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775880 | Not Scheduled | T2 NN SAN LIS BSP-CYCS 14/131 RMV DEBRI |  | SAN LUIS OBISPO-CAYUCOS | 014/131 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-10 | 2022-09-09 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.793588 | 35.3442 | ETL.9090 | 40756587 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775881 | Feb | T3 DI DRUM RIO OSO #1 3/30 RPR INSS | 44476618 | DRUM-RIO OSO #1 | 003/030 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-03-10 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.81673 | 39.2445 | ETL.1420 | 40633456 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775882 | Q2 | T2 DI TRINITY-MAPLE CRK 49/4 RMV PL BUTT | 44470706 | TRINITY-MAPLE CREEK | 049/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-09 | 2022-09-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.787308 | 40.7574 | ETL.8170 | 40751119 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119775883 | Q2 | T2 DI TRINITY-MAPLE CRK 49/4 RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 049/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-09-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.787308 | 40.7574 | ETL.8170 | 40751119 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776030 | Q2 | DI MI-WUK-CURTIS 025/009 RPR WDPKR | 44623635 | ETL.1073.POLE.WDPS | 025/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.303534 | 37.9772 | ETL.1073 | 44774793 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776032 | Feb | T2 DI COLGATE-GRASS VALLY 4/112 REFRAME | 31515627 | COLGATE-GRASS VALLEY | 004/112 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-09-09 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.114348 | 39.3132 | ETL.6490 | 40767732 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776033 | Mar | T3 DI PE-RIO SO-RIO OSO 19/135 RPL INSW | 31454862 | POE-RIO OSO | 019/135 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-09 | 2021-03-09 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.484366 | 39.6991 | ETL.5540 | 40786454 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776208 | Not Scheduled | DI GARBERVILLE-LYTNVL 40/11 RMV IDLE DBR | 44572981 | GARBERVILLE-LAYTONVILLE | 040/011 | ICW | F | 2020_(2) High fire spread TD |  | 2020-09-16 | 2022-09-16 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.577918 | 39.9083 | ETL.8365 | 40906688 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776383 | Mar | T2 EI DIABLO-GATES #1 48/196 BENT STEEL | 44592683 | DIABLO-GATES #1 | 048/196 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.422729 | 35.7837 | ETL.5960 | 40820157 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776429 | Not Scheduled | T2 NN DRUM-SUMMIT #1 25/297 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/297 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.358696 | 39.3096 | ETL.1440 | 44762501 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119776826 | Q2 | MORAGA-SAN LEANDRO 2 8/63 WASH INSU | 44473970 | MORAGA-SAN LEANDRO #2 | 008/063 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-05-27 | 2021-05-26 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.1310831 | 37.7289 | ETL.2780 | 40671350 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777062 | Q3 | T2 NN CARIBOU #2 :0/19 RPL POLE | 31515625 | CARIBOU #2 | :000/019 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.062628 | 40.0116 | ETL.6280 | 44191314 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777111 | Q2 | DI GARBERVILLE-LYTNVL 35/9 RPR WDPK | 44449697 | GARBERVILLE-LAYTONVILLE | 035/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.581824 | 39.8401 | ETL.8365 | 40906589 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777115 | Q2 | DI HAT CREEK #1-WSTWD 49/944 RPLC INSW | 31514229 | HAT CREEK #1-WESTWOOD | 049/944 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-09-14 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.01719 | 40.3903 | ETL.7030 | 40634518 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777268 | Mar | T2 NN KILARC-DESCHUTES 8/172 RPR CONDW | 44406470 | KILARC-DESCHUTES | 008/172 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.979814 | 40.5957 | ETL.7300 | 44837973 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777327 | Feb | T3 NN KILARC-CDAR CREEK 4/107 RPR INSW | 44406464 | KILARC-CEDAR CREEK | 004/107 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2021-02-27 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.7290 | 44175369 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777641 | Q2 | T3 DI UKIH-HPLND-CLVRDLE 10/10 RPL STRW | 31514226 | UKIAH-HOPLAND-CLOVERDALE | 010/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-03-11 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.98962 | 38.8061 | ETL.4050 | 40603867 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777756 | Feb | T3NT NN MNT VISTA-JFRSN#1 16/69 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 016/069 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2022-07-27 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.300736 | 37.4217 | ETL.5220 | 40862673 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777865 | Not Scheduled | T3 DI FULTON-CALISTOGA :3/1 RPL STRW | 31514131 | FULTON-CALISTOGA | :003/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-03-17 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.594934 | 38.634 | ETL.6880 | 40912431 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119777890 | Not Scheduled | T3 DI FULTON-HOPLAND 26/11 RPL STRW | 44579280 | FULTON-HOPLAND | 026/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-03-11 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.991408 | 38.8091 | ETL.6890 | 40601482 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778182 | Mar | T3 NN DRM-GRSS VLLY-WMR 1/25 RPR STRW | 44476731 | DRUM-GRASS VALLEY-WEIMAR | 001/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.758432 | 39.2485 | ETL.6760 | 40693452 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778189 | Mar | T3 NN DRM-GRSS VLLY-WMR 1/25 RPR SHLW | 44476731 | DRUM-GRASS VALLEY-WEIMAR | 001/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-04 | 2021-02-04 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.758432 | 39.2485 | ETL.6760 | 40693452 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778409 | Not Scheduled | T3 DI COLGATE-CHALLENGE 2/47 RPL INSLW | 31514227 | COLGATE-CHALLENGE | 002/047 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-03-11 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.172475 | 39.3576 | ETL.6480 | 44422728 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778644 | Q4 | T3 DI MIDDLE FORK-G H 19/158L RPL X-ARM | 31516282 | MIDDLE FORK-GOLD HILL | 019/158 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-03-11 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.877105 | 38.8878 | ETL.5140 | 44557592 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778681 | Q2 | EI LOS BANOS-MIDWAY #2 129/529 RPR GYWS | 44571724 | LOS BANOS-MIDWAY #2 | 129/529 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2021-09-17 |  |  | 2021-06-14 | 2021-06-01 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.611363 | 35.597 | ETL.6010 | 40863702 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Midway |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119778810 | Q2 | T2 DI BRDGVL CTTNWD 14/128 RPR POLE | 44404807 | BRIDGEVILLE-COTTONWOOD | 014/128 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.529472 | 40.3948 | ETL.1110 | 44423306 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778814 | Feb | DI STANISLAUS MANTECA #2 26/155 RPL INSS | 31519277 | STANISLAUS-MANTECA #2 | 026/155 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-02-26 | 2021-02-26 | [5 empty] | Central | WSIP | [6 empty] | '-120.765075 | 37.924 | ETL.3820 | 40771620 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778817 | Feb | DI STAN MEL SS-RVERBNK J 26/155 RPL INSS | 31519276 | STAN MEL SW STA-RVERBNK JCT SW STA | 026/155 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.765075 | 37.924 | ETL.3840 | 40771622 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778909 | Q2 | T2 DI WOODLEAF-PALERMO 18/193R RPR STRW |  | WOODLEAF-PALERMO | 018/193 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.502522 | 39.4523 | ETL.4220 | 44388428 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119778928 | Q2 | T3 DI SLY CREEK TAP 3/37 RPR DAMW | 44639819 | SLY CREEK TAP | 003/037 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-03-11 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.182257 | 39.5509 | ETL.4221 | 44388102 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779119 | Feb | EI STN MEL SW STA-RVRBNK 27/163 RPL INSS | 31519276 | STAN MEL SW STA-RVERBNK JCT SW STA | 027/163 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-17 | 2021-09-17 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.7789341 | 37.9203 | ETL.3840 | 40669719 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779175 | Q2 | T3 DI WST PNT-VLY SPRNGS 3/43 RPLC POLE | 31516430 | WEST POINT-VALLEY SPRINGS | 003/043 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-03-11 |  |  | 2021-04-03 | 2021-03-29 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.602449 | 38.412 | ETL.8350 | 40768178 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779266 | Q3 | T3 DI DONNELLS-MI-WUK 13/6 L RPR STRW | 44623636 | DONNELLS-CURTIS | 013/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-03-11 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.148155 | 38.0929 | ETL.1400 | 44774107 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779345 | Q2 | NN LAURELES-OTTER 15/0 RPR POLE | 44610149 | LAURELES-OTTER | 015/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-04-02 | 2021-03-31 | [5 empty] | South | WSIP | [6 empty] | '-121.887122 | 36.3822 | ETL.7380 | 44563010 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779378 | Not Scheduled | EI STNSLS-MNTC #2 28/165 HELI WASH |  | STANISLAUS-MANTECA #2 | 028/165 | ICI | E | 2020_(2) High fire spread TD |  | 2020-09-17 | 2021-09-17 | [9 empty] | Central | WSIP | [6 empty] | '-120.7841479 | 37.9188 | ETL.3820 | 40779558 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779466 | Q4 | T3 EI MAPLE CREEK-HOOPA 10/0 RPL POLE | 31516371 | MAPLE CREEK-HOOPA | 010/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-06 | 2021-02-06 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324522 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779542 | Not Scheduled | EI STNSLS-MNTC #2 28/166 HELI WASH |  | STANISLAUS-MANTECA #2 | 028/166 | ICI | E | 2020_(2) High fire spread TD |  | 2020-09-17 | 2021-09-17 | [9 empty] | Central | WSIP | [6 empty] | '-120.786682 | 37.918 | ETL.3820 | 40829092 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779750 | Not Scheduled | NN SAN LUIS OBISPO-CAYUCOS 7/50 RPR PL |  | SAN LUIS OBISPO-CAYUCOS | 007/050 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-09-10 | [9 empty] | South | WSIP | [6 empty] | '-120.677661 | 35.3168 | ETL.9090 | 40653422 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779869 | Q2 | T3NT DI DRUM-SPAULDING 006/156 RMV BUTT | 44477200 | DRUM-SPAULDING | 006/156 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-10 | 2022-09-10 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.687985 | 39.3028 | ETL.6770 | 40825209 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779917 | Q2 | T3 DI DRUM-SPAULDING 006/156 RPL STRW | 31529084 | DRUM-SPAULDING | 006/156 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-03-10 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.687985 | 39.3028 | ETL.6770 | 40825209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119779995 | Not Scheduled | NN GATES-PANOCHE #2 024/112 RPR INSS | 44507621 | GATES-PANOCHE #2 | 024/112 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.369523 | 36.4183 | ETL.4730 | 40714893 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119780342 | Q2 | T2 DI SALINAS-LAURELES 18/332 RPR GYWW | 44640867 | SALINAS-LAURELES | 018/332 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-12 | 2021-09-12 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.733319 | 36.486 | ETL.7930 | 40600141 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780373 | Q2 | T3NT DI DRUM-SPAULDING 004/108 RMV BUTT | 44477409 | DRUM-SPAULDING | 004/108 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-10 | 2022-09-10 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.706665 | 39.289 | ETL.6770 | 40862142 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780374 | Q2 | T3 DI DRUM-SPAULDING 004/108 RPL STRW | 31529084 | DRUM-SPAULDING | 004/108 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-03-10 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.706665 | 39.289 | ETL.6770 | 40862142 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780485 | Q2 | T3NT EI DNLS-CURTIS 21/6 RMV PL BUTTS | 44623637 | ETL.1073.POLE.WDPS | 021/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-17 | 2022-09-17 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.253841 | 38.0207 | ETL.1073 | 44385267 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780486 | Q2 | EI DONNELLS-CURTIS 21/7 SPLIT BOLT | 44623638 | ETL.1073.POLE.WDPS | 021/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.254374 | 38.02 | ETL.1073 | 44963371 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780489 | Q2 | EI T3 MI-WUK-CURTIS 22/5C RPL PL | 31501637 | ETL.1073.POLE.WOOD | 022/005C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-03-17 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.261492 | 38.0128 | ETL.1073 | 44963357 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780540 | Q2 | EI T3 MI-WUK-CURTIS 22/005A RPL PL | 31501637 | ETL.1073.POLE.WOOD | 022/005A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-03-17 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.261543 | 38.0128 | ETL.1073 | 44963356 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780543 | Q2 | EI DONNELLS-CURTIS 21/7 SPLIT BOLT | 44623639 | ETL.1073.POLE.WDPS | 021/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.254374 | 38.02 | ETL.1073 | 44963372 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780799 | Q2 | T2NT DI HT CRK #1-WSTWD 022/438 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 022/438 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-11 | 2022-09-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.238727 | 40.7118 | ETL.7030 | 40827483 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119780826 | Q2 | T3NT NN EGL RK FLTN SLVD T 5/20 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 005/020 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-27 | 2022-07-27 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.760343 | 38.6653 | ETL.4392 | 41129323 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781002 | Feb | T3 DI ROCK CREEK-POE 14/098 RPL INSS | 31500380 | ROCK CREEK-POE | 014/098 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-03-11 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.47679 | 39.7471 | ETL.5630 | 40896996 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781030 | Not Scheduled | T2 DI VLY SPRGS-MARTEL#1 10/16 RPR WDPKR |  | VALLEY SPRINGS-MARTELL #1 | 010/016 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-12 | 2021-09-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.784734 | 38.3459 | ETL.8240 | 40825817 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781031 | Not Scheduled | T2 DI VLY SPRGS-MARTEL#1 9/2 INSL MRKW |  | VALLEY SPRINGS-MARTELL #1 | 009/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-12 | 2022-09-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.770991 | 38.3181 | ETL.8240 | 40697154 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781050 | Feb | NN LAYTONVILLE-COVLO 9/13R RPR STRW | 44610673 | LAYTONVILLE-COVELO | 009/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.315127 | 39.7312 | ETL.7390 | 44412039 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781052 | Feb | DI LAYTONVILLE-COVLO 9/13C RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 009/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.315127 | 39.7312 | ETL.7390 | 44412038 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781094 | Q2 | T2 DI HAT CREEK#1-WSTWD 039/763 REFRAME | 31514136 | HAT CREEK #1-WESTWOOD | 039/763 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-12 | 2021-09-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.036455 | 40.5225 | ETL.7030 | 40770765 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781124 | Q2 | T2 DI HAT CRK#1 WSTWD 24/466 REFRAME | 31514136 | HAT CREEK #1-WESTWOOD | 024/466 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-12 | 2021-09-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.220435 | 40.6951 | ETL.7030 | 40817129 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781125 | Q4 | T2 DI KESWICK-TRINITY 10/132 REFRAME | 31514508 | KESWICK-TRINITY | 010/132 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-12 | 2021-09-12 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.634136 | 40.6705 | ETL.7270 | 40740220 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781173 | Mar | T2 DI VLLY SPRNGS-MRTL #1 10/13 REFRAME | 31517665 | VALLEY SPRINGS-MARTELL #1 | 010/013 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-03-12 | 2021-03-10 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.782877 | 38.3428 | ETL.8240 | 40656223 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781174 | Feb | T2 DI PHILO JCT-ELK 022/011 REFRAME | 31515644 | PHILO JCT-ELK | 022/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-02-09 | 2021-02-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.494078 | 39.0814 | ETL.7780 | 40595282 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781214 | Q3 | T2 NN CRBOU-PLMS JCT 8/10 REFRAME | 44408852 | CARIBOU-PLUMAS JCT | 008/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-12 | 2021-09-12 |  |  | 2021-08-20 | 2021-08-02 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.044392 | 40.0041 | ETL.6290 | 40640486 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781231 | Q2 | T2NT DI HT CRK #1-WSTWD 33/636 RMV DBRIS |  | HAT CREEK #1-WESTWOOD | 033/636 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-12 | 2022-09-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.104913 | 40.6024 | ETL.7030 | 40667962 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781237 | Q2 | T2NT DI HT CRK #1-WSTWD 53/1041 RMV DEBR |  | HAT CREEK #1-WESTWOOD | 053/1041 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-12 | 2022-09-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.000848 | 40.3185 | ETL.7030 | 40825645 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781275 | Q2 | T3 DI KONCTI-EAGLE ROCK 000/013 RPL STRW | 31514225 | KONOCTI-EAGLE ROCK | 000/013 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.798372 | 38.8348 | ETL.6861 | 40666961 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781278 | Q2 | T3 DI LAURELES-OTTER 012/006 RPR GYWW | 44610151 | LAURELES-OTTER | 012/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.847812 | 36.3883 | ETL.7380 | 40827811 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119781290 | Mar | T3 DI LAURELES-OTTER 011/002 RPR STRW | 44587870 | LAURELES-OTTER | 011/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-09 | 2021-03-09 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.835397 | 36.4 | ETL.7380 | 40647417 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119782113 | Q4 | T2 DI KESWICK-TRINITY 28/480 BOND GUY |  | KESWICK-TRINITY | 028/480 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-17 | 2021-09-17 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.892603 | 40.708 | ETL.7270 | 40906117 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119782402 | Q2 | DI GARBRVLLE-LAYTNVLLE 048/003 RMV DBRS | 44311203 | GARBERVILLE-LAYTONVILLE | 048/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-17 | 2021-09-17 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.61809 | 39.9994 | ETL.8365 | 40912538 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119782922 | Q3 | T3 DI BRIDGEVILLE-GRBERVL 03/14 RPR WDPK | 44299806 | BRIDGEVILLE-GARBERVILLE | 003/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.777473 | 40.442 | ETL.6220 | 40769396 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783270 | Q2 | T2 NN FORT-ROSS-GUALL 45/9 INSL WASH |  | GUALALA-MONTE RIO | 045/009 | ICD | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-09-14 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.341517 | 38.7146 | ETL.6980 | 40900551 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783284 | Not Scheduled | T2 DI VALLEY SPRGS-MRTLL #1 4/3 RPL STRW | 31514492 | VALLEY SPRINGS-MARTELL #1 | 004/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2014-09-11 | 2015-09-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.770819 | 38.2573 | ETL.8240 | 40644754 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783406 | Not Scheduled | T3 ROCK CREEK-POE 13/095 RPL HRDT |  | ROCK CREEK-POE | 013/095 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-03-14 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.475511 | 39.7552 | ETL.5630 | 40762419 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783606 | Q3 | T3 DI BRDGEVLL-GARBRVLL 4/2 RPL INSW | 31514509 | BRIDGEVILLE-GARBERVILLE | 004/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44232145 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2021-01-25 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783654 | Feb | T3 DI BRIDGEVILLE-GARBRVLL 5/11 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 005/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.7617 | 40.4226 | ETL.6220 | 40586721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783864 | Q3 | T2 DI CARIBOU #2 017/021 RPR GYWW |  | CARIBOU #2 | 017/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.064902 | 40.0233 | ETL.6280 | 40600640 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783930 | Not Scheduled | T3 DI MONTE RIO-FULTON 8/4 RPR STRW |  | MONTE RIO-FULTON | 008/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.912066 | 38.4889 | ETL.7630 | 40750312 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-05 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119783955 | Mar | T3 DI DRUM-RIO OSO #2 004/051 RPLC INSS | 31503652 | DRUM-RIO OSO #2 | 004/051 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1430 | 44308039 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784295 | Q3 | T3 DI BRIDGVLL-GARBERVILLE 11/6 RPR GYWW | 44476628 | BRIDGEVILLE-GARBERVILLE | 011/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.716134 | 40.3503 | ETL.6220 | 40810923 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784471 | Not Scheduled | T3 DI ROCK CREEK-POE 11/81 RPR HRDT |  | ROCK CREEK-POE | 011/081 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-03-14 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.453587 | 39.7799 | ETL.5630 | 40590795 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784648 | Not Scheduled | T2 NN SPAULDING-SUMMIT 1/50 HIGH SIGN | 44488857 | SPAULDING-SUMMIT | 001/050 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-09-14 | 2022-09-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624284 | 39.3178 | ETL.8060 | 44349479 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784674 | Q2 | T2 DI IGNACIO-BOLINAS #2 14/164 RMV BUTT | 44640732 | IGNACIO-BOLINAS #2 | 014/164 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-14 | 2021-09-14 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.727224 | 38.0604 | ETL.7180 | 40577322 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784747 | Feb | T3 DRUM-HIGGINS - 115 kV_011/111 | 44476669 | DRUM-HIGGINS | 011/111 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-03-18 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.92324 | 39.1738 | ETL.4393 | 44172153 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784764 | Not Scheduled | T2 NN SPAULDING-SUMMIT 1/50 RMV DEBRIS | 44488856 | SPAULDING-SUMMIT | 001/050 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-14 | 2022-09-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624284 | 39.3178 | ETL.8060 | 44349479 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119784785 | Q2 | EI LOS BANOS-MIDWAY #2 131/541 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 131/541 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.582382 | 35.5606 | ETL.6010 | 40587778 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119785031 | Feb | T2 DI PHILO JCT-ELK-ELK 31/0 RPR GYWW | 44610684 | PHILO JCT-ELK | 031/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-09-11 |  |  | 2021-02-10 | 2021-02-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.61146 | 39.1241 | ETL.7780 | 40614151 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785036 | Q3 | T3 DI BRDGVL GRBRVL 3/4 RMV BUTT | 44476761 | BRIDGEVILLE-GARBERVILLE | 003/004 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.787035 | 40.4471 | ETL.6220 | 40769398 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785064 | Q2 | T3 DI WEIMAR #1 6/85 REPLUMB | 44476737 | WEIMAR #1 | 006/085 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-03-14 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.893608 | 39.0189 | ETL.7560 | 40639242 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785083 | Q3 | T3 DI BRDGVL GRBRVL 2/4 RMV BUTT | 44476761 | BRIDGEVILLE-GARBERVILLE | 002/004 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.799065 | 40.4563 | ETL.6220 | 40752604 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785123 | Q3 | T3 DI BRDGVL GRBRVL 2/11 RPR GYWW | 44453320 | BRIDGEVILLE-GARBERVILLE | 002/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.792487 | 40.4503 | ETL.6220 | 40586717 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785183 | Q3 | T3 DI BRDGVL GRBRVL 4/7 RMV DEBRIS | 44476761 | BRIDGEVILLE-GARBERVILLE | 004/007 | ICW | E | 2020_(3) On high spread structure |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.770729 | 40.4386 | ETL.6220 | 40824499 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785191 | Q2 | T3 DI DRUM-SPAULDING 006/167 RPL POLE | 31529084 | DRUM-SPAULDING | 006/167 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-03-14 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.68016 | 39.3063 | ETL.6770 | 40877174 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785370 | Q3 | T3 DI BRDGEVLL-GRBRVLL 3/0 RPR STRW WDPK | 44476628 | BRIDGEVILLE-GARBERVILLE | 003/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.790644 | 40.4492 | ETL.6220 | 40614661 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785433 | Q2 | T2 DI HAT CRK #1-WSTWD 25/484 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 025/484 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-12 | 2021-09-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.208858 | 40.6845 | ETL.7030 | 40770074 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785437 | Not Scheduled | T3NT DI ROCK CREEK-POE 11/83 RPR FOND |  | ROCK CREEK-POE | 011/083 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2022-09-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.455295 | 39.7759 | ETL.5630 | 40655500 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785438 | Feb | T3 DI ROCK CREEK-POE 011/083 RPL INSS | 31500380 | ROCK CREEK-POE | 011/083 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.45553 | 39.7757 | ETL.5630 | 40685017 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785492 | Mar | T3 DI DRM GRSS VLLY WMR 1/28 RPR FIBER | 44476870 | DRUM-GRASS VALLEY-WEIMAR | 001/028 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.760923 | 39.2475 | ETL.6760 | 40892240 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785572 | Q2 | T2 DI TRINITY-MAPLE CREEK 25/4 RPL INSW | 31514141 | TRINITY-MAPLE CREEK | 025/004 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 40913389 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785603 | Q2 | NN MUSTNG SW STA-GREGG X049/207 RPR STRT | 44490886 | GATES-GREGG | X049/207 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-14 | 2021-09-12 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897281 | 36.7328 | ETL.4700 | 40805361 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119785751 | Q2 | T3NT NN GYSRS#12 FLTN 15/65 RPR FOND | 44631264 | GEYSERS #12-FULTON | 015/065 | ICS | F | 2020_(2) High fire spread TD |  | 2020-07-28 | 2022-07-28 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.753708 | 38.6341 | ETL.4750 | 40756496 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785793 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 6/81 RPL INSW | 31516005 | DIVIDE-CABRILLO #2 | 006/081 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-09-15 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436197 | 34.7299 | ETL.1370 | 42574079 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785803 | Q3 | T3 DI BRIDGEVILLE-GARBRVLL 9/17 RPL INSW | 31514509 | BRIDGEVILLE-GARBERVILLE | 009/017 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.742178 | 40.4009 | ETL.6220 | 40835207 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785809 | Q2 | NN BRIDGEVILLE-COTTONWOOD 0/3 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 000/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44423421 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785817 | Q2 | T3NT NN GYSRS#12 FLTN 0/1 RPR FOND | 44631264 | GEYSERS #12-FULTON | 000/001 | ICS | F | 2020_(2) High fire spread TD |  | 2020-07-28 | 2022-07-28 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.782988 | 38.8053 | ETL.4750 | 41129166 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785866 | Not Scheduled | T2 DI CALLENDER MESA 20/93 RPR CONS |  | SAN LUIS OBISPO-SANTA MARIA | 020/093 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-27 | 2021-07-27 | [7 empty] | TR2 |  | South | WSIP | [8 empty] | ETL.3540 | 44337446 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785913 | Q2 | NN BRIDGEVILLE-COTTONWOOD 0/3 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 000/003 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.270624 | 40.399 | ETL.1110 | 40686727 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785919 | Feb | T3 DI DRUM-HIGGINS 011/105 RPLC INSW | 31507789 | DRUM-HIGGINS | 011/105 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-03-18 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.913393 | 39.1776 | ETL.4393 | 40797247 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785980 | Mar | T2NT DI KLRC-DESCHUTES A26/541 INST MRKW | 44406470 | KILARC-DESCHUTES | A026/541 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-11 | 2022-09-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.295149 | 40.5711 | ETL.7300 | 40602867 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785983 | Mar | T2 DI KILARC-DESCHUTES A26/541 RPR WDPK | 44406470 | KILARC-DESCHUTES | A026/541 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.295149 | 40.5711 | ETL.7300 | 40602867 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119785989 | Not Scheduled | T3 DI FULTON-PUEBLO 37/189 RPLC INSS | 31505500 | FULTON-PUEBLO | 037/189 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.658046 | 38.4968 | ETL.1600 | 40893644 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786031 | Q4 | T2 DI MAPLE CREEK-HOOPA 020/006 RPL PL | 31515576 | MAPLE CREEK-HOOPA | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-11 | 2021-09-11 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.637602 | 40.948 | ETL.7490 | 40811059 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786033 | Q2 | T3NT DI DRM-SPAULDING 3/080 RMV PL BUTT | 44477409 | DRUM-SPAULDING | 003/080 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-11 | 2022-09-11 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.724812 | 39.2797 | ETL.6770 | 40667530 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786091 | Q2 | T3 DI DRM-SPAULDING 003/080 RPL POLE | 31529084 | DRUM-SPAULDING | 003/080 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-11 | 2021-03-11 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.724812 | 39.2797 | ETL.6770 | 40667530 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786093 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 10/274 REFRAME | 31514511 | COLGATE-ALLEGHANY | 010/274 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.034459 | 39.384 | ETL.6470 | 40873666 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786116 | Not Scheduled | T3 DI FULTON PUEBLO 39/203 RPLC INSS | 31514510 | FULTON-PUEBLO | 039/203 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.703149 | 38.4966 | ETL.1600 | 40676580 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786140 | Not Scheduled | DI VALLEY SPRGS-MARTELL 12/13 RPL PL | 31514492 | VALLEY SPRINGS-MARTELL #1 | 012/013 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-09-15 | [9 empty] | Central | WSIP | [6 empty] | '-120.79615 | 38.3678 | ETL.8240 | 40644612 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786157 | Not Scheduled | T3 DI EGL RCK-FLTN-SLVRD 39/203 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 039/203 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.70364 | 38.4969 | ETL.4392 | 40676581 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786187 | Not Scheduled | T3 DI FULTON-PUEBLO 35/175 RPLC INSS | 31505500 | FULTON-PUEBLO | 035/175 | 92E | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.618946 | 38.4973 | ETL.1600 | 40778491 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786234 | Mar | T3 DI KILARC-DESCHUTES 000/008 RPR HRDD | 44406470 | KILARC-DESCHUTES | 000/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-03-10 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.873549 | 40.6731 | ETL.7300 | 40592153 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786239 | Q4 | T2 DI MAPLE CREEK-HOOPA 24/6 RPR WDPKR | 44192340 | MAPLE CREEK-HOOPA | 024/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.64638 | 41.0054 | ETL.7490 | 40827974 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786318 | Q3 | DI BRIDGEVILLE-GRBERVILLE 17/4 REPL HRDD | 44476628 | BRIDGEVILLE-GARBERVILLE | 017/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-09-15 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.753453 | 40.2764 | ETL.6220 | 40769357 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786388 | Q2 | T3 DI FULTON-CALISTOGA -18/1 RPL PL | 31514427 | FULTON-CALISTOGA | '-018/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.481283 | 38.48 | ETL.6880 | 40585426 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786421 | Not Scheduled | T3 DI DRUM-SUMMIT #1 3/45 RPR INSW | 31521959 | DRUM-SUMMIT #1 | 003/045 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44180224 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786427 | Q2 | T2 DI TRINITY MPL CRK 40/2 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 040/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-09-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.629196 | 40.7205 | ETL.8170 | 40658318 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786448 | Q2 | T3 DI FULTON-PUEBLO 035/178 RPR FOND | 44306536 | FULTON-PUEBLO | 035/178 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.628992 | 38.4978 | ETL.1600 | 40861095 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786449 | Not Scheduled | T3 DI FULTON-PUEBLO 035/178 RPLC INSS | 31505500 | FULTON-PUEBLO | 035/178 | 92E | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.629316 | 38.4976 | ETL.1600 | 40884248 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786452 | Q2 | T2 DI TRINITY-MAPLE CRK 25/2A REFRAME | 31515577 | TRINITY-MAPLE CREEK | 025/002A | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.363722 | 40.7039 | ETL.8170 | 40906420 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786455 | Q2 | T2 DI TRINITY-MAPLE CRK 25/2A RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 025/002A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.363722 | 40.7039 | ETL.8170 | 40906420 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786458 | Q2 | T3 DI DSLT SPGS-TGR CRK 15/115 RPLC INSS | 31526477 | SALT SPRINGS-TIGER CREEK | 015/115 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.471724 | 38.4543 | ETL.3500 | 40771860 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786463 | Not Scheduled | T3 DI FRNCH MDWS-MDDLE FRK 1/34 RPR HRDW | 44477410 | FRENCH MEADOWS-MIDDLE FORK | 001/034 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.427388 | 39.0624 | ETL.6870 | 40658820 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786490 | Not Scheduled | T3 DI CRESTA-RIO OSO 18/150 RPR FOND |  | CRESTA-RIO OSO | 018/150 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.483261 | 39.7044 | ETL.4590 | 40910165 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786498 | Q2 | T3 DI DRUM-SPAULDING 0/9 RPR GYWW | 44477407 | DRUM-SPAULDING | 000/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-03-16 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.760093 | 39.2553 | ETL.6770 | 40875888 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786544 | Q3 | T2 NN CARIBOU #2 0/21 RMV DEBRIS |  | CARIBOU #2 | 000/021 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-15 | 2022-09-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.154448 | 40.0818 | ETL.6280 | 40591736 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786545 | Q3 | T2 NN CARIBOU #2 0/21 RPL HRDW |  | CARIBOU #2 | 000/021 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-09-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.154448 | 40.0818 | ETL.6280 | 40591736 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786562 | Mar | T2 NN KILARC-DESCHUTES A24/510 REFRAME | 31510881 | KILARC-DESCHUTES | A024/510 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-09-15 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.268409 | 40.5681 | ETL.7300 | 40702805 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786569 | Not Scheduled | T3 DI DRUM-SUMMIT #2 5/62A RPLC INSW | 31522060 | DRUM-SUMMIT #2 | 005/062A | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.698237 | 39.298 | ETL.1450 | 40792025 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786571 | Mar | T3 DI DEER CREEK-DRUM 4/101 REPA STRT | 44477402 | DEER CREEK-DRUM | 004/101 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.800314 | 39.258 | ETL.6690 | 40693765 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786582 | Q2 | T3 DI FULTON-CALISTOGA -18/7 RPL PL | 31514427 | FULTON-CALISTOGA | '-018/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.478205 | 38.488 | ETL.6880 | 40808997 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786617 | Mar | T3NT DI GEYSRS #3-CLVRDLE 9/111 RMV STUB | 44580896 | GEYSERS #3-CLOVERDALE | 009/111 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-15 | 2022-09-15 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.971884 | 38.8007 | ETL.1650 | 40808986 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786618 | Mar | T3 DI GEYSERS #3-CLVRDLE 9/111 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 009/111 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.971884 | 38.8007 | ETL.1650 | 40808986 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786642 | Q2 | T3 DI FULTON-CALISTOGA -014/003 RPR GYWW | 44597303 | FULTON-CALISTOGA | '-014/003 | ICW | E | 2020_(1a) PSPS |  | 2020-09-15 | 2021-03-15 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.507427 | 38.4311 | ETL.6880 | 40649312 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119786654 | Feb | DI HUMBOLDT-MAPLE CRK 10/005 RPLC ANCW |  | HUMBOLDT-MAPLE CREEK | 010/005 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-09-15 |  |  | 2021-02-07 | 2021-02-04 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.93912 | 40.7665 | ETL.7130 | 40751087 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786659 | Feb | T3 DI COLGATE-GRASS VLLEY 5/138 REFRAME | 31514521 | COLGATE-GRASS VALLEY | 005/138 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.105841 | 39.2992 | ETL.6490 | 40697096 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119786770 | Not Scheduled | T3 DI COLGATE-CHALLENGE 6/112 RPL PL | 31514428 | COLGATE-CHALLENGE | 006/112 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-03-16 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.179844 | 39.3999 | ETL.6480 | 40598671 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787065 | Not Scheduled | T3 DI MIDDLE FORK #1 2/40 REFRAME | 31514523 | MIDDLE FORK #1 | 002/040 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.618511 | 39.0014 | ETL.8405 | 40751827 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787071 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 010/290 RPR SPLW | 44477352 | COLGATE-ALLEGHANY | 010/290 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-03-18 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.03143 | 39.3915 | ETL.6470 | 40912097 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787188 | Not Scheduled | T3 DI CRESTA-RIO OSO 15/129 RPR FOND |  | CRESTA-RIO OSO | 015/129 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-03-16 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.477012 | 39.743 | ETL.4590 | 40910146 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787190 | Q2 | T3 NN VOLTA-DESCHUTES 005/121 REGRADE |  | VOLTA-DESCHUTES | 005/121 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-03-16 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.968535 | 40.485 | ETL.8290 | 44911342 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787399 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 19/521 RPR WDPK | 44476722 | COLGATE-ALLEGHANY | 019/521 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-16 | 2021-03-16 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.918409 | 39.4538 | ETL.6470 | 40869665 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787457 | Mar | T3 DI DRUM-RIO OSO #1 4/44 RPL HRDW | 44476617 | DRUM-RIO OSO #1 | 004/044 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.830717 | 39.2307 | ETL.1420 | 40786130 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787476 | Q2 | DI GARBERVILLE-LAYTNVLL 34/0 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 034/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-16 | 2021-09-16 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.565259 | 39.8247 | ETL.8365 | 40587735 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787612 | Mar | T3 DI DRUM-RIO OSO #1 10/104 RMV STEP | 44476619 | DRUM-RIO OSO #1 | 010/104 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-14 | 2021-03-14 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.927509 | 39.1725 | ETL.1420 | 40756304 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787654 | Feb | T2 NN COLGATE-GRSS VLLY 3/89 RPR STRW | 44497304 | COLGATE-GRASS VALLEY | 003/089 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.123187 | 39.3202 | ETL.6490 | 40874570 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787710 | Q2 | T3 DI DRUM-HIGGINS 001/021L RPL PL | 31509929 | DRUM-HIGGINS | 001/021 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-03-17 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.783799 | 39.2332 | ETL.4393 | 44172170 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787728 | Q2 | NN BRDGVLLE-COTTONWD 13/122L RPLC SHLW | 44404807 | BRIDGEVILLE-COTTONWOOD | 013/122 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2021-09-14 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.515678 | 40.3942 | ETL.1110 | 44423915 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787777 | Not Scheduled | T2 NN DRUM-SUMMIT #1 022/265C RPR WDPK | 44645317 | DRUM-SUMMIT #1 | 022/265C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2021-09-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.408799 | 39.3107 | ETL.1440 | 42572718 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787829 | Not Scheduled | T3 NN DRUM-SUMMIT #2 025/309 RPL DAMW | 44497486 | DRUM-SUMMIT #2 | 025/309 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2021-09-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44212243 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119787889 | Not Scheduled | T3NT NN DRUM-SUMMIT #2 3/35 RMV PL BUTT | 44502078 | DRUM-SUMMIT #2 | 003/035 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2022-09-17 | [7 empty] | TR3 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44155573 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788031 | Mar | T2 DI EGL RCK-CRTNA :20/3 RPR INSW | 44563383 | EAGLE ROCK-CORTINA | :020/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-09-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.612153 | 39.0118 | ETL.1470 | 40700644 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788195 | Mar | T2 NN KILARC-DESCHUTES 019/400 RPR INSW | 44406470 | KILARC-DESCHUTES | 019/400 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.175438 | 40.5638 | ETL.7300 | 44957562 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788221 | Mar | T3NT DI DR CRK-DRM 002/073 RMV DBRS | 44477403 | DEER CREEK-DRUM | 002/073 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-19 | 2022-09-19 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.818572 | 39.2629 | ETL.6690 | 40818994 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788231 | Q4 | NN MDL FORK GLD HL 18/144 RPLC STRW | 31516281 | MIDDLE FORK-GOLD HILL | 018/144 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.862072 | 38.9021 | ETL.5140 | 44557705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788233 | Q4 | NN MDL FORK GLD HL 18/144 RPLC STRW | 31516281 | MIDDLE FORK-GOLD HILL | 018/144 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.862072 | 38.9021 | ETL.5140 | 44557510 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788236 | Not Scheduled | T3 DI COLGATE ALLEGHANY 21/570 RPR WDPKR | 44476722 | COLGATE-ALLEGHANY | 021/570 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-17 | 2021-03-17 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.889799 | 39.4677 | ETL.6470 | 40767342 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788541 | Q2 | DI GRBRVL LYTNVL 36/6 RPR CROSSARM | 44476763 | GARBERVILLE-LAYTONVILLE | 036/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.573907 | 39.8539 | ETL.8365 | 40906598 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788552 | Not Scheduled | T2 NN SPAULDING SUMMIT 15/501 RMV PL BUT | 44497664 | SPAULDING-SUMMIT | 015/501 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2021-09-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379195 | 39.3229 | ETL.8060 | 44156137 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788554 | Not Scheduled | T2 NN SPAULDING SUMMIT 15/501 INS MRKW | 44497663 | SPAULDING-SUMMIT | 015/501 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2022-09-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379195 | 39.3229 | ETL.8060 | 44156137 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788556 | Q2 | DI GRBRVL LYTNVL 44/1 RMV DEBRIS | 44311203 | GARBERVILLE-LAYTONVILLE | 044/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-16 | 2022-09-16 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.588324 | 39.9532 | ETL.8365 | 40906685 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788586 | Feb | DI LYTNVLL-CVLO-60 KV_010/005 INST MRKW | 44610673 | LAYTONVILLE-COVELO | 010/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-17 | 2022-09-17 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.304341 | 39.7327 | ETL.7390 | 40750438 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788659 | Q2 | DI GARBERVLLE_LYTNVLL 44/011 RPL STRW | 31514633 | GARBERVILLE-LAYTONVILLE | 044/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.598542 | 39.9589 | ETL.8365 | 40912496 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788675 | Not Scheduled | T3 DI FULTON-PUEBLO 39/202 RPL INSS | 31505500 | FULTON-PUEBLO | 039/202 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-03-18 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.701337 | 38.4969 | ETL.1600 | 40710639 | Insulator-Steel | No Good/Out of Stdrd | Repair | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788677 | Not Scheduled | T3 DI ELG RCK FLTN-SLVRD 37/189 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 037/189 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.65798 | 38.4972 | ETL.4392 | 40893646 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788679 | Not Scheduled | T3 NN EGL RCK-FLTN-SLVR 35/175 RPLC INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 035/175 | 92E | E | 2020_(2) High fire spread TD |  | 2020-09-15 | 2021-03-15 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.618946 | 38.4973 | ETL.4392 | 40778493 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788828 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 15/400 RPR WDPKR | 44476721 | COLGATE-ALLEGHANY | 015/400 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-17 | 2021-03-16 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-120.995281 | 39.4428 | ETL.6470 | 40590441 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788845 | Q4 | T2 NN KESWICK-TRINITY 23/355 REFRAME | 31514508 | KESWICK-TRINITY | 023/355 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.804982 | 40.7135 | ETL.7270 | 40909536 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788913 | Q4 | T3 NN KESWICK-TRINITY 002/039 REFRAME | 31514508 | KESWICK-TRINITY | 002/039 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-09-10 | 2021-03-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-122.495793 | 40.617 | ETL.7270 | 40660731 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788928 | Not Scheduled | NN SAN LUIS OBISPO-ST MAR 19/88 RPL INSS | 31527045 | SAN LUIS OBISPO-SANTA MARIA | 019/088 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 | [9 empty] | South | WSIP | [6 empty] | '-120.461502 | 35.0402 | ETL.3540 | 40886670 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788976 | Not Scheduled | T2 NN DRUM-SUMMIT #1 8/100A RMV DEBRIS | 44497481 | DRUM-SUMMIT #1 | 008/100A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2022-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.642446 | 39.318 | ETL.1440 | 44772583 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119788984 | Q3 | NN CARIBOU-WESTWOOD 020/404 RPR DMPW |  | CARIBOU-WESTWOOD | 020/404 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-09-18 |  |  | 2021-08-27 | 2021-08-16 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.013188 | 40.2981 | ETL.6300 | 40666958 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789010 | Q4 | T3 DI MIDDLE FORK-GLD HILL 8/06 RPR SHLS | 44476670 | MIDDLE FORK-GOLD HILL | 008/069 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-03-18 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.726558 | 38.999 | ETL.5140 | 40892956 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789026 | Not Scheduled | T2 NN DRUM-SUMMIT #2 19/224 RPR JUMPW | 44497486 | DRUM-SUMMIT #2 | 019/224 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.468298 | 39.3192 | ETL.1450 | 44557544 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789073 | Q3 | T2 NN CARIBOU-WESTWD 003/073 RPR GYWW |  | CARIBOU-WESTWOOD | 003/073 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-09-18 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.12608 | 40.1299 | ETL.6300 | 44191074 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789365 | Mar | T2 NN CRTNA-MNDOCINO #1 53/263 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 053/263 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-07-28 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.076553 | 39.216 | ETL.1330 | 40662675 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789370 | Mar | DI MORAGA-SAN LANDRO #1 009/070 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 009/070 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-28 | 2022-07-28 |  |  | 2021-03-13 | 2021-03-08 | [5 empty] | Central | WSIP | [6 empty] | '-122.136636 | 37.7212 | ETL.2770 | 40581580 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789495 | Mar | T2NT NN CORTNA-MENDCN #1 33/161 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 033/161 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-29 | 2022-07-29 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.767019 | 39.0847 | ETL.1330 | 40584924 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789584 | Q3 | T2 DI RIBOU-WESTWOOD 3/61 RPR GYWW |  | CARIBOU-WESTWOOD | 003/061 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-09-18 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127141 | 40.1211 | ETL.6300 | 44235943 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789601 | Q3 | T2 DI CARIBOU-WESTWOOD 13/269 RPR GYWW |  | CARIBOU-WESTWOOD | 013/269 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-09-18 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.077387 | 40.2481 | ETL.6300 | 40675296 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789607 | Not Scheduled | T2 NN DRUM-SUMMIT #1 009/104L RPR STRW | 44523074 | DRUM-SUMMIT #1 | 009/104 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633813 | 39.3173 | ETL.1440 | 44963252 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789608 | Not Scheduled | T2 NN DRUM-SUMMIT #1 009/104C RPR STRW | 44523074 | DRUM-SUMMIT #1 | 009/104 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633813 | 39.3173 | ETL.1440 | 44963253 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789609 | Not Scheduled | T2 NN DRUM-SUMMIT #1 009/104R RPR STRW | 44523074 | DRUM-SUMMIT #1 | 009/104 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633813 | 39.3173 | ETL.1440 | 44963254 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789651 | Not Scheduled | T2NT NN DRUM-SUMMIT #1 9/104 RMV BUTT | 44497481 | DRUM-SUMMIT #1 | 009/104 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2022-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633813 | 39.3173 | ETL.1440 | 44963252 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789652 | Not Scheduled | T2 DI DRUM-SUMMIT #2 008/092C INST MRKW | 44497485 | DRUM-SUMMIT #2 | 008/092B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2022-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.652581 | 39.3138 | ETL.1450 | 44551636 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789696 | Not Scheduled | T3 DI CLGTE-ALLGHNY 015/421 REFRAME | 31514511 | COLGATE-ALLEGHANY | 015/421 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-19 | 2021-03-19 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-120.984108 | 39.4466 | ETL.6470 | 40693540 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789700 | Not Scheduled | T3 NN MORRO BAY-TEMPLETON 9/40 RPR SHLS |  | MORRO BAY-TEMPLETON | 009/040 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-29 | 2021-01-29 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.743958 | 35.4741 | ETL.5933 | 44358900 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789770 | Q3 | T2 NN BRDGVLL-CTTNWD 84/594 RPR STRW | 44542682 | BRIDGEVILLE-COTTONWOOD | 084/594 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-19 | 2021-09-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.757187 | 40.4861 | ETL.1110 | 44424557 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119789771 | Q2 | T2 DI CRESTA-RIO OSO 27/218 RPL INSS | 31500129 | CRESTA-RIO OSO | 027/218 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-09-18 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.526826 | 39.5851 | ETL.4590 | 41140275 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790036 | Not Scheduled | T2 NN DRUM-SUMMIT #2 010/120 RPLC INSW | 31522060 | DRUM-SUMMIT #2 | 010/120 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.612353 | 39.3232 | ETL.1450 | 44553646 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790141 | Q3 | T2 DI BRIDGEVLL-GRBRVLE 14/0A RPLC INSW | 31514126 | BRIDGEVILLE-GARBERVILLE | 014/000A | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-19 | 2021-09-19 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.733887 | 40.3165 | ETL.6220 | 44404635 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790355 | Q2 | T2 NN ELK-GUALALA 060/009 INS MRKW | 44610591 | ELK-GUALALA | 060/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-30 | 2022-07-30 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.579926 | 38.8501 | ETL.8410 | 40876116 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790357 | Q3 | DI DONNELLS-MI-WUK 016/006 RMV BUTT | 44623643 | DONNELLS-CURTIS | 016/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-30 | 2022-07-30 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.194179 | 38.069 | ETL.1400 | 44418041 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790494 | Mar | DI MNDCNO-WLLTS-FRT BRGG 10/4 INS MRKW |  | MENDOCINO-WILLITS-FORT BRAGG | 010/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-31 | 2022-07-29 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7550 | 44211109 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790498 | Q2 | T3NT DI SRNT-GRZY-CLNT #1 A2/14 RPR FOUD |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | A002/014 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-07-31 | 2022-07-31 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.236523 | 37.877 | ETL.3740 | 40746124 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790885 | Q2 | T2 ELK-GUALALA 053/000 REPR SWTS |  | ELK-GUALALA | 053/000 | 93S | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.68032 | 38.9136 | ETL.8410 | 40744207 | Switch-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790886 | Q2 | T2 ELK-GUALALA 053/003 REPR SWTS | 44610597 | ELK-GUALALA | 053/003 | ICE | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-21 | 2021-09-21 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.678183 | 38.9114 | ETL.8410 | 40744204 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119790989 | Mar | T2 DI COLEMAN-RED BLUFF A14/227 RPR JUMW |  | COLEMAN-RED BLUFF | A014/227 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-03-26 | 2021-03-23 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.200807 | 40.2219 | ETL.6440 | 40770035 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119791219 | Q2 | T3 EI DONNELLS-CURTIS 18/6 RPR WDPKR | 44623644 | ETL.1073.POLE.WDPS | 018/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-03-18 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.2195762 | 38.0529 | ETL.1073 | 44837661 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119791236 | Q2 | EI DONNELLS-CURTIS_023/000 RPR STRW | 44623645 | ETL.1073.POLE.WDPS | 023/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-09-18 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.268287 | 38.0062 | ETL.1073 | 44962131 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119791238 | Q2 | EI DONNELLS-CURTIS_023/000 RPR STRW | 44623646 | ETL.1073.POLE.WDPS | 023/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-09-18 |  |  | 2021-04-24 | 2021-03-24 | [5 empty] | Central | WSIP | [6 empty] | '-120.268287 | 38.0062 | ETL.1073 | 44962132 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119791687 | Q2 | T2 DI BRIDGEVILLE-COTTON 19/174 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 019/174 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.622992 | 40.3792 | ETL.1110 | 44423383 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119791926 | Q3 | EI MIDWAY-WHIRLWIND 27/112 RMV VEG |  | MIDWAY-WHIRLWIND | 027/112 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-09-21 | 2021-09-21 |  |  | 2021-09-15 | 2021-09-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.075065 | 35.2054 | ETL.6030 | 40655197 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119792000 | Q2 | T2 DI BRIDGEVILLE-COTTON 21/186 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 021/186 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.661707 | 40.3765 | ETL.1110 | 44515778 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119792831 | Not Scheduled | T2 NN SPAULDING SUMMIT 2/109 RPLC POLE | 31514885 | SPAULDING-SUMMIT | 002/109 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.598343 | 39.3138 | ETL.8060 | 40586081 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119792834 | Not Scheduled | T2NT DI DRUM SUMMIT #1 10/120C RMV BUTT | 44482863 | DRUM-SUMMIT #1 | 010/120C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2022-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.611602 | 39.3236 | ETL.1440 | 42572657 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119793758 | Feb | DI LAYTONVILLE-COVELO 10/7 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 010/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-19 | 2021-09-19 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.301214 | 39.733 | ETL.7390 | 40824451 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119793759 | Feb | DI LAYTONVILLE-COVELO 010/007 INS MRKW |  | LAYTONVILLE-COVELO | 010/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-19 | 2022-09-19 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.301214 | 39.733 | ETL.7390 | 40824451 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794433 | Q2 | WV LOS ESTEROS-MET 26/110A RPL ANCS |  | LOS ESTEROS-METCALF | 025/110A |  | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 |  |  | 2021-05-08 | 2021-05-03 | [5 empty] | Central | WSIP | [6 empty] | '-121.874075 | 37.5647 | ETL.5353 | 41166314 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade |  | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794574 | Q2 | T2 WV FULTON-PUEBLO 16/076 RPR FOND |  | FULTON-PUEBLO | 016/076 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.285579 | 38.5058 | ETL.1600 | 40810965 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794606 | Q4 | T3 DI MDLE FORK GOLD HILL 1/11 RPL SHLW | 44477350 | MIDDLE FORK-GOLD HILL | 001/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-03-18 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.600048 | 39.0103 | ETL.5140 | 40615858 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794607 | Q4 | T3 DI MIDLE FORK GOLD HL 1/11 RPLC INSW |  | MIDDLE FORK-GOLD HILL | 001/011 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-18 | 2021-03-17 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.600048 | 39.0103 | ETL.5140 | 40615858 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794770 | Not Scheduled | T3 DI FULTON PUEBLO 37/188 RPL INSS | 31505500 | FULTON-PUEBLO | 037/188 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-03-18 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.656567 | 38.4969 | ETL.1600 | 40884252 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794775 | Not Scheduled | T3 DI EGL RCK-FLTN SLVRD 37/188 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 037/188 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-03-18 | [7 empty] | TR3 | <30D | North Coast | WSIP | [6 empty] | '-122.65663 | 38.4973 | ETL.4392 | 40884254 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794957 | Q2 | T3NT NN SN LS OBSPO-OCNO 13/59 RPR FOND | 44490884 | SAN LUIS OBISPO-OCEANO | 013/059 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-05 | 2022-08-05 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.502655 | 35.1163 | ETL.3530 | 40870122 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119794958 | Not Scheduled | T3NT NN SN LS OBSP-OCNO 13/59 RMV DEBRI |  | SAN LUIS OBISPO-OCEANO | 013/059 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-05 | 2022-08-05 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.502655 | 35.1163 | ETL.3530 | 40870122 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119795010 | Q3 | DI GATES-MUSTANG SW STA #1 1/8 RPR FOND | 44490873 | SPARE T-LINE RECORD | 001/008 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2022-08-05 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.104988 | 36.1494 | ETL.2604 | 40870796 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119795055 | Q2 | T3 NN DRUM-HIGGINS 000/009C RMV STEPS | 44478502 | DRUM-HIGGINS | 000/009C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-05 | 2021-02-04 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.764689 | 39.2458 | ETL.4393 | 44254475 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119795098 | Mar | DI COALINGA #1-SAN MIGUEL 9/0 RPR FOND | 44571729 | COALINGA #1-SAN MIGUEL | 009/000 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-21 | 2021-09-21 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.478619 | 36.0901 | ETL.8580 | 40609546 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119795099 | Mar | DI COALINGA #1-SAN MIGUEL 9/0 INS MRKS |  | COALINGA #1-SAN MIGUEL | 009/000 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-21 | 2022-09-21 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.478619 | 36.0901 | ETL.8580 | 40609546 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119795101 | Mar | DI COALINGA #1-SAN MIGUEL 9/0 BENT STL | 44571729 | COALINGA #1-SAN MIGUEL | 009/000 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.478619 | 36.0901 | ETL.8580 | 40609546 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119795681 | Feb | EI MIDWAY-WHIRLWIND 24/102 RPL INSS | 31518027 | MIDWAY-WHIRLWIND | 024/102 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 |  |  | 2021-02-11 | 2021-02-08 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.1044793 | 35.2324 | ETL.6030 | 40709768 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119795821 | Q2 | EI LOS BANOS-MIDWAY #2 136/559 RPR STRT | 44589924 | LOS BANOS-MIDWAY #2 | 136/559 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-21 | 2021-09-21 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.538241 | 35.5068 | ETL.6010 | 40872390 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119796507 | Mar | DIABLO-MIDWAY #2 50/204 WASH INSU | 44635611 | DIABLO-MIDWAY #2 | 050/204 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-09-22 | 2021-09-22 |  |  | 2021-03-11 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-119.99006 | 35.2472 | ETL.5970 | 40796349 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119796533 | Mar | DIABLO-MIDWAY #2 50/204 RPL ZENA | 44635609 | DIABLO-MIDWAY #2 | 050/204 | ICB | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-22 | 2021-09-22 |  |  | 2021-03-11 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-119.99006 | 35.2472 | ETL.5970 | 40765165 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119796785 | Q2 | LOS BANOS-MIDWAY #2 139/572 RPR STRT | 44589924 | LOS BANOS-MIDWAY #2 | 139/572 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.506606 | 35.4675 | ETL.6010 | 40679617 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119797085 | Q2 | LOS BANOS-MIDWAY #2 140/574 RPR STRT | 44589924 | LOS BANOS-MIDWAY #2 | 140/574 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.501364 | 35.4611 | ETL.6010 | 40760813 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119797168 | Feb | T3N DI COLGATE GRS VLY 5/144 RMV PL BUTT | 44478902 | COLGATE-GRASS VALLEY | 005/144 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-04 | 2022-08-04 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.103158 | 39.2952 | ETL.6490 | 40874472 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119797743 | Not Scheduled | T2 DI DRUM-SUMMIT #1 012/141C RPR GYWW | 44478430 | DRUM-SUMMIT #1 | 012/141C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2021-09-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.578405 | 39.3323 | ETL.1440 | 44149452 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798208 | Q2 | T2 NN BRDGVL CTTNWD 16/149 RPLC INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 016/149 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-19 | 2021-09-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.57173 | 40.3841 | ETL.1110 | 40789488 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798260 | Q2 | NN BRDGVL CTTNWD 16/149 RPLC HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 016/149 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-19 | 2021-09-19 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424064 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798414 | Q2 | T2 DI HAT CRK #1-WSTWD 53/1037 RPR INSW |  | HAT CREEK #1-WESTWOOD | 053/1037 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-18 | 2021-09-18 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.002068 | 40.3216 | ETL.7030 | 40699462 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798542 | Mar | T2 EI CRTNA-MENDOCINO #1 45/221 RPR FOND |  | CORTINA-MENDOCINO #1 | 045/221 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-22 | 2021-09-22 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.940139 | 39.177 | ETL.1330 | 40584928 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798565 | Q2 | LOS BANOS-MIDWAY #2 142/582 RPL HRDT | 44589924 | LOS BANOS-MIDWAY #2 | 142/582 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.480752 | 35.4358 | ETL.6010 | 40689587 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119798769 | Not Scheduled | NN LAKEVILLE-IGNACIO #1 004/021 RPL INSS |  | LAKEVILLE-IGNACIO #1 | 004/021 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-19 | 2021-09-19 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.524328 | 38.202 | ETL.4940 | 40621541 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798815 | Q2 | NN LAKEVILLE-IGNACIO #1 004/021 RPR FOND | 43761675 | LAKEVILLE-IGNACIO #1 | 004/021 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-09-19 | 2022-09-19 |  |  | 2021-05-28 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.524672 | 38.2019 | ETL.4940 | 40595223 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119798855 | Mar | T3 DI DRUM RIO OSO #2 4/45 RPL INSS | 31528394 | DRUM-RIO OSO #2 | 004/045 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-21 | 2021-03-21 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.831219 | 39.2293 | ETL.1430 | 40774252 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119799215 | Q2 | NN FULTON PUEBLO 40/207 RPR FOND |  | FULTON-PUEBLO | 040/207 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-07 | 2022-08-07 |  |  | 2021-05-14 | 2021-05-10 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.714941 | 38.4968 | ETL.1600 | 40808458 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119799525 | Q4 | T2 NN MPLE CREEK-HOOPA 8/3B BACK FILL | 44482958 | MAPLE CREEK-HOOPA | 008/003B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-19 | 2021-09-19 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.803142 | 40.8638 | ETL.7490 | 44735731 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119800269 | Q2 | EI LOS BANOS-MIDWAY #2 144/591 RPR STRT | 44598111 | LOS BANOS-MIDWAY #2 | 144/591 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 |  |  | 2021-06-14 | 2021-06-01 |  |  | Likely MAT error - delink to correct |  | WECC | South | WSIP | [6 empty] | '-119.461368 | 35.4118 | ETL.6010 | 40587784 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119800340 | Q2 | T3NT NN WEIMAR #1 011/167 RMV DEBRIS | 44484179 | WEIMAR #1 | 011/167 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-06 | 2022-08-05 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.797492 | 39.0126 | ETL.7560 | 40677911 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119800517 | Q2 | NN HUMBOLDT-BRIDGEVILLE 92/02R REGRADE | 44483031 | HUMBOLDT-BRIDGEVILLE | 092/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.841218 | 40.5574 | ETL.1810 | 44395980 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119800518 | Q2 | NN HUMBOLDT-BRIDGEVILLE 92/02L REGRADE | 44483031 | HUMBOLDT-BRIDGEVILLE | 092/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.841218 | 40.5574 | ETL.1810 | 44395979 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119800600 | Not Scheduled | T3 DI COLGATE ALLEGHANY 6/167 RPR WDPK | 44482824 | COLGATE-ALLEGHANY | 006/167 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-03-18 | [7 empty] | TR3 | <30D | North Valley | WSIP | [6 empty] | '-121.082108 | 39.343 | ETL.6470 | 40593284 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119800671 | Q2 | DI HUMBLDT-MAPLE CREEK 9/3A RPL STRW | 31516151 | HUMBOLDT-MAPLE CREEK | 009/003A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-21 | 2021-09-21 |  |  | 2021-06-19 | 2021-06-14 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.958947 | 40.762 | ETL.7130 | 40577299 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119800674 | Not Scheduled | T2 NN DRUM SUMMIT #1 20/241 RPL STRW | 31453474 | DRUM-SUMMIT #1 | 020/241 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.437006 | 39.3207 | ETL.1440 | 40865425 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119801106 | Q2 | T2 EI-WK-CURTIS 25/0L RPL STRW | 44623647 | ETL.1073.POLE.WDPS | 025/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-22 | 2021-09-22 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.293339 | 37.9866 | ETL.1073 | 44962150 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119801115 | Q2 | T2NT EI MI-WUK-CURTIS 25/002 RMV BUTT | 44623649 | ETL.1073.POLE.WDPS | 025/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-22 | 2022-09-22 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294848 | 37.9855 | ETL.1073 | 44962153 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119801117 | Q2 | T2 EI MI-WUK-CURTIS 25/0R RPL STRW | 44623650 | ETL.1073.POLE.WDPS | 025/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-22 | 2021-09-22 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.293339 | 37.9866 | ETL.1073 | 44962151 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119801226 | Q2 | EI LOS BANOS-MIDWAY #2 137/566 RPR STRT | 44589924 | LOS BANOS-MIDWAY #2 | 137/566 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-21 | 2021-09-21 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.521636 | 35.486 | ETL.6010 | 40818583 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119801371 | Q2 | T3NT DI VLT DESCHUTES 7/155 INS MRKW |  | VOLTA-DESCHUTES | 007/155 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-19 | 2022-09-19 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.999792 | 40.4926 | ETL.8290 | 40816171 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119802208 | Q2 | MIDWAY-WHIRLWIND 0/5 RPR GYWS | 44571727 | MIDWAY-WHIRLWIND | 000/005 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-23 | 2021-09-23 |  |  | 2021-06-14 | 2021-06-01 |  |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.44685 | 35.4004 | ETL.6030 | 40748669 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119803102 | Q2 | EI SAN LUIS OBISPO-OCEANO 17/93 RPL POLE | 31517605 | SAN LUIS OBISPO-OCEANO | 017/093 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-23 | 2021-09-23 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.538596 | 35.0974 | ETL.3530 | 40812252 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119803512 | Not Scheduled | T2NT NN DRUM SUMMIT#1 24/293 RMV BUTT | 44502077 | DRUM-SUMMIT #1 | 024/293 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2022-09-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.366044 | 39.3101 | ETL.1440 | 44338248 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119803590 | Mar | T3 DI MORAGA OAKLAND#3 2/24 RPR STRT |  | MORAGA-OAKLAND #3 | 002/024 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-22 | 2021-03-22 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.204603 | 37.8227 | ETL.2740 | 40746996 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119803610 | Q2 | T2 DI NN BRDGVLL-CTTNWD 9/87 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/087 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-23 | 2021-09-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.443995 | 40.3891 | ETL.1110 | 44424055 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119803614 | Q2 | T2 DI NN BRDGVLL-CTNWD 9/87 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/087 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-23 | 2021-09-23 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.443995 | 40.3891 | ETL.1110 | 44424056 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119804054 | Not Scheduled | T3 DI DRUM-SUMMIT#2 2/28 RPL INSLW | 44482685 | DRUM-SUMMIT #2 | 002/028 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-03-22 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.735047 | 39.2707 | ETL.1450 | 40780307 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119804325 | Q3 | EI MIDWAY-WHIRLWIND 11/51 RMV VEG |  | MIDWAY-WHIRLWIND | 011/051 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-09-23 | 2021-09-23 |  |  | 2021-09-15 | 2021-09-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.260162 | 35.3738 | ETL.6030 | 40583981 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119804652 | Not Scheduled | T3NT NN DRUM-SUMMIT #1 5/063 RMV DEBRIS | 44482860 | DRUM-SUMMIT #1 | 005/063 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-07 | 2022-08-07 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.698723 | 39.297 | ETL.1440 | 44961239 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119805445 | Feb | T3NT NN KILRC-CDAR CRK 12/264 RMV DEBRI | 44406464 | KILARC-CEDAR CREEK | 012/264 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-10 | 2022-08-10 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.950282 | 40.7772 | ETL.7290 | 40693125 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119805916 | Q2 | T2 EI MI-WUK-CURTIS 25/004R RPL STRW | 31516010 | ETL.1073.POLE.WDPS | 025/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-23 | 2021-09-23 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.296877 | 37.9836 | ETL.1073 | 44962148 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119805960 | Q2 | T2 EI MI-WUK-CURTIS 25/004L RPL STRW | 31516010 | ETL.1073.POLE.WDPS | 025/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-23 | 2021-09-23 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.296877 | 37.9836 | ETL.1073 | 44962149 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119807493 | Q2 | T2 DI TRINITY-MAPLE CRK 40/3 RPR WDPK | 44295371 | TRINITY-MAPLE CREEK | 040/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-23 | 2021-09-23 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.632547 | 40.721 | ETL.8170 | 40649273 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119808345 | Not Scheduled | T2 NN DRUM-SUMMIT #1 24/290A RMV DEBRIS | 44482863 | DRUM-SUMMIT #1 | 024/290A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370402 | 39.3105 | ETL.1440 | 40814122 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119809181 | Not Scheduled | T2 DI DRUM-SUMMIT #2 25/303R REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/303 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.368884 | 39.3105 | ETL.1450 | 44552483 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119809867 | Q4 | T3NT NN MPLE CRK HOOPA 14/2 RMV PL BUTT | 44461912 | MAPLE CREEK-HOOPA | 014/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-13 | 2022-08-13 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.726315 | 40.9045 | ETL.7490 | 44735738 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119809881 | Not Scheduled | T2NT NN DRUM-SUMMITT #2 9/108B RMV BUTT | 44482693 | DRUM-SUMMIT #2 | 009/108B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2022-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.62773 | 39.321 | ETL.1450 | 42572777 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119809886 | Not Scheduled | T2 NN SPAULNNNG-SUMMIT 17/528 RMV BUTT | 44483532 | SPAULDING-SUMMIT | 017/528 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-17 | 2022-08-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.369337 | 39.3102 | ETL.8060 | 44349566 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119809965 | Not Scheduled | EI DRUM-SUMMIT #1 15/178 RPR GYWW | 44482753 | DRUM-SUMMIT #1 | 015/178 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-24 | 2021-09-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5297 | 39.3072 | ETL.1440 | 44964944 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119809966 | Not Scheduled | EI DRUM-SUMMIT #1 15/178 RPR GYWW | 44482753 | DRUM-SUMMIT #1 | 015/178 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-24 | 2021-09-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5297 | 39.3072 | ETL.1440 | 44964943 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119809967 | Not Scheduled | EI DRUM-SUMMIT #1 15/178 RPR GYWW | 44482753 | DRUM-SUMMIT #1 | 015/178 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-24 | 2021-09-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5297 | 39.3072 | ETL.1440 | 44964945 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119809968 | Not Scheduled | EI DRUM-SUMMIT #1 15/179 RPR GYWW | 44482753 | DRUM-SUMMIT #1 | 015/179 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-24 | 2021-09-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.528114 | 39.3069 | ETL.1440 | 40870572 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119809989 | Not Scheduled | EI DRUM-SUMMIT #1 17/199 RPL STRW | 31521943 | DRUM-SUMMIT #1 | 017/199 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-09-24 | 2021-09-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.499846 | 39.314 | ETL.1440 | 40653614 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119810088 | Not Scheduled | T2NT NN DRUM-SUMMIT #2 006/071 CANCEL | 44482690 | DRUM-SUMMIT #2 | 006/071 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.684338 | 39.3051 | ETL.1450 | 44963542 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119810340 | Q3 | T2NT NN CARIBOU #2 ;003/011 RMV BUTT |  | CARIBOU #2 | ;003/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-13 | 2022-08-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946057 | 39.9859 | ETL.6280 | 40585974 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119810341 | Not Scheduled | T2NT NN DRUM-SUMMIT #1 8/99L INST MRKW | 44482861 | DRUM-SUMMIT #1 | 008/099 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-13 | 2022-08-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.643748 | 39.3169 | ETL.1440 | 44782930 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119810344 | Q2 | T2NT NN HT CK #1-WSTWD 026/499 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 026/499 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-13 | 2022-08-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19933 | 40.6756 | ETL.7030 | 40601621 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119810345 | Q3 | T2NT NN CARIBOU #2 23/613 INST MRKW |  | CARIBOU #2 | 023/613 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-13 | 2022-08-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.974368 | 40.0368 | ETL.6280 | 44259130 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119810484 | Not Scheduled | T2 DI BRDGVLLE-CTTNWD 26/224 RPR FOND |  | BRIDGEVILLE-COTTONWOOD | 026/224 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.760865 | 40.3695 | ETL.1110 | 40589206 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119810486 | Not Scheduled | T3NT DI CARIBOU-TABLE MTN 40/298 MASTIC |  | CARIBOU-TABLE MTN | 040/298 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.501875 | 39.7355 | ETL.4440 | 40867849 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119811218 | Q3 | T2NT NN CARIBOU #2 04/000 RMV BUTT |  | CARIBOU #2 | ;004/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-25 | 2022-08-25 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.946352 | 39.9776 | ETL.6280 | 40593008 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119811219 | Not Scheduled | T2NT NN DRUM-SUMMIT #2 27/332 INST MRKS | 44487703 | DRUM-SUMMIT #2 | 027/332 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-08-25 | 2022-08-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329502 | 39.3163 | ETL.1450 | 40579656 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119811648 | Q2 | EI MIDWAY-WHIRLWIND 10/046 RPR STRT | 44592684 | MIDWAY-WHIRLWIND | 010/046 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-25 | 2021-09-25 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.275467 | 35.3867 | ETL.6030 | 40807964 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119811676 | Q2 | EI MIDWAY-WHIRLWIND 10/046 RPL HRDT | 44589925 | MIDWAY-WHIRLWIND | 010/046 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-25 | 2021-09-25 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.275467 | 35.3867 | ETL.6030 | 40807964 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119812315 | Q2 | T2 NN TRINITY-MAPLE CRK 39/5C RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 039/005C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.61891 | 40.7192 | ETL.8170 | 44947089 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119812507 | Q2 | T2 NN TRINITY-MAPLE CREEK 39/5A RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 039/005A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.618919 | 40.7192 | ETL.8170 | 44947094 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119812557 | Q2 | T2 NN TRINITY-MAPLE CREEK 39/5B RPR GYWW | 44453151 | TRINITY-MAPLE CREEK | 039/005B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-17 | 2021-09-17 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.618915 | 40.7192 | ETL.8170 | 44947142 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119813142 | Not Scheduled | T3NT NN DRUM-SUMMIT #2 3/36C CANCEL | 44482689 | DRUM-SUMMIT #2 | 003/036C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.726429 | 39.2771 | ETL.1450 | 44962172 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119813336 | Not Scheduled | T2 DI BRDGEVILLE-CTTNWD 45/353A MASTIC |  | BRIDGEVILLE-COTTONWOOD | 045/353A | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-27 | 2022-08-27 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.108232 | 40.3966 | ETL.1110 | 40676657 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119813743 | Not Scheduled | NN GATES-PANOCHE #1 30/143 INS MRKW | 44507579 | GATES-PANOCHE #1 | 030/143 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-29 | 2022-08-29 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.440853 | 36.4939 | ETL.4720 | 40651614 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119814307 | Not Scheduled | T2 EI DRUM-SUMMIT #2 8/100 RPL STRW | 31498154 | DRUM-SUMMIT #2 | 008/100 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.64029 | 39.3209 | ETL.1450 | 44553720 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119814421 | Not Scheduled | T2 EI DRUM-SUMMIT #2 8/101 RPL STRW | 31498154 | DRUM-SUMMIT #2 | 008/101 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-19 | 2021-08-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.638589 | 39.3217 | ETL.1450 | 44553685 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119814460 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/357 INST MRKW | 44487982 | SPAULDING-SUMMIT | 010/357 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.468566 | 39.3187 | ETL.8060 | 40619448 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119814465 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/366 RMV BUTT | 44487982 | SPAULDING-SUMMIT | 010/366 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.463338 | 39.319 | ETL.8060 | 44349551 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119814467 | Not Scheduled | T2NT DI SPAULDING-SMT 11/390 INST MRKW | 44487982 | SPAULDING-SUMMIT | 011/390 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.451879 | 39.3178 | ETL.8060 | 44156119 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119814586 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/342 RMV BUTT | 44487982 | SPAULDING-SUMMIT | 010/342 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.477671 | 39.3174 | ETL.8060 | 40751923 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119814791 | Not Scheduled | T2NT DI SPAULDING-SMT 011/404 INST MRKW | 44487982 | SPAULDING-SUMMIT | 011/404 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.445705 | 39.3182 | ETL.8060 | 44156128 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119815028 | Not Scheduled | T2 DI SPAULD SUMMIT 011/394 INST MRKW | 44487982 | SPAULDING-SUMMIT | 011/394 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.449941 | 39.3177 | ETL.8060 | 44156124 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119815207 | Not Scheduled | T2NT DI SPAULDING-SMT 011/401 INST MRKW | 44487982 | SPAULDING-SUMMIT | 011/401 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.447018 | 39.3178 | ETL.8060 | 40668679 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119815208 | Not Scheduled | T2NT DI SPAULDING-SMT 12/421 RMV DEBRIS | 44487982 | SPAULDING-SUMMIT | 012/421 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.436877 | 39.3231 | ETL.8060 | 40668676 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119815641 | Not Scheduled | T3NT DI DRM-GRSS VY-WMR B23/523 RMV BUTT | 44482745 | DRUM-GRASS VALLEY-WEIMAR | B023/523 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.033197 | 39.1983 | ETL.6760 | 40824352 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816024 | Q2 | T2 DI BRDGEVLLE-CTTNWD 49/374 RPR FOND | 44634174 | BRIDGEVILLE-COTTONWOOD | 049/374 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-27 | 2022-08-27 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.175311 | 40.4173 | ETL.1110 | 40586442 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816081 | Q3 | T3NT NN DNNLL-MI-WUK 7/6C RMV PL BUTT | 44623651 | DONNELLS-CURTIS | 007/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.100016 | 38.1685 | ETL.1400 | 44560756 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816088 | Q2 | T3NT DI FULTON-IGNACIO #1 7/42 MASTIC | 44310479 | FULTON-IGNACIO #1 | 007/042 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-29 | 2022-08-29 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.62605 | 38.4979 | ETL.4680 | 40694115 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816118 | Not Scheduled | T2 DI NN BRDGVL-CTTNWD 45/354B RPR FOND |  | BRIDGEVILLE-COTTONWOOD | 045/354 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-25 | 2021-09-25 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.116361 | 40.3981 | ETL.1110 | 42603430 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816120 | Q2 | T2 DI TRINITY-MAPLE CRK 47/1 RPR WDPK | 44295371 | TRINITY-MAPLE CREEK | 047/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-25 | 2021-09-25 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.748844 | 40.7492 | ETL.8170 | 40585390 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816123 | Q2 | T2 NN BRDGVL-GRBRVL 35/4 RPLC HRDW | 44476628 | BRIDGEVILLE-GARBERVILLE | 035/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-25 | 2021-09-25 |  |  | 2021-06-01 | 2021-01-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.782674 | 40.1058 | ETL.6220 | 40769345 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816147 | Feb | T3NT DI KILARC-CEDAR CRK 7/160 RMV ANCW |  | KILARC-CEDAR CREEK | 007/160 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2022-08-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.997983 | 40.7162 | ETL.7290 | 40586358 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816228 | Not Scheduled | T2NT DI BRDGVLL-CTTNWD 039/315 RMV DEBRI |  | BRIDGEVILLE-COTTONWOOD | 039/315 | ICS | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-123.010022 | 40.3798 | ETL.1110 | 40820499 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816252 | Not Scheduled | T2 DI SPAULDING-SUMMIT 9/333 RMV BUTT | 44487982 | SPAULDING-SUMMIT | 009/333 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.482381 | 39.317 | ETL.8060 | 44349542 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816263 | Q2 | T3NT DI GEYSERS #7-EAGLE RCK 1/11 MASTIC | 44306736 | GEYSERS #7-EAGLE ROCK | 001/011 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-31 | 2022-08-31 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.810561 | 38.8286 | ETL.1680 | 40594045 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816328 | Q3 | T2NT DI CARIBOU-WSTWD A15/306 RMV DEBRIS |  | CARIBOU-WESTWOOD | A015/306 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.087574 | 40.2692 | ETL.6300 | 42624263 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816382 | Q2 | T2 DI SOBRANTE-STAND OIL #1 0/4 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 000/004 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-08-29 | 2022-08-29 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.215437 | 37.9109 | ETL.3800 | 40746148 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816383 | Q4 | T2 DI KESWICK-TRINITY 20/290 RMV PL BUTT |  | KESWICK-TRINITY | 020/290 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.752348 | 40.7163 | ETL.7270 | 44649299 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816384 | Q2 | T2NT DI SBRNT-STD OL S S#1 1/10 RPR FOND | 44624392 | SOBRANTE-STANDARD OIL SW STA #2 | 001/010 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-08-26 | 2022-08-26 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.212868 | 37.9249 | ETL.3800 | 40590863 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816385 | Q2 | T3NT NN UKH-HPLND-CLVRDL 11/10 INST MRKW |  | UKIAH-HOPLAND-CLOVERDALE | 011/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-31 | 2022-08-31 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.993299 | 38.8212 | ETL.4050 | 40587979 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816625 | Not Scheduled | T3NT NN DRUM-SUMMIT #2 0/6B RMV DEBRIS | 44482689 | DRUM-SUMMIT #2 | 000/006B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2022-09-10 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.760504 | 39.255 | ETL.1450 | 44868834 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816626 | Not Scheduled | T2NT NN DRUM-SUMMIT #2 9/113C RMV DEBRIS | 44487749 | DRUM-SUMMIT #2 | 009/113C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2022-09-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.62145 | 39.3209 | ETL.1450 | 44270076 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816729 | Q3 | T2 DI BRIDGEVLLE-CTNWD 70/505 RPR WDPKR | 44404493 | BRIDGEVILLE-COTTONWOOD | 070/505 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-03 | 2021-09-03 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.507602 | 40.4592 | ETL.1110 | 44509659 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816740 | Q3 | T2 DI BRIDGEVLLE-CTNWD 70/505 RPR GYWW | 44431445 | BRIDGEVILLE-COTTONWOOD | 070/505 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-03 | 2021-09-03 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.507602 | 40.4592 | ETL.1110 | 44510544 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816761 | Not Scheduled | T3NT NN DRUM-SUMMIT #2 6/073A RMV DEBRIS | 44482689 | DRUM-SUMMIT #2 | 006/073A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2022-09-10 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.681943 | 39.3065 | ETL.1450 | 44820203 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816832 | Not Scheduled | T3NT NN DRUM-SUMMIT #2 2/028 RMV DEBRIS | 44487749 | DRUM-SUMMIT #2 | 002/028 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-12 | 2022-09-12 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.735047 | 39.2707 | ETL.1450 | 44552508 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119816934 | Not Scheduled | DI SPAULDING-SUMMIT 4/166 INST MRKW | 44487981 | SPAULDING-SUMMIT | 004/166 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.568016 | 39.3057 | ETL.8060 | 40862156 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119816958 | Not Scheduled | DI SPAULDING-SUMMIT 007/257 INST MRKW | 44487981 | SPAULDING-SUMMIT | 007/257 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.523798 | 39.307 | ETL.8060 | 40770698 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817032 | Q4 | T2 DI KESWICK-TRINITY 20/292 RMV PL BUTT |  | KESWICK-TRINITY | 020/292 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.753358 | 40.7162 | ETL.7270 | 44649389 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119817202 | Not Scheduled | DI SPAULDING-SUMMIT 4/162 RMV BUTT | 44487981 | SPAULDING-SUMMIT | 004/162 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.570505 | 39.3061 | ETL.8060 | 40771552 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817276 | Not Scheduled | DI SPAULDING-SUMMIT 6/229 INST MRKW | 44487981 | SPAULDING-SUMMIT | 006/229 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.537827 | 39.3086 | ETL.8060 | 40770714 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817278 | Not Scheduled | DI DRUM-SUMMIT #2 00/002 RMV BUTT | 44487749 | DRUM-SUMMIT #2 | 000/002 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-29 | 2022-08-29 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.765009 | 39.2557 | ETL.1450 | 44868862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817413 | Not Scheduled | DI SPAULDING-SUMMIT 05/192 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/192 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.555983 | 39.3053 | ETL.8060 | 40668666 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817467 | Not Scheduled | DI SPAULDING-SUMMIT 5/180 INST MRKW | 44487981 | SPAULDING-SUMMIT | 005/180 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.561375 | 39.3061 | ETL.8060 | 40602246 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817468 | Not Scheduled | DI SPAULDING-SUMMIT 5/180 RMV POLE BUTT | 44487981 | SPAULDING-SUMMIT | 005/180 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.561375 | 39.3061 | ETL.8060 | 40602246 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817614 | Not Scheduled | DI SPAULDING-SUMMIT 5/200 INST MRKW | 44487981 | SPAULDING-SUMMIT | 005/200 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.552275 | 39.3048 | ETL.8060 | 40602248 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119817656 | Not Scheduled | T2 NN SPAULDING-SUMMIT 002/116 RMV BUTT | 44488856 | SPAULDING-SUMMIT | 002/116 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2022-09-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.594994 | 39.3125 | ETL.8060 | 40862152 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119817753 | Not Scheduled | T2NT NN DRUM-SMIT #1 021/254B RMV BUTT | 44487748 | DRUM-SUMMIT #1 | 021/254B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2022-09-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.424674 | 39.3148 | ETL.1440 | 42572715 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119817755 | Not Scheduled | T2NT NN DRUM-SMIT #1 021/254B INST MRKW | 44487748 | DRUM-SUMMIT #1 | 021/254B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2022-09-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.424674 | 39.3148 | ETL.1440 | 42572715 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119817787 | Not Scheduled | DI SPAULDING SUMMIT 7/255 INST GWMW | 44483532 | SPAULDING-SUMMIT | 007/255 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.524344 | 39.3067 | ETL.8060 | 40650047 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818180 | Q2 | T2NT DI HT CRK #1-WSTWD 32/630 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 032/630 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-11 | 2022-09-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.108355 | 40.6061 | ETL.7030 | 40817145 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818218 | Not Scheduled | DI SPAULDING-SUMMIT 005/175 INS MRKW | 44487981 | SPAULDING-SUMMIT | 005/175 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.563611 | 39.3059 | ETL.8060 | 40828128 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818247 | Not Scheduled | DI SPAULDING-SUMMIT 6/209 INS MRKW | 44487981 | SPAULDING-SUMMIT | 006/209 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.548877 | 39.3059 | ETL.8060 | 40590015 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818280 | Not Scheduled | DI SPAULDING-SUMMIT 6/223 RMV DEBRIS | 44487981 | SPAULDING-SUMMIT | 006/223 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.542759 | 39.3076 | ETL.8060 | 40751853 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818289 | Not Scheduled | T2 DI VLY SGS-ML #1 11/6 RMV PL BUTT |  | VALLEY SPRINGS-MARTELL #1 | 011/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-11 | 2022-09-11 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.785554 | 38.3523 | ETL.8240 | 40816463 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818320 | Not Scheduled | DI SPAULDING-SUMMIT 005/174 CANCEL | 44487981 | SPAULDING-SUMMIT | 005/174 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [6 empty] | CANCEL/CNCL |  | WECC | North Valley | WSIP | [6 empty] | '-120.564205 | 39.3059 | ETL.8060 | 40751911 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818325 | Q2 | T3NT NN EGLE RCK-CRTNA :009/052 RPR FOND | 44637020 | EAGLE ROCK-REDBUD | :009/052 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-09-11 | 2022-09-11 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.671619 | 38.8879 | ETL.1480 | 40682405 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818329 | Q2 | T3NT NN FULTON-CALISTOG :3/10 INST MRKW | 44597303 | FULTON-CALISTOGA | :003/010 | ICW | F | 2020_(1a) PSPS |  | 2020-09-11 | 2022-09-11 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.594725 | 38.6429 | ETL.6880 | 40912440 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119818353 | Not Scheduled | DI SPAULDING-SUMMIT 005/189 INS MRKW | 44487981 | SPAULDING-SUMMIT | 005/189 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.557428 | 39.3056 | ETL.8060 | 40618189 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818387 | Not Scheduled | DI SPAULDING-SUMMIT 5/170 INST MRKW | 44487981 | SPAULDING-SUMMIT | 005/170 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.566124 | 39.3058 | ETL.8060 | 40602245 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818388 | Not Scheduled | DI SPAULDING-SUMMIT 5/170 RMV POLE BUTT | 44487981 | SPAULDING-SUMMIT | 005/170 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.566124 | 39.3058 | ETL.8060 | 40602245 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818389 | Not Scheduled | DI SPAULDING-SUMMIT 005/178 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/178 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.562288 | 39.306 | ETL.8060 | 40869723 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818395 | Not Scheduled | DI SPAULDING-SUMMIT 005/179 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/179 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.561837 | 39.3061 | ETL.8060 | 40618186 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818398 | Not Scheduled | DI SPAULDING-SUMMIT 5/179 INS MRKW | 44487981 | SPAULDING-SUMMIT | 005/179 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.561837 | 39.3061 | ETL.8060 | 40618186 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818416 | Not Scheduled | DI SPAULDING-SUMMIT 005/191 INS MRKW | 44487981 | SPAULDING-SUMMIT | 005/191 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556383 | 39.3054 | ETL.8060 | 40660126 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818418 | Not Scheduled | DI SPAULDING-SUMMIT 005/206 INST MRKW | 44487981 | SPAULDING-SUMMIT | 005/206 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.550272 | 39.3054 | ETL.8060 | 40826189 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818632 | Not Scheduled | DI SPAULDING SUMMIT 6/210 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 006/210 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.548576 | 39.306 | ETL.8060 | 40602249 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818633 | Not Scheduled | DI SPAULDING-SUMMIT 5/202 RMV BUTT | 44487981 | SPAULDING-SUMMIT | 005/202 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.551643 | 39.3049 | ETL.8060 | 40668667 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119818723 | Not Scheduled | T2NT DI SPLDNG-SUMT 12/420 RMV DEBRIS | 44487982 | SPAULDING-SUMMIT | 012/420 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.437499 | 39.3226 | ETL.8060 | 40660156 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818724 | Not Scheduled | T2NT DI SPAULDNG-SMMT 11/380 INS MRKW | 44487982 | SPAULDING-SUMMIT | 011/380 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.456652 | 39.3184 | ETL.8060 | 40702018 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818785 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/480 INS MRKW | 44487982 | SPAULDING-SUMMIT | 015/480 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.391319 | 39.329 | ETL.8060 | 40681441 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818830 | Not Scheduled | T2NT DI SPLDNG-SMMT 12/425 INST MRKW | 44487982 | SPAULDING-SUMMIT | 012/425 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.43419 | 39.3242 | ETL.8060 | 40809671 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818913 | Q3 | T2NT NN CARIBU-PLMS JCT 04/11 RMV DEBRIS |  | CARIBOU-PLUMAS JCT | 004/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-12 | 2022-09-12 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.6290 | 44399521 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818915 | Q2 | T2 DI WEIMAR #1 000/006 RMV PL BUTT | 44488867 | WEIMAR #1 | 000/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-12 | 2022-09-12 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.984959 | 39.0355 | ETL.7560 | 44913367 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119818952 | Not Scheduled | T2 DI SPAULDING-SUMMT 10/355 RMV PL BUTT | 44487982 | SPAULDING-SUMMIT | 010/355 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.470513 | 39.3183 | ETL.8060 | 44167347 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119819412 | Not Scheduled | DI SPAULDING-SUMMIT 005/193 INS MRKW | 44487981 | SPAULDING-SUMMIT | 005/193 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.555461 | 39.3053 | ETL.8060 | 40751849 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119819418 | Not Scheduled | DI SPAULDING-SUMMIT 005/196 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/196 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.554214 | 39.305 | ETL.8060 | 40809657 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119819434 | Not Scheduled | T3NT NN RND MTN-CTNWD #3 29/244 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/244 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-14 | 2022-09-14 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.961752 | 40.764 | ETL.5650 | 40765415 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119819436 | Q2 | T2 DI TRIN MPL CRK 47/006 RMV BUTT | 44470706 | TRINITY-MAPLE CREEK | 047/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-14 | 2022-09-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.753021 | 40.7498 | ETL.8170 | 40809436 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119819452 | Q2 | T2 DI TRINITY-MPLE CREK 47/3 RMV BUTT | 44470706 | TRINITY-MAPLE CREEK | 047/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-14 | 2022-09-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.750779 | 40.7495 | ETL.8170 | 40649282 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119819473 | Not Scheduled | DI SPAULDING-SUMMIT 4/167 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 004/167 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2022-09-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.567522 | 39.3057 | ETL.8060 | 42571848 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119819491 | Not Scheduled | SPAULDING-SUMMIT 5/207 RPL SWITCH | 31516965 | SPAULDING-SUMMIT | 005/207 | 93S | E | 2020_(1b) Lines with special commitments |  | 2020-09-26 | 2021-09-26 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549817 | 39.3055 | ETL.8060 | 44167328 | Switch-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119819503 | Q4 | T3NT DI MAPLE CRK-HOOPA 11/3 RMV DEBRIS | 44461912 | MAPLE CREEK-HOOPA | 011/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-02 | 2022-09-02 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.771222 | 40.9001 | ETL.7490 | 40668473 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119819715 | Not Scheduled | T2 SPAULDING-SUMMIT 9/323 REFRAME | 31510883 | SPAULDING-SUMMIT | 009/323 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-09-27 | 2021-09-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.48707 | 39.3161 | ETL.8060 | 40590024 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119820612 | Q3 | EI MIDWAY-WHIRLWIND 2/15 RMV VEG |  | MIDWAY-WHIRLWIND | 002/015 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-09-28 | 2021-09-28 |  |  | 2021-09-15 | 2021-09-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.418625 | 35.3898 | ETL.6030 | 40760856 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119821029 | Not Scheduled | T3 EI TMBLOR-SN LS OBSPO 50/2 RPL INSL | 31526478 | TEMBLOR-SAN LUIS OBISPO | 050/285 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-22 | 2021-03-22 | [7 empty] | TR3 | <60D | South | WSIP | [6 empty] | '-120.54419 | 35.3219 | ETL.3960 | 40751440 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119821188 | Q2 | EI LOS BANOS-MIDWAY #2 66/278 INST HRDT | 44490736 | LOS BANOS-MIDWAY #2 | 066/278 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.286243 | 36.3057 | ETL.6010 | 40863988 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119821230 | Q2 | LOS BANOS-MIDWAY #2 -67/282 RPR STRT | 44490736 | LOS BANOS-MIDWAY #2 | 067/282 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-01 | 2021-09-01 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.276343 | 36.2967 | ETL.6010 | 40664821 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119821233 | Q2 | EI LOS BANOS-MIDWAY #2 82/345 RPR GYWS |  | LOS BANOS-MIDWAY #2 | 082/345 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-09-04 | 2021-09-04 |  |  | 2021-04-15 | 2021-02-16 |  | TLN/TLQ error | Tower guy |  | WECC | South | WSIP | [6 empty] | '-120.112112 | 36.1277 | ETL.6010 | 40753923 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119821746 | Feb | EI MIDWAY-WHIRLWIND 00/005 RPL INSS | 31518027 | MIDWAY-WHIRLWIND | 000/005 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-09-28 | 2021-09-28 |  |  | 2021-02-11 | 2021-02-08 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.4468625 | 35.4004 | ETL.6030 | 40776482 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119821952 | Not Scheduled | T2NT NN DRUM-SUMMIT #2 008/093A INS MRKW | 44502078 | DRUM-SUMMIT #2 | 008/093A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-25 | 2022-09-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.650944 | 39.3141 | ETL.1450 | 44963358 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119821959 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 008/093B INS MRKW | 44502078 | DRUM-SUMMIT #2 | 008/093B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-25 | 2022-09-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.650932 | 39.3141 | ETL.1450 | 44963450 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119822186 | Q2 | EI MORRO BAY-TEMPLETON 13/57 RPR FOND | 44506748 | MORRO BAY-TEMPLETON | 013/057 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-04-15 | 2021-04-01 | [5 empty] | South | WSIP | [6 empty] | '-120.706103 | 35.5266 | ETL.5933 | 40818895 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119822192 | Q3 | EI MORRO BAY-TEMPLETON 13/57 RMV VEG |  | MORRO BAY-TEMPLETON | 013/057 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-28 | 2021-09-28 |  |  | 2021-08-15 | 2021-08-01 | [5 empty] | South | WSIP | [6 empty] | '-120.706103 | 35.5266 | ETL.5933 | 40818895 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119822493 | Q3 | EI MORRO BAY-TEMPLETON 14/58 RMV VEG |  | MORRO BAY-TEMPLETON | 014/058 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-28 | 2021-09-28 |  |  | 2021-08-15 | 2021-08-01 | [5 empty] | South | WSIP | [6 empty] | '-120.7045 | 35.5284 | ETL.5933 | 40863301 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119822718 | Mar | DI COALINGA #1-SAN MIGUEL 5/6 RPR FOND | 44571729 | COALINGA #1-SAN MIGUEL | 005/006 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-25 | 2021-09-25 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.424815 | 36.0981 | ETL.8580 | 40823288 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119823538 | Mar | DI COALINGA#1-SAN MGL 8/0 RPR FOND | 44571729 | COALINGA #1-SAN MIGUEL | 008/000 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.465829 | 36.0971 | ETL.8580 | 40584316 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119823607 | Mar | DI COALINGA#1-SAN MGL 8/4 RPR FOND | 44571729 | COALINGA #1-SAN MIGUEL | 008/004 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-25 | 2021-09-25 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.47673 | 36.0932 | ETL.8580 | 40766051 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119823683 | Q3 | DI HMLTN BRNCH-CHSTR 10/210 RPR GYWW | 43908598 | HAMILTON BRANCH-CHESTER | 010/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-08-31 | 2021-08-30 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.196693 | 40.312 | ETL.7000 | 40701315 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119823689 | Q3 | DI HMLTN BRNCH-CHSTR 10/210 RMV BUTT | 43908598 | HAMILTON BRANCH-CHESTER | 010/210 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-28 | 2022-09-28 |  |  | 2021-08-31 | 2021-08-30 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.196693 | 40.312 | ETL.7000 | 40701315 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119823759 | Not Scheduled | DI SPAULDING-SUMMIT 5/205 RMV PL BUTT | 44487981 | SPAULDING-SUMMIT | 005/205 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-31 | 2022-08-31 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.55056 | 39.3053 | ETL.8060 | 40810161 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119825018 | Q2 | MIDWAY-WHIRLWIND 17/075 RPR STRT | 44589925 | MIDWAY-WHIRLWIND | 017/075 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-28 | 2021-09-28 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.185606 | 35.3088 | ETL.6030 | 40749695 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119825191 | Mar | DI COALINGA #1-SAN MIGUEL 5/5 RPR STRT | 44507661 | COALINGA #1-SAN MIGUEL | 005/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.42067 | 36.0985 | ETL.8580 | 40748092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119825192 | Mar | DI COALINGA #1-SAN MIGUEL 5/5 RPR FOND | 44490795 | COALINGA #1-SAN MIGUEL | 005/005 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.42067 | 36.0985 | ETL.8580 | 40748092 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119825404 | Mar | DI COALINGA #1-SAN MIGUEL 5/7 RPR FOND | 44490795 | COALINGA #1-SAN MIGUEL | 005/007 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-09-28 | 2021-09-28 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.427734 | 36.0979 | ETL.8580 | 40821833 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119825408 | Mar | DI COALINGA #1-SAN MIGUEL 5/7 RPR STRT | 44487991 | COALINGA #1-SAN MIGUEL | 005/007 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-27 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.427734 | 36.0979 | ETL.8580 | 40821833 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119825420 | Q2 | DI MUSTANG-GREGG 16/70 RPR FOND | 44490886 | GATES-GREGG | 016/070 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-09-28 | 2022-09-28 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.868901 | 36.2554 | ETL.4700 | 40604321 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119825571 | Q3 | T2 DI BRDGVLL-CTTNWD 64/464 RPL DAMS | 44477511 | BRIDGEVILLE-COTTONWOOD | 064/464 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-28 | 2021-09-28 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.433435 | 40.4008 | ETL.1110 | 40676706 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119827960 | Not Scheduled | T2 DI SN LS OBSP-SNT MR 17/76 RPLC INSS | 31526378 | SAN LUIS OBISPO-SANTA MARIA | 017/076 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-25 | 2021-09-25 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.481734 | 35.068 | ETL.3540 | 40838244 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829124 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 7/189 RPL STRW | 31515086 | COLGATE-ALLEGHANY | 007/189 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.07091 | 39.3501 | ETL.6470 | 40824246 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829243 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 7/190 RPR STRW | 44487807 | COLGATE-ALLEGHANY | 007/190 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.070382 | 39.3505 | ETL.6470 | 40822719 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829428 | Q2 | T2 NN LAKEVILLE #2 12/251 GRND WASH |  | LAKEVILLE #2 | 012/251 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.692222 | 38.2875 | ETL.7340 | 40641292 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829662 | Q3 | T2 NN CARIBOU-WESTWD 17/357 RPL DAMPER |  | CARIBOU-WESTWOOD | 017/357 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-28 | 2021-09-28 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.057587 | 40.289 | ETL.6300 | 40733895 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829666 | Not Scheduled | T2 DI DRUM-SUMMIT #2 011/137A CANCEL | 44487756 | DRUM-SUMMIT #2 | 011/137A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-28 | 2021-09-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.587827 | 39.3334 | ETL.1450 | 40876971 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829667 | Not Scheduled | T2 NN DRUM-SUMMIT #2 011/137A CANCEL | 44487756 | DRUM-SUMMIT #2 | 011/137A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-28 | 2021-09-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.587827 | 39.3334 | ETL.1450 | 40876971 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829711 | Q2 | T3 NN CRESTA-RIO OSO 014/113 RPL INSS | 31500129 | CRESTA-RIO OSO | 014/113 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-03-28 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-121.461369 | 39.7657 | ETL.4590 | 40919874 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829712 | Q2 | T2 NN IGNCIO-BOLINAS #2 18/204 RPL INSW | 31510958 | IGNACIO-BOLINAS #2 | 018/204 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-28 | 2021-09-28 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.783498 | 38.0408 | ETL.7180 | 40630066 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829907 | Q2 | T3 DI MI-WUK-CURTIS 021/006 X-BRACE | 44623652 | ETL.1073.POLE.WDPS | 021/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.253841 | 38.0207 | ETL.1073 | 44385267 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829913 | Q2 | T2 NN FORT RSS-GUALALA 35/2 RPL INSW | 31516148 | GUALALA-MONTE RIO | 035/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-28 | 2021-09-28 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.301667 | 38.5886 | ETL.6980 | 40710402 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829914 | Q2 | T2 NN IGNCI-BLINS #2 15/174 RMV PL BUT | 44640732 | IGNACIO-BOLINAS #2 | 015/174 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-28 | 2022-09-28 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.741336 | 38.0499 | ETL.7180 | 44376899 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829916 | Q2 | T2 NN SBNT-STD OL SW ST #1 4/23 RPR STRT | 44624392 | SOBRANTE-STANDARD OIL SW STA #2 | 004/023 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-09-28 | 2021-09-28 |  |  | 2021-05-22 | 2021-05-17 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.203451 | 37.9577 | ETL.3800 | 40644454 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829918 | Feb | T3 DI DRUM-RIO OSO #1 015/132 RPR INSS | 44487701 | DRUM-RIO OSO #1 | 015/132 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-03-28 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.006624 | 39.1413 | ETL.1420 | 40670147 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829927 | Mar | DI COALINGA #1-SAN MIGUEL 7/0 RPR GYWS | 44507660 | COALINGA #1-SAN MIGUEL | 007/000 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.45593 | 36.0959 | ETL.8580 | 40609728 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119829929 | Mar | DI COALINGA #1-SAN MIGUEL 7/0 RPLC HRDT | 44490795 | COALINGA #1-SAN MIGUEL | 007/000 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-09-28 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.45593 | 36.0959 | ETL.8580 | 40609728 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119830003 | Q2 | T3 DI MI-WUK-CURTIS 021/004 RPL | 44623655 | ETL.1073.INSL.CERA | 021/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.251244 | 38.0241 | ETL.1073 | 40772932 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119830498 | Not Scheduled | T3 EI NN DIABLO-GATES #1 18/76 RPR GYWS |  | DIABLO-GATES #1 | 018/076 | ICS | E | 2020_(2) High fire spread TD |  | 2020-09-29 | 2021-03-29 | [6 empty] | Tower guy | TR3 | <60D | South | WSIP | [6 empty] | '-120.759087 | 35.4507 | ETL.5960 | 40819001 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119830579 | Not Scheduled | T2 NN SPAULDING-SUMMIT 2/86 RPR SWIW | 44487980 | SPAULDING-SUMMIT | 002/086 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-09-29 | 2021-09-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.609826 | 39.3117 | ETL.8060 | 41158200 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119830727 | Q2 | T2 DI NN BRDGVLL-CTTNWD 21/189 REPLUMB | 44404807 | BRIDGEVILLE-COTTONWOOD | 021/189 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.671242 | 40.3758 | ETL.1110 | 40691065 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119830833 | Q2 | NN BRDGVLL-COTTONWOOD 023/208 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 023/208 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.714728 | 40.3727 | ETL.1110 | 44424435 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831179 | Mar | T3NT DI POE-RIO OSO 19/127 INS MRKS |  | POE-RIO OSO | 019/127 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-08 | 2022-09-08 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.5540 | 44383621 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831399 | Not Scheduled | T3NT DI CRIBOU-TABLE MTN 42/313 RPR FOND |  | CARIBOU-TABLE MTN | 042/313 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-04 | 2022-09-04 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.507377 | 39.7055 | ETL.4440 | 40649847 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831402 | Q2 | EI SAN LUIS OBSPO-OCEANO 16/85 RPL INSLW | 31517606 | SAN LUIS OBISPO-OCEANO | 016/085 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.5288522 | 35.0979 | ETL.3530 | 40712618 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831448 | Q2 | EI SAN LUIS OBSPO-OCEANO 16/84 RPL INSLW | 31517606 | SAN LUIS OBISPO-OCEANO | 016/084 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.5281756 | 35.0979 | ETL.3530 | 40610713 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831502 | Q4 | T3 EI MAPLE CREEK-HOOPA 24/1 REFRAME | 31514684 | MAPLE CREEK-HOOPA | 024/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-03-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.646045 | 40.9992 | ETL.7490 | 40586866 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831527 | Q2 | EI LOS BANOS-MIDWAY #2 47/198 RPR STRT | 44501255 | LOS BANOS-MIDWAY #2 | 047/198 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-30 | 2021-09-30 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.508748 | 36.5204 | ETL.6010 | 40863978 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119831647 | Q2 | EI SAN LUIS OBSPO-OCEANO 16/082 RPL STRW | 31517605 | SAN LUIS OBISPO-OCEANO | 016/082 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.525969 | 35.0979 | ETL.3530 | 40862018 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831738 | Q2 | EI SAN LUIS OBSPO-OCEANO 16/81 RPL INSLW | 31517606 | SAN LUIS OBISPO-OCEANO | 016/081 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.525103 | 35.0979 | ETL.3530 | 40888065 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831834 | Q2 | EI SAN LUIS OBSPO-OCEANO 16/80 RPL INSLW | 31517606 | SAN LUIS OBISPO-OCEANO | 016/080 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.5230687 | 35.0979 | ETL.3530 | 40834478 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831897 | Q2 | EI SAN LUIS OBISPO-OCEAN 16/79 RPL INSLW | 31517606 | SAN LUIS OBISPO-OCEANO | 016/079 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.5214217 | 35.0979 | ETL.3530 | 40837081 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119831992 | Q2 | EI SAN LUIS OBISPO-OCEAN 16/78 RPL INSLW | 31517606 | SAN LUIS OBISPO-OCEANO | 016/078 | 93I | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.5203395 | 35.0979 | ETL.3530 | 40782849 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119832012 | Q2 | EI SAN LUIS OBISPO-OCEANO 16/78 RPR STRW |  | SAN LUIS OBISPO-OCEANO | 016/078 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-04-05 | 2021-04-08 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.520327 | 35.0979 | ETL.3530 | 40753997 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119832056 | Not Scheduled | EI SAN LUIS OBISPO-OCEANO 16/77 RPL STRW | 31517605 | SAN LUIS OBISPO-OCEANO | 016/077 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | [9 empty] | South | WSIP | [6 empty] | '-120.51946 | 35.0979 | ETL.3530 | 40751954 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119832190 | Not Scheduled | EI SAN LUIS OBSP-OCEANO 16/86 RPR ROAD | 44378910 | SAN LUIS OBISPO-OCEANO | 016/086 | CHS | F | 2020_(3) On high spread structure |  | 2020-09-30 | 2022-09-30 |  |  |  | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.530541 | 35.0978 | ETL.3530 | 40652040 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119833895 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 12/340 RPR STRW | 44487807 | COLGATE-ALLEGHANY | 012/340 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-03-30 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.012633 | 39.4167 | ETL.6470 | 40869656 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119833998 | Q2 | NN WEIMAR #1 010/152R RPL STRW | 31514914 | WEIMAR #1 | 010/152 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 |  |  | 2021-04-08 | 2021-03-22 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.7560 | 44414822 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834035 | Q2 | NN WEIMAR #1 010/152 RPL POLE | 31514914 | WEIMAR #1 | 010/152 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 |  |  | 2021-04-08 | 2021-03-22 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.7560 | 44414821 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834064 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 12/314 RPR STRW | 44487807 | COLGATE-ALLEGHANY | 012/314 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-03-30 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.024112 | 39.4074 | ETL.6470 | 40693206 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834074 | Q2 | NN WEIMAR #1 010/152L REPL POLE | 31514914 | WEIMAR #1 | 010/152 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 |  |  | 2021-04-08 | 2021-03-22 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.7560 | 44414820 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834840 | Not Scheduled | T3NT NN DRM-SMIT #1 2/28 CANCEL | 44487746 | DRUM-SUMMIT #1 | 002/028 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.735031 | 39.2702 | ETL.1440 | 44963250 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834939 | Q2 | T3 DI MI-WUK-CURTIS 22/6 RPLC INSW | 31515461 | ETL.1073.INSL.CERA | 022/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.262434 | 38.0119 | ETL.1073 | 40829532 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834959 | Q2 | T3 DI MI-WUK-CURTIS 019/006 RPR INSW | 44623656 | ETL.1073.INSL.CERA | 019/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.23741 | 38.0477 | ETL.1073 | 40829526 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119834993 | Q2 | T3 DI MI-WUK-CURTIS 18/6 RPR POLE | 44623657 | ETL.1073.POLE.WDPS | 018/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.219576 | 38.0529 | ETL.1073 | 44837660 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835049 | Q2 | T3 DI MI-WUK-CURTIS 22/7 RPL POLE | 31501639 | ETL.1073.POLE.WDPS | 022/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.26501 | 38.0094 | ETL.1073 | 44774784 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835092 | Q2 | T3NT DI PTTSBG-SN MAT 13/52 RPR FOND |  | PITTSBURG-SAN MATEO | 013/052 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-02 | 2022-09-02 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.888964 | 37.8575 | ETL.5463 | 40805055 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835160 | Q2 | T3 DI MI-WUK-CURTIS 019/006 RPR GYWW | 44623658 | ETL.1073.POLE.WDPS | 019/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.23741 | 38.0477 | ETL.1073 | 44779571 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835168 | Not Scheduled | T3 NN RND MTN-CTTNWD #3 32/267 RPR STRT | 43932111 | ROUND MTN-COTTONWOOD #3 | 032/267 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-09-30 | 2021-03-29 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.983416 | 40.7381 | ETL.5650 | 40804846 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835303 | Not Scheduled | T3NT NN DRM-SMIT #2 4/57C RMV DEBRIS | 44487749 | DRUM-SUMMIT #2 | 004/057 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-08 | 2022-09-08 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.703281 | 39.2936 | ETL.1450 | 44947122 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835460 | Q2 | T2 DI FORT ROSS-GUALALA 40/0 RPR INSW |  | GUALALA-MONTE RIO | 040/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-09-30 | 2021-09-30 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.314401 | 38.6406 | ETL.6980 | 40628765 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835889 | Mar | T3 MORAGA-OAKLAND #3 00/006 RPL STRT | 44623421 | MORAGA-OAKLAND #3 | 000/006 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-01 | 2021-04-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.17228 | 37.8458 | ETL.2740 | 40804648 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 426 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119835892 | Feb | T3 MORAGA-OAKLAND #1 /005 RPL STRT | 44611129 | MORAGA-OAKLAND #1 | 000/005 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-01 | 2021-04-01 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.172219 | 37.846 | ETL.2720 | 40745882 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 426 | Bay |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119836088 | Not Scheduled | T2 DI CONTRA CSTA-MRGA #1 24/113 PAINT | 44587769 | CONTRA COSTA-MORAGA #1 | 024/113 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.120888 | 37.8621 | ETL.5452 | 40822239 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119836890 | Q2 | T2 DI MI-WUK-CURTIS 21/3 RPL POLE | 31516011 | ETL.1073.POLE.WDPS | 021/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.249445 | 38.0264 | ETL.1073 | 44774773 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119836898 | Q2 | T2 DI MI-WUK-CURTIS 21/3 RPL POLE | 31516011 | ETL.1073.POLE.WDPS | 021/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.249445 | 38.0264 | ETL.1073 | 44774774 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119836929 | Not Scheduled | EI MRO BY-SN LUIS OBISPO #2 0/2 RPL INSS |  | MORRO BAY-SAN LUIS OBISPO #2 | 000/002 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-10-01 | [9 empty] | South | WSIP | [6 empty] | '-120.8533045 | 35.376 | ETL.2820 | 44274757 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837053 | Q2 | T3 DI MI-WUK-CURTIS 021/005 RPR WDPKR | 44623680 | ETL.1073.POLE.WDPS | 021/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-03-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-120.251756 | 38.0234 | ETL.1073 | 40744854 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837377 | Mar | T3 DI MONTA VISTA-BURNS 012/095 RPR GYWW | 44610148 | MONTA VISTA-BURNS | 012/095 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-09-28 | 2021-03-28 | 2021-03-17 | 2021-03-18 | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.166515 | 37.1678 | ETL.7590 | 44229328 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837442 | Q2 | T2 DI MI-WUK-CURTIS 019/000 RPR GYWW | 44623684 | ETL.1073.POLE.WDPS | 019/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.224541 | 38.0511 | ETL.1073 | 44774768 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837444 | Q2 | T2 DI MI-WUK-CURTIS 019/000 RPR GYWW | 44623685 | ETL.1073.POLE.WDPS | 019/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-24 | 2021-08-03 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.224541 | 38.0511 | ETL.1073 | 44774767 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837506 | Not Scheduled | EI MORRO BAY-TEMPLETON 0/5 RPL INSS | 31515414 | MORRO BAY-TEMPLETON | 000/005 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-10-01 | [9 empty] | South | WSIP | [6 empty] | '-120.8429098 | 35.3763 | ETL.5933 | 40781744 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837507 | Not Scheduled | EI MORRO BY-CALIF. FLTS SW STA 0/5 RPL I | 31527642 | MORRO BAY-GATES #2 | 000/005 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-10-01 | [9 empty] | South | WSIP | [6 empty] | '-120.8429098 | 35.3763 | ETL.5280 | 40781746 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119837985 | Not Scheduled | EI MORRO BAY-TEMPLETON 00/06 RPL INSS | 31527295 | MORRO BAY-TEMPLETON | 000/006 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-10-01 | [9 empty] | South | WSIP | [6 empty] | '-120.8411346 | 35.3776 | ETL.5933 | 40851699 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119838433 | Mar | T3 EI DIABLO-GATES #1 21/088 RPR STRT | 44490734 | DIABLO-GATES #1 | 021/088 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-04-01 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.736174 | 35.4914 | ETL.5960 | 40873355 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119838562 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/486 RPR GYWW | 44487980 | SPAULDING-SUMMIT | 015/486 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.387052 | 39.3284 | ETL.8060 | 44349561 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119838727 | Q2 | T2 DI PEORIA TAP 0/3 RPLC INSW | 31515467 | PEORIA TAP | 000/003 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-10-01 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.489292 | 37.907 | ETL.2391 | 40681754 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-05 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119838761 | Not Scheduled | T2 DI SPAULDING-SUMMIT 9/330 RPR GYWW | 44487980 | SPAULDING-SUMMIT | 009/330 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.483508 | 39.3168 | ETL.8060 | 44349539 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119838767 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/398 RMV DEBRIS | 44487981 | SPAULDING-SUMMIT | 011/398 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2022-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.448092 | 39.3175 | ETL.8060 | 40618256 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119838770 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/398 HIGH SIGN | 44487981 | SPAULDING-SUMMIT | 011/398 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2022-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.448092 | 39.3175 | ETL.8060 | 40618256 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119839018 | Q3 | T2 DI CARIBOU #2 :004/005 RPR GYWW |  | CARIBOU #2 | :004/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-01 | 2021-10-01 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.005889 | 39.9856 | ETL.6280 | 40758773 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119839429 | Q4 | T3 DI MAPLE CREEK-HOOPA 25/06 RPL PL | 31515411 | MAPLE CREEK-HOOPA | 025/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-30 | 2021-01-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.646194 | 41.0173 | ETL.7490 | 40811061 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119840573 | Not Scheduled | T2 DI SPAULDING-SUMMIT 13/448 RPR BOND | 44565237 | SPAULDING-SUMMIT | 013/448 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.416097 | 39.3282 | ETL.8060 | 40810179 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119840994 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 6/176 RPL STRW | 31515445 | COLGATE-ALLEGHANY | 006/176 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-01 | 2021-04-01 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.077494 | 39.3456 | ETL.6470 | 40873658 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119843987 | Not Scheduled | EI DIABLO-GATES #1 13/057 REPL INSS | 31527292 | DIABLO-GATES #1 | 013/057 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 | [9 empty] | South | WSIP | [6 empty] | '-120.774257 | 35.3834 | ETL.5960 | 40821273 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119844804 | Not Scheduled | DI SPAULDING-SUMMIT 9/311 RPL INSW | 31515500 | SPAULDING-SUMMIT | 009/311 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.8060 | 44349624 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119844808 | Not Scheduled | DI SPAULDING-SUMMIT 9/311 RPR GYWW | 44487980 | SPAULDING-SUMMIT | 009/311 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.49274 | 39.3147 | ETL.8060 | 44349534 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119846104 | Not Scheduled | T2 WV DRUM-SUMMIT#2 27/325 RPL PLE |  | DRUM-SUMMIT #2 | 027/325 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-05-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3336546 | 39.3118 | ETL.1450 | 44553713 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119846107 | Not Scheduled | T2 WV DRUM-SUMMIT#2 27/325 RPL PLE |  | DRUM-SUMMIT #2 | 027/325 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-05-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3336544 | 39.3118 | ETL.1450 | 44553546 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119847644 | Mar | T3NT NN LAURELES-OTTER 8/14 RMV PL BUTT | 44587870 | LAURELES-OTTER | 008/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-09 | 2022-09-09 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.801512 | 36.4182 | ETL.7380 | 40771071 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119847917 | Not Scheduled | DI SPAULDING-SUMMIT 8/279 RPL POLE | 31515501 | SPAULDING-SUMMIT | 008/279 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-10-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.510741 | 39.3139 | ETL.8060 | 40602251 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119848250 | Not Scheduled | DI GATES-PANOCHE #2 041/196 RPR INSS | 44507621 | GATES-PANOCHE #2 | 041/196 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.558863 | 36.6264 | ETL.4730 | 40839197 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119848581 | Mar | T3NT DI DRM-GRSS VLLY-WMR 0/12 RMV BUTT | 44487887 | DRUM-GRASS VALLEY-WEIMAR | 000/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-08 | 2022-09-08 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.759258 | 39.2543 | ETL.6760 | 40598639 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850022 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/374 BOND WIRE | 44488770 | SPAULDING-SUMMIT | 011/374 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.459207 | 39.3189 | ETL.8060 | 40828146 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850051 | Not Scheduled | DI SPAULDING-SUMMIT 006/227 RPR GYWW | 44488770 | SPAULDING-SUMMIT | 006/227 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-10-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.538817 | 39.3088 | ETL.8060 | 44341343 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119850083 | Q2 | BRIDGEVILLE-COTTONWOOD 29/245L RPL POLE | 31526498 | BRIDGEVILLE-COTTONWOOD | 029/245 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-03 | 2021-09-03 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.815161 | 40.3656 | ETL.1110 | 44561128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850084 | Mar | EI GEYSERS #3-CLOVERDALE 9/107 RPL STRW | 31515454 | GEYSERS #3-CLOVERDALE | 009/107 | 70Y | E | 2020_(1a) PSPS |  | 2020-09-03 | 2021-09-03 |  |  | 2021-03-27 | 2021-03-08 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1650 | 44298331 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119850087 | Q2 | T2 DI HAT CRK #1-WSTWD 12/246 RPL STRW | 31516312 | HAT CREEK #1-WESTWOOD | 012/246 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.37032 | 40.8192 | ETL.7030 | 40600197 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850104 | Not Scheduled | T3NT NN DRUM-SUMMIT #2 0/6A RMV PL BUTT | 44487749 | DRUM-SUMMIT #2 | 000/006A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-16 | 2022-09-16 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.760504 | 39.255 | ETL.1450 | 44868809 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850141 | Not Scheduled | T3NT DI MORAG-SN LENDRO #3 5/39 PNT STRS | 43728142 | MORAGA-SAN LEANDRO #3 | 005/039 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-02 | 2022-10-02 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.123211 | 37.7768 | ETL.2790 | 40857660 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850142 | Mar | T3 DI MORAGA-SAN LENDRO #3 5/39 RPL HRDT |  | MORAGA-SAN LEANDRO #3 | 005/039 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-04-02 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.123211 | 37.7768 | ETL.2790 | 40857660 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850160 | Q2 | T2 DI HAT CREEK #1-WSTWD 0/17 REFRAME | 31512257 | HAT CREEK #1-WESTWOOD | 000/017 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.530702 | 40.9261 | ETL.7030 | 40760940 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850165 | Q2 | T2 DI HAT CREEK #1-WSTWD 15/297 RPR POLE |  | HAT CREEK #1-WESTWOOD | 015/297 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.334983 | 40.7907 | ETL.7030 | 40827471 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850204 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/352 INS GMKW | 44488778 | SPAULDING-SUMMIT | 010/352 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2022-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.47289 | 39.3179 | ETL.8060 | 40770696 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850449 | Not Scheduled | NN ATSCDRO-SN LS OBISPO 6/118 INS MRKW |  | ATASCADERO-SAN LUIS OBISPO | 006/118 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-17 | 2022-09-16 | [9 empty] | South | WSIP | [6 empty] | '-120.62473 | 35.3841 | ETL.8490 | 42699985 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119850927 | Feb | DI LAYTONVILLE-COVELO 011/008 RMV BUTT | 44579512 | LAYTONVILLE-COVELO | 011/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-09-16 | 2022-09-16 |  |  | 2021-02-24 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.285811 | 39.7432 | ETL.7390 | 40878663 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119851041 | Not Scheduled | T3NT NN DRUM-SUMMIT #1 1/19 RMV PL BUTT | 44497481 | DRUM-SUMMIT #1 | 001/019 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2022-09-17 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.742626 | 39.2588 | ETL.1440 | 44338115 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119851314 | Q2 | T3NT NN MSRI FLT-GLD H#1 17/152 INS MRKS | 44488761 | MISSOURI FLAT-GOLD HILL #1 | 017/152 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-17 | 2022-09-17 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.870283 | 38.6698 | ETL.2660 | 40660285 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119851637 | Not Scheduled | T2 NN SPAULDING-SUMIT 0/32 RMV PL BUT | 44502587 | SPAULDING-SUMMIT | 000/032 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2022-09-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.629841 | 39.3216 | ETL.8060 | 40660108 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119852240 | Not Scheduled | DI SPAULDING-SUMMIT 008/276 RPR BOND | 44488866 | SPAULDING-SUMMIT | 008/276 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-10-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.51422 | 39.3147 | ETL.8060 | 40885549 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119852244 | Q2 | T2 DI HAT CRK #1-WESTWD 9/177 REPL POLE | 31515623 | HAT CREEK #1-WESTWOOD | 009/177 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.406102 | 40.8635 | ETL.7030 | 40759003 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119853346 | Q2 | EI MIDWAY-WHIRLWIND 37/153 BENT STL | 44490869 | MIDWAY-WHIRLWIND | 037/153 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-118.935575 | 35.1257 | ETL.6030 | 40648007 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119854051 | Not Scheduled | EI IGNACIO-MRE ISLAND #2 23/160 RPL INSS | 31527362 | IGNACIO-MARE ISLAND #2 | 023/160 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-10 | 2021-09-10 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.16881 | 38.146 | ETL.1840 | 40889603 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119854058 | Not Scheduled | EI VC-VCVL-JMSN-NORTH 23/164 RPL INSS |  | VACA-VACAVILLE-JAMESON-NTH TWR | 023/164 | 93K | E | 2020_(2) High fire spread TD |  | 2020-09-08 | 2021-09-08 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.17466 | 38.1372 | ETL.4100 | 40725777 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119854147 | Mar | T3 DEER CREEK-DRUM 4/103 REFRAME | 31515571 | DEER CREEK-DRUM | 004/103 | 93E | E | 2020_(2) High fire spread TD |  | 2020-10-05 | 2021-04-05 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.799181 | 39.2575 | ETL.6690 | 40757026 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119854835 | Q2 | EI MIDWAY-WHIRLWIND 38/157 RPR STRT | 44506752 | MIDWAY-WHIRLWIND | 038/157 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-118.917008 | 35.1255 | ETL.6030 | 40807845 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119854887 | Mar | T2 EI DIABLO-GATES #1 6/30 BENT STEEL | 44506750 | DIABLO-GATES #1 | 006/030 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.811372 | 35.2809 | ETL.5960 | 40592904 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119855706 | Q3 | T2 EI TESLA-METCALF 32/135 RPR GYWW | 44621455 | TESLA-METCALF | 032/135 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-07-10 | 2021-07-05 |  | TLN/TLQ error | Tower guy | TR2 |  | Central | WSIP | [6 empty] | '-121.729081 | 37.2585 | ETL.6110 | 40753708 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119855716 | Q3 | T2 EI TESLA-METCALF 32/135 BENT STL |  | TESLA-METCALF | 032/135 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.729081 | 37.2585 | ETL.6110 | 40753708 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119855912 | Q3 | T2 EI TESLA-METCALF 32/134 RPR FOND |  | TESLA-METCALF | 032/134 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.727699 | 37.2623 | ETL.6110 | 40761166 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119856128 | Q3 | T2NT NN BRDGVLL-CTTNWD 63/459 RMV DBRS | 44477511 | BRIDGEVILLE-COTTONWOOD | 063/459 | ICS | F | 2020_(3) On high spread structure |  | 2020-10-03 | 2022-10-03 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.421282 | 40.3923 | ETL.1110 | 40759205 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119856374 | Q2 | T2 DI HAT CREEK #1-WESTWD 9/182 RPL STRW | 31515623 | HAT CREEK #1-WESTWOOD | 009/182 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.403737 | 40.8601 | ETL.7030 | 40600140 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119856589 | Q2 | T2 DI HAT CRK #1-WSTWD 15/301 RPR STRW |  | HAT CREEK #1-WESTWOOD | 015/301 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.332242 | 40.7885 | ETL.7030 | 40770727 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119856662 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/489 RPL INSW | 31515500 | SPAULDING-SUMMIT | 015/489 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.384766 | 39.3289 | ETL.8060 | 40628965 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119857404 | Q4 | T3NT DI MAPLE CREEK-HPA 15/0 RMV DEBRIS | 44461912 | MAPLE CREEK-HOOPA | 015/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-24 | 2022-09-24 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.711605 | 40.9086 | ETL.7490 | 44963388 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119857405 | Q4 | T3 DI MAPLE CREEK-HOOPA 15/0 RPLC GYWW | 44482958 | MAPLE CREEK-HOOPA | 015/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-24 | 2021-03-24 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.711605 | 40.9086 | ETL.7490 | 44963388 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119857474 | Q4 | T2 EI MAPLE CREEK-HOOPA 8/5 INS GYWW | 44497905 | MAPLE CREEK-HOOPA | 008/005 | ICW | E | 2020_(3) On high spread structure |  | 2020-10-05 | 2021-10-05 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.801362 | 40.8638 | ETL.7490 | 44707296 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119858062 | Not Scheduled | DI SPAULDING-SUMMIT 7/256 BOND GUY | 44497664 | SPAULDING-SUMMIT | 007/256 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2021-10-05 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.524125 | 39.3068 | ETL.8060 | 40771564 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119858299 | Q3 | EI TESLA-METCALF 34/144 RPR FOND |  | TESLA-METCALF | 034/144 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-10-06 |  |  | 2021-07-10 | 2021-07-05 | [5 empty] | Central | WSIP | [6 empty] | '-121.743752 | 37.2289 | ETL.6110 | 40761197 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119858614 | Q2 | EI MIDWAY-WHIRLWIND 40/166 RPR FOUND | 44506752 | MIDWAY-WHIRLWIND | 040/166 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2021-10-06 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-118.879641 | 35.125 | ETL.6030 | 40808224 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Midway |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119858710 | Q2 | DI GATES-PANOCHE #1 43/205 RPR FOND | 44490730 | GATES-PANOCHE #1 | 043/205 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.579652 | 36.649 | ETL.4720 | 40761082 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119859386 | Not Scheduled | T2 WV DRUM-SUMMIT #2 10/121B RPL PLE | 31438533 | DRUM-SUMMIT #2 | 010/121B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2021-10-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.611789 | 39.3238 | ETL.1450 | 44212216 | Structure-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119860623 | Not Scheduled | T2 DIABLO-MIDWAY #2 31/127 RPR INSS |  | DIABLO-MIDWAY #2 | 031/127 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-10-06 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.311446 | 35.1698 | ETL.5970 | 40836732 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119861152 | Q3 | T2 EI TESLA-METCALF 31/129 RPR GYWS | 44621455 | TESLA-METCALF | 031/129 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-10-06 |  |  | 2021-07-10 | 2021-07-05 |  | TLN/TLQ error | Tower guy | TR2 |  | Central | WSIP | [6 empty] | '-121.718846 | 37.2811 | ETL.6110 | 40869327 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119861553 | Not Scheduled | T3 EI GYSRS #9-LKVILL :0/02 RPL INSS |  | GEYSERS #9-LAKEVILLE | :000/002 | 93K | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.761909 | 38.7371 | ETL.4780 | 44907401 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119862681 | Q2 | T2 DI BRIDGVLLE-CTTNWD 11/102R RPLC STRW | 31526498 | BRIDGEVILLE-COTTONWOOD | 011/102 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-09-08 | 2021-09-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423205 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119862773 | Not Scheduled | DI GATES-PANOCHE #1 5/27 RPL INSLS | 31514618 | GATES-PANOCHE #1 | 005/027 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.177268 | 36.2063 | ETL.4720 | 40836445 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119863078 | Q2 | DI GATES-PANOCHE #1 040/191 RPR FOND | 44490954 | GATES-PANOCHE #1 | 040/191 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2022-10-06 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.547907 | 36.6144 | ETL.4720 | 40594750 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119863546 | Not Scheduled | DI SPAULDING-SUMMIT 006/224 RPR GYWW | 44497664 | SPAULDING-SUMMIT | 006/224 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2021-10-05 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.542004 | 39.3077 | ETL.8060 | 40751913 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119863809 | Not Scheduled | T3 DI FULTON-CALISTOGA :3/3 RPR GYWW | 44597303 | FULTON-CALISTOGA | :003/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.594802 | 38.6355 | ETL.6880 | 40912433 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119863897 | Not Scheduled | DIABLO-GATES #1 13/57 RPL INSS | 31527292 | DIABLO-GATES #1 | 013/057 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 | [9 empty] | South | WSIP | [6 empty] | '-120.7742744 | 35.3834 | ETL.5960 | 40848340 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119864052 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/489 RPR GUY | 44497664 | SPAULDING-SUMMIT | 015/489 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2021-10-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.384793 | 39.3287 | ETL.8060 | 40602265 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119864658 | Not Scheduled | T3 MIDDLE FORK #1 0/001 INST DAMPERS | 44497490 | MIDDLE FORK #1 | 000/001 | ICW | E | 2020_(3) On high spread structure |  | 2020-10-07 | 2021-04-07 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-120.596263 | 39.024 | ETL.8405 | 40598748 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119864718 | Mar | T3 MIDDLE FORK #1 0/1 RMV STEPS | 44508966 | MIDDLE FORK #1 | 000/001 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-04-07 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.596263 | 39.024 | ETL.8405 | 44979005 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119866007 | Not Scheduled | T3 DI MNTE RIO-FRT ROSS 019/002 RPL INSW | 31515746 | ETL.6979.INSL.NCER | 019/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-123.084409 | 38.4816 | ETL.6979 | 40710381 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119867553 | Mar | T3 EI DIABLO-GATES #1 1/008 RPR STRT | 44490734 | DIABLO-GATES #1 | 001/008 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.830317 | 35.221 | ETL.5960 | 40869980 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119867772 | Q3 | T2 EI TESLA-METCALF 29/120 BENT STEEL |  | TESLA-METCALF | 029/120 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.701989 | 37.3073 | ETL.6110 | 40592647 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119868572 | Not Scheduled | DI GATES-PANOCHE #1 37/173 RPL INSS | 31527293 | GATES-PANOCHE #1 | 037/173 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-10-02 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.509631 | 36.5673 | ETL.4720 | 40680461 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119868574 | Q2 | DI GATES-PANOCHE #1 37/173 RPR STRT | 44501250 | GATES-PANOCHE #1 | 037/173 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.509868 | 36.5676 | ETL.4720 | 40651617 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119868575 | Q2 | DI GATES-PANOCHE #1 37/173 RPR FOND | 44501250 | GATES-PANOCHE #1 | 037/173 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2022-10-02 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.509868 | 36.5676 | ETL.4720 | 40651617 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119869417 | Mar | T3 EI DIABLO-GATES #1 3/017 RPR STRU | 44595661 | DIABLO-GATES #1 | 003/017 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-04-07 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.80518 | 35.2367 | ETL.5960 | 40819456 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119869445 | Not Scheduled | T3 EI DIABLO-GATES #1 2/013 RPR GYWW |  | DIABLO-GATES #1 | 002/013 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 | [6 empty] | Tower guy | TR3 | <60D | South | WSIP | [6 empty] | '-120.817968 | 35.2271 | ETL.5960 | 40658784 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119869597 | Q2 | T2 DI HAT CRK #1-WESTWD 10/210 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 010/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.390905 | 40.8417 | ETL.7030 | 40876183 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119870108 | Q3 | T2 DI CARIBOU-PLUMAS JCT 6/12 RPR GYWW |  | CARIBOU-PLUMAS JCT | 006/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-08-13 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.06262 | 40.0214 | ETL.6290 | 40659864 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119870357 | Mar | T3 DI DRUM-RIO OSO #1 11/112 RPR STRT | 44501800 | DRUM-RIO OSO #1 | 011/112 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-05 | 2021-04-05 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945327 | 39.1657 | ETL.1420 | 40689725 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119870438 | Q2 | T2 DI HAT CREEK #1-WESTWD 8/155 RPR STRW |  | HAT CREEK #1-WESTWOOD | 008/155 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.416455 | 40.8783 | ETL.7030 | 40600137 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871049 | Q2 | T2 DI HAT CREEK #1-WSTWOOD 1/39 RPL STRW | 31516312 | HAT CREEK #1-WESTWOOD | 001/039 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.509383 | 40.9228 | ETL.7030 | 40596890 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871146 | Q3 | T2 EI TESLA-METCALF 26/107 BENT STEEL |  | TESLA-METCALF | 026/107 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-08 | 2021-10-08 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.677296 | 37.347 | ETL.6110 | 40811303 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871289 | Not Scheduled | DI GATES-PANOCHE #1 036/169B RPL INSS | 31527293 | GATES-PANOCHE #1 | 036/169B | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2021-10-02 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.501256 | 36.5571 | ETL.4720 | 40741120 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119871319 | Not Scheduled | EI MRR BY-SN LS OBSP #2 13/73 RPL INSLS | 31527051 | MORRO BAY-SAN LUIS OBISPO #2 | 013/073 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-08 | 2021-10-08 | [9 empty] | South | WSIP | [6 empty] | '-120.6765013 | 35.2593 | ETL.2820 | 40679246 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871456 | Not Scheduled | DI SPAULDING-SUMMIT 005/201 RMV BUTT | 44497663 | SPAULDING-SUMMIT | 005/201 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2022-10-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.552036 | 39.3048 | ETL.8060 | 40681430 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119871459 | Not Scheduled | DI SPAULDING-SUMMIT 005/201 HIGH SIGN | 44497300 | SPAULDING-SUMMIT | 005/201 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2022-10-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.552036 | 39.3048 | ETL.8060 | 40681430 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119871536 | Feb | EI LAYTONVILLE-COVELO 14/001 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-02-25 | 2021-02-25 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.265541 | 39.7694 | ETL.7390 | 44412045 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871538 | Feb | EI LAYTONVILLE-COVELO 14/001 RPR GYWW | 44610673 | LAYTONVILLE-COVELO | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-09-16 | 2021-09-16 |  |  | 2021-02-25 | 2021-02-25 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.265541 | 39.7694 | ETL.7390 | 44412046 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871717 | Q2 | T2 DI HAT CREEK #1-WESTWOD 1/31 REFRAME | 31512257 | HAT CREEK #1-WESTWOOD | 001/031 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.51726 | 40.924 | ETL.7030 | 40598392 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871828 | Mar | T3 DI DRUM-RIO OSO #2 11/112 RPR STRT | 44501803 | DRUM-RIO OSO #2 | 011/112 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-05 | 2021-04-05 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945398 | 39.1655 | ETL.1430 | 40647222 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119871901 | Mar | T3 DRUM-GRS VLY-WMR 8/201 REFRAME | 31514120 | DRUM-GRASS VALLEY-WEIMAR | 008/201 | 93E | E | 2020_(2) High fire spread TD |  | 2020-10-08 | 2021-04-08 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.855296 | 39.185 | ETL.6760 | 40874779 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119872152 | Q2 | T2 DI HAT CRK #1-WSTWD 16/317 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 016/317 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-02 | 2021-10-02 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.32119 | 40.7796 | ETL.7030 | 40616880 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119872652 | Q2 | DI GATES-PANOCHE #1 042/201 RPR STRT | 44501250 | GATES-PANOCHE #1 | 042/201 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.57045 | 36.639 | ETL.4720 | 40587486 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119873323 | Q2 | DI GATES-PANOCHE #1 38/180 RPR STRT | 44501250 | GATES-PANOCHE #1 | 038/180 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2021-10-06 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.524554 | 36.5858 | ETL.4720 | 40604963 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119873464 | Q2 | T2 DI TRINITY-MAPLE CREEK 29/4 RPR GYWW | 44484765 | TRINITY-MAPLE CREEK | 029/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.440378 | 40.6996 | ETL.8170 | 40906451 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119873465 | Q2 | T2NT DI TRNTY-MAPLE CRK 29/4 RMV DEBRIS | 44470706 | TRINITY-MAPLE CREEK | 029/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.440378 | 40.6996 | ETL.8170 | 40906451 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119873564 | Not Scheduled | DI SPAULDING-SUMMIT 7/254 RPR GYWW | 44506585 | SPAULDING-SUMMIT | 007/254 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2021-10-06 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.524507 | 39.3067 | ETL.8060 | 40702000 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119873565 | Not Scheduled | DI SPAULDING-SUMMIT 7/254 RMV PL BUTT | 44506586 | SPAULDING-SUMMIT | 007/254 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2022-10-06 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.524507 | 39.3067 | ETL.8060 | 40702000 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119873698 | Q2 | T2 DI HAT CRK #1-WSTWOOD 11/217 RPR STRW |  | HAT CREEK #1-WESTWOOD | 011/217 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.387557 | 40.837 | ETL.7030 | 40617056 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119878866 | Q2 | T2 DI HAT CREEK #1-WSTWD 16/326 RPR STRW |  | HAT CREEK #1-WESTWOOD | 016/326 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.315032 | 40.7746 | ETL.7030 | 40877476 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119878869 | Q2 | T2 DI HAT CRK#1-WESTWOOD 04/90 REFRAME | 31512257 | HAT CREEK #1-WESTWOOD | 004/090 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.45935 | 40.915 | ETL.7030 | 40598386 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887435 | Q2 | T2 DI HAT CRK #1-WSTWD 18/346 RPR GYWW |  | HAT CREEK #1-WESTWOOD | 018/346 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.301011 | 40.7633 | ETL.7030 | 40592089 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887437 | Q2 | T2 DI HAT CRK 1-WSTWOOD 4/80 RPR STRW |  | HAT CREEK #1-WESTWOOD | 004/080 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.468715 | 40.9165 | ETL.7030 | 40598383 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887446 | Q2 | T2 DI HT CRK #1 WSTWD 015/304 RPR STRW |  | HAT CREEK #1-WESTWOOD | 015/304 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.330255 | 40.7868 | ETL.7030 | 40616871 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887447 | Q2 | T2 DI HT CRK #1 WSTWD 015/304 REFRAME | 31512257 | HAT CREEK #1-WESTWOOD | 015/304 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.330255 | 40.7868 | ETL.7030 | 40616871 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887551 | Not Scheduled | DI DIVIDE-CABRILLO #1 2/40 RMV PL BUTT |  | DIVIDE-CABRILLO #1 | 002/040 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-06 | 2022-10-06 | [9 empty] | South | WSIP | [6 empty] | '-120.441583 | 34.7855 | ETL.1380 | 40598008 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887554 | Q2 | T2NT DI HT CRK#1 WWD 009/180 REFRAME | 31512257 | HAT CREEK #1-WESTWOOD | 009/180 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.404658 | 40.8615 | ETL.7030 | 40868430 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887555 | Q2 | T2NT DI HT CRK#1 WWD 009/180 RMV DEBRIS |  | HAT CREEK #1-WESTWOOD | 009/180 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-05 | 2022-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.404658 | 40.8615 | ETL.7030 | 40868430 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887621 | Feb | T3 DI DRUM-RIO OSO #2 012/113 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 012/113 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-04-05 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.951542 | 39.1636 | ETL.1430 | 40684689 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887622 | Not Scheduled | T3 DI DRUM-RIO OSO #2 012/113 RPR STRT | 44501803 | DRUM-RIO OSO #2 | 012/113 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-04-05 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-120.950991 | 39.1638 | ETL.1430 | 40655212 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887624 | Not Scheduled | T3 DI DRUM-RIO OSO#1 12/113 RPR STRT | 44501800 | DRUM-RIO OSO #1 | 012/113 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-120.951119 | 39.164 | ETL.1420 | 40660105 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887643 | Q2 | DI GARBERVLLE-LAYTNVILL 045/000 RMV BUTT | 44484408 | GARBERVILLE-LAYTONVILLE | 045/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-09 | 2022-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.602321 | 39.9609 | ETL.8365 | 40912498 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119887690 | Mar | T2 DI KONOCTI-MDLTWN 13/6 RPL HRDW | 44610651 | KONOCTI-MIDDLETOWN | 013/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.587482 | 38.7682 | ETL.6380 | 40810812 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119888474 | Not Scheduled | T3 COLGATE-CHALLENGE 8/140 RPL POLE | 31515950 | COLGATE-CHALLENGE | 008/140 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-10 | 2021-04-10 | [7 empty] | TR3 | <60D | North Valley | WSIP | [6 empty] | '-121.197523 | 39.4231 | ETL.6480 | 40655143 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119889948 | Q2 | T2 EI MIDWAY-WHIRLWIND 51/207 RPR GYWS | 44571727 | MIDWAY-WHIRLWIND | 051/207 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-08 | 2022-02-03 |  |  | 2021-06-14 | 2021-06-01 |  |  | Tower guy | TR2 | WECC | South | WSIP | [6 empty] | '-118.709135 | 35.0836 | ETL.6030 | 40807881 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119890044 | Feb | T2 EI MIDWAY-WHIRLWIND 52/214 RMV NEST | 44516057 | MIDWAY-WHIRLWIND | 052/214 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-09 | 2021-10-09 |  |  | 2021-02-11 | 2021-02-08 |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.68936 | 35.0674 | ETL.6030 | 40762999 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119890045 | Q2 | T2 EI MIDWAY-WHIRLWIND 50/205 RPR GYWS | 44571727 | MIDWAY-WHIRLWIND | 050/205 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-08 | 2021-10-08 |  |  | 2021-06-14 | 2021-06-01 |  |  | Tower guy | TR2 | WECC | South | WSIP | [6 empty] | '-118.715685 | 35.087 | ETL.6030 | 40764251 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119890343 | Q2 | T3 DI DRUM-HIGGINS 000/11R RPL STRW | 31509929 | DRUM-HIGGINS | 000/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.767471 | 39.2432 | ETL.4393 | 44172235 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119890345 | Q2 | T3 DI DRUM-HIGGINS 1/13R RPL STRW | 31509929 | DRUM-HIGGINS | 001/013 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.770864 | 39.2402 | ETL.4393 | 44172219 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119890347 | Q2 | T3 DI DRUM-HIGGINS 0/12R RPL STRW | 31509929 | DRUM-HIGGINS | 000/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.769053 | 39.2419 | ETL.4393 | 44172203 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119890994 | Q2 | T2 DI HAT CREEK #1-WESTWOOD 0/3 RPL STRW | 31515622 | HAT CREEK #1-WESTWOOD | 000/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.543478 | 40.9286 | ETL.7030 | 40701311 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119891352 | Q2 | DI GRBERVILLE-LAYTONVILLE 44/10 REPL POL | 31516141 | GARBERVILLE-LAYTONVILLE | 044/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.596929 | 39.958 | ETL.8365 | 40912495 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119891649 | Feb | EI RND MTN-CTTNWD #3 28/229 INS MRKS | 44624619 | ROUND MTN-COTTONWOOD #3 | 028/229 | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2022-10-12 |  |  | 2021-02-19 | 2021-02-15 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.945842 | 40.7831 | ETL.5650 | 44965633 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119892132 | Q2 | T2 MALIN-ROUND MTN #2 86/436 RPR SHLS | 44408444 | MALIN-ROUND MTN #2 | 086/436 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-12 | 2021-10-12 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.917628 | 40.9203 | ETL.6020 | 40810540 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119892417 | Not Scheduled | EI SN LS OBISPO-SNTA MR 21/102 INST MRKS | 31528662 | SAN LUIS OBISPO-SANTA MARIA | 021/102 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2021-10-12 | [9 empty] | South | WSIP | [6 empty] | '-120.445263 | 35.0055 | ETL.3540 | 44284860 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119892481 | Not Scheduled | T2 DI FULTON-HOPLAND 024/005 RPL STRW | 31514632 | FULTON-HOPLAND | 024/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2021-10-12 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.963532 | 38.7664 | ETL.6890 | 40750526 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119892736 | Q2 | T2 DI FORT ROSS-GUALAL 51/005 RPL INSW | 31516663 | GUALALA-MONTE RIO | 051/005 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 | 2021-06-07 | 2021-06-14 | 2021-06-09 | 2021-06-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.429899 | 38.7317 | ETL.6980 | 40778295 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119892963 | Mar | T3 DI MONTA VISTA-BURNS 14/114 RPR GYWW | 44610148 | MONTA VISTA-BURNS | 014/114 | ICD | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | 2021-03-17 | 2021-03-18 | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.175944 | 37.1364 | ETL.7590 | 40767268 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893023 | Q2 | T2 DI SALINAS-LAURELES 9/206 RPR GYWW | 44610150 | SALINAS-LAURELES | 009/206 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71941 | 36.5805 | ETL.7930 | 40588377 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893132 | Mar | T3 DI DRUM-GRSS VLLY-WEIMR 0/15 RPL STRW | 31512367 | DRUM-GRASS VALLEY-WEIMAR | 000/015 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.758276 | 39.2525 | ETL.6760 | 40756228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893356 | Q2 | T2 DI HT CRK #1-WSTWD 016/308 INS INSLBW |  | HAT CREEK #1-WESTWOOD | 016/308 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.327438 | 40.7846 | ETL.7030 | 44311019 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893531 | Not Scheduled | T2 DI MONTA VISTA-BURNS 2/28 RPR GYWW |  | MONTA VISTA-BURNS | 002/028 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-122.100831 | 37.29 | ETL.7590 | 44320359 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893538 | Q2 | T2 DI FORT ROSS-GUALAL 50/005 RMV BUTT |  | GUALALA-MONTE RIO | 050/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.414257 | 38.7262 | ETL.6980 | 40750315 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893559 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/368 RPR GYWW | 44502302 | SPAULDING-SUMMIT | 011/368 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2021-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.462406 | 39.3189 | ETL.8060 | 44349553 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893626 | Q2 | T2 DI HT CRK #1-WESTWD 003/078 RPR STRW |  | HAT CREEK #1-WESTWOOD | 003/078 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2021-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.470678 | 40.9168 | ETL.7030 | 40815931 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893701 | Not Scheduled | T3NT DI FLTN-CALISTOGA :006/002 RMV BUTT | 44597303 | FULTON-CALISTOGA | :006/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.587269 | 38.6733 | ETL.6880 | 40912472 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893742 | Not Scheduled | T2 DI VLLY SPRNGS-MRTLL #1 8/11 RMV BUTT |  | VALLEY SPRINGS-MARTELL #1 | 008/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.768549 | 38.3124 | ETL.8240 | 40600041 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893747 | Q2 | T2 DI TRINITY-MAPLE CREEK 14/6 RPR GYWW | 44484765 | TRINITY-MAPLE CREEK | 014/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.168109 | 40.751 | ETL.8170 | 40810474 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893749 | Q3 | T2 DI CARIBOU #2 020/543 RPR GYWS |  | CARIBOU #2 | 020/543 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.012641 | 40.0322 | ETL.6280 | 44259062 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893760 | Q2 | T3 DI FLTN-CALISTOGA :001/005 RPL STRW | 31516146 | FULTON-CALISTOGA | :001/005 | 70Y | E | 2020_(1a) PSPS |  | 2020-10-06 | 2021-04-06 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.585688 | 38.6187 | ETL.6880 | 40912422 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119893883 | Q2 | T2 DI KONOCTI-MIDDLETON 20/0 RPL GMRK |  | KONOCTI-MIDDLETOWN | 020/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.586176 | 38.8518 | ETL.6380 | 40615071 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893884 | Q2 | T2 DI TRINITY-MAPLE CREEK 13/7 RMV BUTT | 44470706 | TRINITY-MAPLE CREEK | 013/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.153101 | 40.7592 | ETL.8170 | 44846603 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119893892 | Not Scheduled | DI SPAULDING-SUMMIT 008/277 RPLC STRW | 31516737 | SPAULDING-SUMMIT | 008/277 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2021-10-06 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.512754 | 39.3144 | ETL.8060 | 40876689 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119893938 | Q2 | DI GATES-PANOCHE #1 036/171 RPR FOUND | 44501250 | GATES-PANOCHE #1 | 036/171 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2022-10-06 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.505658 | 36.5624 | ETL.4720 | 40587483 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119893960 | Not Scheduled | DI SPAULDING-SUMMIT 8/278 RMV DEBRIS | 44502587 | SPAULDING-SUMMIT | 008/278 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-06 | 2022-10-06 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.511695 | 39.3142 | ETL.8060 | 40618268 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119894254 | Mar | EI T3NT DIABLO-MIDWAY #2 1/005 RPR FOND | 44501253 | DIABLO-MIDWAY #2 | 001/005 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-10-12 | 2022-10-12 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.832792 | 35.2126 | ETL.5970 | 40753805 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119894296 | Not Scheduled | T2 DI SN LS OBISPO-OCEANO 6/32 RPL INSS | 31527004 | SAN LUIS OBISPO-OCEANO | 006/032 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2021-10-12 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | 120.552 | 35.1915 | ETL.3530 | 40713847 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119894449 | Q2 | DI GARBERVILLE-LYTNVL 41/0 RPL POLE | 31516141 | GARBERVILLE-LAYTONVILLE | 041/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2021-10-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.577485 | 39.911 | ETL.8365 | 40906653 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119895649 | Mar | T3 EI DIABLO-MIDWAY #3 2/012 RPR STRT | 44501254 | DIABLO-MIDWAY #3 | 002/012 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-04-13 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.804747 | 35.2137 | ETL.5980 | 40664648 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119895691 | Not Scheduled | T2 MALIN-ROUND MTN #2 56/280 BENT STEEL |  | MALIN-ROUND MTN #2 | 056/280 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-13 | 2021-10-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.616978 | 41.2523 | ETL.6020 | 40601161 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896114 | Mar | EI COALINGA #1-SAN MIGUEL 18/002 RMV VEG |  | COALINGA #1-SAN MIGUEL | 018/002 | HNA | E | 2020_(3) On high spread structure |  | 2020-10-13 | 2021-10-13 |  |  | 2021-03-31 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.580493 | 35.9999 | ETL.8580 | 40690798 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | HNA | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896116 | Feb | EI COALINGA #1-SAN MIGUEL 18/002 RPR STR | 44507305 | COALINGA #1-SAN MIGUEL | 018/002 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-10-13 |  |  | 2021-02-26 | 2021-02-15 | [5 empty] | South | WSIP | [6 empty] | '-120.580493 | 35.9999 | ETL.8580 | 40690798 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896332 | Q2 | DI GARBERVILLE-LAYTONVILLE 46/8 REFRAME | 31516221 | GARBERVILLE-LAYTONVILLE | 046/008 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625102 | 39.9769 | ETL.8365 | 40912518 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896383 | Mar | T2 DI MNTA VSTA-JFFRSN #1 5/21 RPL INSS | 31528463 | MONTA VISTA-JEFFERSON #1 | 005/021 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | 122.1098 | 37.3199 | ETL.5220 | 40611896 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896385 | Mar | T2 DI MNTA VSTA-JFFRSN #1 5/21 HANGER |  | MONTA VISTA-JEFFERSON #1 | 005/021 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.164018 | 37.3315 | ETL.5220 | 40587097 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896555 | Q2 | DI GARBERVILLE-LAYTONVILLE 40/4 RPL HRDW | 44476763 | GARBERVILLE-LAYTONVILLE | 040/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-12 | 2021-10-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.579198 | 39.9004 | ETL.8365 | 44241872 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896598 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 3/013A RPR GYWR |  | DIABLO-MIDWAY #3 | 003/013A | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-04-13 | [6 empty] | Tower guy | TR3 | <60D | South | WSIP | [6 empty] | '-120.793053 | 35.2128 | ETL.5980 | 40576269 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119896871 | Mar | T3 EI DIABLO-MIDWAY #2 3/014 RGRD FOND | 44501253 | DIABLO-MIDWAY #2 | 003/014 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-04-13 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.78759 | 35.2117 | ETL.5970 | 40753879 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119897802 | Not Scheduled | T3 DI FULTON-CALISTOGA :7/06 RPL POLE | 31516146 | FULTON-CALISTOGA | :007/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.597173 | 38.6945 | ETL.6880 | 40912488 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898149 | Q4 | T2 DI KESWICK-TRINITY 021/311 RPR GYWW |  | KESWICK-TRINITY | 021/311 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.772299 | 40.7172 | ETL.7270 | 44649280 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898185 | Q4 | T2 DI KESWICK-TRINITY 021/311 RMV BUTT |  | KESWICK-TRINITY | 021/311 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.772299 | 40.7172 | ETL.7270 | 44649280 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898252 | Q2 | T3 DI DRUM SPAULDING 0/17 RPR GYWW | 44502189 | DRUM-SPAULDING | 000/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-04-07 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.75554 | 39.2505 | ETL.6770 | 44396919 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898258 | Not Scheduled | T3NT DI CLGT-CHLLNG 10/174 RMV DEBRIS | 44502513 | COLGATE-CHALLENGE | 010/174 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.207195 | 39.4494 | ETL.6480 | 40693469 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898293 | Mar | T3 DI DRM-GRSS VLLY-WMR-010/241 RPR GYWW | 44502253 | DRUM-GRASS VALLEY-WEIMAR | 010/241 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.881157 | 39.1624 | ETL.6760 | 40813445 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898377 | Q2 | T3 DI WEIMAR #1 012/176 RMV HRDW | 44502180 | WEIMAR #1 | 012/176 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.768469 | 39.0139 | ETL.7560 | 44913349 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898378 | Q2 | T3NT DI WEIMAR #1 012/176 RMV BUTT | 44503556 | WEIMAR #1 | 012/176 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.768469 | 39.0139 | ETL.7560 | 44913349 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898421 | Q2 | T2 DI FRT RSS-GUALALA 042/008 RMV PL BUT |  | GUALALA-MONTE RIO | 042/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 | 2021-06-15 | 2021-06-18 | 2021-06-18 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.314348 | 38.6775 | ETL.6980 | 40877391 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898427 | Mar | T2 DI SALINAS-LAURELES A011/251 RMV STEP | 44625135 | SALINAS-LAURELES | A011/251 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-03-04 | 2021-03-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.757002 | 36.5697 | ETL.7930 | 40864643 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898450 | Not Scheduled | T2 DI CLGTE-SMRTVLLE #2 10/123 RPR GYWW | 44502125 | COLGATE-SMARTVILLE #2 | 010/123 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.303369 | 39.214 | ETL.6520 | 40828234 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898451 | Not Scheduled | T2 DI CLGTE-SMRTVLL #2 10/123 RMV BUTT | 44502125 | COLGATE-SMARTVILLE #2 | 010/123 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2021-10-07 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.303369 | 39.214 | ETL.6520 | 40828234 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898454 | Q2 | T2 DI TRNTY-MAPLE CRK 013/009 RPL INSW | 31514141 | TRINITY-MAPLE CREEK | 013/009 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.297988 | 40.7095 | ETL.8170 | 40893773 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898458 | Feb | T2 DI TRNTY-MAPLE CRK 002/010 RPR GYWW | 44484765 | TRINITY-MAPLE CREEK | 002/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 | 2021-02-22 | 2021-02-27 | 2021-02-24 | 2021-02-24 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.973681 | 40.7346 | ETL.8170 | 40906272 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898480 | Q2 | T3 DI SNTH LN-PACIFICA 6/67 RPR GYWW | 44621673 | SNEATH LANE-PACIFICA | 006/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-04-06 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.479105 | 37.5985 | ETL.7575 | 40768064 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898481 | Q2 | T3 DI DRUM-SPAULDING 000/019 RPR GYWW | 44502252 | DRUM-SPAULDING | 000/019 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-04-07 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.754782 | 39.2501 | ETL.6770 | 44396921 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898482 | Q2 | T3NT DI DRUM-SPAULDING 000/019 RMV BUTT | 44502518 | DRUM-SPAULDING | 000/019 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.754782 | 39.2501 | ETL.6770 | 44396921 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898484 | Not Scheduled | T3NT DI SNTH LN-HLF MNBY ?7/009 RMV HRDW | 44621950 | SNEATH LANE-HALF MOON BAY | ?007/009 | ICW | F | 2020_(2) High fire spread TD |  | 2020-10-07 | 2022-10-07 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.42797 | 37.5232 | ETL.7212 | 44649361 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898486 | Not Scheduled | T3NT DI SNTH LN-HLF MNBY ?7/009 RMV DEBR | 44621950 | SNEATH LANE-HALF MOON BAY | ?007/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.42797 | 37.5232 | ETL.7212 | 44649361 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898488 | Q3 | T2 DI CRBOU-WESTWD 000/004 RPR CRSW |  | CARIBOU-WESTWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.14707 | 40.0859 | ETL.6300 | 40656481 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898510 | Q3 | T2 DI CRBOU-WESTWD 000/004 RMV DEBRIS |  | CARIBOU-WESTWOOD | 000/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.14707 | 40.0859 | ETL.6300 | 40656481 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898511 | Q3 | T2 DI CRBOU-WESTWD 000/004 RPR GYWW |  | CARIBOU-WESTWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.14707 | 40.0859 | ETL.6300 | 40656481 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898513 | Not Scheduled | T3 DI FLTN-CALISTOGA :004/010 RMV DEBRIS | 44597303 | FULTON-CALISTOGA | :004/010 | ICW | E | 2020_(3) On high spread structure |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.588761 | 38.6547 | ETL.6880 | 40912453 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898515 | Not Scheduled | T3 DI FLTN-CALISTOGA :004/010 RPL STRW | 31516146 | FULTON-CALISTOGA | :004/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.588761 | 38.6547 | ETL.6880 | 40912453 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898517 | Not Scheduled | T3NT DI FLTN-CALISTOGA :7/001 RMV BUTT | 44597303 | FULTON-CALISTOGA | :007/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.594551 | 38.6878 | ETL.6880 | 40912483 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898532 | Q4 | T2 DI KSWCK-TRNTY 21/315 RPR GYWW |  | KESWICK-TRINITY | 021/315 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.775255 | 40.7177 | ETL.7270 | 44649264 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898533 | Q2 | T2 DI FORT ROSS-GUALALA 045/008 RPR GYWW |  | GUALALA-MONTE RIO | 045/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.34073 | 38.7139 | ETL.6980 | 40860964 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898537 | Q2 | T2 DI FT RSS-GLLA 40/002 RPR GYWW |  | GUALALA-MONTE RIO | 040/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.314172 | 38.6436 | ETL.6980 | 40656375 | Guy Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898539 | Not Scheduled | T3NT DI FLTN-CALISTOGA :7/004 RMV BUTT | 44597303 | FULTON-CALISTOGA | :007/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.596423 | 38.6903 | ETL.6880 | 40912486 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898580 | Not Scheduled | T3 DI FLTN-CALISTOGA :7/004 RPL HRDW | 44597303 | FULTON-CALISTOGA | :007/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.596423 | 38.6903 | ETL.6880 | 40912486 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898581 | Not Scheduled | T3NT DI FLTN-CALISTOGA :7/004 INST MRKW | 44597303 | FULTON-CALISTOGA | :007/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.596423 | 38.6903 | ETL.6880 | 40912486 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898918 | Mar | EI COALINGA #1-SAN MIGUEL 16/1 RPL INSW | 31519494 | COALINGA #1-SAN MIGUEL | 016/001 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 | 2021-03-15 | 2021-03-18 | 2021-03-18 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.54101 | 36.0071 | ETL.8580 | 40624447 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119898930 | Not Scheduled | EI COALINGA #1-SAN MIGUEL 16/2 RPL SPLS |  | COALINGA #1-SAN MIGUEL | 016/002 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-10-13 | [9 empty] | South | WSIP | [6 empty] | '-120.54436 | 36.0065 | ETL.8580 | 40690794 | Splice-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119899364 | Q2 | T2 DI FORT ROSS-GUALALA 037/009 RMV BUTT |  | GUALALA-MONTE RIO | 037/009 | ICW | E | 2020_(3) On high spread structure |  | 2020-10-07 | 2021-10-07 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.300817 | 38.6214 | ETL.6980 | 40871400 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119899366 | Q2 | T2 DI FORT ROSS-GUALALA 037/009 RPR GYWW |  | GUALALA-MONTE RIO | 037/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.300817 | 38.6214 | ETL.6980 | 40871400 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119899424 | Q2 | T2 DI TRINITY-MAPLE CREEK 27/1 RPR GYWW | 44484765 | TRINITY-MAPLE CREEK | 027/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.396924 | 40.7048 | ETL.8170 | 44846598 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119900079 | Q2 | T2 DI TRINITY-MAPLE CREEK 27/1 RMV BUTT | 44470706 | TRINITY-MAPLE CREEK | 027/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.396924 | 40.7048 | ETL.8170 | 44846598 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119900127 | Q4 | T2 DI KESWICK-TRINITY 26/440 RMV STEP |  | KESWICK-TRINITY | 026/440 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.864333 | 40.6962 | ETL.7270 | 44164735 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119900329 | Q3 | EI COALINGA #1-SAN MIGUEL 19/1 RMV VEG |  | COALINGA #1-SAN MIGUEL | 019/001 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-14 | 2021-10-14 |  |  | 2021-08-15 | 2021-08-01 | [5 empty] | South | WSIP | [6 empty] | '-120.59577 | 35.9967 | ETL.8580 | 40597698 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119900957 | Not Scheduled | T3 EI DIABLO-MIDWAY #2 2/012 RPR INSS |  | DIABLO-MIDWAY #2 | 002/012 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-04-13 | [7 empty] | TR3 | <60D | South | WSIP | [6 empty] | '-120.800136 | 35.2127 | ETL.5970 | 40664610 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119902523 | Not Scheduled | T2 MALIN-ROUND MTN #2 59/294 RPR GYWS | 44408444 | MALIN-ROUND MTN #2 | 059/294 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-14 | 2021-10-14 | [6 empty] | Tower guy | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.642521 | 41.2208 | ETL.6020 | 40761922 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119906072 | Q2 | T2 BRIDGEVILLE-COTTONWD 57/418 INST JUMS | 44625172 | BRIDGEVILLE-COTTONWOOD | 057/418 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-14 | 2021-10-14 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.310324 | 40.3757 | ETL.1110 | 40596845 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119906219 | Mar | T3 WV MONTA VISTA-BURNS 8/066 RPL INSW | 31516523 | MONTA VISTA-BURNS | 008/066 | 93I | E | 2020_(1a) PSPS |  | 2020-10-14 | 2021-04-14 | 2021-03-17 | 2021-03-18 | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.1446511 | 37.2223 | ETL.7590 | 44631863 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119906307 | Q2 | T2 DI IGNACIO-BLNS #2 11/139 RPL INSW | 31516664 | IGNACIO-BOLINAS #2 | 011/139 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-07 | 2021-10-07 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.692814 | 38.0901 | ETL.7180 | 40855687 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119906425 | Q3 | T2 DI CARIBOU-PLUMAS JCT 14/7A RMV DBRS |  | CARIBOU-PLUMAS JCT | 014/007A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 |  |  | 2021-08-13 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.953736 | 39.9571 | ETL.6290 | 42601243 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119906502 | Not Scheduled | EI COALINGA #1-SAN MIGUEL 18/002 INST FE | 31529019 | COALINGA #1-SAN MIGUEL | 018/002 | 71Y | F | 2020_(3) On high spread structure |  | 2020-10-13 | 2022-10-13 | [9 empty] | South | WSIP | [6 empty] | '-120.580493 | 35.9999 | ETL.8580 | 40690798 | Fence / Gate | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907245 | Not Scheduled | DI LAYTONVILLE-COVELO 002/002 HIGH SIGN |  | LAYTONVILLE-COVELO | 002/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-09 | 2022-10-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.438455 | 39.6943 | ETL.7390 | 44837898 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907248 | Not Scheduled | DI DIVIDE-CABRILLO #1 3/41 RMV BUTT |  | DIVIDE-CABRILLO #1 | 003/041 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-08 | 2022-10-08 | [9 empty] | South | WSIP | [6 empty] | '-120.441438 | 34.7849 | ETL.1380 | 40602558 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907405 | Q2 | DI GARBERVLL-LAYTONVILL 043/005 RPL DAMW | 44476763 | GARBERVILLE-LAYTONVILLE | 043/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.581167 | 39.9469 | ETL.8365 | 40916350 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907581 | Mar | T3 DI GYSRS #3-CLVRDL 5/64 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 005/064 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.908734 | 38.8158 | ETL.1650 | 40808982 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907584 | Q2 | T3 DI DRUM-SPAULDING 002/054 RPR GYWW | 44502189 | DRUM-SPAULDING | 002/054 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.736877 | 39.2659 | ETL.6770 | 40869653 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907585 | Not Scheduled | T3 DI MONTE RIO-FULTON 007/018 RPR GYWW |  | MONTE RIO-FULTON | 007/018 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.900174 | 38.4907 | ETL.7630 | 40877369 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907591 | Feb | T3 DI DESABLA-CNTERVILLE 1/23 RPR GWRW | 44356201 | DESABLA-CENTERVILLE | 001/023 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-08 | 2021-04-08 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.631388 | 39.8499 | ETL.6720 | 40649884 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907592 | Feb | T3 DI DESABLA-CNTERVILLE 1/23 RPR INSW | 44356201 | DESABLA-CENTERVILLE | 001/023 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-08 | 2021-04-08 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.631405 | 39.8498 | ETL.6720 | 40678036 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907622 | Feb | T3 DI DSBLA-CNTRVLLE 004/050 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 004/050 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.64743 | 39.8061 | ETL.6720 | 44324208 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907623 | Feb | T3 DI DSBLA-CNTRVLLE 004/050 INS BOND | 44356201 | DESABLA-CENTERVILLE | 004/050 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.64743 | 39.8061 | ETL.6720 | 44324208 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907624 | Q2 | T3 DI DRUM-SPAULDING 2/053 RPL POLE | 31529084 | DRUM-SPAULDING | 002/053 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-06 | 2021-04-06 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | SCHD | North Valley | WSIP | [6 empty] | '-120.737069 | 39.2656 | ETL.6770 | 40870470 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119907626 | Q2 | T3NT DI DRUM-SPAULDING 002/053 RMV BUTT | 44502518 | DRUM-SPAULDING | 002/053 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-06 | 2022-10-06 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.737069 | 39.2656 | ETL.6770 | 40870470 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119908117 | Not Scheduled | T3 DI FULTON-CALISTOGA :008/006 RPL HRDD | 44597303 | FULTON-CALISTOGA | :008/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.603742 | 38.7073 | ETL.6880 | 40905733 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119908215 | Q2 | T3 DI IGNACIO-BOLINAS #2 20/229 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 020/229 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-04-06 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.765034 | 38.0202 | ETL.7180 | 40585020 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119908647 | Q2 | T3NT DI IGNACIO-BOLINS #2 20/237 INS MRK | 44640732 | IGNACIO-BOLINAS #2 | 020/237 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-06 | 2022-10-06 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.756669 | 38.0106 | ETL.7180 | 40665557 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909196 | Q2 | T3NT MI-WUK-CURTIS 19/2 REPLUMB | 44623687 | ETL.1073.INSL.CERA | 019/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-04-13 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.229764 | 38.0491 | ETL.1073 | 40703632 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909255 | Q3 | EI DONNELLS-CURTIS 10/001 RPR STRW | 44623688 | DONNELLS-CURTIS | 010/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-10-13 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.1179242 | 38.1343 | ETL.1400 | 44770790 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909398 | Q2 | T2 DI TRINITY-MAPLE CRK 28/0 RMV DEBRIS | 44470706 | TRINITY-MAPLE CREEK | 028/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.413178 | 40.7002 | ETL.8170 | 44846600 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909548 | Not Scheduled | T3 WV MONTE RIO-FORT ROSS 22/0 INST DAMW |  | ETL.6979.INSL.NCER | 022/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-15 | 2021-04-15 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-123.127845 | 38.4745 | ETL.6979 | 40741534 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909560 | Q2 | T2 DI SALINAS-LAURELES 009/210 RPR GYWW | 44610150 | SALINAS-LAURELES | 009/210 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.722499 | 36.579 | ETL.7930 | 40812854 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909579 | Not Scheduled | LOS BANOS-GATES #1 39/162 INS MRKS | 44507429 | LOS BANOS-GATES #1 | 039/162 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-15 | 2022-10-15 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.620218 | 36.5985 | ETL.6000 | 40680389 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119909708 | Q4 | T3 DI MAPLE CREEK-HOOPA 023/009 RPR GYWW | 44482958 | MAPLE CREEK-HOOPA | 023/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-04-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.645935 | 40.9959 | ETL.7490 | 44145872 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909709 | Q4 | T3NT DI MAPLE CREEK-HOOPA 23/9 RMV BUTT | 44461912 | MAPLE CREEK-HOOPA | 023/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.645935 | 40.9959 | ETL.7490 | 44145872 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119909783 | Not Scheduled | T2 DI VLLY SPRNGS-MRTL #1 11/7 RPR STRW |  | VALLEY SPRINGS-MARTELL #1 | 011/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-07 | 2021-10-07 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.785678 | 38.3528 | ETL.8240 | 40815492 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 25 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119910075 | Not Scheduled | T2 MALIN-ROUND MTN #2 048/236 GWR FOND |  | MALIN-ROUND MTN #2 | 048/236 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-15 | 2021-10-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.529495 | 41.3597 | ETL.6020 | 40817693 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119910491 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 9/036 RPR GYWS |  | DIABLO-MIDWAY #3 | 009/036 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-15 | 2021-04-15 | [6 empty] | Tower guy | TR3 | <60D | South | WSIP | [6 empty] | '-120.68433 | 35.2009 | ETL.5980 | 40823052 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119910984 | Not Scheduled | WV T2 DIABLO-GATES #1 9/043 RPR INSS |  | DIABLO-GATES #1 | 009/043 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-15 | 2021-10-15 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.78168 | 35.3296 | ETL.5960 | 40659976 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119911097 | Not Scheduled | T3 WV DIABLO-MIDWAY #2 3/014 RPR INSS |  | DIABLO-MIDWAY #2 | 003/014 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-15 | 2021-04-15 | [7 empty] | TR3 | <60D | South | WSIP | [6 empty] | '-120.7876028 | 35.2117 | ETL.5970 | 40783504 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119911103 | Not Scheduled | WV T2 DIABLO-MIDWAY #2 20/081 RPR INSS |  | DIABLO-MIDWAY #2 | 020/081 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-15 | 2021-10-15 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.510321 | 35.1696 | ETL.5970 | 40587683 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119911176 | Not Scheduled | T3 WV DIABLO-MIDWAY #2 9/035 RPR INSS |  | DIABLO-MIDWAY #2 | 009/035 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-15 | 2021-04-15 | [7 empty] | TR3 | <60D | South | WSIP | [6 empty] | '-120.6865041 | 35.2002 | ETL.5970 | 40795574 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119911391 | Not Scheduled | T3NT DI FULTON-CALISTOGA :2/6 RMV BUTT | 44597303 | FULTON-CALISTOGA | :002/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.595314 | 38.6306 | ETL.6880 | 44923812 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119911393 | Not Scheduled | T3 DI FULTON-CALISTOGA :2/6 RPR GYWW | 44597303 | FULTON-CALISTOGA | :002/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-06 | 2021-04-06 | [7 empty] | TR3 | <60D | North Coast | WSIP | [6 empty] | '-122.595314 | 38.6306 | ETL.6880 | 44923812 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119912097 | Q2 | DI GARBERVLL-LAYTNVILL 035/010 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 035/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.581366 | 39.8413 | ETL.8365 | 43603136 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119912388 | Q2 | DI GARBERVILLE-LAYTONVILLE 46/6 INS MRKW | 44476763 | GARBERVILLE-LAYTONVILLE | 046/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-09 | 2022-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6234 | 39.9743 | ETL.8365 | 40912516 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119912500 | Q2 | DI GARBERVILLE-LAYTONVILLE 46/6 RPL INSW | 31516317 | GARBERVILLE-LAYTONVILLE | 046/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8365 | 40922325 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119912607 | Q2 | DI GRBRVLL-LYTNVLLE 33/1 RPR GYWW | 44476763 | GARBERVILLE-LAYTONVILLE | 033/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.556241 | 39.8132 | ETL.8365 | 40600475 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119912608 | Q2 | DI GRBRVLLE-LYTNVLLE 33/1 RPL INSW | 31516317 | GARBERVILLE-LAYTONVILLE | 033/001 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.556241 | 39.8132 | ETL.8365 | 40627168 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119912646 | Q2 | T3 DI IGNACIO-BOLINS #2 25/279R RPR STRW | 44640732 | IGNACIO-BOLINAS #2 | 025/279 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-04-13 |  |  | 2021-04-23 | 2021-04-16 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-122.711408 | 37.9573 | ETL.7180 | 44837697 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119915112 | Q2 | DI GARBERVLLE-LATNOVILL 033/005 RPL INSW | 31516862 | GARBERVILLE-LAYTONVILLE | 033/005 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-09 | 2021-10-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.563381 | 39.8224 | ETL.8365 | 40778482 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119915174 | Not Scheduled | EI T3NT DIABLO-MIDWAY #2 9/036 RPR ANCS |  | DIABLO-MIDWAY #2 | 009/036 | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-10-16 | 2022-10-16 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.683804 | 35.2001 | ETL.5970 | 40820143 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119915298 | Mar | T3 EI DIABLO-MIDWAY #2 9/037 RPR FOND | 44501253 | DIABLO-MIDWAY #2 | 009/037 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-16 | 2021-04-16 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.680352 | 35.1992 | ETL.5970 | 40811435 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119915764 | Q2 | WV T2 FORT ROSS-GUALALA 36/5 INST DAMPER |  | GUALALA-MONTE RIO | 036/005 | ICW | E | 2020_(3) On high spread structure |  | 2020-10-16 | 2021-10-16 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.296653 | 38.6055 | ETL.6980 | 40741535 | Damper-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916364 | Q2 | T2 DI TRNTY-MPLE CRK 34/006 RPR GYWW | 44484765 | TRINITY-MAPLE CREEK | 034/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-16 | 2021-10-16 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.53059 | 40.7127 | ETL.8170 | 40810494 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916583 | Q2 | T2 DI SBRT-STRD OIL SS#1 8/49 RPL INSS |  | SOBRANTE-STANDARD OIL SW STA #2 | 008/049 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2021-10-12 |  |  | 2021-05-04 | 2021-05-04 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.248763 | 37.9956 | ETL.3800 | 40884379 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916614 | Mar | T2 CARIBOU-TABLE MTN 034/254 INST DAMS |  | CARIBOU-TABLE MTN | 034/254 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-16 | 2021-10-16 |  |  | 2021-03-11 | 2021-03-11 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.45502 | 39.8147 | ETL.4440 | 40761220 | Damper-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916641 | Q4 | T3NT NN MPLE CRK-HOOPA 011/005 INS MRKW | 44482958 | MAPLE CREEK-HOOPA | 011/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-18 | 2022-09-18 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.770848 | 40.9011 | ETL.7490 | 40770458 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916684 | Mar | T3 WV DIABLO-MIDWAY #3 24/097 RPR HRDT | 44501254 | DIABLO-MIDWAY #3 | 024/097 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-16 | 2021-04-16 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.43889 | 35.1622 | ETL.5980 | 40819447 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916687 | Mar | T3 WV DIABLO-MIDWAY #3 10/038 RPL HRDT | 44501254 | DIABLO-MIDWAY #3 | 010/038 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-16 | 2021-04-16 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.675803 | 35.1985 | ETL.5980 | 40871223 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916735 | Q2 | T2NT DI CRESTA-RIO OS 029/235 RMV DEBRIS |  | CRESTA-RIO OSO | 029/235 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-09 | 2022-10-09 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.535578 | 39.5565 | ETL.4590 | 41083096 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916878 | Q2 | NN GATES-PANOCHE #1 022/105 MASTIC | 44506742 | GATES-PANOCHE #1 | 022/105 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-09-18 | 2022-09-18 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.353002 | 36.4002 | ETL.4720 | 40753540 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119916940 | Q2 | T2 DI BRIDGEVLLE-COTTNWD 9/88L RPR HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/088 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.446166 | 40.3891 | ETL.1110 | 44424024 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916942 | Q2 | T2NT NN HT CRK #1-WSTWD 31/605 RMV BUTT |  | HAT CREEK #1-WESTWOOD | 031/605 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-09-19 | 2022-09-19 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.124457 | 40.6207 | ETL.7030 | 40600247 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916944 | Q2 | T2 DI BRIDGEVILLE-COTTNWD 9/88R RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/088 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.446166 | 40.3891 | ETL.1110 | 44424025 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916970 | Not Scheduled | T2 NN SPAULDING-SUMMIT 1/70 INS MRKW | 44503548 | SPAULDING-SUMMIT | 001/070 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-09-19 | 2022-09-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.617504 | 39.3111 | ETL.8060 | 40863727 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916973 | Mar | T2 DI BAHIA-MORAGA 15/88 RPL INSS | 31527243 | BAHIA-MORAGA | 015/088 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.2087 | 37.9688 | ETL.4340 | 40841852 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119916979 | Q2 | T2NT DI BRIDGVLL-CTTNWD 28/239R RMV BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 028/239 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-13 | 2022-10-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.798731 | 40.3668 | ETL.1110 | 44561127 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917020 | Q2 | T2 DI BRIDGEVLLE-CTTNWD 28/239 RPLC INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 028/239 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.798731 | 40.3668 | ETL.1110 | 40678632 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917427 | Mar | T3NT DI LAURELES-OTTER 010/002A RMV DBRS | 44587870 | LAURELES-OTTER | 010/002A | ICW | F | 2020_(3) On high spread structure |  | 2020-09-21 | 2022-09-21 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.826617 | 36.4068 | ETL.7380 | 44562892 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917477 | Feb | T3 DI DRUM-RIO OSO #1 2/23 RPR INSS | 44503315 | DRUM-RIO OSO #1 | 002/023 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-13 | 2021-04-13 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.806649 | 39.2512 | ETL.1420 | 44665189 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917701 | Q2 | T2 DI PHILO JCT-ELK 007/003 RPL INSW | 31514497 | PHILO JCT-ELK | 007/003 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-13 | 2021-10-13 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.252512 | 39.0457 | ETL.7780 | 40697958 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917760 | Mar | DI CLNGA #1-SN MGL 6/1 MASTIC | 44507305 | COALINGA #1-SAN MIGUEL | 006/001 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-09-25 | 2022-09-25 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.440528 | 36.0978 | ETL.8580 | 40582579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917795 | Q2 | T2 DI MORRO BAY-MESA 008/039 RPR FOUND | 44506746 | MORRO BAY-MESA | 008/039 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-09-25 | 2022-09-25 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.739479 | 35.2975 | ETL.5290 | 40865518 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917872 | Q3 | NN DONNELLS-MI-WUK 10/4 RMV DEBRIS | 44623689 | DONNELLS-CURTIS | 010/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-29 | 2022-07-29 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.119734 | 38.1309 | ETL.1400 | 44806630 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917965 | Q2 | T2 NN KNCTI MDDLTWN 18/7 INST MRKW |  | KONOCTI-MIDDLETOWN | 018/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2022-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.581242 | 38.8363 | ETL.6380 | 40824705 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119917966 | Q2 | T2 NN KNCTI MDDLTWN 18/7 RMV DEBRIS | 44610651 | KONOCTI-MIDDLETOWN | 018/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-31 | 2022-07-31 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.581242 | 38.8363 | ETL.6380 | 40824705 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119918395 | Not Scheduled | T2 NN SPAULDING-SMMT 11/405 INST MRKW | 44503548 | SPAULDING-SUMMIT | 011/405 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-08-28 | 2022-08-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.445374 | 39.3183 | ETL.8060 | 44156129 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119920429 | Not Scheduled | T3 EI DIABLO-MIDWY #3 6/24 RPR SHIELD W |  | DIABLO-MIDWAY #3 | 006/024 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-19 | 2021-04-19 | [7 empty] | TR3 | <90D | South | WSIP | [6 empty] | '-120.740809 | 35.2056 | ETL.5980 | 40753903 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119920437 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 6/24 RPR GYWS |  | DIABLO-MIDWAY #3 | 006/024 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-19 | 2021-04-19 | [6 empty] | Tower guy | TR3 | <90D | South | WSIP | [6 empty] | '-120.740809 | 35.2056 | ETL.5980 | 40753903 | Guy Wire-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119921260 | Q2 | T2 DI KONOCTI-MIDDLETOWN 18/5 RPLC HRDW | 44610651 | KONOCTI-MIDDLETOWN | 018/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-16 | 2021-10-16 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.580266 | 38.8333 | ETL.6380 | 40768970 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119923199 | Q3 | DONNELLS-MI-WUK 10/4 RPLC DAMW | 44623690 | DONNELLS-CURTIS | 010/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-19 | 2021-10-19 |  |  | 2021-09-07 | 2021-08-07 | [5 empty] | Central | WSIP | [6 empty] | '-120.119734 | 38.1309 | ETL.1400 | 44806630 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31